## Fixed Data
S.No. | Project ID | Project Name | Region | District | Sector | Plot | Latitude | Longitude | Commencement Date | Completion Date | 18 Projects | Facility Type Primary | Capacity | Built-up Area | Design Consultant | Supervision Consultant | Contractor | Project Stage | Type of Construction | Procurement Route | Construction Contract Amount | Cumulative Variations | Final Contract Value | Supervision Contract amount | Authority Cost | Total Poject Cost | Certified till Date | Image 1 | Image 2 | Image 3
1 | MJ-01 | Al Bateen-Majlis-P1 | Abu Dhabi | Al Bateen | W25 | P1 | 24.4333 | 54.3727 | 2020-01-01 | 2022-07-01 |  | Majlis | 300 | 3000 | Leodaly | Leodaly | Silvercoast | Operation | New | Design Bid Build
2 | MJ-02 | Al Shahama-Majlis-P547 | Abu Dhabi | Al Shahama | Old Shahama | P547 | 24.5396 | 54.6808 | 2023-12-05 | 2025-07-24 | 18 Projects | Majlis | 666 | 5270 | Altorath | Altorath | Yas Projects | Construction | New | Design Bid Build
3 | MJ-03 | Mohamed Bin Zayed City -Majlis-P19 | Abu Dhabi | Mohamed Bin Zayed City | Z15 | P19 | 24.3398 | 54.556 | 2023-12-05 | 2025-07-24 | 18 Projects | Majlis | 408 | 6715 | Altorath | Altorath | Yas Projects | Construction | New | Design Bid Build
4 | MJ-04 | Zayed City-Majlis-P17 | Abu Dhabi | Zayed City | MZ8 | P17 | 24.3901 | 54.6151 | 2024-06-03 | 2026-01-01 | 18 Projects | Majlis | 1040 | 7048 | APG | APG | Kharafi | Construction | New | Design Bid Build
5 | MJ-05 | Baniyas-Majlis-P13 | Abu Dhabi | Baniyas | EB11-03 | P13 | 24.3053 | 54.6524 | 2024-06-03 | 2026-06-01 | 18 Projects | Majlis | 606 | 6020 | APG | APG | Kharafi | Construction | New | Design Bid Build
6 | MJ-06 | Khalifa City-Majlis-P2 | Abu Dhabi | Khalifa City | SW_06 | P2 | 24.3986 | 54.5647 | 2024-05-15 | 2025-12-08 | 18 Projects | Majlis | 970 | 7113 | APG | APG | Yas Projects | Construction | New | Design Bid Build
7 | MJ-07 | Mohamed Bin Zayed City-Majlis-P9 | Abu Dhabi | Mohamed Bin Zayed City | Z30 | P9 | 24.3028 | 54.5658 | 2024-05-15 | 2025-12-15 | 18 Projects | Majlis | 736 | 6415 | APG | APG | Yas Projects | Construction | New | Design Bid Build
8 | MJ-08 | Madinat Al Riyad-Majlis-P3 | Abu Dhabi | Madinat Al Riyad | RD133 | P3 | 24.2925 | 54.7432 | 2024-07-01 | 2026-08-01 | 18 Projects | Majlis | 1200 | 8000 | Altorath | Altorath | GBH | Construction | New | Design Bid Build
9 | MJ-09 | Al Shamkhah-Majlis-P6 | Abu Dhabi | Al Shamkhah | SH29 | P6 | 24.3412 | 54.6983 | 2024-07-01 | 2026-08-01 | 18 Projects | Majlis | 4000 | 18440 | Altorath | Altorath | GBH | Construction | New | Design Bid Build
10 | MJ-10 | Al Hili-Majlis-10 | Al Ain | Al Hili | Al Nayfa | 10 | 24.3071 | 55.7607 | 2024-07-01 | 2026-03-01 | 18 Projects | Majlis | 1800 | 7000 | Capital | Capital | China National | Construction | New | Design Bid Build
11 | MJ-11 | Al Tiwayya-Majlis-13 | Al Ain | Al Tiwayya | MAADHI | 13 | 24.2426 | 55.6888 | 2024-07-01 | 2026-03-01 | 18 Projects | Majlis | 658 | 6000 | Capital | Capital | China National | Construction | New | Design Bid Build
12 | MJ-12 | Mohamed Bin Zayed City-Majlis-P2 | Abu Dhabi | Mohamed Bin Zayed City | ME5 | P2 | 24.3647 | 54.5344 | 2024-07-16 | 2026-03-15 | 18 Projects | Majlis | 1206 | 8237.71 | APG | APG | Yas Projects | Construction | New | Design Bid Build
13 | MJ-13 | Madinat Al Riyad-Majlis-P162 | Abu Dhabi | Madinat Al Riyad | RD25 | P162 | 24.3353 | 54.7656 | 2024-07-16 | 2026-03-01 | 18 Projects | Majlis | 800 | 6674 | APG | APG | Yas Projects | Construction | New | Design Bid Build
14 | MJ-14 | Al Samhah-Majlis-P206 | Abu Dhabi | Al Samhah | Al Samha East | P206 | 24.6549 | 54.7597 | 2024-07-16 | 2026-03-01 | 18 Projects | Majlis | 992 | 7781.76 | APG | APG | Yas Projects | Construction | New | Design Bid Build
15 | MJ-15 | Al Shawamekh-Majlis-P15 | Abu Dhabi | Al Shawamekh | SHM13 | P15 | 24.3148 | 54.6555 | 2024-09-01 | 2026-03-01 | 18 Projects | Majlis | 1348 | 6999 | APG | APG | Yas Projects | Construction | New | Design Bid Build
16 | MJ-16 | Al Hili-Majlis-2 | Al Ain | Al Hili | Umm Al Mader | 2 | 24.2878 | 55.7659 | 2024-12-01 | 2026-08-01 |  | Majlis | 1400 |  | Capital | Capital |  | Design | New | Design Bid Build
17 | CP-01 | Al Danah-Car Park-P24 | Abu Dhabi | Al Danah | E3 - Hamdan | P24 | 24.4895 | 54.3651 | 2022-10-01 | 2024-05-31 |  | Car Park | 3184 | 21660 | Tangram | Tangram | Trojan | Operation | Retrofit | Design Bid Build
18 | CP-02 | Al Danah-Car Park-P6 | Abu Dhabi | Al Danah | E5 - Corniche | P6 | 24.4919 | 54.3592 | 2022-10-01 | 2024-05-31 |  | Car Park | 5075 | 38955 | Tangram | Tangram | Trojan | Operation | Retrofit | Design Bid Build
19 | CP-03 | Al Danah-Car Park-P7 | Abu Dhabi | Al Danah | E6 | P7 | 24.4892 | 54.359 | 2024-07-01 | 2026-03-01 | 18 Projects | Car Park | 2299 | 14197 | Capital | Capital | Trojan | Construction | Retrofit | Design Bid Build
20 | CP-04 | Al Danah-Car Park-P5 | Abu Dhabi | Al Danah | E6 | P5 | 24.4898 | 54.3605 | 2024-07-01 | 2026-03-01 | 18 Projects | Car Park | 6950 | 44230 | Capital | Capital | Trojan | Construction | Retrofit | Design Bid Build
21 | CP-05 | Al Danah-Car Park-P22 | Abu Dhabi | Al Danah | E11 | P22 | 24.4844 | 54.3761 | 2024-07-01 | 2026-03-01 | 18 Projects | Car Park | 4470 | 24908 | Capital | Capital | Trojan | Construction | Retrofit | Design Bid Build
22 | CP-06 | Al Danah-Car Park-P8 | Abu Dhabi | Al Danah | E8 | P8 | 24.4935 | 54.3659 | 2024-07-01 | 2026-03-01 | 18 Projects | Car Park | 3292 | 22046 | Capital | Capital | Trojan | Construction | Retrofit | Design Bid Build
23 | CP-10 | Al Zahiyah-Car Park-TMP7 | Abu Dhabi | Al Zahiyah | E16_01 | TMP7 | 24.4911 | 54.3812 | 2024-11-01 | 2026-10-31 |  | Car Park | 2080 |  | Capital |  |  | Tender | New | Design & Build
24 | CP-11 | Al Danah-Car Park-P8-E09_02 | Abu Dhabi | Al Danah | E9_02 | P8 | 24.4966 | 54.368 | 2024-11-01 | 2026-10-31 |  | Car Park | 3846 | 29360 | Capital |  |  | Tender | New | Design & Build
25 | MU-01 | Al Danah-Vertical Farm-P47 | Abu Dhabi | Al Danah | E18_03 | P47 | 24.4823 | 54.3796 | 2024-10-01 | 2027-09-30 |  | Vertical Farm | 1550 | 22498 | Tebodin |  |  | Feasibility | New | Design Bid Build
26 | MU-02 | Al Nahyan-Vertical Farm-P59 | Abu Dhabi | Al Nahyan | E25 | P59 | 24.4676 | 54.3861 | 2024-10-01 | 2027-09-30 |  | Vertical Farm | 1550 |  | Asteco |  |  | Feasibility | New | Design Bid Build
27 | MU-03 | Al Danah-Vertical Farm-P132 | Abu Dhabi | Al Danah | E4_01 | P132 | 24.4795 | 54.3638 | 2024-10-01 | 2027-09-30 |  | Vertical Farm | 1550 |  | Asteco |  |  | Feasibility | New | Design Bid Build
28 | MU-04 | Al Maqam-Vertical Farm-46 | Al Ain | Al Maqam | Al Maqam | 46 | 24.1846 | 55.6148 | 2025-04-01 | 2027-09-30 |  | Vertical Farm | 1550 |  | Asteco |  |  | Feasibility | New | Design Bid Build
29 | MU-05 | Al Fou'ah-Vertical Farm-10 | Al Ain | Al Fou'ah | Al Raqiyah | 10 | 24.3444 | 55.785 | 2025-04-01 | 2027-09-30 |  | Vertical Farm | 1550 |  | Asteco |  |  | Feasibility | New | Design Bid Build
30 | MU-06 | Zakhir-Vertical Farm-2 | Al Ain | Zakhir | Umm Al-Qatta | 2 | 24.116 | 55.6951 | 2025-04-01 | 2027-09-30 |  | Vertical Farm | 1550 |  | Asteco |  |  | Feasibility | New | Design Bid Build
31 | MU-07 | Mohamed Bin Zayed City-Vertical Farm-G1 | Abu Dhabi | Mohamed Bin Zayed City | ME9 | G1 | 24.3423 | 54.5321 | 2025-04-01 | 2027-09-30 |  | Vertical Farm | 1550 |  | Asteco |  |  | Feasibility | New | Design Bid Build
32 | MU-08 | Bani Yas-Vertical Farm-P28 | Abu Dhabi | Bani Yas | WB2_01 | P28 | 24.2961 | 54.6167 | 2025-04-01 | 2027-09-30 |  | Vertical Farm | 1550 |  | Asteco |  |  | Feasibility | New | Design Bid Build
33 | MU-09 | Shakhbout City-Vertical Farm-P10 | Abu Dhabi | Shakhbout City | MSH11 | P10 | 24.3633 | 54.6306 | 2025-04-01 | 2027-09-30 |  | Vertical Farm | 1550 |  | Asteco |  |  | Feasibility | New | Design Bid Build
34 | MU-10 | Al Shamkha-Vertical Farm-P15 | Abu Dhabi | Al Shamkha | SH3 | P15 | 24.4036 | 54.7396 | 2025-04-01 | 2027-09-30 |  | Vertical Farm | 1550 |  | Asteco |  |  | Feasibility | New | Design Bid Build
35 | MU-11 | Dhanna City-Vertical Farm-P1252 | Al Dhafrah | Dhanna City | Dannah City | P1252 | 24.0934 | 52.6462 | 2025-11-01 | 2028-05-02 |  | Vertical Farm | 1550 |  | Asteco |  |  | Feasibility | New | Design Bid Build
36 | MU-12 | Madinat Zayed-Vertical Farm-P6 | Al Dhafrah | Madinat Zayed | MZW17 | P6 | 23.6399 | 53.6902 | 2025-11-01 | 2028-05-02 |  | Vertical Farm | 1550 |  | Asteco |  |  | Feasibility | New | Design Bid Build
37 | MU-13 | Al Mirfa-Vertical Farm-P229 | Al Dhafrah | Al Mirfa | MR5 | P229 | 24.0733 | 53.4709 | 2025-11-01 | 2028-05-02 |  | Vertical Farm | 1550 |  | Asteco |  |  | Feasibility | New | Design Bid Build
38 | SC-01 | Baniyas-School-P77 | Abu Dhabi | Baniyas | Al Shawamekh School | P77 | 24.3299 | 54.6456 | 2023-03-05 | 2025-09-04 |  | School | 240 | 2620 | Capital | Geo | L&T | Construction | Retrofit | Design & Build
39 | SC-02 | Al Shahama-School-P17 | Abu Dhabi | Al Shahama | Al Reef School | P17 | 24.5416 | 54.6807 | 2023-09-18 | 2025-08-31 |  | School | 240 | 2658 | Capital | Geo | L&T | Construction | Retrofit | Design & Build
40 | SC-03 | Al Sarouj-School-P2 | Al Ain | Al Sarouj | Atika School | P2 | 24.2026 | 55.7747 | 2023-11-30 | 2025-05-31 |  | School | 240 | 2651 | Capital | Geo | L&T | Construction | Retrofit | Design & Build
41 | SC-04 | Al Sarouj-School-P16 | Al Ain | Al Sarouj | Al Salasel School | P16 | 24.1988 | 55.7977 | 2023-09-18 | 2025-05-31 |  | School | 240 | 2723 | Capital | Geo | L&T | Construction | Retrofit | Design & Build
42 | SC-05 | Al Sila-School-P43 | Al Dhafrah | Al Sila | Al Areej School | P43 | 24.0764 | 51.7656 | 2023-09-18 | 2025-05-31 |  | School | 240 | 2535 | Capital | Geo | L&T | Construction | Retrofit | Design & Build
43 | SC-06 | Madinat Zayed-School-P105 | Al Dhafrah | Madinat Zayed | HCT School | P105 | 23.644 | 53.6206 | 2023-09-26 | 2025-05-31 |  | School | 240 | 2804 | Capital | Geo | L&T | Construction | Retrofit | Design & Build
44 | SC-07 | Madinat Zayed-School-P38 | Al Dhafrah | Madinat Zayed | Hamdaniya School | P38 | 23.6541 | 53.7087 | 2023-09-26 | 2025-05-31 |  | School | 240 | 2556 | Capital | Geo | L&T | Construction | Retrofit | Design & Build
45 | MJ-17 | Saadiyat Island-Majlis-Aldar | Abu Dhabi | Saadiyat Island | Saadiyat Lagoons | Aldar | 24.5264 | 54.4496 | 2024-10-01 | 2026-09-30 |  | Majlis | 975 |  | Leodaly |  |  | Design | New | Design Bid Build
46 | MJ-18 | Balghaiylam-Majlis-Aldar | Abu Dhabi | Balghaiylam | Balghaiylam | Aldar | 24.569 | 54.541 | 2024-10-01 | 2026-09-30 |  | Majlis | 975 |  | Leodaly |  |  | Design | New | Design Bid Build
Formulas:
Completion Date = +[Commencement Date]+365*2-1
Completion Date = +[Commencement Date]+910+4-1-1

## Variable Data
Reporting Week | Project ID | Plot | Actual ID | Time Elapsed | Time Remaining | Total Duration | Key Achievements | Key Decisions | Plan % | Actual % | Variance % | Milestones | Planned Date | Actual Date | Forecast Date | Data Date | Risks & Challenges | Mitigation Measures | 4 Week Look Ahead Activities | Construction Contract Amount | Cumulative Variations | Final Contract Value | Supervision Contract amount | Authority Cost | Total Poject Cost | Certified till Date | Supervision Certified Amount | Formula 1 | Image 1 | Formula 2 | Image 2 | Formula 3 | Image 3
2024-08-12 | Madinat Al Riyad-Majlis-P3 | P3 | MJ-08 | 25 | 765 | 790 | • Sign board & Fencing Installation completion • Contractor Site Office Installation in progress . • Demarcation done by ADM for Al Shamkhah • Received Building Permits & Approved ADM Drawings | The contractor has submitted the Project Baseline (BL), and it is currently under review by AIC. | 0% | 0% | 0% | Notice to Commence | 2024-07-23 | 2024-07-23 |  | 2024-08-16 | The delay in issuing the IFC Drawings for Shamkha and Madinat Al Riyad to the contractor may affect the engineering submission / approval progress . | Although the IFC drawing is not yet available, AIC is supporting the contractor proactively to start the engineering and procurement phases.” | •PQ for Shoring, Piling, Dewatering, Waterproofing and Anti termite •Material Submittal for Concrete, Rebar and Anti termite . •Commence Site Office Activities for the Client and Engineer |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1N4Zo1nyoTRwV-8yeADEdYoewjbxnID-Z&sz=w1000 | https://drive.google.com/file/d/1N4Zo1nyoTRwV-8yeADEdYoewjbxnID-Z/view | https://drive.google.com/thumbnail?id=1u7fyxEhz5ZBdqEUOis7aQ3eZaoNHO5t6&sz=w1000 | https://drive.google.com/file/d/1u7fyxEhz5ZBdqEUOis7aQ3eZaoNHO5t6/view | https://drive.google.com/thumbnail?id=1p2iUJtng5C_UXPw0fI_hg5oznXFeBhpI&sz=w1000 | https://drive.google.com/file/d/1p2iUJtng5C_UXPw0fI_hg5oznXFeBhpI/view
2024-08-12 | Madinat Al Riyad-Majlis-P3 | P3 | MJ-08 | 25 | 765 | 790 | • Sign board & Fencing Installation completion • Contractor Site Office Installation in progress . • Demarcation done by ADM for Al Shamkhah • Received Building Permits & Approved ADM Drawings | The contractor has submitted the Project Baseline (BL), and it is currently under review by AIC. | 0% | 0% | 0% | Construction Permit | 2024-08-15 | 2024-08-15 |  | 2024-08-16 | The delay in issuing the IFC Drawings for Shamkha and Madinat Al Riyad to the contractor may affect the engineering submission / approval progress . | Although the IFC drawing is not yet available, AIC is supporting the contractor proactively to start the engineering and procurement phases.” | •PQ for Shoring, Piling, Dewatering, Waterproofing and Anti termite •Material Submittal for Concrete, Rebar and Anti termite . •Commence Site Office Activities for the Client and Engineer |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1N4Zo1nyoTRwV-8yeADEdYoewjbxnID-Z&sz=w1000 | https://drive.google.com/file/d/1N4Zo1nyoTRwV-8yeADEdYoewjbxnID-Z/view | https://drive.google.com/thumbnail?id=1u7fyxEhz5ZBdqEUOis7aQ3eZaoNHO5t6&sz=w1000 | https://drive.google.com/file/d/1u7fyxEhz5ZBdqEUOis7aQ3eZaoNHO5t6/view | https://drive.google.com/thumbnail?id=1p2iUJtng5C_UXPw0fI_hg5oznXFeBhpI&sz=w1000 | https://drive.google.com/file/d/1p2iUJtng5C_UXPw0fI_hg5oznXFeBhpI/view
2024-08-12 | Madinat Al Riyad-Majlis-P3 | P3 | MJ-08 | 25 | 765 | 790 | • Sign board & Fencing Installation completion • Contractor Site Office Installation in progress . • Demarcation done by ADM for Al Shamkhah • Received Building Permits & Approved ADM Drawings | The contractor has submitted the Project Baseline (BL), and it is currently under review by AIC. | 0% | 0% | 0% | Site Mobilization | 2024-09-19 |  | 2024-09-19 | 2024-08-16 | The delay in issuing the IFC Drawings for Shamkha and Madinat Al Riyad to the contractor may affect the engineering submission / approval progress . | Although the IFC drawing is not yet available, AIC is supporting the contractor proactively to start the engineering and procurement phases.” | •PQ for Shoring, Piling, Dewatering, Waterproofing and Anti termite •Material Submittal for Concrete, Rebar and Anti termite . •Commence Site Office Activities for the Client and Engineer |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1N4Zo1nyoTRwV-8yeADEdYoewjbxnID-Z&sz=w1000 | https://drive.google.com/file/d/1N4Zo1nyoTRwV-8yeADEdYoewjbxnID-Z/view | https://drive.google.com/thumbnail?id=1u7fyxEhz5ZBdqEUOis7aQ3eZaoNHO5t6&sz=w1000 | https://drive.google.com/file/d/1u7fyxEhz5ZBdqEUOis7aQ3eZaoNHO5t6/view | https://drive.google.com/thumbnail?id=1p2iUJtng5C_UXPw0fI_hg5oznXFeBhpI&sz=w1000 | https://drive.google.com/file/d/1p2iUJtng5C_UXPw0fI_hg5oznXFeBhpI/view
2024-08-12 | Madinat Al Riyad-Majlis-P3 | P3 | MJ-08 | 25 | 765 | 790 | • Sign board & Fencing Installation completion • Contractor Site Office Installation in progress . • Demarcation done by ADM for Al Shamkhah • Received Building Permits & Approved ADM Drawings | The contractor has submitted the Project Baseline (BL), and it is currently under review by AIC. | 0% | 0% | 0% | Substructure | 2025-11-18 |  | 2025-11-18 | 2024-08-16 | The delay in issuing the IFC Drawings for Shamkha and Madinat Al Riyad to the contractor may affect the engineering submission / approval progress . | Although the IFC drawing is not yet available, AIC is supporting the contractor proactively to start the engineering and procurement phases.” | •PQ for Shoring, Piling, Dewatering, Waterproofing and Anti termite •Material Submittal for Concrete, Rebar and Anti termite . •Commence Site Office Activities for the Client and Engineer |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1N4Zo1nyoTRwV-8yeADEdYoewjbxnID-Z&sz=w1000 | https://drive.google.com/file/d/1N4Zo1nyoTRwV-8yeADEdYoewjbxnID-Z/view | https://drive.google.com/thumbnail?id=1u7fyxEhz5ZBdqEUOis7aQ3eZaoNHO5t6&sz=w1000 | https://drive.google.com/file/d/1u7fyxEhz5ZBdqEUOis7aQ3eZaoNHO5t6/view | https://drive.google.com/thumbnail?id=1p2iUJtng5C_UXPw0fI_hg5oznXFeBhpI&sz=w1000 | https://drive.google.com/file/d/1p2iUJtng5C_UXPw0fI_hg5oznXFeBhpI/view
2024-08-12 | Madinat Al Riyad-Majlis-P3 | P3 | MJ-08 | 25 | 765 | 790 | • Sign board & Fencing Installation completion • Contractor Site Office Installation in progress . • Demarcation done by ADM for Al Shamkhah • Received Building Permits & Approved ADM Drawings | The contractor has submitted the Project Baseline (BL), and it is currently under review by AIC. | 0% | 0% | 0% | Superstructure | 2025-12-11 |  | 2025-12-11 | 2024-08-16 | The delay in issuing the IFC Drawings for Shamkha and Madinat Al Riyad to the contractor may affect the engineering submission / approval progress . | Although the IFC drawing is not yet available, AIC is supporting the contractor proactively to start the engineering and procurement phases.” | •PQ for Shoring, Piling, Dewatering, Waterproofing and Anti termite •Material Submittal for Concrete, Rebar and Anti termite . •Commence Site Office Activities for the Client and Engineer |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1N4Zo1nyoTRwV-8yeADEdYoewjbxnID-Z&sz=w1000 | https://drive.google.com/file/d/1N4Zo1nyoTRwV-8yeADEdYoewjbxnID-Z/view | https://drive.google.com/thumbnail?id=1u7fyxEhz5ZBdqEUOis7aQ3eZaoNHO5t6&sz=w1000 | https://drive.google.com/file/d/1u7fyxEhz5ZBdqEUOis7aQ3eZaoNHO5t6/view | https://drive.google.com/thumbnail?id=1p2iUJtng5C_UXPw0fI_hg5oznXFeBhpI&sz=w1000 | https://drive.google.com/file/d/1p2iUJtng5C_UXPw0fI_hg5oznXFeBhpI/view
2024-08-12 | Madinat Al Riyad-Majlis-P3 | P3 | MJ-08 | 25 | 765 | 790 | • Sign board & Fencing Installation completion • Contractor Site Office Installation in progress . • Demarcation done by ADM for Al Shamkhah • Received Building Permits & Approved ADM Drawings | The contractor has submitted the Project Baseline (BL), and it is currently under review by AIC. | 0% | 0% | 0% | MEP | 2026-06-25 |  | 2026-06-25 | 2024-08-16 | The delay in issuing the IFC Drawings for Shamkha and Madinat Al Riyad to the contractor may affect the engineering submission / approval progress . | Although the IFC drawing is not yet available, AIC is supporting the contractor proactively to start the engineering and procurement phases.” | •PQ for Shoring, Piling, Dewatering, Waterproofing and Anti termite •Material Submittal for Concrete, Rebar and Anti termite . •Commence Site Office Activities for the Client and Engineer |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1N4Zo1nyoTRwV-8yeADEdYoewjbxnID-Z&sz=w1000 | https://drive.google.com/file/d/1N4Zo1nyoTRwV-8yeADEdYoewjbxnID-Z/view | https://drive.google.com/thumbnail?id=1u7fyxEhz5ZBdqEUOis7aQ3eZaoNHO5t6&sz=w1000 | https://drive.google.com/file/d/1u7fyxEhz5ZBdqEUOis7aQ3eZaoNHO5t6/view | https://drive.google.com/thumbnail?id=1p2iUJtng5C_UXPw0fI_hg5oznXFeBhpI&sz=w1000 | https://drive.google.com/file/d/1p2iUJtng5C_UXPw0fI_hg5oznXFeBhpI/view
2024-08-12 | Madinat Al Riyad-Majlis-P3 | P3 | MJ-08 | 25 | 765 | 790 | • Sign board & Fencing Installation completion • Contractor Site Office Installation in progress . • Demarcation done by ADM for Al Shamkhah • Received Building Permits & Approved ADM Drawings | The contractor has submitted the Project Baseline (BL), and it is currently under review by AIC. | 0% | 0% | 0% | Interior Finishes | 2026-07-16 |  | 2026-07-16 | 2024-08-16 | The delay in issuing the IFC Drawings for Shamkha and Madinat Al Riyad to the contractor may affect the engineering submission / approval progress . | Although the IFC drawing is not yet available, AIC is supporting the contractor proactively to start the engineering and procurement phases.” | •PQ for Shoring, Piling, Dewatering, Waterproofing and Anti termite •Material Submittal for Concrete, Rebar and Anti termite . •Commence Site Office Activities for the Client and Engineer |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1N4Zo1nyoTRwV-8yeADEdYoewjbxnID-Z&sz=w1000 | https://drive.google.com/file/d/1N4Zo1nyoTRwV-8yeADEdYoewjbxnID-Z/view | https://drive.google.com/thumbnail?id=1u7fyxEhz5ZBdqEUOis7aQ3eZaoNHO5t6&sz=w1000 | https://drive.google.com/file/d/1u7fyxEhz5ZBdqEUOis7aQ3eZaoNHO5t6/view | https://drive.google.com/thumbnail?id=1p2iUJtng5C_UXPw0fI_hg5oznXFeBhpI&sz=w1000 | https://drive.google.com/file/d/1p2iUJtng5C_UXPw0fI_hg5oznXFeBhpI/view
2024-08-12 | Madinat Al Riyad-Majlis-P3 | P3 | MJ-08 | 25 | 765 | 790 | • Sign board & Fencing Installation completion • Contractor Site Office Installation in progress . • Demarcation done by ADM for Al Shamkhah • Received Building Permits & Approved ADM Drawings | The contractor has submitted the Project Baseline (BL), and it is currently under review by AIC. | 0% | 0% | 0% | Substantial Completion | 2026-09-23 |  | 2026-09-23 | 2024-08-16 | The delay in issuing the IFC Drawings for Shamkha and Madinat Al Riyad to the contractor may affect the engineering submission / approval progress . | Although the IFC drawing is not yet available, AIC is supporting the contractor proactively to start the engineering and procurement phases.” | •PQ for Shoring, Piling, Dewatering, Waterproofing and Anti termite •Material Submittal for Concrete, Rebar and Anti termite . •Commence Site Office Activities for the Client and Engineer |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1N4Zo1nyoTRwV-8yeADEdYoewjbxnID-Z&sz=w1000 | https://drive.google.com/file/d/1N4Zo1nyoTRwV-8yeADEdYoewjbxnID-Z/view | https://drive.google.com/thumbnail?id=1u7fyxEhz5ZBdqEUOis7aQ3eZaoNHO5t6&sz=w1000 | https://drive.google.com/file/d/1u7fyxEhz5ZBdqEUOis7aQ3eZaoNHO5t6/view | https://drive.google.com/thumbnail?id=1p2iUJtng5C_UXPw0fI_hg5oznXFeBhpI&sz=w1000 | https://drive.google.com/file/d/1p2iUJtng5C_UXPw0fI_hg5oznXFeBhpI/view
2024-08-12 | Al Shamkhah-Majlis-P6 | P6 | MJ-09 | 25 | 765 | 790 | • Sign board & Fencing Installation completion • Contractor Site Office Installation in progress . • Demarcation done by ADM for Al Shamkhah • Received Building Permits & Approved ADM Drawings | The contractor has submitted the Project Baseline (BL), and it is currently under review by AIC. | 0% | 0% | 0% | Notice to Commence | 2024-07-23 | 2024-07-23 |  | 2024-08-16 | The delay in issuing the IFC Drawings for Shamkha and Madinat Al Riyad to the contractor may affect the engineering submission / approval progress . | Although the IFC drawing is not yet available, AIC is supporting the contractor proactively to start the engineering and procurement phases.” | •PQ for Shoring, Piling, Dewatering, Waterproofing and Anti termite •Material Submittal for Concrete, Rebar and Anti termite . •Commence Site Office Activities for the Client and Engineer |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1N4Zo1nyoTRwV-8yeADEdYoewjbxnID-Z&sz=w1000 | https://drive.google.com/file/d/1N4Zo1nyoTRwV-8yeADEdYoewjbxnID-Z/view | https://drive.google.com/thumbnail?id=1u7fyxEhz5ZBdqEUOis7aQ3eZaoNHO5t6&sz=w1000 | https://drive.google.com/file/d/1u7fyxEhz5ZBdqEUOis7aQ3eZaoNHO5t6/view | https://drive.google.com/thumbnail?id=1p2iUJtng5C_UXPw0fI_hg5oznXFeBhpI&sz=w1000 | https://drive.google.com/file/d/1p2iUJtng5C_UXPw0fI_hg5oznXFeBhpI/view
2024-08-12 | Al Shamkhah-Majlis-P6 | P6 | MJ-09 | 25 | 765 | 790 | • Sign board & Fencing Installation completion • Contractor Site Office Installation in progress . • Demarcation done by ADM for Al Shamkhah • Received Building Permits & Approved ADM Drawings | The contractor has submitted the Project Baseline (BL), and it is currently under review by AIC. | 0% | 0% | 0% | Construction Permit | 2024-08-15 | 2024-08-15 |  | 2024-08-16 | The delay in issuing the IFC Drawings for Shamkha and Madinat Al Riyad to the contractor may affect the engineering submission / approval progress . | Although the IFC drawing is not yet available, AIC is supporting the contractor proactively to start the engineering and procurement phases.” | •PQ for Shoring, Piling, Dewatering, Waterproofing and Anti termite •Material Submittal for Concrete, Rebar and Anti termite . •Commence Site Office Activities for the Client and Engineer |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1N4Zo1nyoTRwV-8yeADEdYoewjbxnID-Z&sz=w1000 | https://drive.google.com/file/d/1N4Zo1nyoTRwV-8yeADEdYoewjbxnID-Z/view | https://drive.google.com/thumbnail?id=1u7fyxEhz5ZBdqEUOis7aQ3eZaoNHO5t6&sz=w1000 | https://drive.google.com/file/d/1u7fyxEhz5ZBdqEUOis7aQ3eZaoNHO5t6/view | https://drive.google.com/thumbnail?id=1p2iUJtng5C_UXPw0fI_hg5oznXFeBhpI&sz=w1000 | https://drive.google.com/file/d/1p2iUJtng5C_UXPw0fI_hg5oznXFeBhpI/view
2024-08-12 | Al Shamkhah-Majlis-P6 | P6 | MJ-09 | 25 | 765 | 790 | • Sign board & Fencing Installation completion • Contractor Site Office Installation in progress . • Demarcation done by ADM for Al Shamkhah • Received Building Permits & Approved ADM Drawings | The contractor has submitted the Project Baseline (BL), and it is currently under review by AIC. | 0% | 0% | 0% | Site Mobilization | 2024-09-19 |  | 2024-09-19 | 2024-08-16 | The delay in issuing the IFC Drawings for Shamkha and Madinat Al Riyad to the contractor may affect the engineering submission / approval progress . | Although the IFC drawing is not yet available, AIC is supporting the contractor proactively to start the engineering and procurement phases.” | •PQ for Shoring, Piling, Dewatering, Waterproofing and Anti termite •Material Submittal for Concrete, Rebar and Anti termite . •Commence Site Office Activities for the Client and Engineer |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1N4Zo1nyoTRwV-8yeADEdYoewjbxnID-Z&sz=w1000 | https://drive.google.com/file/d/1N4Zo1nyoTRwV-8yeADEdYoewjbxnID-Z/view | https://drive.google.com/thumbnail?id=1u7fyxEhz5ZBdqEUOis7aQ3eZaoNHO5t6&sz=w1000 | https://drive.google.com/file/d/1u7fyxEhz5ZBdqEUOis7aQ3eZaoNHO5t6/view | https://drive.google.com/thumbnail?id=1p2iUJtng5C_UXPw0fI_hg5oznXFeBhpI&sz=w1000 | https://drive.google.com/file/d/1p2iUJtng5C_UXPw0fI_hg5oznXFeBhpI/view
2024-08-12 | Al Shamkhah-Majlis-P6 | P6 | MJ-09 | 25 | 765 | 790 | • Sign board & Fencing Installation completion • Contractor Site Office Installation in progress . • Demarcation done by ADM for Al Shamkhah • Received Building Permits & Approved ADM Drawings | The contractor has submitted the Project Baseline (BL), and it is currently under review by AIC. | 0% | 0% | 0% | Substructure | 2025-11-18 |  | 2025-11-18 | 2024-08-16 | The delay in issuing the IFC Drawings for Shamkha and Madinat Al Riyad to the contractor may affect the engineering submission / approval progress . | Although the IFC drawing is not yet available, AIC is supporting the contractor proactively to start the engineering and procurement phases.” | •PQ for Shoring, Piling, Dewatering, Waterproofing and Anti termite •Material Submittal for Concrete, Rebar and Anti termite . •Commence Site Office Activities for the Client and Engineer |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1N4Zo1nyoTRwV-8yeADEdYoewjbxnID-Z&sz=w1000 | https://drive.google.com/file/d/1N4Zo1nyoTRwV-8yeADEdYoewjbxnID-Z/view | https://drive.google.com/thumbnail?id=1u7fyxEhz5ZBdqEUOis7aQ3eZaoNHO5t6&sz=w1000 | https://drive.google.com/file/d/1u7fyxEhz5ZBdqEUOis7aQ3eZaoNHO5t6/view | https://drive.google.com/thumbnail?id=1p2iUJtng5C_UXPw0fI_hg5oznXFeBhpI&sz=w1000 | https://drive.google.com/file/d/1p2iUJtng5C_UXPw0fI_hg5oznXFeBhpI/view
2024-08-12 | Al Shamkhah-Majlis-P6 | P6 | MJ-09 | 25 | 765 | 790 | • Sign board & Fencing Installation completion • Contractor Site Office Installation in progress . • Demarcation done by ADM for Al Shamkhah • Received Building Permits & Approved ADM Drawings | The contractor has submitted the Project Baseline (BL), and it is currently under review by AIC. | 0% | 0% | 0% | Superstructure | 2025-12-11 |  | 2025-12-11 | 2024-08-16 | The delay in issuing the IFC Drawings for Shamkha and Madinat Al Riyad to the contractor may affect the engineering submission / approval progress . | Although the IFC drawing is not yet available, AIC is supporting the contractor proactively to start the engineering and procurement phases.” | •PQ for Shoring, Piling, Dewatering, Waterproofing and Anti termite •Material Submittal for Concrete, Rebar and Anti termite . •Commence Site Office Activities for the Client and Engineer |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1N4Zo1nyoTRwV-8yeADEdYoewjbxnID-Z&sz=w1000 | https://drive.google.com/file/d/1N4Zo1nyoTRwV-8yeADEdYoewjbxnID-Z/view | https://drive.google.com/thumbnail?id=1u7fyxEhz5ZBdqEUOis7aQ3eZaoNHO5t6&sz=w1000 | https://drive.google.com/file/d/1u7fyxEhz5ZBdqEUOis7aQ3eZaoNHO5t6/view | https://drive.google.com/thumbnail?id=1p2iUJtng5C_UXPw0fI_hg5oznXFeBhpI&sz=w1000 | https://drive.google.com/file/d/1p2iUJtng5C_UXPw0fI_hg5oznXFeBhpI/view
2024-08-12 | Al Shamkhah-Majlis-P6 | P6 | MJ-09 | 25 | 765 | 790 | • Sign board & Fencing Installation completion • Contractor Site Office Installation in progress . • Demarcation done by ADM for Al Shamkhah • Received Building Permits & Approved ADM Drawings | The contractor has submitted the Project Baseline (BL), and it is currently under review by AIC. | 0% | 0% | 0% | MEP | 2026-06-25 |  | 2026-06-25 | 2024-08-16 | The delay in issuing the IFC Drawings for Shamkha and Madinat Al Riyad to the contractor may affect the engineering submission / approval progress . | Although the IFC drawing is not yet available, AIC is supporting the contractor proactively to start the engineering and procurement phases.” | •PQ for Shoring, Piling, Dewatering, Waterproofing and Anti termite •Material Submittal for Concrete, Rebar and Anti termite . •Commence Site Office Activities for the Client and Engineer |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1N4Zo1nyoTRwV-8yeADEdYoewjbxnID-Z&sz=w1000 | https://drive.google.com/file/d/1N4Zo1nyoTRwV-8yeADEdYoewjbxnID-Z/view | https://drive.google.com/thumbnail?id=1u7fyxEhz5ZBdqEUOis7aQ3eZaoNHO5t6&sz=w1000 | https://drive.google.com/file/d/1u7fyxEhz5ZBdqEUOis7aQ3eZaoNHO5t6/view | https://drive.google.com/thumbnail?id=1p2iUJtng5C_UXPw0fI_hg5oznXFeBhpI&sz=w1000 | https://drive.google.com/file/d/1p2iUJtng5C_UXPw0fI_hg5oznXFeBhpI/view
2024-08-12 | Al Shamkhah-Majlis-P6 | P6 | MJ-09 | 25 | 765 | 790 | • Sign board & Fencing Installation completion • Contractor Site Office Installation in progress . • Demarcation done by ADM for Al Shamkhah • Received Building Permits & Approved ADM Drawings | The contractor has submitted the Project Baseline (BL), and it is currently under review by AIC. | 0% | 0% | 0% | Interior Finishes | 2026-07-16 |  | 2026-07-16 | 2024-08-16 | The delay in issuing the IFC Drawings for Shamkha and Madinat Al Riyad to the contractor may affect the engineering submission / approval progress . | Although the IFC drawing is not yet available, AIC is supporting the contractor proactively to start the engineering and procurement phases.” | •PQ for Shoring, Piling, Dewatering, Waterproofing and Anti termite •Material Submittal for Concrete, Rebar and Anti termite . •Commence Site Office Activities for the Client and Engineer |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1N4Zo1nyoTRwV-8yeADEdYoewjbxnID-Z&sz=w1000 | https://drive.google.com/file/d/1N4Zo1nyoTRwV-8yeADEdYoewjbxnID-Z/view | https://drive.google.com/thumbnail?id=1u7fyxEhz5ZBdqEUOis7aQ3eZaoNHO5t6&sz=w1000 | https://drive.google.com/file/d/1u7fyxEhz5ZBdqEUOis7aQ3eZaoNHO5t6/view | https://drive.google.com/thumbnail?id=1p2iUJtng5C_UXPw0fI_hg5oznXFeBhpI&sz=w1000 | https://drive.google.com/file/d/1p2iUJtng5C_UXPw0fI_hg5oznXFeBhpI/view
2024-08-12 | Al Shamkhah-Majlis-P6 | P6 | MJ-09 | 25 | 765 | 790 | • Sign board & Fencing Installation completion • Contractor Site Office Installation in progress . • Demarcation done by ADM for Al Shamkhah • Received Building Permits & Approved ADM Drawings | The contractor has submitted the Project Baseline (BL), and it is currently under review by AIC. | 0% | 0% | 0% | Substantial Completion | 2026-09-23 |  | 2026-09-23 | 2024-08-16 | The delay in issuing the IFC Drawings for Shamkha and Madinat Al Riyad to the contractor may affect the engineering submission / approval progress . | Although the IFC drawing is not yet available, AIC is supporting the contractor proactively to start the engineering and procurement phases.” | •PQ for Shoring, Piling, Dewatering, Waterproofing and Anti termite •Material Submittal for Concrete, Rebar and Anti termite . •Commence Site Office Activities for the Client and Engineer |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1N4Zo1nyoTRwV-8yeADEdYoewjbxnID-Z&sz=w1000 | https://drive.google.com/file/d/1N4Zo1nyoTRwV-8yeADEdYoewjbxnID-Z/view | https://drive.google.com/thumbnail?id=1u7fyxEhz5ZBdqEUOis7aQ3eZaoNHO5t6&sz=w1000 | https://drive.google.com/file/d/1u7fyxEhz5ZBdqEUOis7aQ3eZaoNHO5t6/view | https://drive.google.com/thumbnail?id=1p2iUJtng5C_UXPw0fI_hg5oznXFeBhpI&sz=w1000 | https://drive.google.com/file/d/1p2iUJtng5C_UXPw0fI_hg5oznXFeBhpI/view
2024-08-12 | Baniyas-Majlis-P13 | P13 | MJ-05 | 75 | 655 | 730 | • Shoring guide wall Completed. • Secant piles in progress. • AWQAF approved Mosque Design. • ADDC accepted protection of existing FH/ water pipeline. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. & PS diversion of existing utilities at Plot P1. • Mosque design assigned to APG. | 6.33% | 3.7% | -2.63% | Notice to Commence | 2024-06-03 | 2024-06-03 |  | 2024-08-16 | •Risks / Challenges •Delay permeant piling start, due to new optimized pile submission, dated 06 Aug.2024. •Secant pile productivity rate less than planned. •Delay appoint MEP & specialist for shelter special system due to improper submission, affecting builder works & long lead items. •Appoint specialist for diversion of existing fire hydrant at Plot P1 (Mosque), to avoid delay in building permit issuance. •ADM approval for shelter design (if any) | •Mitigation Measures •Expedite technical & shop drawings submission. •Notice lack of progress issued to MAK. •Workshop meetings held with MAK to expedite re-submission. •Expedite bidders' proposals re-submission. •Sevene to initiate a time schedule for ADM review. | •Secant pile in progress. •BL resubmission. •Engineering submissions. |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1fD7AWmASsFIlXlxUeMDyf0RwmeJ-UJ8T&sz=w1000 | https://drive.google.com/file/d/1fD7AWmASsFIlXlxUeMDyf0RwmeJ-UJ8T/view | https://drive.google.com/thumbnail?id=1Ri-YAEWJjvz1PE2D5W_tY9aB0o-kD3Cx&sz=w1000 | https://drive.google.com/file/d/1Ri-YAEWJjvz1PE2D5W_tY9aB0o-kD3Cx/view | https://drive.google.com/thumbnail?id=17kFHEbF-AEDFcJjjgAoxnDoBUieKKDg3&sz=w1000 | https://drive.google.com/file/d/17kFHEbF-AEDFcJjjgAoxnDoBUieKKDg3/view
2024-08-12 | Baniyas-Majlis-P13 | P13 | MJ-05 | 75 | 655 | 730 | • Shoring guide wall Completed. • Secant piles in progress. • AWQAF approved Mosque Design. • ADDC accepted protection of existing FH/ water pipeline. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. & PS diversion of existing utilities at Plot P1. • Mosque design assigned to APG. | 6.33% | 3.7% | -2.63% | Construction Permit | 2024-06-12 | 2024-05-22 |  | 2024-08-16 | •Risks / Challenges •Delay permeant piling start, due to new optimized pile submission, dated 06 Aug.2024. •Secant pile productivity rate less than planned. •Delay appoint MEP & specialist for shelter special system due to improper submission, affecting builder works & long lead items. •Appoint specialist for diversion of existing fire hydrant at Plot P1 (Mosque), to avoid delay in building permit issuance. •ADM approval for shelter design (if any) | •Mitigation Measures •Expedite technical & shop drawings submission. •Notice lack of progress issued to MAK. •Workshop meetings held with MAK to expedite re-submission. •Expedite bidders' proposals re-submission. •Sevene to initiate a time schedule for ADM review. | •Secant pile in progress. •BL resubmission. •Engineering submissions. |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1fD7AWmASsFIlXlxUeMDyf0RwmeJ-UJ8T&sz=w1000 | https://drive.google.com/file/d/1fD7AWmASsFIlXlxUeMDyf0RwmeJ-UJ8T/view | https://drive.google.com/thumbnail?id=1Ri-YAEWJjvz1PE2D5W_tY9aB0o-kD3Cx&sz=w1000 | https://drive.google.com/file/d/1Ri-YAEWJjvz1PE2D5W_tY9aB0o-kD3Cx/view | https://drive.google.com/thumbnail?id=17kFHEbF-AEDFcJjjgAoxnDoBUieKKDg3&sz=w1000 | https://drive.google.com/file/d/17kFHEbF-AEDFcJjjgAoxnDoBUieKKDg3/view
2024-08-12 | Baniyas-Majlis-P13 | P13 | MJ-05 | 75 | 655 | 730 | • Shoring guide wall Completed. • Secant piles in progress. • AWQAF approved Mosque Design. • ADDC accepted protection of existing FH/ water pipeline. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. & PS diversion of existing utilities at Plot P1. • Mosque design assigned to APG. | 6.33% | 3.7% | -2.63% | Site Mobilization | 2024-08-02 |  | 2024-08-08 | 2024-08-16 | •Risks / Challenges •Delay permeant piling start, due to new optimized pile submission, dated 06 Aug.2024. •Secant pile productivity rate less than planned. •Delay appoint MEP & specialist for shelter special system due to improper submission, affecting builder works & long lead items. •Appoint specialist for diversion of existing fire hydrant at Plot P1 (Mosque), to avoid delay in building permit issuance. •ADM approval for shelter design (if any) | •Mitigation Measures •Expedite technical & shop drawings submission. •Notice lack of progress issued to MAK. •Workshop meetings held with MAK to expedite re-submission. •Expedite bidders' proposals re-submission. •Sevene to initiate a time schedule for ADM review. | •Secant pile in progress. •BL resubmission. •Engineering submissions. |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1fD7AWmASsFIlXlxUeMDyf0RwmeJ-UJ8T&sz=w1000 | https://drive.google.com/file/d/1fD7AWmASsFIlXlxUeMDyf0RwmeJ-UJ8T/view | https://drive.google.com/thumbnail?id=1Ri-YAEWJjvz1PE2D5W_tY9aB0o-kD3Cx&sz=w1000 | https://drive.google.com/file/d/1Ri-YAEWJjvz1PE2D5W_tY9aB0o-kD3Cx/view | https://drive.google.com/thumbnail?id=17kFHEbF-AEDFcJjjgAoxnDoBUieKKDg3&sz=w1000 | https://drive.google.com/file/d/17kFHEbF-AEDFcJjjgAoxnDoBUieKKDg3/view
2024-08-12 | Baniyas-Majlis-P13 | P13 | MJ-05 | 75 | 655 | 730 | • Shoring guide wall Completed. • Secant piles in progress. • AWQAF approved Mosque Design. • ADDC accepted protection of existing FH/ water pipeline. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. & PS diversion of existing utilities at Plot P1. • Mosque design assigned to APG. | 6.33% | 3.7% | -2.63% | Shoring Drilling & Casting | 2024-09-25 |  | 2024-09-25 | 2024-08-16 | •Risks / Challenges •Delay permeant piling start, due to new optimized pile submission, dated 06 Aug.2024. •Secant pile productivity rate less than planned. •Delay appoint MEP & specialist for shelter special system due to improper submission, affecting builder works & long lead items. •Appoint specialist for diversion of existing fire hydrant at Plot P1 (Mosque), to avoid delay in building permit issuance. •ADM approval for shelter design (if any) | •Mitigation Measures •Expedite technical & shop drawings submission. •Notice lack of progress issued to MAK. •Workshop meetings held with MAK to expedite re-submission. •Expedite bidders' proposals re-submission. •Sevene to initiate a time schedule for ADM review. | •Secant pile in progress. •BL resubmission. •Engineering submissions. |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1fD7AWmASsFIlXlxUeMDyf0RwmeJ-UJ8T&sz=w1000 | https://drive.google.com/file/d/1fD7AWmASsFIlXlxUeMDyf0RwmeJ-UJ8T/view | https://drive.google.com/thumbnail?id=1Ri-YAEWJjvz1PE2D5W_tY9aB0o-kD3Cx&sz=w1000 | https://drive.google.com/file/d/1Ri-YAEWJjvz1PE2D5W_tY9aB0o-kD3Cx/view | https://drive.google.com/thumbnail?id=17kFHEbF-AEDFcJjjgAoxnDoBUieKKDg3&sz=w1000 | https://drive.google.com/file/d/17kFHEbF-AEDFcJjjgAoxnDoBUieKKDg3/view
2024-08-12 | Baniyas-Majlis-P13 | P13 | MJ-05 | 75 | 655 | 730 | • Shoring guide wall Completed. • Secant piles in progress. • AWQAF approved Mosque Design. • ADDC accepted protection of existing FH/ water pipeline. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. & PS diversion of existing utilities at Plot P1. • Mosque design assigned to APG. | 6.33% | 3.7% | -2.63% | Piling Drilling & Casting | 2024-10-20 |  | 2024-10-20 | 2024-08-16 | •Risks / Challenges •Delay permeant piling start, due to new optimized pile submission, dated 06 Aug.2024. •Secant pile productivity rate less than planned. •Delay appoint MEP & specialist for shelter special system due to improper submission, affecting builder works & long lead items. •Appoint specialist for diversion of existing fire hydrant at Plot P1 (Mosque), to avoid delay in building permit issuance. •ADM approval for shelter design (if any) | •Mitigation Measures •Expedite technical & shop drawings submission. •Notice lack of progress issued to MAK. •Workshop meetings held with MAK to expedite re-submission. •Expedite bidders' proposals re-submission. •Sevene to initiate a time schedule for ADM review. | •Secant pile in progress. •BL resubmission. •Engineering submissions. |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1fD7AWmASsFIlXlxUeMDyf0RwmeJ-UJ8T&sz=w1000 | https://drive.google.com/file/d/1fD7AWmASsFIlXlxUeMDyf0RwmeJ-UJ8T/view | https://drive.google.com/thumbnail?id=1Ri-YAEWJjvz1PE2D5W_tY9aB0o-kD3Cx&sz=w1000 | https://drive.google.com/file/d/1Ri-YAEWJjvz1PE2D5W_tY9aB0o-kD3Cx/view | https://drive.google.com/thumbnail?id=17kFHEbF-AEDFcJjjgAoxnDoBUieKKDg3&sz=w1000 | https://drive.google.com/file/d/17kFHEbF-AEDFcJjjgAoxnDoBUieKKDg3/view
2024-08-12 | Baniyas-Majlis-P13 | P13 | MJ-05 | 75 | 655 | 730 | • Shoring guide wall Completed. • Secant piles in progress. • AWQAF approved Mosque Design. • ADDC accepted protection of existing FH/ water pipeline. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. & PS diversion of existing utilities at Plot P1. • Mosque design assigned to APG. | 6.33% | 3.7% | -2.63% | Excavation | 2024-12-08 |  | 2024-12-08 | 2024-08-16 | •Risks / Challenges •Delay permeant piling start, due to new optimized pile submission, dated 06 Aug.2024. •Secant pile productivity rate less than planned. •Delay appoint MEP & specialist for shelter special system due to improper submission, affecting builder works & long lead items. •Appoint specialist for diversion of existing fire hydrant at Plot P1 (Mosque), to avoid delay in building permit issuance. •ADM approval for shelter design (if any) | •Mitigation Measures •Expedite technical & shop drawings submission. •Notice lack of progress issued to MAK. •Workshop meetings held with MAK to expedite re-submission. •Expedite bidders' proposals re-submission. •Sevene to initiate a time schedule for ADM review. | •Secant pile in progress. •BL resubmission. •Engineering submissions. |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1fD7AWmASsFIlXlxUeMDyf0RwmeJ-UJ8T&sz=w1000 | https://drive.google.com/file/d/1fD7AWmASsFIlXlxUeMDyf0RwmeJ-UJ8T/view | https://drive.google.com/thumbnail?id=1Ri-YAEWJjvz1PE2D5W_tY9aB0o-kD3Cx&sz=w1000 | https://drive.google.com/file/d/1Ri-YAEWJjvz1PE2D5W_tY9aB0o-kD3Cx/view | https://drive.google.com/thumbnail?id=17kFHEbF-AEDFcJjjgAoxnDoBUieKKDg3&sz=w1000 | https://drive.google.com/file/d/17kFHEbF-AEDFcJjjgAoxnDoBUieKKDg3/view
2024-08-12 | Baniyas-Majlis-P13 | P13 | MJ-05 | 75 | 655 | 730 | • Shoring guide wall Completed. • Secant piles in progress. • AWQAF approved Mosque Design. • ADDC accepted protection of existing FH/ water pipeline. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. & PS diversion of existing utilities at Plot P1. • Mosque design assigned to APG. | 6.33% | 3.7% | -2.63% | Substructure | 2025-03-25 |  | 2025-03-25 | 2024-08-16 | •Risks / Challenges •Delay permeant piling start, due to new optimized pile submission, dated 06 Aug.2024. •Secant pile productivity rate less than planned. •Delay appoint MEP & specialist for shelter special system due to improper submission, affecting builder works & long lead items. •Appoint specialist for diversion of existing fire hydrant at Plot P1 (Mosque), to avoid delay in building permit issuance. •ADM approval for shelter design (if any) | •Mitigation Measures •Expedite technical & shop drawings submission. •Notice lack of progress issued to MAK. •Workshop meetings held with MAK to expedite re-submission. •Expedite bidders' proposals re-submission. •Sevene to initiate a time schedule for ADM review. | •Secant pile in progress. •BL resubmission. •Engineering submissions. |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1fD7AWmASsFIlXlxUeMDyf0RwmeJ-UJ8T&sz=w1000 | https://drive.google.com/file/d/1fD7AWmASsFIlXlxUeMDyf0RwmeJ-UJ8T/view | https://drive.google.com/thumbnail?id=1Ri-YAEWJjvz1PE2D5W_tY9aB0o-kD3Cx&sz=w1000 | https://drive.google.com/file/d/1Ri-YAEWJjvz1PE2D5W_tY9aB0o-kD3Cx/view | https://drive.google.com/thumbnail?id=17kFHEbF-AEDFcJjjgAoxnDoBUieKKDg3&sz=w1000 | https://drive.google.com/file/d/17kFHEbF-AEDFcJjjgAoxnDoBUieKKDg3/view
2024-08-12 | Baniyas-Majlis-P13 | P13 | MJ-05 | 75 | 655 | 730 | • Shoring guide wall Completed. • Secant piles in progress. • AWQAF approved Mosque Design. • ADDC accepted protection of existing FH/ water pipeline. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. & PS diversion of existing utilities at Plot P1. • Mosque design assigned to APG. | 6.33% | 3.7% | -2.63% | Superstructure | 2025-07-18 |  | 2025-07-18 | 2024-08-16 | •Risks / Challenges •Delay permeant piling start, due to new optimized pile submission, dated 06 Aug.2024. •Secant pile productivity rate less than planned. •Delay appoint MEP & specialist for shelter special system due to improper submission, affecting builder works & long lead items. •Appoint specialist for diversion of existing fire hydrant at Plot P1 (Mosque), to avoid delay in building permit issuance. •ADM approval for shelter design (if any) | •Mitigation Measures •Expedite technical & shop drawings submission. •Notice lack of progress issued to MAK. •Workshop meetings held with MAK to expedite re-submission. •Expedite bidders' proposals re-submission. •Sevene to initiate a time schedule for ADM review. | •Secant pile in progress. •BL resubmission. •Engineering submissions. |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1fD7AWmASsFIlXlxUeMDyf0RwmeJ-UJ8T&sz=w1000 | https://drive.google.com/file/d/1fD7AWmASsFIlXlxUeMDyf0RwmeJ-UJ8T/view | https://drive.google.com/thumbnail?id=1Ri-YAEWJjvz1PE2D5W_tY9aB0o-kD3Cx&sz=w1000 | https://drive.google.com/file/d/1Ri-YAEWJjvz1PE2D5W_tY9aB0o-kD3Cx/view | https://drive.google.com/thumbnail?id=17kFHEbF-AEDFcJjjgAoxnDoBUieKKDg3&sz=w1000 | https://drive.google.com/file/d/17kFHEbF-AEDFcJjjgAoxnDoBUieKKDg3/view
2024-08-12 | Baniyas-Majlis-P13 | P13 | MJ-05 | 75 | 655 | 730 | • Shoring guide wall Completed. • Secant piles in progress. • AWQAF approved Mosque Design. • ADDC accepted protection of existing FH/ water pipeline. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. & PS diversion of existing utilities at Plot P1. • Mosque design assigned to APG. | 6.33% | 3.7% | -2.63% | MEP & Finishes | 2026-06-02 |  | 2026-06-02 | 2024-08-16 | •Risks / Challenges •Delay permeant piling start, due to new optimized pile submission, dated 06 Aug.2024. •Secant pile productivity rate less than planned. •Delay appoint MEP & specialist for shelter special system due to improper submission, affecting builder works & long lead items. •Appoint specialist for diversion of existing fire hydrant at Plot P1 (Mosque), to avoid delay in building permit issuance. •ADM approval for shelter design (if any) | •Mitigation Measures •Expedite technical & shop drawings submission. •Notice lack of progress issued to MAK. •Workshop meetings held with MAK to expedite re-submission. •Expedite bidders' proposals re-submission. •Sevene to initiate a time schedule for ADM review. | •Secant pile in progress. •BL resubmission. •Engineering submissions. |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1fD7AWmASsFIlXlxUeMDyf0RwmeJ-UJ8T&sz=w1000 | https://drive.google.com/file/d/1fD7AWmASsFIlXlxUeMDyf0RwmeJ-UJ8T/view | https://drive.google.com/thumbnail?id=1Ri-YAEWJjvz1PE2D5W_tY9aB0o-kD3Cx&sz=w1000 | https://drive.google.com/file/d/1Ri-YAEWJjvz1PE2D5W_tY9aB0o-kD3Cx/view | https://drive.google.com/thumbnail?id=17kFHEbF-AEDFcJjjgAoxnDoBUieKKDg3&sz=w1000 | https://drive.google.com/file/d/17kFHEbF-AEDFcJjjgAoxnDoBUieKKDg3/view
2024-08-12 | Baniyas-Majlis-P13 | P13 | MJ-05 | 75 | 655 | 730 | • Shoring guide wall Completed. • Secant piles in progress. • AWQAF approved Mosque Design. • ADDC accepted protection of existing FH/ water pipeline. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. & PS diversion of existing utilities at Plot P1. • Mosque design assigned to APG. | 6.33% | 3.7% | -2.63% | Authorities NOCs/BCC | 2026-05-11 |  | 2026-05-11 | 2024-08-16 | •Risks / Challenges •Delay permeant piling start, due to new optimized pile submission, dated 06 Aug.2024. •Secant pile productivity rate less than planned. •Delay appoint MEP & specialist for shelter special system due to improper submission, affecting builder works & long lead items. •Appoint specialist for diversion of existing fire hydrant at Plot P1 (Mosque), to avoid delay in building permit issuance. •ADM approval for shelter design (if any) | •Mitigation Measures •Expedite technical & shop drawings submission. •Notice lack of progress issued to MAK. •Workshop meetings held with MAK to expedite re-submission. •Expedite bidders' proposals re-submission. •Sevene to initiate a time schedule for ADM review. | •Secant pile in progress. •BL resubmission. •Engineering submissions. |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1fD7AWmASsFIlXlxUeMDyf0RwmeJ-UJ8T&sz=w1000 | https://drive.google.com/file/d/1fD7AWmASsFIlXlxUeMDyf0RwmeJ-UJ8T/view | https://drive.google.com/thumbnail?id=1Ri-YAEWJjvz1PE2D5W_tY9aB0o-kD3Cx&sz=w1000 | https://drive.google.com/file/d/1Ri-YAEWJjvz1PE2D5W_tY9aB0o-kD3Cx/view | https://drive.google.com/thumbnail?id=17kFHEbF-AEDFcJjjgAoxnDoBUieKKDg3&sz=w1000 | https://drive.google.com/file/d/17kFHEbF-AEDFcJjjgAoxnDoBUieKKDg3/view
2024-08-12 | Baniyas-Majlis-P13 | P13 | MJ-05 | 75 | 655 | 730 | • Shoring guide wall Completed. • Secant piles in progress. • AWQAF approved Mosque Design. • ADDC accepted protection of existing FH/ water pipeline. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. & PS diversion of existing utilities at Plot P1. • Mosque design assigned to APG. | 6.33% | 3.7% | -2.63% | External Works | 2026-05-15 |  | 2026-05-15 | 2024-08-16 | •Risks / Challenges •Delay permeant piling start, due to new optimized pile submission, dated 06 Aug.2024. •Secant pile productivity rate less than planned. •Delay appoint MEP & specialist for shelter special system due to improper submission, affecting builder works & long lead items. •Appoint specialist for diversion of existing fire hydrant at Plot P1 (Mosque), to avoid delay in building permit issuance. •ADM approval for shelter design (if any) | •Mitigation Measures •Expedite technical & shop drawings submission. •Notice lack of progress issued to MAK. •Workshop meetings held with MAK to expedite re-submission. •Expedite bidders' proposals re-submission. •Sevene to initiate a time schedule for ADM review. | •Secant pile in progress. •BL resubmission. •Engineering submissions. |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1fD7AWmASsFIlXlxUeMDyf0RwmeJ-UJ8T&sz=w1000 | https://drive.google.com/file/d/1fD7AWmASsFIlXlxUeMDyf0RwmeJ-UJ8T/view | https://drive.google.com/thumbnail?id=1Ri-YAEWJjvz1PE2D5W_tY9aB0o-kD3Cx&sz=w1000 | https://drive.google.com/file/d/1Ri-YAEWJjvz1PE2D5W_tY9aB0o-kD3Cx/view | https://drive.google.com/thumbnail?id=17kFHEbF-AEDFcJjjgAoxnDoBUieKKDg3&sz=w1000 | https://drive.google.com/file/d/17kFHEbF-AEDFcJjjgAoxnDoBUieKKDg3/view
2024-08-12 | Baniyas-Majlis-P13 | P13 | MJ-05 | 75 | 655 | 730 | • Shoring guide wall Completed. • Secant piles in progress. • AWQAF approved Mosque Design. • ADDC accepted protection of existing FH/ water pipeline. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. & PS diversion of existing utilities at Plot P1. • Mosque design assigned to APG. | 6.33% | 3.7% | -2.63% | Testing & Commissioning | 2026-06-01 |  | 2026-06-01 | 2024-08-16 | •Risks / Challenges •Delay permeant piling start, due to new optimized pile submission, dated 06 Aug.2024. •Secant pile productivity rate less than planned. •Delay appoint MEP & specialist for shelter special system due to improper submission, affecting builder works & long lead items. •Appoint specialist for diversion of existing fire hydrant at Plot P1 (Mosque), to avoid delay in building permit issuance. •ADM approval for shelter design (if any) | •Mitigation Measures •Expedite technical & shop drawings submission. •Notice lack of progress issued to MAK. •Workshop meetings held with MAK to expedite re-submission. •Expedite bidders' proposals re-submission. •Sevene to initiate a time schedule for ADM review. | •Secant pile in progress. •BL resubmission. •Engineering submissions. |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1fD7AWmASsFIlXlxUeMDyf0RwmeJ-UJ8T&sz=w1000 | https://drive.google.com/file/d/1fD7AWmASsFIlXlxUeMDyf0RwmeJ-UJ8T/view | https://drive.google.com/thumbnail?id=1Ri-YAEWJjvz1PE2D5W_tY9aB0o-kD3Cx&sz=w1000 | https://drive.google.com/file/d/1Ri-YAEWJjvz1PE2D5W_tY9aB0o-kD3Cx/view | https://drive.google.com/thumbnail?id=17kFHEbF-AEDFcJjjgAoxnDoBUieKKDg3&sz=w1000 | https://drive.google.com/file/d/17kFHEbF-AEDFcJjjgAoxnDoBUieKKDg3/view
2024-08-12 | Baniyas-Majlis-P13 | P13 | MJ-05 | 75 | 655 | 730 | • Shoring guide wall Completed. • Secant piles in progress. • AWQAF approved Mosque Design. • ADDC accepted protection of existing FH/ water pipeline. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. & PS diversion of existing utilities at Plot P1. • Mosque design assigned to APG. | 6.33% | 3.7% | -2.63% | Substantial Completion | 2026-06-02 |  | 2026-06-02 | 2024-08-16 | •Risks / Challenges •Delay permeant piling start, due to new optimized pile submission, dated 06 Aug.2024. •Secant pile productivity rate less than planned. •Delay appoint MEP & specialist for shelter special system due to improper submission, affecting builder works & long lead items. •Appoint specialist for diversion of existing fire hydrant at Plot P1 (Mosque), to avoid delay in building permit issuance. •ADM approval for shelter design (if any) | •Mitigation Measures •Expedite technical & shop drawings submission. •Notice lack of progress issued to MAK. •Workshop meetings held with MAK to expedite re-submission. •Expedite bidders' proposals re-submission. •Sevene to initiate a time schedule for ADM review. | •Secant pile in progress. •BL resubmission. •Engineering submissions. |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1fD7AWmASsFIlXlxUeMDyf0RwmeJ-UJ8T&sz=w1000 | https://drive.google.com/file/d/1fD7AWmASsFIlXlxUeMDyf0RwmeJ-UJ8T/view | https://drive.google.com/thumbnail?id=1Ri-YAEWJjvz1PE2D5W_tY9aB0o-kD3Cx&sz=w1000 | https://drive.google.com/file/d/1Ri-YAEWJjvz1PE2D5W_tY9aB0o-kD3Cx/view | https://drive.google.com/thumbnail?id=17kFHEbF-AEDFcJjjgAoxnDoBUieKKDg3&sz=w1000 | https://drive.google.com/file/d/17kFHEbF-AEDFcJjjgAoxnDoBUieKKDg3/view
2024-08-12 | Zayed City-Majlis-P17 | P17 | MJ-04 | 75 | 655 | 730 | • Shoring guide wall in progress. • Shoring pilling in progress. • Site office utilities connection in progress. • Welfare facilities in progress. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. | 6.33% | 3.29% | -3.04% | Notice to Commence | 2024-06-03 | 2024-06-03 |  | 2024-08-16 | • Risks / Challenges • Delay permeant piling start, due to new optimized pile submission, dated 06 Aug.2024. • Secant pile productivity rate less than planned. • Delay appoint MEP & specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval for shelter design (if any) | • Mitigation Measures • Expedite technical & shop drawings submission. • Notice lack of progress issued to MAK. • Workshop meetings held with MAK to expedite re-submission. • sevene to initiate a time schedule for ADM review. | • Shoring Guide wall completion. • Secant pile in progress. • BL resubmission. • Engineering submissions. |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1fD7AWmASsFIlXlxUeMDyf0RwmeJ-UJ8T&sz=w1000 | https://drive.google.com/file/d/1fD7AWmASsFIlXlxUeMDyf0RwmeJ-UJ8T/view | https://drive.google.com/thumbnail?id=1Ri-YAEWJjvz1PE2D5W_tY9aB0o-kD3Cx&sz=w1000 | https://drive.google.com/file/d/1Ri-YAEWJjvz1PE2D5W_tY9aB0o-kD3Cx/view | https://drive.google.com/thumbnail?id=17kFHEbF-AEDFcJjjgAoxnDoBUieKKDg3&sz=w1000 | https://drive.google.com/file/d/17kFHEbF-AEDFcJjjgAoxnDoBUieKKDg3/view
2024-08-12 | Zayed City-Majlis-P17 | P17 | MJ-04 | 75 | 655 | 730 | • Shoring guide wall in progress. • Shoring pilling in progress. • Site office utilities connection in progress. • Welfare facilities in progress. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. | 6.33% | 3.29% | -3.04% | Construction Permit | 2024-06-12 | 2024-05-27 |  | 2024-08-16 | • Risks / Challenges • Delay permeant piling start, due to new optimized pile submission, dated 06 Aug.2024. • Secant pile productivity rate less than planned. • Delay appoint MEP & specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval for shelter design (if any) | • Mitigation Measures • Expedite technical & shop drawings submission. • Notice lack of progress issued to MAK. • Workshop meetings held with MAK to expedite re-submission. • sevene to initiate a time schedule for ADM review. | • Shoring Guide wall completion. • Secant pile in progress. • BL resubmission. • Engineering submissions. |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1fD7AWmASsFIlXlxUeMDyf0RwmeJ-UJ8T&sz=w1000 | https://drive.google.com/file/d/1fD7AWmASsFIlXlxUeMDyf0RwmeJ-UJ8T/view | https://drive.google.com/thumbnail?id=1Ri-YAEWJjvz1PE2D5W_tY9aB0o-kD3Cx&sz=w1000 | https://drive.google.com/file/d/1Ri-YAEWJjvz1PE2D5W_tY9aB0o-kD3Cx/view | https://drive.google.com/thumbnail?id=17kFHEbF-AEDFcJjjgAoxnDoBUieKKDg3&sz=w1000 | https://drive.google.com/file/d/17kFHEbF-AEDFcJjjgAoxnDoBUieKKDg3/view
2024-08-12 | Zayed City-Majlis-P17 | P17 | MJ-04 | 75 | 655 | 730 | • Shoring guide wall in progress. • Shoring pilling in progress. • Site office utilities connection in progress. • Welfare facilities in progress. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. | 6.33% | 3.29% | -3.04% | Site Mobilization | 2024-08-02 | 2024-08-03 |  | 2024-08-16 | • Risks / Challenges • Delay permeant piling start, due to new optimized pile submission, dated 06 Aug.2024. • Secant pile productivity rate less than planned. • Delay appoint MEP & specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval for shelter design (if any) | • Mitigation Measures • Expedite technical & shop drawings submission. • Notice lack of progress issued to MAK. • Workshop meetings held with MAK to expedite re-submission. • sevene to initiate a time schedule for ADM review. | • Shoring Guide wall completion. • Secant pile in progress. • BL resubmission. • Engineering submissions. |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1fD7AWmASsFIlXlxUeMDyf0RwmeJ-UJ8T&sz=w1000 | https://drive.google.com/file/d/1fD7AWmASsFIlXlxUeMDyf0RwmeJ-UJ8T/view | https://drive.google.com/thumbnail?id=1Ri-YAEWJjvz1PE2D5W_tY9aB0o-kD3Cx&sz=w1000 | https://drive.google.com/file/d/1Ri-YAEWJjvz1PE2D5W_tY9aB0o-kD3Cx/view | https://drive.google.com/thumbnail?id=17kFHEbF-AEDFcJjjgAoxnDoBUieKKDg3&sz=w1000 | https://drive.google.com/file/d/17kFHEbF-AEDFcJjjgAoxnDoBUieKKDg3/view
2024-08-12 | Zayed City-Majlis-P17 | P17 | MJ-04 | 75 | 655 | 730 | • Shoring guide wall in progress. • Shoring pilling in progress. • Site office utilities connection in progress. • Welfare facilities in progress. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. | 6.33% | 3.29% | -3.04% | Shoring Drilling & Casting | 2024-09-26 |  | 2024-09-26 | 2024-08-16 | • Risks / Challenges • Delay permeant piling start, due to new optimized pile submission, dated 06 Aug.2024. • Secant pile productivity rate less than planned. • Delay appoint MEP & specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval for shelter design (if any) | • Mitigation Measures • Expedite technical & shop drawings submission. • Notice lack of progress issued to MAK. • Workshop meetings held with MAK to expedite re-submission. • sevene to initiate a time schedule for ADM review. | • Shoring Guide wall completion. • Secant pile in progress. • BL resubmission. • Engineering submissions. |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1fD7AWmASsFIlXlxUeMDyf0RwmeJ-UJ8T&sz=w1000 | https://drive.google.com/file/d/1fD7AWmASsFIlXlxUeMDyf0RwmeJ-UJ8T/view | https://drive.google.com/thumbnail?id=1Ri-YAEWJjvz1PE2D5W_tY9aB0o-kD3Cx&sz=w1000 | https://drive.google.com/file/d/1Ri-YAEWJjvz1PE2D5W_tY9aB0o-kD3Cx/view | https://drive.google.com/thumbnail?id=17kFHEbF-AEDFcJjjgAoxnDoBUieKKDg3&sz=w1000 | https://drive.google.com/file/d/17kFHEbF-AEDFcJjjgAoxnDoBUieKKDg3/view
2024-08-12 | Zayed City-Majlis-P17 | P17 | MJ-04 | 75 | 655 | 730 | • Shoring guide wall in progress. • Shoring pilling in progress. • Site office utilities connection in progress. • Welfare facilities in progress. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. | 6.33% | 3.29% | -3.04% | Piling Drilling & Casting | 2024-10-21 |  | 2024-10-21 | 2024-08-16 | • Risks / Challenges • Delay permeant piling start, due to new optimized pile submission, dated 06 Aug.2024. • Secant pile productivity rate less than planned. • Delay appoint MEP & specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval for shelter design (if any) | • Mitigation Measures • Expedite technical & shop drawings submission. • Notice lack of progress issued to MAK. • Workshop meetings held with MAK to expedite re-submission. • sevene to initiate a time schedule for ADM review. | • Shoring Guide wall completion. • Secant pile in progress. • BL resubmission. • Engineering submissions. |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1fD7AWmASsFIlXlxUeMDyf0RwmeJ-UJ8T&sz=w1000 | https://drive.google.com/file/d/1fD7AWmASsFIlXlxUeMDyf0RwmeJ-UJ8T/view | https://drive.google.com/thumbnail?id=1Ri-YAEWJjvz1PE2D5W_tY9aB0o-kD3Cx&sz=w1000 | https://drive.google.com/file/d/1Ri-YAEWJjvz1PE2D5W_tY9aB0o-kD3Cx/view | https://drive.google.com/thumbnail?id=17kFHEbF-AEDFcJjjgAoxnDoBUieKKDg3&sz=w1000 | https://drive.google.com/file/d/17kFHEbF-AEDFcJjjgAoxnDoBUieKKDg3/view
2024-08-12 | Zayed City-Majlis-P17 | P17 | MJ-04 | 75 | 655 | 730 | • Shoring guide wall in progress. • Shoring pilling in progress. • Site office utilities connection in progress. • Welfare facilities in progress. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. | 6.33% | 3.29% | -3.04% | Excavation | 2024-12-12 |  | 2024-12-12 | 2024-08-16 | • Risks / Challenges • Delay permeant piling start, due to new optimized pile submission, dated 06 Aug.2024. • Secant pile productivity rate less than planned. • Delay appoint MEP & specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval for shelter design (if any) | • Mitigation Measures • Expedite technical & shop drawings submission. • Notice lack of progress issued to MAK. • Workshop meetings held with MAK to expedite re-submission. • sevene to initiate a time schedule for ADM review. | • Shoring Guide wall completion. • Secant pile in progress. • BL resubmission. • Engineering submissions. |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1fD7AWmASsFIlXlxUeMDyf0RwmeJ-UJ8T&sz=w1000 | https://drive.google.com/file/d/1fD7AWmASsFIlXlxUeMDyf0RwmeJ-UJ8T/view | https://drive.google.com/thumbnail?id=1Ri-YAEWJjvz1PE2D5W_tY9aB0o-kD3Cx&sz=w1000 | https://drive.google.com/file/d/1Ri-YAEWJjvz1PE2D5W_tY9aB0o-kD3Cx/view | https://drive.google.com/thumbnail?id=17kFHEbF-AEDFcJjjgAoxnDoBUieKKDg3&sz=w1000 | https://drive.google.com/file/d/17kFHEbF-AEDFcJjjgAoxnDoBUieKKDg3/view
2024-08-12 | Zayed City-Majlis-P17 | P17 | MJ-04 | 75 | 655 | 730 | • Shoring guide wall in progress. • Shoring pilling in progress. • Site office utilities connection in progress. • Welfare facilities in progress. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. | 6.33% | 3.29% | -3.04% | Substructure | 2025-04-04 |  | 2025-04-04 | 2024-08-16 | • Risks / Challenges • Delay permeant piling start, due to new optimized pile submission, dated 06 Aug.2024. • Secant pile productivity rate less than planned. • Delay appoint MEP & specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval for shelter design (if any) | • Mitigation Measures • Expedite technical & shop drawings submission. • Notice lack of progress issued to MAK. • Workshop meetings held with MAK to expedite re-submission. • sevene to initiate a time schedule for ADM review. | • Shoring Guide wall completion. • Secant pile in progress. • BL resubmission. • Engineering submissions. |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1fD7AWmASsFIlXlxUeMDyf0RwmeJ-UJ8T&sz=w1000 | https://drive.google.com/file/d/1fD7AWmASsFIlXlxUeMDyf0RwmeJ-UJ8T/view | https://drive.google.com/thumbnail?id=1Ri-YAEWJjvz1PE2D5W_tY9aB0o-kD3Cx&sz=w1000 | https://drive.google.com/file/d/1Ri-YAEWJjvz1PE2D5W_tY9aB0o-kD3Cx/view | https://drive.google.com/thumbnail?id=17kFHEbF-AEDFcJjjgAoxnDoBUieKKDg3&sz=w1000 | https://drive.google.com/file/d/17kFHEbF-AEDFcJjjgAoxnDoBUieKKDg3/view
2024-08-12 | Zayed City-Majlis-P17 | P17 | MJ-04 | 75 | 655 | 730 | • Shoring guide wall in progress. • Shoring pilling in progress. • Site office utilities connection in progress. • Welfare facilities in progress. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. | 6.33% | 3.29% | -3.04% | Superstructure | 2025-07-21 |  | 2025-07-21 | 2024-08-16 | • Risks / Challenges • Delay permeant piling start, due to new optimized pile submission, dated 06 Aug.2024. • Secant pile productivity rate less than planned. • Delay appoint MEP & specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval for shelter design (if any) | • Mitigation Measures • Expedite technical & shop drawings submission. • Notice lack of progress issued to MAK. • Workshop meetings held with MAK to expedite re-submission. • sevene to initiate a time schedule for ADM review. | • Shoring Guide wall completion. • Secant pile in progress. • BL resubmission. • Engineering submissions. |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1fD7AWmASsFIlXlxUeMDyf0RwmeJ-UJ8T&sz=w1000 | https://drive.google.com/file/d/1fD7AWmASsFIlXlxUeMDyf0RwmeJ-UJ8T/view | https://drive.google.com/thumbnail?id=1Ri-YAEWJjvz1PE2D5W_tY9aB0o-kD3Cx&sz=w1000 | https://drive.google.com/file/d/1Ri-YAEWJjvz1PE2D5W_tY9aB0o-kD3Cx/view | https://drive.google.com/thumbnail?id=17kFHEbF-AEDFcJjjgAoxnDoBUieKKDg3&sz=w1000 | https://drive.google.com/file/d/17kFHEbF-AEDFcJjjgAoxnDoBUieKKDg3/view
2024-08-12 | Zayed City-Majlis-P17 | P17 | MJ-04 | 75 | 655 | 730 | • Shoring guide wall in progress. • Shoring pilling in progress. • Site office utilities connection in progress. • Welfare facilities in progress. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. | 6.33% | 3.29% | -3.04% | MEP & Finishes | 2026-06-02 |  | 2026-06-02 | 2024-08-16 | • Risks / Challenges • Delay permeant piling start, due to new optimized pile submission, dated 06 Aug.2024. • Secant pile productivity rate less than planned. • Delay appoint MEP & specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval for shelter design (if any) | • Mitigation Measures • Expedite technical & shop drawings submission. • Notice lack of progress issued to MAK. • Workshop meetings held with MAK to expedite re-submission. • sevene to initiate a time schedule for ADM review. | • Shoring Guide wall completion. • Secant pile in progress. • BL resubmission. • Engineering submissions. |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1fD7AWmASsFIlXlxUeMDyf0RwmeJ-UJ8T&sz=w1000 | https://drive.google.com/file/d/1fD7AWmASsFIlXlxUeMDyf0RwmeJ-UJ8T/view | https://drive.google.com/thumbnail?id=1Ri-YAEWJjvz1PE2D5W_tY9aB0o-kD3Cx&sz=w1000 | https://drive.google.com/file/d/1Ri-YAEWJjvz1PE2D5W_tY9aB0o-kD3Cx/view | https://drive.google.com/thumbnail?id=17kFHEbF-AEDFcJjjgAoxnDoBUieKKDg3&sz=w1000 | https://drive.google.com/file/d/17kFHEbF-AEDFcJjjgAoxnDoBUieKKDg3/view
2024-08-12 | Zayed City-Majlis-P17 | P17 | MJ-04 | 75 | 655 | 730 | • Shoring guide wall in progress. • Shoring pilling in progress. • Site office utilities connection in progress. • Welfare facilities in progress. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. | 6.33% | 3.29% | -3.04% | Authorities NOCs/BCC | 2026-05-21 |  | 2026-05-21 | 2024-08-16 | • Risks / Challenges • Delay permeant piling start, due to new optimized pile submission, dated 06 Aug.2024. • Secant pile productivity rate less than planned. • Delay appoint MEP & specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval for shelter design (if any) | • Mitigation Measures • Expedite technical & shop drawings submission. • Notice lack of progress issued to MAK. • Workshop meetings held with MAK to expedite re-submission. • sevene to initiate a time schedule for ADM review. | • Shoring Guide wall completion. • Secant pile in progress. • BL resubmission. • Engineering submissions. |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1fD7AWmASsFIlXlxUeMDyf0RwmeJ-UJ8T&sz=w1000 | https://drive.google.com/file/d/1fD7AWmASsFIlXlxUeMDyf0RwmeJ-UJ8T/view | https://drive.google.com/thumbnail?id=1Ri-YAEWJjvz1PE2D5W_tY9aB0o-kD3Cx&sz=w1000 | https://drive.google.com/file/d/1Ri-YAEWJjvz1PE2D5W_tY9aB0o-kD3Cx/view | https://drive.google.com/thumbnail?id=17kFHEbF-AEDFcJjjgAoxnDoBUieKKDg3&sz=w1000 | https://drive.google.com/file/d/17kFHEbF-AEDFcJjjgAoxnDoBUieKKDg3/view
2024-08-12 | Zayed City-Majlis-P17 | P17 | MJ-04 | 75 | 655 | 730 | • Shoring guide wall in progress. • Shoring pilling in progress. • Site office utilities connection in progress. • Welfare facilities in progress. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. | 6.33% | 3.29% | -3.04% | External Works | 2026-06-01 |  | 2026-06-01 | 2024-08-16 | • Risks / Challenges • Delay permeant piling start, due to new optimized pile submission, dated 06 Aug.2024. • Secant pile productivity rate less than planned. • Delay appoint MEP & specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval for shelter design (if any) | • Mitigation Measures • Expedite technical & shop drawings submission. • Notice lack of progress issued to MAK. • Workshop meetings held with MAK to expedite re-submission. • sevene to initiate a time schedule for ADM review. | • Shoring Guide wall completion. • Secant pile in progress. • BL resubmission. • Engineering submissions. |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1fD7AWmASsFIlXlxUeMDyf0RwmeJ-UJ8T&sz=w1000 | https://drive.google.com/file/d/1fD7AWmASsFIlXlxUeMDyf0RwmeJ-UJ8T/view | https://drive.google.com/thumbnail?id=1Ri-YAEWJjvz1PE2D5W_tY9aB0o-kD3Cx&sz=w1000 | https://drive.google.com/file/d/1Ri-YAEWJjvz1PE2D5W_tY9aB0o-kD3Cx/view | https://drive.google.com/thumbnail?id=17kFHEbF-AEDFcJjjgAoxnDoBUieKKDg3&sz=w1000 | https://drive.google.com/file/d/17kFHEbF-AEDFcJjjgAoxnDoBUieKKDg3/view
2024-08-12 | Zayed City-Majlis-P17 | P17 | MJ-04 | 75 | 655 | 730 | • Shoring guide wall in progress. • Shoring pilling in progress. • Site office utilities connection in progress. • Welfare facilities in progress. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. | 6.33% | 3.29% | -3.04% | Testing & Commissioning | 2026-06-01 |  | 2026-06-01 | 2024-08-16 | • Risks / Challenges • Delay permeant piling start, due to new optimized pile submission, dated 06 Aug.2024. • Secant pile productivity rate less than planned. • Delay appoint MEP & specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval for shelter design (if any) | • Mitigation Measures • Expedite technical & shop drawings submission. • Notice lack of progress issued to MAK. • Workshop meetings held with MAK to expedite re-submission. • sevene to initiate a time schedule for ADM review. | • Shoring Guide wall completion. • Secant pile in progress. • BL resubmission. • Engineering submissions. |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1fD7AWmASsFIlXlxUeMDyf0RwmeJ-UJ8T&sz=w1000 | https://drive.google.com/file/d/1fD7AWmASsFIlXlxUeMDyf0RwmeJ-UJ8T/view | https://drive.google.com/thumbnail?id=1Ri-YAEWJjvz1PE2D5W_tY9aB0o-kD3Cx&sz=w1000 | https://drive.google.com/file/d/1Ri-YAEWJjvz1PE2D5W_tY9aB0o-kD3Cx/view | https://drive.google.com/thumbnail?id=17kFHEbF-AEDFcJjjgAoxnDoBUieKKDg3&sz=w1000 | https://drive.google.com/file/d/17kFHEbF-AEDFcJjjgAoxnDoBUieKKDg3/view
2024-08-12 | Zayed City-Majlis-P17 | P17 | MJ-04 | 75 | 655 | 730 | • Shoring guide wall in progress. • Shoring pilling in progress. • Site office utilities connection in progress. • Welfare facilities in progress. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. | 6.33% | 3.29% | -3.04% | Substantial Completion | 2026-06-02 |  | 2026-06-02 | 2024-08-16 | • Risks / Challenges • Delay permeant piling start, due to new optimized pile submission, dated 06 Aug.2024. • Secant pile productivity rate less than planned. • Delay appoint MEP & specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval for shelter design (if any) | • Mitigation Measures • Expedite technical & shop drawings submission. • Notice lack of progress issued to MAK. • Workshop meetings held with MAK to expedite re-submission. • sevene to initiate a time schedule for ADM review. | • Shoring Guide wall completion. • Secant pile in progress. • BL resubmission. • Engineering submissions. |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1fD7AWmASsFIlXlxUeMDyf0RwmeJ-UJ8T&sz=w1000 | https://drive.google.com/file/d/1fD7AWmASsFIlXlxUeMDyf0RwmeJ-UJ8T/view | https://drive.google.com/thumbnail?id=1Ri-YAEWJjvz1PE2D5W_tY9aB0o-kD3Cx&sz=w1000 | https://drive.google.com/file/d/1Ri-YAEWJjvz1PE2D5W_tY9aB0o-kD3Cx/view | https://drive.google.com/thumbnail?id=17kFHEbF-AEDFcJjjgAoxnDoBUieKKDg3&sz=w1000 | https://drive.google.com/file/d/17kFHEbF-AEDFcJjjgAoxnDoBUieKKDg3/view
2024-08-12 | Al Shahama-Majlis-P547 | P547 | MJ-02 | 255 | 343 | 598 | • Relocation Services ongoing. • Project Signboard Completed. • Site office Mobilization Completed . • Guide Wall Excavation and Casting Completed. • Casting 147 of 167 Hard Piles . • Casting 157 of 167 of Soft piles. • Casted 4 of 301 of Main piles • Dewatering Installation total 7 nos pipes | As the recommendation from project's Engineer, Engineer have identified the need for an additional construction team by the contractor . *For COD 08.08.24 Engineer raised critical issue regarding the recent submission by contractor which is unacceptable readjusting of the planned percentage to minimize the variance between PL and ACT. , which significantly deviates from the agreed-upon terms and basic roles in the project BL that is why the progress % not mentioned . | 44.76% | 36.08% | -8.68% | Notice to Commence | 2023-12-05 | 2023-12-05 |  | 2024-08-16 | Delivery of Long Lead Items ( Chillers & Generator & Air handling Unit ) • Special items date of installation CBRN • completion of Excavation , pile head breaking ,Pile integrity test Start of Reinforcement for raft . • Contractor anticipation found inaccurate , and require Contractor action to increase the required resources to achieve anticipated productivity as committed during progress meeting that held .(as Contractor advised that excavation work will be completed within 12 • • working days from the date of progress meeting dated10th of July 2024 which is obviously will not able to attended ). | • Contractor to submit the submit the recovery program to mitigate the delays to achieve the original planned completion date. | • Completion of Excavate Soil Till Raft Foundation • Completion of Disposal of Excavated Materials • Completion of Site Cleaning and Preparation • Completion of Pile Head Breaking . • Completion of Raft PCC works . • Completion of Steel Reinforcement for Raft Foundation Fabrication and Delivery . • Start of TRM & Dynamic test • Completion of Pile Integrity Test |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1xNwrwZ-kLTM_YhVN0HOVWrlrlMM1DCgm&sz=w1000 | https://drive.google.com/file/d/1xNwrwZ-kLTM_YhVN0HOVWrlrlMM1DCgm/view | https://drive.google.com/thumbnail?id=1ubpEtvc1oWuPQhwTMdh21fiJQLJ6YQjL&sz=w1000 | https://drive.google.com/file/d/1ubpEtvc1oWuPQhwTMdh21fiJQLJ6YQjL/view | https://drive.google.com/thumbnail?id=16BMdQPUP_243M9ZY1BsJCcqCz75Uhylv&sz=w1000 | https://drive.google.com/file/d/16BMdQPUP_243M9ZY1BsJCcqCz75Uhylv/view
2024-08-12 | Al Shahama-Majlis-P547 | P547 | MJ-02 | 255 | 343 | 598 | • Relocation Services ongoing. • Project Signboard Completed. • Site office Mobilization Completed . • Guide Wall Excavation and Casting Completed. • Casting 147 of 167 Hard Piles . • Casting 157 of 167 of Soft piles. • Casted 4 of 301 of Main piles • Dewatering Installation total 7 nos pipes | As the recommendation from project's Engineer, Engineer have identified the need for an additional construction team by the contractor . *For COD 08.08.24 Engineer raised critical issue regarding the recent submission by contractor which is unacceptable readjusting of the planned percentage to minimize the variance between PL and ACT. , which significantly deviates from the agreed-upon terms and basic roles in the project BL that is why the progress % not mentioned . | 44.76% | 36.08% | -8.68% | Establishment Site Office Mobilization | 2024-03-23 | 2024-06-07 |  | 2024-08-16 | Delivery of Long Lead Items ( Chillers & Generator & Air handling Unit ) • Special items date of installation CBRN • completion of Excavation , pile head breaking ,Pile integrity test Start of Reinforcement for raft . • Contractor anticipation found inaccurate , and require Contractor action to increase the required resources to achieve anticipated productivity as committed during progress meeting that held .(as Contractor advised that excavation work will be completed within 12 • • working days from the date of progress meeting dated10th of July 2024 which is obviously will not able to attended ). | • Contractor to submit the submit the recovery program to mitigate the delays to achieve the original planned completion date. | • Completion of Excavate Soil Till Raft Foundation • Completion of Disposal of Excavated Materials • Completion of Site Cleaning and Preparation • Completion of Pile Head Breaking . • Completion of Raft PCC works . • Completion of Steel Reinforcement for Raft Foundation Fabrication and Delivery . • Start of TRM & Dynamic test • Completion of Pile Integrity Test |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1xNwrwZ-kLTM_YhVN0HOVWrlrlMM1DCgm&sz=w1000 | https://drive.google.com/file/d/1xNwrwZ-kLTM_YhVN0HOVWrlrlMM1DCgm/view | https://drive.google.com/thumbnail?id=1ubpEtvc1oWuPQhwTMdh21fiJQLJ6YQjL&sz=w1000 | https://drive.google.com/file/d/1ubpEtvc1oWuPQhwTMdh21fiJQLJ6YQjL/view | https://drive.google.com/thumbnail?id=16BMdQPUP_243M9ZY1BsJCcqCz75Uhylv&sz=w1000 | https://drive.google.com/file/d/16BMdQPUP_243M9ZY1BsJCcqCz75Uhylv/view
2024-08-12 | Al Shahama-Majlis-P547 | P547 | MJ-02 | 255 | 343 | 598 | • Relocation Services ongoing. • Project Signboard Completed. • Site office Mobilization Completed . • Guide Wall Excavation and Casting Completed. • Casting 147 of 167 Hard Piles . • Casting 157 of 167 of Soft piles. • Casted 4 of 301 of Main piles • Dewatering Installation total 7 nos pipes | As the recommendation from project's Engineer, Engineer have identified the need for an additional construction team by the contractor . *For COD 08.08.24 Engineer raised critical issue regarding the recent submission by contractor which is unacceptable readjusting of the planned percentage to minimize the variance between PL and ACT. , which significantly deviates from the agreed-upon terms and basic roles in the project BL that is why the progress % not mentioned . | 44.76% | 36.08% | -8.68% | Substructure- Earth work | 2024-07-30 |  | 2024-08-22 | 2024-08-16 | Delivery of Long Lead Items ( Chillers & Generator & Air handling Unit ) • Special items date of installation CBRN • completion of Excavation , pile head breaking ,Pile integrity test Start of Reinforcement for raft . • Contractor anticipation found inaccurate , and require Contractor action to increase the required resources to achieve anticipated productivity as committed during progress meeting that held .(as Contractor advised that excavation work will be completed within 12 • • working days from the date of progress meeting dated10th of July 2024 which is obviously will not able to attended ). | • Contractor to submit the submit the recovery program to mitigate the delays to achieve the original planned completion date. | • Completion of Excavate Soil Till Raft Foundation • Completion of Disposal of Excavated Materials • Completion of Site Cleaning and Preparation • Completion of Pile Head Breaking . • Completion of Raft PCC works . • Completion of Steel Reinforcement for Raft Foundation Fabrication and Delivery . • Start of TRM & Dynamic test • Completion of Pile Integrity Test |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1xNwrwZ-kLTM_YhVN0HOVWrlrlMM1DCgm&sz=w1000 | https://drive.google.com/file/d/1xNwrwZ-kLTM_YhVN0HOVWrlrlMM1DCgm/view | https://drive.google.com/thumbnail?id=1ubpEtvc1oWuPQhwTMdh21fiJQLJ6YQjL&sz=w1000 | https://drive.google.com/file/d/1ubpEtvc1oWuPQhwTMdh21fiJQLJ6YQjL/view | https://drive.google.com/thumbnail?id=16BMdQPUP_243M9ZY1BsJCcqCz75Uhylv&sz=w1000 | https://drive.google.com/file/d/16BMdQPUP_243M9ZY1BsJCcqCz75Uhylv/view
2024-08-12 | Al Shahama-Majlis-P547 | P547 | MJ-02 | 255 | 343 | 598 | • Relocation Services ongoing. • Project Signboard Completed. • Site office Mobilization Completed . • Guide Wall Excavation and Casting Completed. • Casting 147 of 167 Hard Piles . • Casting 157 of 167 of Soft piles. • Casted 4 of 301 of Main piles • Dewatering Installation total 7 nos pipes | As the recommendation from project's Engineer, Engineer have identified the need for an additional construction team by the contractor . *For COD 08.08.24 Engineer raised critical issue regarding the recent submission by contractor which is unacceptable readjusting of the planned percentage to minimize the variance between PL and ACT. , which significantly deviates from the agreed-upon terms and basic roles in the project BL that is why the progress % not mentioned . | 44.76% | 36.08% | -8.68% | Substructure-Basement Level | 2024-09-04 |  | 2024-11-20 | 2024-08-16 | Delivery of Long Lead Items ( Chillers & Generator & Air handling Unit ) • Special items date of installation CBRN • completion of Excavation , pile head breaking ,Pile integrity test Start of Reinforcement for raft . • Contractor anticipation found inaccurate , and require Contractor action to increase the required resources to achieve anticipated productivity as committed during progress meeting that held .(as Contractor advised that excavation work will be completed within 12 • • working days from the date of progress meeting dated10th of July 2024 which is obviously will not able to attended ). | • Contractor to submit the submit the recovery program to mitigate the delays to achieve the original planned completion date. | • Completion of Excavate Soil Till Raft Foundation • Completion of Disposal of Excavated Materials • Completion of Site Cleaning and Preparation • Completion of Pile Head Breaking . • Completion of Raft PCC works . • Completion of Steel Reinforcement for Raft Foundation Fabrication and Delivery . • Start of TRM & Dynamic test • Completion of Pile Integrity Test |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1xNwrwZ-kLTM_YhVN0HOVWrlrlMM1DCgm&sz=w1000 | https://drive.google.com/file/d/1xNwrwZ-kLTM_YhVN0HOVWrlrlMM1DCgm/view | https://drive.google.com/thumbnail?id=1ubpEtvc1oWuPQhwTMdh21fiJQLJ6YQjL&sz=w1000 | https://drive.google.com/file/d/1ubpEtvc1oWuPQhwTMdh21fiJQLJ6YQjL/view | https://drive.google.com/thumbnail?id=16BMdQPUP_243M9ZY1BsJCcqCz75Uhylv&sz=w1000 | https://drive.google.com/file/d/16BMdQPUP_243M9ZY1BsJCcqCz75Uhylv/view
2024-08-12 | Al Shahama-Majlis-P547 | P547 | MJ-02 | 255 | 343 | 598 | • Relocation Services ongoing. • Project Signboard Completed. • Site office Mobilization Completed . • Guide Wall Excavation and Casting Completed. • Casting 147 of 167 Hard Piles . • Casting 157 of 167 of Soft piles. • Casted 4 of 301 of Main piles • Dewatering Installation total 7 nos pipes | As the recommendation from project's Engineer, Engineer have identified the need for an additional construction team by the contractor . *For COD 08.08.24 Engineer raised critical issue regarding the recent submission by contractor which is unacceptable readjusting of the planned percentage to minimize the variance between PL and ACT. , which significantly deviates from the agreed-upon terms and basic roles in the project BL that is why the progress % not mentioned . | 44.76% | 36.08% | -8.68% | Superstructure-Majlis | 2025-07-18 |  | 2025-07-18 | 2024-08-16 | Delivery of Long Lead Items ( Chillers & Generator & Air handling Unit ) • Special items date of installation CBRN • completion of Excavation , pile head breaking ,Pile integrity test Start of Reinforcement for raft . • Contractor anticipation found inaccurate , and require Contractor action to increase the required resources to achieve anticipated productivity as committed during progress meeting that held .(as Contractor advised that excavation work will be completed within 12 • • working days from the date of progress meeting dated10th of July 2024 which is obviously will not able to attended ). | • Contractor to submit the submit the recovery program to mitigate the delays to achieve the original planned completion date. | • Completion of Excavate Soil Till Raft Foundation • Completion of Disposal of Excavated Materials • Completion of Site Cleaning and Preparation • Completion of Pile Head Breaking . • Completion of Raft PCC works . • Completion of Steel Reinforcement for Raft Foundation Fabrication and Delivery . • Start of TRM & Dynamic test • Completion of Pile Integrity Test |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1xNwrwZ-kLTM_YhVN0HOVWrlrlMM1DCgm&sz=w1000 | https://drive.google.com/file/d/1xNwrwZ-kLTM_YhVN0HOVWrlrlMM1DCgm/view | https://drive.google.com/thumbnail?id=1ubpEtvc1oWuPQhwTMdh21fiJQLJ6YQjL&sz=w1000 | https://drive.google.com/file/d/1ubpEtvc1oWuPQhwTMdh21fiJQLJ6YQjL/view | https://drive.google.com/thumbnail?id=16BMdQPUP_243M9ZY1BsJCcqCz75Uhylv&sz=w1000 | https://drive.google.com/file/d/16BMdQPUP_243M9ZY1BsJCcqCz75Uhylv/view
2024-08-12 | Al Shahama-Majlis-P547 | P547 | MJ-02 | 255 | 343 | 598 | • Relocation Services ongoing. • Project Signboard Completed. • Site office Mobilization Completed . • Guide Wall Excavation and Casting Completed. • Casting 147 of 167 Hard Piles . • Casting 157 of 167 of Soft piles. • Casted 4 of 301 of Main piles • Dewatering Installation total 7 nos pipes | As the recommendation from project's Engineer, Engineer have identified the need for an additional construction team by the contractor . *For COD 08.08.24 Engineer raised critical issue regarding the recent submission by contractor which is unacceptable readjusting of the planned percentage to minimize the variance between PL and ACT. , which significantly deviates from the agreed-upon terms and basic roles in the project BL that is why the progress % not mentioned . | 44.76% | 36.08% | -8.68% | Substantial Completion | 2025-08-20 |  | 2025-08-30 | 2024-08-16 | Delivery of Long Lead Items ( Chillers & Generator & Air handling Unit ) • Special items date of installation CBRN • completion of Excavation , pile head breaking ,Pile integrity test Start of Reinforcement for raft . • Contractor anticipation found inaccurate , and require Contractor action to increase the required resources to achieve anticipated productivity as committed during progress meeting that held .(as Contractor advised that excavation work will be completed within 12 • • working days from the date of progress meeting dated10th of July 2024 which is obviously will not able to attended ). | • Contractor to submit the submit the recovery program to mitigate the delays to achieve the original planned completion date. | • Completion of Excavate Soil Till Raft Foundation • Completion of Disposal of Excavated Materials • Completion of Site Cleaning and Preparation • Completion of Pile Head Breaking . • Completion of Raft PCC works . • Completion of Steel Reinforcement for Raft Foundation Fabrication and Delivery . • Start of TRM & Dynamic test • Completion of Pile Integrity Test |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1xNwrwZ-kLTM_YhVN0HOVWrlrlMM1DCgm&sz=w1000 | https://drive.google.com/file/d/1xNwrwZ-kLTM_YhVN0HOVWrlrlMM1DCgm/view | https://drive.google.com/thumbnail?id=1ubpEtvc1oWuPQhwTMdh21fiJQLJ6YQjL&sz=w1000 | https://drive.google.com/file/d/1ubpEtvc1oWuPQhwTMdh21fiJQLJ6YQjL/view | https://drive.google.com/thumbnail?id=16BMdQPUP_243M9ZY1BsJCcqCz75Uhylv&sz=w1000 | https://drive.google.com/file/d/16BMdQPUP_243M9ZY1BsJCcqCz75Uhylv/view
2024-08-12 | Mohamed Bin Zayed City -Majlis-P19 | P19 | MJ-03 | 255 | 343 | 598 | • Relocation Services ongoing. • Project Signboard Completed. • Site office Mobilization Completed . • Guide Wall Excavation and Casting Completed. • Casting 147 of 167 Hard Piles . • Casting 157 of 167 of Soft piles. • Casted 4 of 301 of Main piles • Dewatering Installation total 7 nos pipes | As the recommendation from project's Engineer, Engineer have identified the need for an additional construction team by the contractor . | 40.71% | 17.23% | -23.48% | Notice to Commence | 2024-12-05 | 2024-12-05 |  | 2024-08-16 | • Delay commencement of MBZ project due to NOC’s for Utility Relocation. • The affection plan without conditions on 29thMay 2024. • Delay of NOCs for MCC, Strom Water ,and Etisalat. • The project will require night shift operations. This adjustment is essential to meet our deadlines . • Contractor anticipation to enable work night shift (24 days ) is totally not applicable at this site due to the nature of the required activities that will not be allowed at such sensitive area , and Contractor should increase the resources to enable compensate the above mentioned restriction . • Working adjacent to the sensitive building/area , and anticipated restriction sensitive | • Contractor to submit the recovery plan to mitigate the delays • Senior management support required to expedite NOC approvals and authority support. | • Relocation Services. • Mobilization (Site offices ). • Complete the Shoring Piles. • Complete the Guide wall Activities. • Start Main Piles. |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1PN5QKrWfuLNLtg-y5ctP3wPnqv2s1Rlm&sz=w1000 | https://drive.google.com/file/d/1PN5QKrWfuLNLtg-y5ctP3wPnqv2s1Rlm/view | https://drive.google.com/thumbnail?id=1Xv5IhBhdmlrvaY32k_gxD4v2dwCxj2S0&sz=w1000 | https://drive.google.com/file/d/1Xv5IhBhdmlrvaY32k_gxD4v2dwCxj2S0/view | https://drive.google.com/thumbnail?id=1cGFZl0t3lci1ilX5gjjOKnRFdDklY_8G&sz=w1000 | https://drive.google.com/file/d/1cGFZl0t3lci1ilX5gjjOKnRFdDklY_8G/view
2024-08-12 | Mohamed Bin Zayed City -Majlis-P19 | P19 | MJ-03 | 255 | 343 | 598 | • Relocation Services ongoing. • Project Signboard Completed. • Site office Mobilization Completed . • Guide Wall Excavation and Casting Completed. • Casting 147 of 167 Hard Piles . • Casting 157 of 167 of Soft piles. • Casted 4 of 301 of Main piles • Dewatering Installation total 7 nos pipes | As the recommendation from project's Engineer, Engineer have identified the need for an additional construction team by the contractor . | 40.71% | 17.23% | -23.48% | Establishment Site Office Mobilization | 2024-03-28 | 2024-08-08 |  | 2024-08-16 | • Delay commencement of MBZ project due to NOC’s for Utility Relocation. • The affection plan without conditions on 29thMay 2024. • Delay of NOCs for MCC, Strom Water ,and Etisalat. • The project will require night shift operations. This adjustment is essential to meet our deadlines . • Contractor anticipation to enable work night shift (24 days ) is totally not applicable at this site due to the nature of the required activities that will not be allowed at such sensitive area , and Contractor should increase the resources to enable compensate the above mentioned restriction . • Working adjacent to the sensitive building/area , and anticipated restriction sensitive | • Contractor to submit the recovery plan to mitigate the delays • Senior management support required to expedite NOC approvals and authority support. | • Relocation Services. • Mobilization (Site offices ). • Complete the Shoring Piles. • Complete the Guide wall Activities. • Start Main Piles. |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1PN5QKrWfuLNLtg-y5ctP3wPnqv2s1Rlm&sz=w1000 | https://drive.google.com/file/d/1PN5QKrWfuLNLtg-y5ctP3wPnqv2s1Rlm/view | https://drive.google.com/thumbnail?id=1Xv5IhBhdmlrvaY32k_gxD4v2dwCxj2S0&sz=w1000 | https://drive.google.com/file/d/1Xv5IhBhdmlrvaY32k_gxD4v2dwCxj2S0/view | https://drive.google.com/thumbnail?id=1cGFZl0t3lci1ilX5gjjOKnRFdDklY_8G&sz=w1000 | https://drive.google.com/file/d/1cGFZl0t3lci1ilX5gjjOKnRFdDklY_8G/view
2024-08-12 | Mohamed Bin Zayed City -Majlis-P19 | P19 | MJ-03 | 255 | 343 | 598 | • Relocation Services ongoing. • Project Signboard Completed. • Site office Mobilization Completed . • Guide Wall Excavation and Casting Completed. • Casting 147 of 167 Hard Piles . • Casting 157 of 167 of Soft piles. • Casted 4 of 301 of Main piles • Dewatering Installation total 7 nos pipes | As the recommendation from project's Engineer, Engineer have identified the need for an additional construction team by the contractor . | 40.71% | 17.23% | -23.48% | Substructure- Earth work up to Raft Foundation | 2024-08-13 |  | 2024-10-05 | 2024-08-16 | • Delay commencement of MBZ project due to NOC’s for Utility Relocation. • The affection plan without conditions on 29thMay 2024. • Delay of NOCs for MCC, Strom Water ,and Etisalat. • The project will require night shift operations. This adjustment is essential to meet our deadlines . • Contractor anticipation to enable work night shift (24 days ) is totally not applicable at this site due to the nature of the required activities that will not be allowed at such sensitive area , and Contractor should increase the resources to enable compensate the above mentioned restriction . • Working adjacent to the sensitive building/area , and anticipated restriction sensitive | • Contractor to submit the recovery plan to mitigate the delays • Senior management support required to expedite NOC approvals and authority support. | • Relocation Services. • Mobilization (Site offices ). • Complete the Shoring Piles. • Complete the Guide wall Activities. • Start Main Piles. |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1PN5QKrWfuLNLtg-y5ctP3wPnqv2s1Rlm&sz=w1000 | https://drive.google.com/file/d/1PN5QKrWfuLNLtg-y5ctP3wPnqv2s1Rlm/view | https://drive.google.com/thumbnail?id=1Xv5IhBhdmlrvaY32k_gxD4v2dwCxj2S0&sz=w1000 | https://drive.google.com/file/d/1Xv5IhBhdmlrvaY32k_gxD4v2dwCxj2S0/view | https://drive.google.com/thumbnail?id=1cGFZl0t3lci1ilX5gjjOKnRFdDklY_8G&sz=w1000 | https://drive.google.com/file/d/1cGFZl0t3lci1ilX5gjjOKnRFdDklY_8G/view
2024-08-12 | Mohamed Bin Zayed City -Majlis-P19 | P19 | MJ-03 | 255 | 343 | 598 | • Relocation Services ongoing. • Project Signboard Completed. • Site office Mobilization Completed . • Guide Wall Excavation and Casting Completed. • Casting 147 of 167 Hard Piles . • Casting 157 of 167 of Soft piles. • Casted 4 of 301 of Main piles • Dewatering Installation total 7 nos pipes | As the recommendation from project's Engineer, Engineer have identified the need for an additional construction team by the contractor . | 40.71% | 17.23% | -23.48% | Substructure-Basement Level | 2025-07-19 |  | 2025-12-20 | 2024-08-16 | • Delay commencement of MBZ project due to NOC’s for Utility Relocation. • The affection plan without conditions on 29thMay 2024. • Delay of NOCs for MCC, Strom Water ,and Etisalat. • The project will require night shift operations. This adjustment is essential to meet our deadlines . • Contractor anticipation to enable work night shift (24 days ) is totally not applicable at this site due to the nature of the required activities that will not be allowed at such sensitive area , and Contractor should increase the resources to enable compensate the above mentioned restriction . • Working adjacent to the sensitive building/area , and anticipated restriction sensitive | • Contractor to submit the recovery plan to mitigate the delays • Senior management support required to expedite NOC approvals and authority support. | • Relocation Services. • Mobilization (Site offices ). • Complete the Shoring Piles. • Complete the Guide wall Activities. • Start Main Piles. |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1PN5QKrWfuLNLtg-y5ctP3wPnqv2s1Rlm&sz=w1000 | https://drive.google.com/file/d/1PN5QKrWfuLNLtg-y5ctP3wPnqv2s1Rlm/view | https://drive.google.com/thumbnail?id=1Xv5IhBhdmlrvaY32k_gxD4v2dwCxj2S0&sz=w1000 | https://drive.google.com/file/d/1Xv5IhBhdmlrvaY32k_gxD4v2dwCxj2S0/view | https://drive.google.com/thumbnail?id=1cGFZl0t3lci1ilX5gjjOKnRFdDklY_8G&sz=w1000 | https://drive.google.com/file/d/1cGFZl0t3lci1ilX5gjjOKnRFdDklY_8G/view
2024-08-12 | Mohamed Bin Zayed City -Majlis-P19 | P19 | MJ-03 | 255 | 343 | 598 | • Relocation Services ongoing. • Project Signboard Completed. • Site office Mobilization Completed . • Guide Wall Excavation and Casting Completed. • Casting 147 of 167 Hard Piles . • Casting 157 of 167 of Soft piles. • Casted 4 of 301 of Main piles • Dewatering Installation total 7 nos pipes | As the recommendation from project's Engineer, Engineer have identified the need for an additional construction team by the contractor . | 40.71% | 17.23% | -23.48% | Superstructure-Majlis | 2025-07-24 |  | 2025-12-24 | 2024-08-16 | • Delay commencement of MBZ project due to NOC’s for Utility Relocation. • The affection plan without conditions on 29thMay 2024. • Delay of NOCs for MCC, Strom Water ,and Etisalat. • The project will require night shift operations. This adjustment is essential to meet our deadlines . • Contractor anticipation to enable work night shift (24 days ) is totally not applicable at this site due to the nature of the required activities that will not be allowed at such sensitive area , and Contractor should increase the resources to enable compensate the above mentioned restriction . • Working adjacent to the sensitive building/area , and anticipated restriction sensitive | • Contractor to submit the recovery plan to mitigate the delays • Senior management support required to expedite NOC approvals and authority support. | • Relocation Services. • Mobilization (Site offices ). • Complete the Shoring Piles. • Complete the Guide wall Activities. • Start Main Piles. |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1PN5QKrWfuLNLtg-y5ctP3wPnqv2s1Rlm&sz=w1000 | https://drive.google.com/file/d/1PN5QKrWfuLNLtg-y5ctP3wPnqv2s1Rlm/view | https://drive.google.com/thumbnail?id=1Xv5IhBhdmlrvaY32k_gxD4v2dwCxj2S0&sz=w1000 | https://drive.google.com/file/d/1Xv5IhBhdmlrvaY32k_gxD4v2dwCxj2S0/view | https://drive.google.com/thumbnail?id=1cGFZl0t3lci1ilX5gjjOKnRFdDklY_8G&sz=w1000 | https://drive.google.com/file/d/1cGFZl0t3lci1ilX5gjjOKnRFdDklY_8G/view
2024-08-12 | Mohamed Bin Zayed City -Majlis-P19 | P19 | MJ-03 | 255 | 343 | 598 | • Relocation Services ongoing. • Project Signboard Completed. • Site office Mobilization Completed . • Guide Wall Excavation and Casting Completed. • Casting 147 of 167 Hard Piles . • Casting 157 of 167 of Soft piles. • Casted 4 of 301 of Main piles • Dewatering Installation total 7 nos pipes | As the recommendation from project's Engineer, Engineer have identified the need for an additional construction team by the contractor . | 40.71% | 17.23% | -23.48% | Substantial Completion | 2025-07-19 |  | 2025-12-10 | 2024-08-16 | • Delay commencement of MBZ project due to NOC’s for Utility Relocation. • The affection plan without conditions on 29thMay 2024. • Delay of NOCs for MCC, Strom Water ,and Etisalat. • The project will require night shift operations. This adjustment is essential to meet our deadlines . • Contractor anticipation to enable work night shift (24 days ) is totally not applicable at this site due to the nature of the required activities that will not be allowed at such sensitive area , and Contractor should increase the resources to enable compensate the above mentioned restriction . • Working adjacent to the sensitive building/area , and anticipated restriction sensitive | • Contractor to submit the recovery plan to mitigate the delays • Senior management support required to expedite NOC approvals and authority support. | • Relocation Services. • Mobilization (Site offices ). • Complete the Shoring Piles. • Complete the Guide wall Activities. • Start Main Piles. |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1PN5QKrWfuLNLtg-y5ctP3wPnqv2s1Rlm&sz=w1000 | https://drive.google.com/file/d/1PN5QKrWfuLNLtg-y5ctP3wPnqv2s1Rlm/view | https://drive.google.com/thumbnail?id=1Xv5IhBhdmlrvaY32k_gxD4v2dwCxj2S0&sz=w1000 | https://drive.google.com/file/d/1Xv5IhBhdmlrvaY32k_gxD4v2dwCxj2S0/view | https://drive.google.com/thumbnail?id=1cGFZl0t3lci1ilX5gjjOKnRFdDklY_8G&sz=w1000 | https://drive.google.com/file/d/1cGFZl0t3lci1ilX5gjjOKnRFdDklY_8G/view
2024-08-12 | Mohamed Bin Zayed City -Majlis-P19 | P19 | MJ-03 | 255 | 343 | 598 | • Relocation Services ongoing. • Project Signboard Completed. • Site office Mobilization Completed . • Guide Wall Excavation and Casting Completed. • Casting 147 of 167 Hard Piles . • Casting 157 of 167 of Soft piles. • Casted 4 of 301 of Main piles • Dewatering Installation total 7 nos pipes | As the recommendation from project's Engineer, Engineer have identified the need for an additional construction team by the contractor . | 40.71% | 17.23% | -23.48% | Under Ground Facilities T&C | 2025-07-19 |  | 2025-07-15 | 2024-08-16 | • Delay commencement of MBZ project due to NOC’s for Utility Relocation. • The affection plan without conditions on 29thMay 2024. • Delay of NOCs for MCC, Strom Water ,and Etisalat. • The project will require night shift operations. This adjustment is essential to meet our deadlines . • Contractor anticipation to enable work night shift (24 days ) is totally not applicable at this site due to the nature of the required activities that will not be allowed at such sensitive area , and Contractor should increase the resources to enable compensate the above mentioned restriction . • Working adjacent to the sensitive building/area , and anticipated restriction sensitive | • Contractor to submit the recovery plan to mitigate the delays • Senior management support required to expedite NOC approvals and authority support. | • Relocation Services. • Mobilization (Site offices ). • Complete the Shoring Piles. • Complete the Guide wall Activities. • Start Main Piles. |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1PN5QKrWfuLNLtg-y5ctP3wPnqv2s1Rlm&sz=w1000 | https://drive.google.com/file/d/1PN5QKrWfuLNLtg-y5ctP3wPnqv2s1Rlm/view | https://drive.google.com/thumbnail?id=1Xv5IhBhdmlrvaY32k_gxD4v2dwCxj2S0&sz=w1000 | https://drive.google.com/file/d/1Xv5IhBhdmlrvaY32k_gxD4v2dwCxj2S0/view | https://drive.google.com/thumbnail?id=1cGFZl0t3lci1ilX5gjjOKnRFdDklY_8G&sz=w1000 | https://drive.google.com/file/d/1cGFZl0t3lci1ilX5gjjOKnRFdDklY_8G/view
2024-08-12 | Mohamed Bin Zayed City -Majlis-P19 | P19 | MJ-03 | 255 | 343 | 598 | • Relocation Services ongoing. • Project Signboard Completed. • Site office Mobilization Completed . • Guide Wall Excavation and Casting Completed. • Casting 147 of 167 Hard Piles . • Casting 157 of 167 of Soft piles. • Casted 4 of 301 of Main piles • Dewatering Installation total 7 nos pipes | As the recommendation from project's Engineer, Engineer have identified the need for an additional construction team by the contractor . | 40.71% | 17.23% | -23.48% | Majlis Testing & Commissioning | 2025-07-17 |  | 2025-12-10 | 2024-08-16 | • Delay commencement of MBZ project due to NOC’s for Utility Relocation. • The affection plan without conditions on 29thMay 2024. • Delay of NOCs for MCC, Strom Water ,and Etisalat. • The project will require night shift operations. This adjustment is essential to meet our deadlines . • Contractor anticipation to enable work night shift (24 days ) is totally not applicable at this site due to the nature of the required activities that will not be allowed at such sensitive area , and Contractor should increase the resources to enable compensate the above mentioned restriction . • Working adjacent to the sensitive building/area , and anticipated restriction sensitive | • Contractor to submit the recovery plan to mitigate the delays • Senior management support required to expedite NOC approvals and authority support. | • Relocation Services. • Mobilization (Site offices ). • Complete the Shoring Piles. • Complete the Guide wall Activities. • Start Main Piles. |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1PN5QKrWfuLNLtg-y5ctP3wPnqv2s1Rlm&sz=w1000 | https://drive.google.com/file/d/1PN5QKrWfuLNLtg-y5ctP3wPnqv2s1Rlm/view | https://drive.google.com/thumbnail?id=1Xv5IhBhdmlrvaY32k_gxD4v2dwCxj2S0&sz=w1000 | https://drive.google.com/file/d/1Xv5IhBhdmlrvaY32k_gxD4v2dwCxj2S0/view | https://drive.google.com/thumbnail?id=1cGFZl0t3lci1ilX5gjjOKnRFdDklY_8G&sz=w1000 | https://drive.google.com/file/d/1cGFZl0t3lci1ilX5gjjOKnRFdDklY_8G/view
2024-08-12 | Mohamed Bin Zayed City -Majlis-P19 | P19 | MJ-03 | 255 | 343 | 598 | • Relocation Services ongoing. • Project Signboard Completed. • Site office Mobilization Completed . • Guide Wall Excavation and Casting Completed. • Casting 147 of 167 Hard Piles . • Casting 157 of 167 of Soft piles. • Casted 4 of 301 of Main piles • Dewatering Installation total 7 nos pipes | As the recommendation from project's Engineer, Engineer have identified the need for an additional construction team by the contractor . | 40.71% | 17.23% | -23.48% | Majlis – Power | 2025-07-24 |  | 2025-12-20 | 2024-08-16 | • Delay commencement of MBZ project due to NOC’s for Utility Relocation. • The affection plan without conditions on 29thMay 2024. • Delay of NOCs for MCC, Strom Water ,and Etisalat. • The project will require night shift operations. This adjustment is essential to meet our deadlines . • Contractor anticipation to enable work night shift (24 days ) is totally not applicable at this site due to the nature of the required activities that will not be allowed at such sensitive area , and Contractor should increase the resources to enable compensate the above mentioned restriction . • Working adjacent to the sensitive building/area , and anticipated restriction sensitive | • Contractor to submit the recovery plan to mitigate the delays • Senior management support required to expedite NOC approvals and authority support. | • Relocation Services. • Mobilization (Site offices ). • Complete the Shoring Piles. • Complete the Guide wall Activities. • Start Main Piles. |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1PN5QKrWfuLNLtg-y5ctP3wPnqv2s1Rlm&sz=w1000 | https://drive.google.com/file/d/1PN5QKrWfuLNLtg-y5ctP3wPnqv2s1Rlm/view | https://drive.google.com/thumbnail?id=1Xv5IhBhdmlrvaY32k_gxD4v2dwCxj2S0&sz=w1000 | https://drive.google.com/file/d/1Xv5IhBhdmlrvaY32k_gxD4v2dwCxj2S0/view | https://drive.google.com/thumbnail?id=1cGFZl0t3lci1ilX5gjjOKnRFdDklY_8G&sz=w1000 | https://drive.google.com/file/d/1cGFZl0t3lci1ilX5gjjOKnRFdDklY_8G/view
2024-08-12 | Mohamed Bin Zayed City -Majlis-P19 | P19 | MJ-03 | 255 | 343 | 598 | • Relocation Services ongoing. • Project Signboard Completed. • Site office Mobilization Completed . • Guide Wall Excavation and Casting Completed. • Casting 147 of 167 Hard Piles . • Casting 157 of 167 of Soft piles. • Casted 4 of 301 of Main piles • Dewatering Installation total 7 nos pipes | As the recommendation from project's Engineer, Engineer have identified the need for an additional construction team by the contractor . | 40.71% | 17.23% | -23.48% | Project Finish Date | 2025-07-24 |  | 2025-12-24 | 2024-08-16 | • Delay commencement of MBZ project due to NOC’s for Utility Relocation. • The affection plan without conditions on 29thMay 2024. • Delay of NOCs for MCC, Strom Water ,and Etisalat. • The project will require night shift operations. This adjustment is essential to meet our deadlines . • Contractor anticipation to enable work night shift (24 days ) is totally not applicable at this site due to the nature of the required activities that will not be allowed at such sensitive area , and Contractor should increase the resources to enable compensate the above mentioned restriction . • Working adjacent to the sensitive building/area , and anticipated restriction sensitive | • Contractor to submit the recovery plan to mitigate the delays • Senior management support required to expedite NOC approvals and authority support. | • Relocation Services. • Mobilization (Site offices ). • Complete the Shoring Piles. • Complete the Guide wall Activities. • Start Main Piles. |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1PN5QKrWfuLNLtg-y5ctP3wPnqv2s1Rlm&sz=w1000 | https://drive.google.com/file/d/1PN5QKrWfuLNLtg-y5ctP3wPnqv2s1Rlm/view | https://drive.google.com/thumbnail?id=1Xv5IhBhdmlrvaY32k_gxD4v2dwCxj2S0&sz=w1000 | https://drive.google.com/file/d/1Xv5IhBhdmlrvaY32k_gxD4v2dwCxj2S0/view | https://drive.google.com/thumbnail?id=1cGFZl0t3lci1ilX5gjjOKnRFdDklY_8G&sz=w1000 | https://drive.google.com/file/d/1cGFZl0t3lci1ilX5gjjOKnRFdDklY_8G/view
2024-08-12 | Khalifa City-Majlis-P2 | P2 | MJ-06 | 89 | 521 | 610 | • Building Permits issued on 21/05/2024. • Shoring Approval 16/07/2024. • Completion of site fencing and installation of signboard 24/07/2024. • Delivery of Site offices. | Commencement Date 15/05/2024 | 3.15% | 1.96% | -1.19% | Notice to Commence | 2024-05-15 | 2024-05-15 |  | 2024-08-16 | • Relocation of existing services two (2) ADDC cables with feeder pillar. • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • Delay in submissions of and insurances and grantees. • NOCs for fencing permit.(ADDC rejection) | • Approved contractor to re-route the existing services-started the process to obtain Work order from ADDC.(ongoing) • Submission of MEP subcontractor to Engineer for approval. • Technical workshop with specialist to finalize all required clarifications. • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities • Re-route the existing services-commence the execution of re-routing.(PS) • Finalized the selection of shelter special equipment. • Procurement of MEP subcontractor. |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=19ZTyE2xeT2sZ01YGBhW0hDNK1zkOgzov&sz=w1000 | https://drive.google.com/file/d/19ZTyE2xeT2sZ01YGBhW0hDNK1zkOgzov/view | https://drive.google.com/thumbnail?id=1Jq87qjyP8CX6GzfZ6UTJqN8h3tUDVJ4L&sz=w1000 | https://drive.google.com/file/d/1Jq87qjyP8CX6GzfZ6UTJqN8h3tUDVJ4L/view | https://drive.google.com/thumbnail?id=11ckN00HUeGC8mZ4NTbuNo3XBAKRafCzJ&sz=w1000 | https://drive.google.com/file/d/11ckN00HUeGC8mZ4NTbuNo3XBAKRafCzJ/view
2024-08-12 | Khalifa City-Majlis-P2 | P2 | MJ-06 | 89 | 521 | 610 | • Building Permits issued on 21/05/2024. • Shoring Approval 16/07/2024. • Completion of site fencing and installation of signboard 24/07/2024. • Delivery of Site offices. | Commencement Date 15/05/2024 | 3.15% | 1.96% | -1.19% | Building Permit | 2024-05-21 | 2024-05-21 |  | 2024-08-16 | • Relocation of existing services two (2) ADDC cables with feeder pillar. • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • Delay in submissions of and insurances and grantees. • NOCs for fencing permit.(ADDC rejection) | • Approved contractor to re-route the existing services-started the process to obtain Work order from ADDC.(ongoing) • Submission of MEP subcontractor to Engineer for approval. • Technical workshop with specialist to finalize all required clarifications. • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities • Re-route the existing services-commence the execution of re-routing.(PS) • Finalized the selection of shelter special equipment. • Procurement of MEP subcontractor. |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=19ZTyE2xeT2sZ01YGBhW0hDNK1zkOgzov&sz=w1000 | https://drive.google.com/file/d/19ZTyE2xeT2sZ01YGBhW0hDNK1zkOgzov/view | https://drive.google.com/thumbnail?id=1Jq87qjyP8CX6GzfZ6UTJqN8h3tUDVJ4L&sz=w1000 | https://drive.google.com/file/d/1Jq87qjyP8CX6GzfZ6UTJqN8h3tUDVJ4L/view | https://drive.google.com/thumbnail?id=11ckN00HUeGC8mZ4NTbuNo3XBAKRafCzJ&sz=w1000 | https://drive.google.com/file/d/11ckN00HUeGC8mZ4NTbuNo3XBAKRafCzJ/view
2024-08-12 | Khalifa City-Majlis-P2 | P2 | MJ-06 | 89 | 521 | 610 | • Building Permits issued on 21/05/2024. • Shoring Approval 16/07/2024. • Completion of site fencing and installation of signboard 24/07/2024. • Delivery of Site offices. | Commencement Date 15/05/2024 | 3.15% | 1.96% | -1.19% | Site Mobilization | 2024-07-22 | 2024-08-15 |  | 2024-08-16 | • Relocation of existing services two (2) ADDC cables with feeder pillar. • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • Delay in submissions of and insurances and grantees. • NOCs for fencing permit.(ADDC rejection) | • Approved contractor to re-route the existing services-started the process to obtain Work order from ADDC.(ongoing) • Submission of MEP subcontractor to Engineer for approval. • Technical workshop with specialist to finalize all required clarifications. • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities • Re-route the existing services-commence the execution of re-routing.(PS) • Finalized the selection of shelter special equipment. • Procurement of MEP subcontractor. |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=19ZTyE2xeT2sZ01YGBhW0hDNK1zkOgzov&sz=w1000 | https://drive.google.com/file/d/19ZTyE2xeT2sZ01YGBhW0hDNK1zkOgzov/view | https://drive.google.com/thumbnail?id=1Jq87qjyP8CX6GzfZ6UTJqN8h3tUDVJ4L&sz=w1000 | https://drive.google.com/file/d/1Jq87qjyP8CX6GzfZ6UTJqN8h3tUDVJ4L/view | https://drive.google.com/thumbnail?id=11ckN00HUeGC8mZ4NTbuNo3XBAKRafCzJ&sz=w1000 | https://drive.google.com/file/d/11ckN00HUeGC8mZ4NTbuNo3XBAKRafCzJ/view
2024-08-12 | Khalifa City-Majlis-P2 | P2 | MJ-06 | 89 | 521 | 610 | • Building Permits issued on 21/05/2024. • Shoring Approval 16/07/2024. • Completion of site fencing and installation of signboard 24/07/2024. • Delivery of Site offices. | Commencement Date 15/05/2024 | 3.15% | 1.96% | -1.19% | Shoring and Piling Completion | 2024-11-06 |  | 2024-12-02 | 2024-08-16 | • Relocation of existing services two (2) ADDC cables with feeder pillar. • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • Delay in submissions of and insurances and grantees. • NOCs for fencing permit.(ADDC rejection) | • Approved contractor to re-route the existing services-started the process to obtain Work order from ADDC.(ongoing) • Submission of MEP subcontractor to Engineer for approval. • Technical workshop with specialist to finalize all required clarifications. • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities • Re-route the existing services-commence the execution of re-routing.(PS) • Finalized the selection of shelter special equipment. • Procurement of MEP subcontractor. |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=19ZTyE2xeT2sZ01YGBhW0hDNK1zkOgzov&sz=w1000 | https://drive.google.com/file/d/19ZTyE2xeT2sZ01YGBhW0hDNK1zkOgzov/view | https://drive.google.com/thumbnail?id=1Jq87qjyP8CX6GzfZ6UTJqN8h3tUDVJ4L&sz=w1000 | https://drive.google.com/file/d/1Jq87qjyP8CX6GzfZ6UTJqN8h3tUDVJ4L/view | https://drive.google.com/thumbnail?id=11ckN00HUeGC8mZ4NTbuNo3XBAKRafCzJ&sz=w1000 | https://drive.google.com/file/d/11ckN00HUeGC8mZ4NTbuNo3XBAKRafCzJ/view
2024-08-12 | Khalifa City-Majlis-P2 | P2 | MJ-06 | 89 | 521 | 610 | • Building Permits issued on 21/05/2024. • Shoring Approval 16/07/2024. • Completion of site fencing and installation of signboard 24/07/2024. • Delivery of Site offices. | Commencement Date 15/05/2024 | 3.15% | 1.96% | -1.19% | Substructure | 2024-12-08 |  | 2024-12-11 | 2024-08-16 | • Relocation of existing services two (2) ADDC cables with feeder pillar. • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • Delay in submissions of and insurances and grantees. • NOCs for fencing permit.(ADDC rejection) | • Approved contractor to re-route the existing services-started the process to obtain Work order from ADDC.(ongoing) • Submission of MEP subcontractor to Engineer for approval. • Technical workshop with specialist to finalize all required clarifications. • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities • Re-route the existing services-commence the execution of re-routing.(PS) • Finalized the selection of shelter special equipment. • Procurement of MEP subcontractor. |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=19ZTyE2xeT2sZ01YGBhW0hDNK1zkOgzov&sz=w1000 | https://drive.google.com/file/d/19ZTyE2xeT2sZ01YGBhW0hDNK1zkOgzov/view | https://drive.google.com/thumbnail?id=1Jq87qjyP8CX6GzfZ6UTJqN8h3tUDVJ4L&sz=w1000 | https://drive.google.com/file/d/1Jq87qjyP8CX6GzfZ6UTJqN8h3tUDVJ4L/view | https://drive.google.com/thumbnail?id=11ckN00HUeGC8mZ4NTbuNo3XBAKRafCzJ&sz=w1000 | https://drive.google.com/file/d/11ckN00HUeGC8mZ4NTbuNo3XBAKRafCzJ/view
2024-08-12 | Khalifa City-Majlis-P2 | P2 | MJ-06 | 89 | 521 | 610 | • Building Permits issued on 21/05/2024. • Shoring Approval 16/07/2024. • Completion of site fencing and installation of signboard 24/07/2024. • Delivery of Site offices. | Commencement Date 15/05/2024 | 3.15% | 1.96% | -1.19% | Superstructure | 2025-09-01 |  | 2025-10-05 | 2024-08-16 | • Relocation of existing services two (2) ADDC cables with feeder pillar. • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • Delay in submissions of and insurances and grantees. • NOCs for fencing permit.(ADDC rejection) | • Approved contractor to re-route the existing services-started the process to obtain Work order from ADDC.(ongoing) • Submission of MEP subcontractor to Engineer for approval. • Technical workshop with specialist to finalize all required clarifications. • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities • Re-route the existing services-commence the execution of re-routing.(PS) • Finalized the selection of shelter special equipment. • Procurement of MEP subcontractor. |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=19ZTyE2xeT2sZ01YGBhW0hDNK1zkOgzov&sz=w1000 | https://drive.google.com/file/d/19ZTyE2xeT2sZ01YGBhW0hDNK1zkOgzov/view | https://drive.google.com/thumbnail?id=1Jq87qjyP8CX6GzfZ6UTJqN8h3tUDVJ4L&sz=w1000 | https://drive.google.com/file/d/1Jq87qjyP8CX6GzfZ6UTJqN8h3tUDVJ4L/view | https://drive.google.com/thumbnail?id=11ckN00HUeGC8mZ4NTbuNo3XBAKRafCzJ&sz=w1000 | https://drive.google.com/file/d/11ckN00HUeGC8mZ4NTbuNo3XBAKRafCzJ/view
2024-08-12 | Khalifa City-Majlis-P2 | P2 | MJ-06 | 89 | 521 | 610 | • Building Permits issued on 21/05/2024. • Shoring Approval 16/07/2024. • Completion of site fencing and installation of signboard 24/07/2024. • Delivery of Site offices. | Commencement Date 15/05/2024 | 3.15% | 1.96% | -1.19% | MEP | 2025-11-04 |  | 2025-12-06 | 2024-08-16 | • Relocation of existing services two (2) ADDC cables with feeder pillar. • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • Delay in submissions of and insurances and grantees. • NOCs for fencing permit.(ADDC rejection) | • Approved contractor to re-route the existing services-started the process to obtain Work order from ADDC.(ongoing) • Submission of MEP subcontractor to Engineer for approval. • Technical workshop with specialist to finalize all required clarifications. • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities • Re-route the existing services-commence the execution of re-routing.(PS) • Finalized the selection of shelter special equipment. • Procurement of MEP subcontractor. |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=19ZTyE2xeT2sZ01YGBhW0hDNK1zkOgzov&sz=w1000 | https://drive.google.com/file/d/19ZTyE2xeT2sZ01YGBhW0hDNK1zkOgzov/view | https://drive.google.com/thumbnail?id=1Jq87qjyP8CX6GzfZ6UTJqN8h3tUDVJ4L&sz=w1000 | https://drive.google.com/file/d/1Jq87qjyP8CX6GzfZ6UTJqN8h3tUDVJ4L/view | https://drive.google.com/thumbnail?id=11ckN00HUeGC8mZ4NTbuNo3XBAKRafCzJ&sz=w1000 | https://drive.google.com/file/d/11ckN00HUeGC8mZ4NTbuNo3XBAKRafCzJ/view
2024-08-12 | Khalifa City-Majlis-P2 | P2 | MJ-06 | 89 | 521 | 610 | • Building Permits issued on 21/05/2024. • Shoring Approval 16/07/2024. • Completion of site fencing and installation of signboard 24/07/2024. • Delivery of Site offices. | Commencement Date 15/05/2024 | 3.15% | 1.96% | -1.19% | Interior Finishes | 2025-11-14 |  | 2025-12-10 | 2024-08-16 | • Relocation of existing services two (2) ADDC cables with feeder pillar. • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • Delay in submissions of and insurances and grantees. • NOCs for fencing permit.(ADDC rejection) | • Approved contractor to re-route the existing services-started the process to obtain Work order from ADDC.(ongoing) • Submission of MEP subcontractor to Engineer for approval. • Technical workshop with specialist to finalize all required clarifications. • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities • Re-route the existing services-commence the execution of re-routing.(PS) • Finalized the selection of shelter special equipment. • Procurement of MEP subcontractor. |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=19ZTyE2xeT2sZ01YGBhW0hDNK1zkOgzov&sz=w1000 | https://drive.google.com/file/d/19ZTyE2xeT2sZ01YGBhW0hDNK1zkOgzov/view | https://drive.google.com/thumbnail?id=1Jq87qjyP8CX6GzfZ6UTJqN8h3tUDVJ4L&sz=w1000 | https://drive.google.com/file/d/1Jq87qjyP8CX6GzfZ6UTJqN8h3tUDVJ4L/view | https://drive.google.com/thumbnail?id=11ckN00HUeGC8mZ4NTbuNo3XBAKRafCzJ&sz=w1000 | https://drive.google.com/file/d/11ckN00HUeGC8mZ4NTbuNo3XBAKRafCzJ/view
2024-08-12 | Khalifa City-Majlis-P2 | P2 | MJ-06 | 89 | 521 | 610 | • Building Permits issued on 21/05/2024. • Shoring Approval 16/07/2024. • Completion of site fencing and installation of signboard 24/07/2024. • Delivery of Site offices. | Commencement Date 15/05/2024 | 3.15% | 1.96% | -1.19% | Power On | 2025-11-20 |  | 2025-12-16 | 2024-08-16 | • Relocation of existing services two (2) ADDC cables with feeder pillar. • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • Delay in submissions of and insurances and grantees. • NOCs for fencing permit.(ADDC rejection) | • Approved contractor to re-route the existing services-started the process to obtain Work order from ADDC.(ongoing) • Submission of MEP subcontractor to Engineer for approval. • Technical workshop with specialist to finalize all required clarifications. • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities • Re-route the existing services-commence the execution of re-routing.(PS) • Finalized the selection of shelter special equipment. • Procurement of MEP subcontractor. |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=19ZTyE2xeT2sZ01YGBhW0hDNK1zkOgzov&sz=w1000 | https://drive.google.com/file/d/19ZTyE2xeT2sZ01YGBhW0hDNK1zkOgzov/view | https://drive.google.com/thumbnail?id=1Jq87qjyP8CX6GzfZ6UTJqN8h3tUDVJ4L&sz=w1000 | https://drive.google.com/file/d/1Jq87qjyP8CX6GzfZ6UTJqN8h3tUDVJ4L/view | https://drive.google.com/thumbnail?id=11ckN00HUeGC8mZ4NTbuNo3XBAKRafCzJ&sz=w1000 | https://drive.google.com/file/d/11ckN00HUeGC8mZ4NTbuNo3XBAKRafCzJ/view
2024-08-12 | Khalifa City-Majlis-P2 | P2 | MJ-06 | 89 | 521 | 610 | • Building Permits issued on 21/05/2024. • Shoring Approval 16/07/2024. • Completion of site fencing and installation of signboard 24/07/2024. • Delivery of Site offices. | Commencement Date 15/05/2024 | 3.15% | 1.96% | -1.19% | Substantial Completion | 2025-12-08 |  | 2026-01-03 | 2024-08-16 | • Relocation of existing services two (2) ADDC cables with feeder pillar. • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • Delay in submissions of and insurances and grantees. • NOCs for fencing permit.(ADDC rejection) | • Approved contractor to re-route the existing services-started the process to obtain Work order from ADDC.(ongoing) • Submission of MEP subcontractor to Engineer for approval. • Technical workshop with specialist to finalize all required clarifications. • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities • Re-route the existing services-commence the execution of re-routing.(PS) • Finalized the selection of shelter special equipment. • Procurement of MEP subcontractor. |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=19ZTyE2xeT2sZ01YGBhW0hDNK1zkOgzov&sz=w1000 | https://drive.google.com/file/d/19ZTyE2xeT2sZ01YGBhW0hDNK1zkOgzov/view | https://drive.google.com/thumbnail?id=1Jq87qjyP8CX6GzfZ6UTJqN8h3tUDVJ4L&sz=w1000 | https://drive.google.com/file/d/1Jq87qjyP8CX6GzfZ6UTJqN8h3tUDVJ4L/view | https://drive.google.com/thumbnail?id=11ckN00HUeGC8mZ4NTbuNo3XBAKRafCzJ&sz=w1000 | https://drive.google.com/file/d/11ckN00HUeGC8mZ4NTbuNo3XBAKRafCzJ/view
2024-08-12 | Khalifa City-Majlis-P2 | P2 | MJ-06 | 89 | 521 | 610 | • Building Permits issued on 21/05/2024. • Shoring Approval 16/07/2024. • Completion of site fencing and installation of signboard 24/07/2024. • Delivery of Site offices. | Commencement Date 15/05/2024 | 3.15% | 1.96% | -1.19% | Handing Over | 2026-01-14 |  | 2026-02-15 | 2024-08-16 | • Relocation of existing services two (2) ADDC cables with feeder pillar. • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • Delay in submissions of and insurances and grantees. • NOCs for fencing permit.(ADDC rejection) | • Approved contractor to re-route the existing services-started the process to obtain Work order from ADDC.(ongoing) • Submission of MEP subcontractor to Engineer for approval. • Technical workshop with specialist to finalize all required clarifications. • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities • Re-route the existing services-commence the execution of re-routing.(PS) • Finalized the selection of shelter special equipment. • Procurement of MEP subcontractor. |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=19ZTyE2xeT2sZ01YGBhW0hDNK1zkOgzov&sz=w1000 | https://drive.google.com/file/d/19ZTyE2xeT2sZ01YGBhW0hDNK1zkOgzov/view | https://drive.google.com/thumbnail?id=1Jq87qjyP8CX6GzfZ6UTJqN8h3tUDVJ4L&sz=w1000 | https://drive.google.com/file/d/1Jq87qjyP8CX6GzfZ6UTJqN8h3tUDVJ4L/view | https://drive.google.com/thumbnail?id=11ckN00HUeGC8mZ4NTbuNo3XBAKRafCzJ&sz=w1000 | https://drive.google.com/file/d/11ckN00HUeGC8mZ4NTbuNo3XBAKRafCzJ/view
2024-08-12 | Mohamed Bin Zayed City-Majlis-P9 | P9 | MJ-07 | 89 | 521 | 610 | • Building Permits issued on 21/05/2024. • Completion of site fencing and signboard installation 23/07/2024. • Shoring Design approval 23/07/2024. | Commencement Date instruction 15/05/2024 | 3.61% | 2.84% | -0.77% | Notice to Commence | 2024-05-15 | 2024-05-15 |  | 2024-08-16 | • Delay in establishment of site offices. • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • NOCs for fencing permit. • Finalize the authorities approval for the Mosque | • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities.(ongoing) • Finalized the selection of shelter special equipment.(ongoing) • Procurement of MEP subcontractor. • Guide Beam and secant Piles for shoring works(ongoing) • Commence the shoring works. |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1XRwotDLG4Wn7ltT3YhUdshMCpqVktKT8&sz=w1000 | https://drive.google.com/file/d/1XRwotDLG4Wn7ltT3YhUdshMCpqVktKT8/view | https://drive.google.com/thumbnail?id=1m0sCGqTc1t6OyfiPeptI64GQWmQuBkv8&sz=w1000 | https://drive.google.com/file/d/1m0sCGqTc1t6OyfiPeptI64GQWmQuBkv8/view?usp=drive_link | https://drive.google.com/thumbnail?id=1davhSxDuZNhi5xMvx1qc6yUbp9a-alvk&sz=w1000 | https://drive.google.com/file/d/1davhSxDuZNhi5xMvx1qc6yUbp9a-alvk/view?usp=drive_link
2024-08-12 | Mohamed Bin Zayed City-Majlis-P9 | P9 | MJ-07 | 89 | 521 | 610 | • Building Permits issued on 21/05/2024. • Completion of site fencing and signboard installation 23/07/2024. • Shoring Design approval 23/07/2024. | Commencement Date instruction 15/05/2024 | 3.61% | 2.84% | -0.77% | Building Permit | 2024-05-21 | 2024-05-21 |  | 2024-08-16 | • Delay in establishment of site offices. • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • NOCs for fencing permit. • Finalize the authorities approval for the Mosque | • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities.(ongoing) • Finalized the selection of shelter special equipment.(ongoing) • Procurement of MEP subcontractor. • Guide Beam and secant Piles for shoring works(ongoing) • Commence the shoring works. |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1XRwotDLG4Wn7ltT3YhUdshMCpqVktKT8&sz=w1000 | https://drive.google.com/file/d/1XRwotDLG4Wn7ltT3YhUdshMCpqVktKT8/view | https://drive.google.com/thumbnail?id=1m0sCGqTc1t6OyfiPeptI64GQWmQuBkv8&sz=w1000 | https://drive.google.com/file/d/1m0sCGqTc1t6OyfiPeptI64GQWmQuBkv8/view?usp=drive_link | https://drive.google.com/thumbnail?id=1davhSxDuZNhi5xMvx1qc6yUbp9a-alvk&sz=w1000 | https://drive.google.com/file/d/1davhSxDuZNhi5xMvx1qc6yUbp9a-alvk/view?usp=drive_link
2024-08-12 | Mohamed Bin Zayed City-Majlis-P9 | P9 | MJ-07 | 89 | 521 | 610 | • Building Permits issued on 21/05/2024. • Completion of site fencing and signboard installation 23/07/2024. • Shoring Design approval 23/07/2024. | Commencement Date instruction 15/05/2024 | 3.61% | 2.84% | -0.77% | Site Mobilization | 2024-07-20 |  | 2024-09-09 | 2024-08-16 | • Delay in establishment of site offices. • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • NOCs for fencing permit. • Finalize the authorities approval for the Mosque | • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities.(ongoing) • Finalized the selection of shelter special equipment.(ongoing) • Procurement of MEP subcontractor. • Guide Beam and secant Piles for shoring works(ongoing) • Commence the shoring works. |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1XRwotDLG4Wn7ltT3YhUdshMCpqVktKT8&sz=w1000 | https://drive.google.com/file/d/1XRwotDLG4Wn7ltT3YhUdshMCpqVktKT8/view | https://drive.google.com/thumbnail?id=1m0sCGqTc1t6OyfiPeptI64GQWmQuBkv8&sz=w1000 | https://drive.google.com/file/d/1m0sCGqTc1t6OyfiPeptI64GQWmQuBkv8/view?usp=drive_link | https://drive.google.com/thumbnail?id=1davhSxDuZNhi5xMvx1qc6yUbp9a-alvk&sz=w1000 | https://drive.google.com/file/d/1davhSxDuZNhi5xMvx1qc6yUbp9a-alvk/view?usp=drive_link
2024-08-12 | Mohamed Bin Zayed City-Majlis-P9 | P9 | MJ-07 | 89 | 521 | 610 | • Building Permits issued on 21/05/2024. • Completion of site fencing and signboard installation 23/07/2024. • Shoring Design approval 23/07/2024. | Commencement Date instruction 15/05/2024 | 3.61% | 2.84% | -0.77% | Shoring and Piling Completion | 2024-11-07 |  | 2024-11-23 | 2024-08-16 | • Delay in establishment of site offices. • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • NOCs for fencing permit. • Finalize the authorities approval for the Mosque | • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities.(ongoing) • Finalized the selection of shelter special equipment.(ongoing) • Procurement of MEP subcontractor. • Guide Beam and secant Piles for shoring works(ongoing) • Commence the shoring works. |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1XRwotDLG4Wn7ltT3YhUdshMCpqVktKT8&sz=w1000 | https://drive.google.com/file/d/1XRwotDLG4Wn7ltT3YhUdshMCpqVktKT8/view | https://drive.google.com/thumbnail?id=1m0sCGqTc1t6OyfiPeptI64GQWmQuBkv8&sz=w1000 | https://drive.google.com/file/d/1m0sCGqTc1t6OyfiPeptI64GQWmQuBkv8/view?usp=drive_link | https://drive.google.com/thumbnail?id=1davhSxDuZNhi5xMvx1qc6yUbp9a-alvk&sz=w1000 | https://drive.google.com/file/d/1davhSxDuZNhi5xMvx1qc6yUbp9a-alvk/view?usp=drive_link
2024-08-12 | Mohamed Bin Zayed City-Majlis-P9 | P9 | MJ-07 | 89 | 521 | 610 | • Building Permits issued on 21/05/2024. • Completion of site fencing and signboard installation 23/07/2024. • Shoring Design approval 23/07/2024. | Commencement Date instruction 15/05/2024 | 3.61% | 2.84% | -0.77% | Substructure | 2024-12-18 |  | 2025-01-02 | 2024-08-16 | • Delay in establishment of site offices. • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • NOCs for fencing permit. • Finalize the authorities approval for the Mosque | • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities.(ongoing) • Finalized the selection of shelter special equipment.(ongoing) • Procurement of MEP subcontractor. • Guide Beam and secant Piles for shoring works(ongoing) • Commence the shoring works. |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1XRwotDLG4Wn7ltT3YhUdshMCpqVktKT8&sz=w1000 | https://drive.google.com/file/d/1XRwotDLG4Wn7ltT3YhUdshMCpqVktKT8/view | https://drive.google.com/thumbnail?id=1m0sCGqTc1t6OyfiPeptI64GQWmQuBkv8&sz=w1000 | https://drive.google.com/file/d/1m0sCGqTc1t6OyfiPeptI64GQWmQuBkv8/view?usp=drive_link | https://drive.google.com/thumbnail?id=1davhSxDuZNhi5xMvx1qc6yUbp9a-alvk&sz=w1000 | https://drive.google.com/file/d/1davhSxDuZNhi5xMvx1qc6yUbp9a-alvk/view?usp=drive_link
2024-08-12 | Mohamed Bin Zayed City-Majlis-P9 | P9 | MJ-07 | 89 | 521 | 610 | • Building Permits issued on 21/05/2024. • Completion of site fencing and signboard installation 23/07/2024. • Shoring Design approval 23/07/2024. | Commencement Date instruction 15/05/2024 | 3.61% | 2.84% | -0.77% | Superstructure | 2025-08-28 |  | 2025-09-17 | 2024-08-16 | • Delay in establishment of site offices. • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • NOCs for fencing permit. • Finalize the authorities approval for the Mosque | • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities.(ongoing) • Finalized the selection of shelter special equipment.(ongoing) • Procurement of MEP subcontractor. • Guide Beam and secant Piles for shoring works(ongoing) • Commence the shoring works. |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1XRwotDLG4Wn7ltT3YhUdshMCpqVktKT8&sz=w1000 | https://drive.google.com/file/d/1XRwotDLG4Wn7ltT3YhUdshMCpqVktKT8/view | https://drive.google.com/thumbnail?id=1m0sCGqTc1t6OyfiPeptI64GQWmQuBkv8&sz=w1000 | https://drive.google.com/file/d/1m0sCGqTc1t6OyfiPeptI64GQWmQuBkv8/view?usp=drive_link | https://drive.google.com/thumbnail?id=1davhSxDuZNhi5xMvx1qc6yUbp9a-alvk&sz=w1000 | https://drive.google.com/file/d/1davhSxDuZNhi5xMvx1qc6yUbp9a-alvk/view?usp=drive_link
2024-08-12 | Mohamed Bin Zayed City-Majlis-P9 | P9 | MJ-07 | 89 | 521 | 610 | • Building Permits issued on 21/05/2024. • Completion of site fencing and signboard installation 23/07/2024. • Shoring Design approval 23/07/2024. | Commencement Date instruction 15/05/2024 | 3.61% | 2.84% | -0.77% | MEP | 2025-11-04 |  | 2025-11-24 | 2024-08-16 | • Delay in establishment of site offices. • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • NOCs for fencing permit. • Finalize the authorities approval for the Mosque | • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities.(ongoing) • Finalized the selection of shelter special equipment.(ongoing) • Procurement of MEP subcontractor. • Guide Beam and secant Piles for shoring works(ongoing) • Commence the shoring works. |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1XRwotDLG4Wn7ltT3YhUdshMCpqVktKT8&sz=w1000 | https://drive.google.com/file/d/1XRwotDLG4Wn7ltT3YhUdshMCpqVktKT8/view | https://drive.google.com/thumbnail?id=1m0sCGqTc1t6OyfiPeptI64GQWmQuBkv8&sz=w1000 | https://drive.google.com/file/d/1m0sCGqTc1t6OyfiPeptI64GQWmQuBkv8/view?usp=drive_link | https://drive.google.com/thumbnail?id=1davhSxDuZNhi5xMvx1qc6yUbp9a-alvk&sz=w1000 | https://drive.google.com/file/d/1davhSxDuZNhi5xMvx1qc6yUbp9a-alvk/view?usp=drive_link
2024-08-12 | Mohamed Bin Zayed City-Majlis-P9 | P9 | MJ-07 | 89 | 521 | 610 | • Building Permits issued on 21/05/2024. • Completion of site fencing and signboard installation 23/07/2024. • Shoring Design approval 23/07/2024. | Commencement Date instruction 15/05/2024 | 3.61% | 2.84% | -0.77% | Power On | 2025-11-22 |  | 2025-12-12 | 2024-08-16 | • Delay in establishment of site offices. • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • NOCs for fencing permit. • Finalize the authorities approval for the Mosque | • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities.(ongoing) • Finalized the selection of shelter special equipment.(ongoing) • Procurement of MEP subcontractor. • Guide Beam and secant Piles for shoring works(ongoing) • Commence the shoring works. |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1XRwotDLG4Wn7ltT3YhUdshMCpqVktKT8&sz=w1000 | https://drive.google.com/file/d/1XRwotDLG4Wn7ltT3YhUdshMCpqVktKT8/view | https://drive.google.com/thumbnail?id=1m0sCGqTc1t6OyfiPeptI64GQWmQuBkv8&sz=w1000 | https://drive.google.com/file/d/1m0sCGqTc1t6OyfiPeptI64GQWmQuBkv8/view?usp=drive_link | https://drive.google.com/thumbnail?id=1davhSxDuZNhi5xMvx1qc6yUbp9a-alvk&sz=w1000 | https://drive.google.com/file/d/1davhSxDuZNhi5xMvx1qc6yUbp9a-alvk/view?usp=drive_link
2024-08-12 | Mohamed Bin Zayed City-Majlis-P9 | P9 | MJ-07 | 89 | 521 | 610 | • Building Permits issued on 21/05/2024. • Completion of site fencing and signboard installation 23/07/2024. • Shoring Design approval 23/07/2024. | Commencement Date instruction 15/05/2024 | 3.61% | 2.84% | -0.77% | Interior Finishes | 2025-11-22 |  | 2025-12-12 | 2024-08-16 | • Delay in establishment of site offices. • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • NOCs for fencing permit. • Finalize the authorities approval for the Mosque | • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities.(ongoing) • Finalized the selection of shelter special equipment.(ongoing) • Procurement of MEP subcontractor. • Guide Beam and secant Piles for shoring works(ongoing) • Commence the shoring works. |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1XRwotDLG4Wn7ltT3YhUdshMCpqVktKT8&sz=w1000 | https://drive.google.com/file/d/1XRwotDLG4Wn7ltT3YhUdshMCpqVktKT8/view | https://drive.google.com/thumbnail?id=1m0sCGqTc1t6OyfiPeptI64GQWmQuBkv8&sz=w1000 | https://drive.google.com/file/d/1m0sCGqTc1t6OyfiPeptI64GQWmQuBkv8/view?usp=drive_link | https://drive.google.com/thumbnail?id=1davhSxDuZNhi5xMvx1qc6yUbp9a-alvk&sz=w1000 | https://drive.google.com/file/d/1davhSxDuZNhi5xMvx1qc6yUbp9a-alvk/view?usp=drive_link
2024-08-12 | Mohamed Bin Zayed City-Majlis-P9 | P9 | MJ-07 | 89 | 521 | 610 | • Building Permits issued on 21/05/2024. • Completion of site fencing and signboard installation 23/07/2024. • Shoring Design approval 23/07/2024. | Commencement Date instruction 15/05/2024 | 3.61% | 2.84% | -0.77% | Substantial Completion | 2025-12-15 |  | 2026-01-04 | 2024-08-16 | • Delay in establishment of site offices. • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • NOCs for fencing permit. • Finalize the authorities approval for the Mosque | • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities.(ongoing) • Finalized the selection of shelter special equipment.(ongoing) • Procurement of MEP subcontractor. • Guide Beam and secant Piles for shoring works(ongoing) • Commence the shoring works. |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1XRwotDLG4Wn7ltT3YhUdshMCpqVktKT8&sz=w1000 | https://drive.google.com/file/d/1XRwotDLG4Wn7ltT3YhUdshMCpqVktKT8/view | https://drive.google.com/thumbnail?id=1m0sCGqTc1t6OyfiPeptI64GQWmQuBkv8&sz=w1000 | https://drive.google.com/file/d/1m0sCGqTc1t6OyfiPeptI64GQWmQuBkv8/view?usp=drive_link | https://drive.google.com/thumbnail?id=1davhSxDuZNhi5xMvx1qc6yUbp9a-alvk&sz=w1000 | https://drive.google.com/file/d/1davhSxDuZNhi5xMvx1qc6yUbp9a-alvk/view?usp=drive_link
2024-08-12 | Mohamed Bin Zayed City-Majlis-P9 | P9 | MJ-07 | 89 | 521 | 610 | • Building Permits issued on 21/05/2024. • Completion of site fencing and signboard installation 23/07/2024. • Shoring Design approval 23/07/2024. | Commencement Date instruction 15/05/2024 | 3.61% | 2.84% | -0.77% | Handing Over | 2026-01-14 |  | 2026-02-04 | 2024-08-16 | • Delay in establishment of site offices. • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • NOCs for fencing permit. • Finalize the authorities approval for the Mosque | • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities.(ongoing) • Finalized the selection of shelter special equipment.(ongoing) • Procurement of MEP subcontractor. • Guide Beam and secant Piles for shoring works(ongoing) • Commence the shoring works. |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1XRwotDLG4Wn7ltT3YhUdshMCpqVktKT8&sz=w1000 | https://drive.google.com/file/d/1XRwotDLG4Wn7ltT3YhUdshMCpqVktKT8/view | https://drive.google.com/thumbnail?id=1m0sCGqTc1t6OyfiPeptI64GQWmQuBkv8&sz=w1000 | https://drive.google.com/file/d/1m0sCGqTc1t6OyfiPeptI64GQWmQuBkv8/view?usp=drive_link | https://drive.google.com/thumbnail?id=1davhSxDuZNhi5xMvx1qc6yUbp9a-alvk&sz=w1000 | https://drive.google.com/file/d/1davhSxDuZNhi5xMvx1qc6yUbp9a-alvk/view?usp=drive_link
2024-08-12 | Al Shawamekh-Majlis-P15 | P15 | MJ-15 | 0 | 610 | 610 |  |  | 0% | 0% | 0% | Notice to Commence | 2024-09-15 |  |  | 2024-08-16 | Delay of Building permit. | • Lab completed Topographic and Geophysical survey. • ADM approval to proceed with Geotechnical survey and soil investigation report. • Contractor to obtain approval from A lDar for logistic and mobilization plans. • Contractor to deliver the signboard and fencing material to the site. • Hiring sufficient and qualified staff. • Procurement for major subcontractor. • Procurement of long lead items. | • Completion of geotechnical report. • Finalize structural design and complete Building Permit process. • Fencing and sign board. • Finalize the contractor submission for variation (additional majlis) • Engineering works. |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1dOSANF0t0AMhLvT5qlmKuF_szpDrFIOV&sz=w1000 | https://drive.google.com/file/d/1dOSANF0t0AMhLvT5qlmKuF_szpDrFIOV/view | https://drive.google.com/thumbnail?id=1UQjOfPn-C05A2ksrxMwMtksI2P0xlIz8&sz=w1000 | https://drive.google.com/file/d/1UQjOfPn-C05A2ksrxMwMtksI2P0xlIz8/view | https://drive.google.com/thumbnail?id=1OnwdPVGGVlXHeDo0NSoyMOqv2DdSXlPD&sz=w1000 | https://drive.google.com/file/d/1OnwdPVGGVlXHeDo0NSoyMOqv2DdSXlPD/view
2024-08-12 | Al Shawamekh-Majlis-P15 | P15 | MJ-15 | 0 | 610 | 610 |  |  | 0% | 0% | 0% | Building Permit | 2024-09-21 |  |  | 2024-08-16 | Delay of Building permit. | • Lab completed Topographic and Geophysical survey. • ADM approval to proceed with Geotechnical survey and soil investigation report. • Contractor to obtain approval from A lDar for logistic and mobilization plans. • Contractor to deliver the signboard and fencing material to the site. • Hiring sufficient and qualified staff. • Procurement for major subcontractor. • Procurement of long lead items. | • Completion of geotechnical report. • Finalize structural design and complete Building Permit process. • Fencing and sign board. • Finalize the contractor submission for variation (additional majlis) • Engineering works. |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1dOSANF0t0AMhLvT5qlmKuF_szpDrFIOV&sz=w1000 | https://drive.google.com/file/d/1dOSANF0t0AMhLvT5qlmKuF_szpDrFIOV/view | https://drive.google.com/thumbnail?id=1UQjOfPn-C05A2ksrxMwMtksI2P0xlIz8&sz=w1000 | https://drive.google.com/file/d/1UQjOfPn-C05A2ksrxMwMtksI2P0xlIz8/view | https://drive.google.com/thumbnail?id=1OnwdPVGGVlXHeDo0NSoyMOqv2DdSXlPD&sz=w1000 | https://drive.google.com/file/d/1OnwdPVGGVlXHeDo0NSoyMOqv2DdSXlPD/view
2024-08-12 | Al Shawamekh-Majlis-P15 | P15 | MJ-15 | 0 | 610 | 610 |  |  | 0% | 0% | 0% | Site Mobilization | 2024-10-14 |  |  | 2024-08-16 | Delay of Building permit. | • Lab completed Topographic and Geophysical survey. • ADM approval to proceed with Geotechnical survey and soil investigation report. • Contractor to obtain approval from A lDar for logistic and mobilization plans. • Contractor to deliver the signboard and fencing material to the site. • Hiring sufficient and qualified staff. • Procurement for major subcontractor. • Procurement of long lead items. | • Completion of geotechnical report. • Finalize structural design and complete Building Permit process. • Fencing and sign board. • Finalize the contractor submission for variation (additional majlis) • Engineering works. |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1dOSANF0t0AMhLvT5qlmKuF_szpDrFIOV&sz=w1000 | https://drive.google.com/file/d/1dOSANF0t0AMhLvT5qlmKuF_szpDrFIOV/view | https://drive.google.com/thumbnail?id=1UQjOfPn-C05A2ksrxMwMtksI2P0xlIz8&sz=w1000 | https://drive.google.com/file/d/1UQjOfPn-C05A2ksrxMwMtksI2P0xlIz8/view | https://drive.google.com/thumbnail?id=1OnwdPVGGVlXHeDo0NSoyMOqv2DdSXlPD&sz=w1000 | https://drive.google.com/file/d/1OnwdPVGGVlXHeDo0NSoyMOqv2DdSXlPD/view
2024-08-12 | Mohamed Bin Zayed City-Majlis-P2 | P2 | MJ-12 | 28 | 580 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/08/2024. | Commencement Date 16/07/2024 | 0% | 0% | 0% | Notice to Commence | 2024-07-16 | 2024-07-16 |  | 2024-08-16 | • Engaging with the authorities regarding the adjacent plot 5 cm impact. • Submit construction NOC to explore the crossing cables if any. • YAS is to submit the Advance Payment guarantee, Bonds and insurances. • Resources availability • Legal and Regulatory • Delays in engineering /procurement and subs • Safety risk • Delays in Sign board and fence installation | • Follow up to obtain the required construction NOCs approval. • Finalize staff deployment • Evaluate and appoint the shoring subcontractor • Submission of Engineering log /procurement log especially the long lead items. • Ensure Adherence to safety plan and codes and international standards. • Asses Shelter Special systems suppliers for recommendation and appointment • submission of Baseline program in accordance with the contract. | • submission the baseline program along with construction methodology target date(12/08/2024) • Revise the Project HSE plan summation the and construction environment management plan target date(12/08/2024) • submission the Advance Payment guarantee, Bonds and insurances target date(15/08/2024) • submission the Pre-Qualifications of shoring Sub-Contractors target date (12/08/2024) • submission the Pre-Qualifications of Piles Sub-Contractors target date (20/08/2024) • Contract agreement target date(25/08/2024) • Contract deliverables target date(31/08/2024) |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1Xx52lP-CL3Mjgh7XgJuGe8OZtl_A0Kie&sz=w1000 | https://drive.google.com/file/d/1Xx52lP-CL3Mjgh7XgJuGe8OZtl_A0Kie/view | https://drive.google.com/thumbnail?id=1TL9IrzKlPKxuk1hHUSBJEQg3OHu9BPMb&sz=w1000 | https://drive.google.com/file/d/1TL9IrzKlPKxuk1hHUSBJEQg3OHu9BPMb/view | https://drive.google.com/thumbnail?id=1mjk5nvW4b1WflrBJK-EEPQRX1KlRm6e2&sz=w1000 | https://drive.google.com/file/d/1mjk5nvW4b1WflrBJK-EEPQRX1KlRm6e2/view
2024-08-12 | Mohamed Bin Zayed City-Majlis-P2 | P2 | MJ-12 | 28 | 580 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/08/2024. | Commencement Date 16/07/2024 | 0% | 0% | 0% | Building Permit | 2024-07-04 |  | 2024-08-03 | 2024-08-16 | • Engaging with the authorities regarding the adjacent plot 5 cm impact. • Submit construction NOC to explore the crossing cables if any. • YAS is to submit the Advance Payment guarantee, Bonds and insurances. • Resources availability • Legal and Regulatory • Delays in engineering /procurement and subs • Safety risk • Delays in Sign board and fence installation | • Follow up to obtain the required construction NOCs approval. • Finalize staff deployment • Evaluate and appoint the shoring subcontractor • Submission of Engineering log /procurement log especially the long lead items. • Ensure Adherence to safety plan and codes and international standards. • Asses Shelter Special systems suppliers for recommendation and appointment • submission of Baseline program in accordance with the contract. | • submission the baseline program along with construction methodology target date(12/08/2024) • Revise the Project HSE plan summation the and construction environment management plan target date(12/08/2024) • submission the Advance Payment guarantee, Bonds and insurances target date(15/08/2024) • submission the Pre-Qualifications of shoring Sub-Contractors target date (12/08/2024) • submission the Pre-Qualifications of Piles Sub-Contractors target date (20/08/2024) • Contract agreement target date(25/08/2024) • Contract deliverables target date(31/08/2024) |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1Xx52lP-CL3Mjgh7XgJuGe8OZtl_A0Kie&sz=w1000 | https://drive.google.com/file/d/1Xx52lP-CL3Mjgh7XgJuGe8OZtl_A0Kie/view | https://drive.google.com/thumbnail?id=1TL9IrzKlPKxuk1hHUSBJEQg3OHu9BPMb&sz=w1000 | https://drive.google.com/file/d/1TL9IrzKlPKxuk1hHUSBJEQg3OHu9BPMb/view | https://drive.google.com/thumbnail?id=1mjk5nvW4b1WflrBJK-EEPQRX1KlRm6e2&sz=w1000 | https://drive.google.com/file/d/1mjk5nvW4b1WflrBJK-EEPQRX1KlRm6e2/view
2024-08-12 | Mohamed Bin Zayed City-Majlis-P2 | P2 | MJ-12 | 28 | 580 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/08/2024. | Commencement Date 16/07/2024 | 0% | 0% | 0% | Demarcation | 2024-07-26 |  | 2024-07-26 | 2024-08-16 | • Engaging with the authorities regarding the adjacent plot 5 cm impact. • Submit construction NOC to explore the crossing cables if any. • YAS is to submit the Advance Payment guarantee, Bonds and insurances. • Resources availability • Legal and Regulatory • Delays in engineering /procurement and subs • Safety risk • Delays in Sign board and fence installation | • Follow up to obtain the required construction NOCs approval. • Finalize staff deployment • Evaluate and appoint the shoring subcontractor • Submission of Engineering log /procurement log especially the long lead items. • Ensure Adherence to safety plan and codes and international standards. • Asses Shelter Special systems suppliers for recommendation and appointment • submission of Baseline program in accordance with the contract. | • submission the baseline program along with construction methodology target date(12/08/2024) • Revise the Project HSE plan summation the and construction environment management plan target date(12/08/2024) • submission the Advance Payment guarantee, Bonds and insurances target date(15/08/2024) • submission the Pre-Qualifications of shoring Sub-Contractors target date (12/08/2024) • submission the Pre-Qualifications of Piles Sub-Contractors target date (20/08/2024) • Contract agreement target date(25/08/2024) • Contract deliverables target date(31/08/2024) |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1Xx52lP-CL3Mjgh7XgJuGe8OZtl_A0Kie&sz=w1000 | https://drive.google.com/file/d/1Xx52lP-CL3Mjgh7XgJuGe8OZtl_A0Kie/view | https://drive.google.com/thumbnail?id=1TL9IrzKlPKxuk1hHUSBJEQg3OHu9BPMb&sz=w1000 | https://drive.google.com/file/d/1TL9IrzKlPKxuk1hHUSBJEQg3OHu9BPMb/view | https://drive.google.com/thumbnail?id=1mjk5nvW4b1WflrBJK-EEPQRX1KlRm6e2&sz=w1000 | https://drive.google.com/file/d/1mjk5nvW4b1WflrBJK-EEPQRX1KlRm6e2/view
2024-08-12 | Mohamed Bin Zayed City-Majlis-P2 | P2 | MJ-12 | 28 | 580 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/08/2024. | Commencement Date 16/07/2024 | 0% | 0% | 0% | Fencing & Signboard Fabrication | 2024-07-30 |  | 2024-07-30 | 2024-08-16 | • Engaging with the authorities regarding the adjacent plot 5 cm impact. • Submit construction NOC to explore the crossing cables if any. • YAS is to submit the Advance Payment guarantee, Bonds and insurances. • Resources availability • Legal and Regulatory • Delays in engineering /procurement and subs • Safety risk • Delays in Sign board and fence installation | • Follow up to obtain the required construction NOCs approval. • Finalize staff deployment • Evaluate and appoint the shoring subcontractor • Submission of Engineering log /procurement log especially the long lead items. • Ensure Adherence to safety plan and codes and international standards. • Asses Shelter Special systems suppliers for recommendation and appointment • submission of Baseline program in accordance with the contract. | • submission the baseline program along with construction methodology target date(12/08/2024) • Revise the Project HSE plan summation the and construction environment management plan target date(12/08/2024) • submission the Advance Payment guarantee, Bonds and insurances target date(15/08/2024) • submission the Pre-Qualifications of shoring Sub-Contractors target date (12/08/2024) • submission the Pre-Qualifications of Piles Sub-Contractors target date (20/08/2024) • Contract agreement target date(25/08/2024) • Contract deliverables target date(31/08/2024) |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1Xx52lP-CL3Mjgh7XgJuGe8OZtl_A0Kie&sz=w1000 | https://drive.google.com/file/d/1Xx52lP-CL3Mjgh7XgJuGe8OZtl_A0Kie/view | https://drive.google.com/thumbnail?id=1TL9IrzKlPKxuk1hHUSBJEQg3OHu9BPMb&sz=w1000 | https://drive.google.com/file/d/1TL9IrzKlPKxuk1hHUSBJEQg3OHu9BPMb/view | https://drive.google.com/thumbnail?id=1mjk5nvW4b1WflrBJK-EEPQRX1KlRm6e2&sz=w1000 | https://drive.google.com/file/d/1mjk5nvW4b1WflrBJK-EEPQRX1KlRm6e2/view
2024-08-12 | Mohamed Bin Zayed City-Majlis-P2 | P2 | MJ-12 | 28 | 580 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/08/2024. | Commencement Date 16/07/2024 | 0% | 0% | 0% | Signboard Installation | 2024-08-03 |  | 2024-08-09 | 2024-08-16 | • Engaging with the authorities regarding the adjacent plot 5 cm impact. • Submit construction NOC to explore the crossing cables if any. • YAS is to submit the Advance Payment guarantee, Bonds and insurances. • Resources availability • Legal and Regulatory • Delays in engineering /procurement and subs • Safety risk • Delays in Sign board and fence installation | • Follow up to obtain the required construction NOCs approval. • Finalize staff deployment • Evaluate and appoint the shoring subcontractor • Submission of Engineering log /procurement log especially the long lead items. • Ensure Adherence to safety plan and codes and international standards. • Asses Shelter Special systems suppliers for recommendation and appointment • submission of Baseline program in accordance with the contract. | • submission the baseline program along with construction methodology target date(12/08/2024) • Revise the Project HSE plan summation the and construction environment management plan target date(12/08/2024) • submission the Advance Payment guarantee, Bonds and insurances target date(15/08/2024) • submission the Pre-Qualifications of shoring Sub-Contractors target date (12/08/2024) • submission the Pre-Qualifications of Piles Sub-Contractors target date (20/08/2024) • Contract agreement target date(25/08/2024) • Contract deliverables target date(31/08/2024) |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1Xx52lP-CL3Mjgh7XgJuGe8OZtl_A0Kie&sz=w1000 | https://drive.google.com/file/d/1Xx52lP-CL3Mjgh7XgJuGe8OZtl_A0Kie/view | https://drive.google.com/thumbnail?id=1TL9IrzKlPKxuk1hHUSBJEQg3OHu9BPMb&sz=w1000 | https://drive.google.com/file/d/1TL9IrzKlPKxuk1hHUSBJEQg3OHu9BPMb/view | https://drive.google.com/thumbnail?id=1mjk5nvW4b1WflrBJK-EEPQRX1KlRm6e2&sz=w1000 | https://drive.google.com/file/d/1mjk5nvW4b1WflrBJK-EEPQRX1KlRm6e2/view
2024-08-12 | Mohamed Bin Zayed City-Majlis-P2 | P2 | MJ-12 | 28 | 580 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/08/2024. | Commencement Date 16/07/2024 | 0% | 0% | 0% | Fencing Installation | 2024-08-03 |  | 2024-08-09 | 2024-08-16 | • Engaging with the authorities regarding the adjacent plot 5 cm impact. • Submit construction NOC to explore the crossing cables if any. • YAS is to submit the Advance Payment guarantee, Bonds and insurances. • Resources availability • Legal and Regulatory • Delays in engineering /procurement and subs • Safety risk • Delays in Sign board and fence installation | • Follow up to obtain the required construction NOCs approval. • Finalize staff deployment • Evaluate and appoint the shoring subcontractor • Submission of Engineering log /procurement log especially the long lead items. • Ensure Adherence to safety plan and codes and international standards. • Asses Shelter Special systems suppliers for recommendation and appointment • submission of Baseline program in accordance with the contract. | • submission the baseline program along with construction methodology target date(12/08/2024) • Revise the Project HSE plan summation the and construction environment management plan target date(12/08/2024) • submission the Advance Payment guarantee, Bonds and insurances target date(15/08/2024) • submission the Pre-Qualifications of shoring Sub-Contractors target date (12/08/2024) • submission the Pre-Qualifications of Piles Sub-Contractors target date (20/08/2024) • Contract agreement target date(25/08/2024) • Contract deliverables target date(31/08/2024) |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1Xx52lP-CL3Mjgh7XgJuGe8OZtl_A0Kie&sz=w1000 | https://drive.google.com/file/d/1Xx52lP-CL3Mjgh7XgJuGe8OZtl_A0Kie/view | https://drive.google.com/thumbnail?id=1TL9IrzKlPKxuk1hHUSBJEQg3OHu9BPMb&sz=w1000 | https://drive.google.com/file/d/1TL9IrzKlPKxuk1hHUSBJEQg3OHu9BPMb/view | https://drive.google.com/thumbnail?id=1mjk5nvW4b1WflrBJK-EEPQRX1KlRm6e2&sz=w1000 | https://drive.google.com/file/d/1mjk5nvW4b1WflrBJK-EEPQRX1KlRm6e2/view
2024-08-12 | Mohamed Bin Zayed City-Majlis-P2 | P2 | MJ-12 | 28 | 580 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/08/2024. | Commencement Date 16/07/2024 | 0% | 0% | 0% | Site offices Fabrication | 2024-08-07 |  | 2024-08-07 | 2024-08-16 | • Engaging with the authorities regarding the adjacent plot 5 cm impact. • Submit construction NOC to explore the crossing cables if any. • YAS is to submit the Advance Payment guarantee, Bonds and insurances. • Resources availability • Legal and Regulatory • Delays in engineering /procurement and subs • Safety risk • Delays in Sign board and fence installation | • Follow up to obtain the required construction NOCs approval. • Finalize staff deployment • Evaluate and appoint the shoring subcontractor • Submission of Engineering log /procurement log especially the long lead items. • Ensure Adherence to safety plan and codes and international standards. • Asses Shelter Special systems suppliers for recommendation and appointment • submission of Baseline program in accordance with the contract. | • submission the baseline program along with construction methodology target date(12/08/2024) • Revise the Project HSE plan summation the and construction environment management plan target date(12/08/2024) • submission the Advance Payment guarantee, Bonds and insurances target date(15/08/2024) • submission the Pre-Qualifications of shoring Sub-Contractors target date (12/08/2024) • submission the Pre-Qualifications of Piles Sub-Contractors target date (20/08/2024) • Contract agreement target date(25/08/2024) • Contract deliverables target date(31/08/2024) |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1Xx52lP-CL3Mjgh7XgJuGe8OZtl_A0Kie&sz=w1000 | https://drive.google.com/file/d/1Xx52lP-CL3Mjgh7XgJuGe8OZtl_A0Kie/view | https://drive.google.com/thumbnail?id=1TL9IrzKlPKxuk1hHUSBJEQg3OHu9BPMb&sz=w1000 | https://drive.google.com/file/d/1TL9IrzKlPKxuk1hHUSBJEQg3OHu9BPMb/view | https://drive.google.com/thumbnail?id=1mjk5nvW4b1WflrBJK-EEPQRX1KlRm6e2&sz=w1000 | https://drive.google.com/file/d/1mjk5nvW4b1WflrBJK-EEPQRX1KlRm6e2/view
2024-08-12 | Mohamed Bin Zayed City-Majlis-P2 | P2 | MJ-12 | 28 | 580 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/08/2024. | Commencement Date 16/07/2024 | 0% | 0% | 0% | Site offices Installation | 2024-08-28 |  | 2024-08-28 | 2024-08-16 | • Engaging with the authorities regarding the adjacent plot 5 cm impact. • Submit construction NOC to explore the crossing cables if any. • YAS is to submit the Advance Payment guarantee, Bonds and insurances. • Resources availability • Legal and Regulatory • Delays in engineering /procurement and subs • Safety risk • Delays in Sign board and fence installation | • Follow up to obtain the required construction NOCs approval. • Finalize staff deployment • Evaluate and appoint the shoring subcontractor • Submission of Engineering log /procurement log especially the long lead items. • Ensure Adherence to safety plan and codes and international standards. • Asses Shelter Special systems suppliers for recommendation and appointment • submission of Baseline program in accordance with the contract. | • submission the baseline program along with construction methodology target date(12/08/2024) • Revise the Project HSE plan summation the and construction environment management plan target date(12/08/2024) • submission the Advance Payment guarantee, Bonds and insurances target date(15/08/2024) • submission the Pre-Qualifications of shoring Sub-Contractors target date (12/08/2024) • submission the Pre-Qualifications of Piles Sub-Contractors target date (20/08/2024) • Contract agreement target date(25/08/2024) • Contract deliverables target date(31/08/2024) |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1Xx52lP-CL3Mjgh7XgJuGe8OZtl_A0Kie&sz=w1000 | https://drive.google.com/file/d/1Xx52lP-CL3Mjgh7XgJuGe8OZtl_A0Kie/view | https://drive.google.com/thumbnail?id=1TL9IrzKlPKxuk1hHUSBJEQg3OHu9BPMb&sz=w1000 | https://drive.google.com/file/d/1TL9IrzKlPKxuk1hHUSBJEQg3OHu9BPMb/view | https://drive.google.com/thumbnail?id=1mjk5nvW4b1WflrBJK-EEPQRX1KlRm6e2&sz=w1000 | https://drive.google.com/file/d/1mjk5nvW4b1WflrBJK-EEPQRX1KlRm6e2/view
2024-08-12 | Mohamed Bin Zayed City-Majlis-P2 | P2 | MJ-12 | 28 | 580 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/08/2024. | Commencement Date 16/07/2024 | 0% | 0% | 0% | Handing Over | 2026-03-15 |  | 2026-03-15 | 2024-08-16 | • Engaging with the authorities regarding the adjacent plot 5 cm impact. • Submit construction NOC to explore the crossing cables if any. • YAS is to submit the Advance Payment guarantee, Bonds and insurances. • Resources availability • Legal and Regulatory • Delays in engineering /procurement and subs • Safety risk • Delays in Sign board and fence installation | • Follow up to obtain the required construction NOCs approval. • Finalize staff deployment • Evaluate and appoint the shoring subcontractor • Submission of Engineering log /procurement log especially the long lead items. • Ensure Adherence to safety plan and codes and international standards. • Asses Shelter Special systems suppliers for recommendation and appointment • submission of Baseline program in accordance with the contract. | • submission the baseline program along with construction methodology target date(12/08/2024) • Revise the Project HSE plan summation the and construction environment management plan target date(12/08/2024) • submission the Advance Payment guarantee, Bonds and insurances target date(15/08/2024) • submission the Pre-Qualifications of shoring Sub-Contractors target date (12/08/2024) • submission the Pre-Qualifications of Piles Sub-Contractors target date (20/08/2024) • Contract agreement target date(25/08/2024) • Contract deliverables target date(31/08/2024) |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1Xx52lP-CL3Mjgh7XgJuGe8OZtl_A0Kie&sz=w1000 | https://drive.google.com/file/d/1Xx52lP-CL3Mjgh7XgJuGe8OZtl_A0Kie/view | https://drive.google.com/thumbnail?id=1TL9IrzKlPKxuk1hHUSBJEQg3OHu9BPMb&sz=w1000 | https://drive.google.com/file/d/1TL9IrzKlPKxuk1hHUSBJEQg3OHu9BPMb/view | https://drive.google.com/thumbnail?id=1mjk5nvW4b1WflrBJK-EEPQRX1KlRm6e2&sz=w1000 | https://drive.google.com/file/d/1mjk5nvW4b1WflrBJK-EEPQRX1KlRm6e2/view
2024-08-12 | Al Samhah-Majlis-P206 | P206 | MJ-14 | 28 | 580 | 608 | Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024. | Commencement Date 16/07/2024 | 0% | 0% | 0% | Notice to Commence | 2024-07-16 | 2024-07-16 |  | 2024-08-16 | • Engaging with the authorities regarding the adjacent plot 5 cm impact to explore the crossing cables if any. • Submission the Advance Payment guarantee, Performance Bond and insurance polices • Resources availability • Safety risk • Shoring Subcontractor appointment • Shelter Special systems appointment • Base line Programme | • Follow up to obtain the required construction NOCs approval. • Finalize staff deployment • Evaluate and appoint the shoring subcontractor • Submission of Engineering log /procurement log especially the long lead items. • Ensure Adherence to safety plan and codes and international standards. • Asses Shelter Special systems suppliers for recommendation and appointment • submission of Baseline program in accordance with the contract. | • submission the baseline program along with construction methodology target date(12/08/2024) • Revise the Project HSE plan summation the and construction environment management plan. target date(12/08/2024) • submission the Advance Payment guarantee, Bonds and insurances target date(15/08/2024) • submission the Pre-Qualifications of shoring Sub-Contractors target date (12/08/2024) • submission the Pre-Qualifications of Piles Sub-Contractors target date (20/08/2024) • Contract agreement target date(25/08/2024) • Contract deliverables target date(31/08/2024) |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1aotzsm6c1YRrRltmEBM3La85GahLY-Sa&sz=w1000 | https://drive.google.com/file/d/1aotzsm6c1YRrRltmEBM3La85GahLY-Sa/view | https://drive.google.com/thumbnail?id=16ZFwzklgzbqlTBk2PblSupsG8QWIVKhr&sz=w1000 | https://drive.google.com/file/d/16ZFwzklgzbqlTBk2PblSupsG8QWIVKhr/view | https://drive.google.com/thumbnail?id=14_e23Fks39g6eB6scWs8oJVkvBf-w1QV&sz=w1000 | https://drive.google.com/file/d/14_e23Fks39g6eB6scWs8oJVkvBf-w1QV/view
2024-08-12 | Al Samhah-Majlis-P206 | P206 | MJ-14 | 28 | 580 | 608 | Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024. | Commencement Date 16/07/2024 | 0% | 0% | 0% | Building Permit | 2024-07-04 |  | 2024-08-03 | 2024-08-16 | • Engaging with the authorities regarding the adjacent plot 5 cm impact to explore the crossing cables if any. • Submission the Advance Payment guarantee, Performance Bond and insurance polices • Resources availability • Safety risk • Shoring Subcontractor appointment • Shelter Special systems appointment • Base line Programme | • Follow up to obtain the required construction NOCs approval. • Finalize staff deployment • Evaluate and appoint the shoring subcontractor • Submission of Engineering log /procurement log especially the long lead items. • Ensure Adherence to safety plan and codes and international standards. • Asses Shelter Special systems suppliers for recommendation and appointment • submission of Baseline program in accordance with the contract. | • submission the baseline program along with construction methodology target date(12/08/2024) • Revise the Project HSE plan summation the and construction environment management plan. target date(12/08/2024) • submission the Advance Payment guarantee, Bonds and insurances target date(15/08/2024) • submission the Pre-Qualifications of shoring Sub-Contractors target date (12/08/2024) • submission the Pre-Qualifications of Piles Sub-Contractors target date (20/08/2024) • Contract agreement target date(25/08/2024) • Contract deliverables target date(31/08/2024) |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1aotzsm6c1YRrRltmEBM3La85GahLY-Sa&sz=w1000 | https://drive.google.com/file/d/1aotzsm6c1YRrRltmEBM3La85GahLY-Sa/view | https://drive.google.com/thumbnail?id=16ZFwzklgzbqlTBk2PblSupsG8QWIVKhr&sz=w1000 | https://drive.google.com/file/d/16ZFwzklgzbqlTBk2PblSupsG8QWIVKhr/view | https://drive.google.com/thumbnail?id=14_e23Fks39g6eB6scWs8oJVkvBf-w1QV&sz=w1000 | https://drive.google.com/file/d/14_e23Fks39g6eB6scWs8oJVkvBf-w1QV/view
2024-08-12 | Al Samhah-Majlis-P206 | P206 | MJ-14 | 28 | 580 | 608 | Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024. | Commencement Date 16/07/2024 | 0% | 0% | 0% | Demarcation | 2024-07-26 |  | 2024-07-26 | 2024-08-16 | • Engaging with the authorities regarding the adjacent plot 5 cm impact to explore the crossing cables if any. • Submission the Advance Payment guarantee, Performance Bond and insurance polices • Resources availability • Safety risk • Shoring Subcontractor appointment • Shelter Special systems appointment • Base line Programme | • Follow up to obtain the required construction NOCs approval. • Finalize staff deployment • Evaluate and appoint the shoring subcontractor • Submission of Engineering log /procurement log especially the long lead items. • Ensure Adherence to safety plan and codes and international standards. • Asses Shelter Special systems suppliers for recommendation and appointment • submission of Baseline program in accordance with the contract. | • submission the baseline program along with construction methodology target date(12/08/2024) • Revise the Project HSE plan summation the and construction environment management plan. target date(12/08/2024) • submission the Advance Payment guarantee, Bonds and insurances target date(15/08/2024) • submission the Pre-Qualifications of shoring Sub-Contractors target date (12/08/2024) • submission the Pre-Qualifications of Piles Sub-Contractors target date (20/08/2024) • Contract agreement target date(25/08/2024) • Contract deliverables target date(31/08/2024) |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1aotzsm6c1YRrRltmEBM3La85GahLY-Sa&sz=w1000 | https://drive.google.com/file/d/1aotzsm6c1YRrRltmEBM3La85GahLY-Sa/view | https://drive.google.com/thumbnail?id=16ZFwzklgzbqlTBk2PblSupsG8QWIVKhr&sz=w1000 | https://drive.google.com/file/d/16ZFwzklgzbqlTBk2PblSupsG8QWIVKhr/view | https://drive.google.com/thumbnail?id=14_e23Fks39g6eB6scWs8oJVkvBf-w1QV&sz=w1000 | https://drive.google.com/file/d/14_e23Fks39g6eB6scWs8oJVkvBf-w1QV/view
2024-08-12 | Al Samhah-Majlis-P206 | P206 | MJ-14 | 28 | 580 | 608 | Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024. | Commencement Date 16/07/2024 | 0% | 0% | 0% | Fencing & Signboard Fabrication | 2024-07-30 |  | 2024-07-30 | 2024-08-16 | • Engaging with the authorities regarding the adjacent plot 5 cm impact to explore the crossing cables if any. • Submission the Advance Payment guarantee, Performance Bond and insurance polices • Resources availability • Safety risk • Shoring Subcontractor appointment • Shelter Special systems appointment • Base line Programme | • Follow up to obtain the required construction NOCs approval. • Finalize staff deployment • Evaluate and appoint the shoring subcontractor • Submission of Engineering log /procurement log especially the long lead items. • Ensure Adherence to safety plan and codes and international standards. • Asses Shelter Special systems suppliers for recommendation and appointment • submission of Baseline program in accordance with the contract. | • submission the baseline program along with construction methodology target date(12/08/2024) • Revise the Project HSE plan summation the and construction environment management plan. target date(12/08/2024) • submission the Advance Payment guarantee, Bonds and insurances target date(15/08/2024) • submission the Pre-Qualifications of shoring Sub-Contractors target date (12/08/2024) • submission the Pre-Qualifications of Piles Sub-Contractors target date (20/08/2024) • Contract agreement target date(25/08/2024) • Contract deliverables target date(31/08/2024) |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1aotzsm6c1YRrRltmEBM3La85GahLY-Sa&sz=w1000 | https://drive.google.com/file/d/1aotzsm6c1YRrRltmEBM3La85GahLY-Sa/view | https://drive.google.com/thumbnail?id=16ZFwzklgzbqlTBk2PblSupsG8QWIVKhr&sz=w1000 | https://drive.google.com/file/d/16ZFwzklgzbqlTBk2PblSupsG8QWIVKhr/view | https://drive.google.com/thumbnail?id=14_e23Fks39g6eB6scWs8oJVkvBf-w1QV&sz=w1000 | https://drive.google.com/file/d/14_e23Fks39g6eB6scWs8oJVkvBf-w1QV/view
2024-08-12 | Al Samhah-Majlis-P206 | P206 | MJ-14 | 28 | 580 | 608 | Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024. | Commencement Date 16/07/2024 | 0% | 0% | 0% | Signboard Installation | 2024-08-03 |  | 2024-08-09 | 2024-08-16 | • Engaging with the authorities regarding the adjacent plot 5 cm impact to explore the crossing cables if any. • Submission the Advance Payment guarantee, Performance Bond and insurance polices • Resources availability • Safety risk • Shoring Subcontractor appointment • Shelter Special systems appointment • Base line Programme | • Follow up to obtain the required construction NOCs approval. • Finalize staff deployment • Evaluate and appoint the shoring subcontractor • Submission of Engineering log /procurement log especially the long lead items. • Ensure Adherence to safety plan and codes and international standards. • Asses Shelter Special systems suppliers for recommendation and appointment • submission of Baseline program in accordance with the contract. | • submission the baseline program along with construction methodology target date(12/08/2024) • Revise the Project HSE plan summation the and construction environment management plan. target date(12/08/2024) • submission the Advance Payment guarantee, Bonds and insurances target date(15/08/2024) • submission the Pre-Qualifications of shoring Sub-Contractors target date (12/08/2024) • submission the Pre-Qualifications of Piles Sub-Contractors target date (20/08/2024) • Contract agreement target date(25/08/2024) • Contract deliverables target date(31/08/2024) |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1aotzsm6c1YRrRltmEBM3La85GahLY-Sa&sz=w1000 | https://drive.google.com/file/d/1aotzsm6c1YRrRltmEBM3La85GahLY-Sa/view | https://drive.google.com/thumbnail?id=16ZFwzklgzbqlTBk2PblSupsG8QWIVKhr&sz=w1000 | https://drive.google.com/file/d/16ZFwzklgzbqlTBk2PblSupsG8QWIVKhr/view | https://drive.google.com/thumbnail?id=14_e23Fks39g6eB6scWs8oJVkvBf-w1QV&sz=w1000 | https://drive.google.com/file/d/14_e23Fks39g6eB6scWs8oJVkvBf-w1QV/view
2024-08-12 | Al Samhah-Majlis-P206 | P206 | MJ-14 | 28 | 580 | 608 | Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024. | Commencement Date 16/07/2024 | 0% | 0% | 0% | Fencing Installation | 2024-08-03 |  | 2024-08-09 | 2024-08-16 | • Engaging with the authorities regarding the adjacent plot 5 cm impact to explore the crossing cables if any. • Submission the Advance Payment guarantee, Performance Bond and insurance polices • Resources availability • Safety risk • Shoring Subcontractor appointment • Shelter Special systems appointment • Base line Programme | • Follow up to obtain the required construction NOCs approval. • Finalize staff deployment • Evaluate and appoint the shoring subcontractor • Submission of Engineering log /procurement log especially the long lead items. • Ensure Adherence to safety plan and codes and international standards. • Asses Shelter Special systems suppliers for recommendation and appointment • submission of Baseline program in accordance with the contract. | • submission the baseline program along with construction methodology target date(12/08/2024) • Revise the Project HSE plan summation the and construction environment management plan. target date(12/08/2024) • submission the Advance Payment guarantee, Bonds and insurances target date(15/08/2024) • submission the Pre-Qualifications of shoring Sub-Contractors target date (12/08/2024) • submission the Pre-Qualifications of Piles Sub-Contractors target date (20/08/2024) • Contract agreement target date(25/08/2024) • Contract deliverables target date(31/08/2024) |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1aotzsm6c1YRrRltmEBM3La85GahLY-Sa&sz=w1000 | https://drive.google.com/file/d/1aotzsm6c1YRrRltmEBM3La85GahLY-Sa/view | https://drive.google.com/thumbnail?id=16ZFwzklgzbqlTBk2PblSupsG8QWIVKhr&sz=w1000 | https://drive.google.com/file/d/16ZFwzklgzbqlTBk2PblSupsG8QWIVKhr/view | https://drive.google.com/thumbnail?id=14_e23Fks39g6eB6scWs8oJVkvBf-w1QV&sz=w1000 | https://drive.google.com/file/d/14_e23Fks39g6eB6scWs8oJVkvBf-w1QV/view
2024-08-12 | Al Samhah-Majlis-P206 | P206 | MJ-14 | 28 | 580 | 608 | Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024. | Commencement Date 16/07/2024 | 0% | 0% | 0% | Site offices Fabrication | 2024-08-07 |  | 2024-08-07 | 2024-08-16 | • Engaging with the authorities regarding the adjacent plot 5 cm impact to explore the crossing cables if any. • Submission the Advance Payment guarantee, Performance Bond and insurance polices • Resources availability • Safety risk • Shoring Subcontractor appointment • Shelter Special systems appointment • Base line Programme | • Follow up to obtain the required construction NOCs approval. • Finalize staff deployment • Evaluate and appoint the shoring subcontractor • Submission of Engineering log /procurement log especially the long lead items. • Ensure Adherence to safety plan and codes and international standards. • Asses Shelter Special systems suppliers for recommendation and appointment • submission of Baseline program in accordance with the contract. | • submission the baseline program along with construction methodology target date(12/08/2024) • Revise the Project HSE plan summation the and construction environment management plan. target date(12/08/2024) • submission the Advance Payment guarantee, Bonds and insurances target date(15/08/2024) • submission the Pre-Qualifications of shoring Sub-Contractors target date (12/08/2024) • submission the Pre-Qualifications of Piles Sub-Contractors target date (20/08/2024) • Contract agreement target date(25/08/2024) • Contract deliverables target date(31/08/2024) |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1aotzsm6c1YRrRltmEBM3La85GahLY-Sa&sz=w1000 | https://drive.google.com/file/d/1aotzsm6c1YRrRltmEBM3La85GahLY-Sa/view | https://drive.google.com/thumbnail?id=16ZFwzklgzbqlTBk2PblSupsG8QWIVKhr&sz=w1000 | https://drive.google.com/file/d/16ZFwzklgzbqlTBk2PblSupsG8QWIVKhr/view | https://drive.google.com/thumbnail?id=14_e23Fks39g6eB6scWs8oJVkvBf-w1QV&sz=w1000 | https://drive.google.com/file/d/14_e23Fks39g6eB6scWs8oJVkvBf-w1QV/view
2024-08-12 | Al Samhah-Majlis-P206 | P206 | MJ-14 | 28 | 580 | 608 | Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024. | Commencement Date 16/07/2024 | 0% | 0% | 0% | Site offices Installation | 2024-08-28 |  | 2024-08-28 | 2024-08-16 | • Engaging with the authorities regarding the adjacent plot 5 cm impact to explore the crossing cables if any. • Submission the Advance Payment guarantee, Performance Bond and insurance polices • Resources availability • Safety risk • Shoring Subcontractor appointment • Shelter Special systems appointment • Base line Programme | • Follow up to obtain the required construction NOCs approval. • Finalize staff deployment • Evaluate and appoint the shoring subcontractor • Submission of Engineering log /procurement log especially the long lead items. • Ensure Adherence to safety plan and codes and international standards. • Asses Shelter Special systems suppliers for recommendation and appointment • submission of Baseline program in accordance with the contract. | • submission the baseline program along with construction methodology target date(12/08/2024) • Revise the Project HSE plan summation the and construction environment management plan. target date(12/08/2024) • submission the Advance Payment guarantee, Bonds and insurances target date(15/08/2024) • submission the Pre-Qualifications of shoring Sub-Contractors target date (12/08/2024) • submission the Pre-Qualifications of Piles Sub-Contractors target date (20/08/2024) • Contract agreement target date(25/08/2024) • Contract deliverables target date(31/08/2024) |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1aotzsm6c1YRrRltmEBM3La85GahLY-Sa&sz=w1000 | https://drive.google.com/file/d/1aotzsm6c1YRrRltmEBM3La85GahLY-Sa/view | https://drive.google.com/thumbnail?id=16ZFwzklgzbqlTBk2PblSupsG8QWIVKhr&sz=w1000 | https://drive.google.com/file/d/16ZFwzklgzbqlTBk2PblSupsG8QWIVKhr/view | https://drive.google.com/thumbnail?id=14_e23Fks39g6eB6scWs8oJVkvBf-w1QV&sz=w1000 | https://drive.google.com/file/d/14_e23Fks39g6eB6scWs8oJVkvBf-w1QV/view
2024-08-12 | Al Samhah-Majlis-P206 | P206 | MJ-14 | 28 | 580 | 608 | Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024. | Commencement Date 16/07/2024 | 0% | 0% | 0% | Handing Over | 2026-03-15 |  | 2026-03-15 | 2024-08-16 | • Engaging with the authorities regarding the adjacent plot 5 cm impact to explore the crossing cables if any. • Submission the Advance Payment guarantee, Performance Bond and insurance polices • Resources availability • Safety risk • Shoring Subcontractor appointment • Shelter Special systems appointment • Base line Programme | • Follow up to obtain the required construction NOCs approval. • Finalize staff deployment • Evaluate and appoint the shoring subcontractor • Submission of Engineering log /procurement log especially the long lead items. • Ensure Adherence to safety plan and codes and international standards. • Asses Shelter Special systems suppliers for recommendation and appointment • submission of Baseline program in accordance with the contract. | • submission the baseline program along with construction methodology target date(12/08/2024) • Revise the Project HSE plan summation the and construction environment management plan. target date(12/08/2024) • submission the Advance Payment guarantee, Bonds and insurances target date(15/08/2024) • submission the Pre-Qualifications of shoring Sub-Contractors target date (12/08/2024) • submission the Pre-Qualifications of Piles Sub-Contractors target date (20/08/2024) • Contract agreement target date(25/08/2024) • Contract deliverables target date(31/08/2024) |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1aotzsm6c1YRrRltmEBM3La85GahLY-Sa&sz=w1000 | https://drive.google.com/file/d/1aotzsm6c1YRrRltmEBM3La85GahLY-Sa/view | https://drive.google.com/thumbnail?id=16ZFwzklgzbqlTBk2PblSupsG8QWIVKhr&sz=w1000 | https://drive.google.com/file/d/16ZFwzklgzbqlTBk2PblSupsG8QWIVKhr/view | https://drive.google.com/thumbnail?id=14_e23Fks39g6eB6scWs8oJVkvBf-w1QV&sz=w1000 | https://drive.google.com/file/d/14_e23Fks39g6eB6scWs8oJVkvBf-w1QV/view
2024-08-12 | Madinat Al Riyad-Majlis-P162 | P162 | MJ-13 | 28 | 580 | 608 | Building Permit issued on 23/07/2024 Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024. | Commencement Date 16/07/2024 | 0% | 0% | 0% | Notice to Commence | 2024-07-16 | 2024-07-16 |  | 2024-08-16 | • Risks / Challenges • Engaging with the authorities regarding the adjacent plot 5 cm impact. to explore the crossing cables if any. • Submission the Advance Payment guarantee, Performance Bond and insurance polices • Resources availability • Safety risk • Shoring Subcontractor appointment • Shelter Special systems appointment • Base line Programme | • Follow up to obtain the required construction NOCs approval. • Finalize staff deployment • Evaluate and appoint the shoring subcontractor • Submission of Engineering log /procurement log especially the long lead items. • Ensure Adherence to safety plan and codes and international standards. • Asses Shelter Special systems suppliers for recommendation and appointment • submission of Baseline program in accordance with the contract. | • submission the baseline program along with construction methodology target date(12/08/2024) • Revise the Project HSE plan summation the and construction environment management plan. target date(12/08/2024) • submission the Advance Payment guarantee, Bonds and insurances target date(15/08/2024) • submission the Pre-Qualifications of shoring Sub-Contractors target date (12/08/2024) • submission the Pre-Qualifications of Piles Sub-Contractors target date (20/08/2024) • Contract agreement target date(25/08/2024) • Contract deliverables target date(31/08/2024) |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1erAewuQjYKuSzO2J7M_BGEAM7u-DEnI2&sz=w1000 | https://drive.google.com/file/d/1erAewuQjYKuSzO2J7M_BGEAM7u-DEnI2/view | https://drive.google.com/thumbnail?id=1c3FBPHHZ7t7n-uvjJkQ1bEwKAXm0RkFQ&sz=w1000 | https://drive.google.com/file/d/1c3FBPHHZ7t7n-uvjJkQ1bEwKAXm0RkFQ/view | https://drive.google.com/thumbnail?id=1iggJgkxEIi33_uzKlp_ENRo47YLn90I8&sz=w1000 | https://drive.google.com/file/d/1iggJgkxEIi33_uzKlp_ENRo47YLn90I8/view
2024-08-12 | Madinat Al Riyad-Majlis-P162 | P162 | MJ-13 | 28 | 580 | 608 | Building Permit issued on 23/07/2024 Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024. | Commencement Date 16/07/2024 | 0% | 0% | 0% | Building Permit | 2024-07-04 |  | 2024-07-23 | 2024-08-16 | • Risks / Challenges • Engaging with the authorities regarding the adjacent plot 5 cm impact. to explore the crossing cables if any. • Submission the Advance Payment guarantee, Performance Bond and insurance polices • Resources availability • Safety risk • Shoring Subcontractor appointment • Shelter Special systems appointment • Base line Programme | • Follow up to obtain the required construction NOCs approval. • Finalize staff deployment • Evaluate and appoint the shoring subcontractor • Submission of Engineering log /procurement log especially the long lead items. • Ensure Adherence to safety plan and codes and international standards. • Asses Shelter Special systems suppliers for recommendation and appointment • submission of Baseline program in accordance with the contract. | • submission the baseline program along with construction methodology target date(12/08/2024) • Revise the Project HSE plan summation the and construction environment management plan. target date(12/08/2024) • submission the Advance Payment guarantee, Bonds and insurances target date(15/08/2024) • submission the Pre-Qualifications of shoring Sub-Contractors target date (12/08/2024) • submission the Pre-Qualifications of Piles Sub-Contractors target date (20/08/2024) • Contract agreement target date(25/08/2024) • Contract deliverables target date(31/08/2024) |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1erAewuQjYKuSzO2J7M_BGEAM7u-DEnI2&sz=w1000 | https://drive.google.com/file/d/1erAewuQjYKuSzO2J7M_BGEAM7u-DEnI2/view | https://drive.google.com/thumbnail?id=1c3FBPHHZ7t7n-uvjJkQ1bEwKAXm0RkFQ&sz=w1000 | https://drive.google.com/file/d/1c3FBPHHZ7t7n-uvjJkQ1bEwKAXm0RkFQ/view | https://drive.google.com/thumbnail?id=1iggJgkxEIi33_uzKlp_ENRo47YLn90I8&sz=w1000 | https://drive.google.com/file/d/1iggJgkxEIi33_uzKlp_ENRo47YLn90I8/view
2024-08-12 | Madinat Al Riyad-Majlis-P162 | P162 | MJ-13 | 28 | 580 | 608 | Building Permit issued on 23/07/2024 Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024. | Commencement Date 16/07/2024 | 0% | 0% | 0% | Demarcation | 2024-07-26 |  | 2024-07-26 | 2024-08-16 | • Risks / Challenges • Engaging with the authorities regarding the adjacent plot 5 cm impact. to explore the crossing cables if any. • Submission the Advance Payment guarantee, Performance Bond and insurance polices • Resources availability • Safety risk • Shoring Subcontractor appointment • Shelter Special systems appointment • Base line Programme | • Follow up to obtain the required construction NOCs approval. • Finalize staff deployment • Evaluate and appoint the shoring subcontractor • Submission of Engineering log /procurement log especially the long lead items. • Ensure Adherence to safety plan and codes and international standards. • Asses Shelter Special systems suppliers for recommendation and appointment • submission of Baseline program in accordance with the contract. | • submission the baseline program along with construction methodology target date(12/08/2024) • Revise the Project HSE plan summation the and construction environment management plan. target date(12/08/2024) • submission the Advance Payment guarantee, Bonds and insurances target date(15/08/2024) • submission the Pre-Qualifications of shoring Sub-Contractors target date (12/08/2024) • submission the Pre-Qualifications of Piles Sub-Contractors target date (20/08/2024) • Contract agreement target date(25/08/2024) • Contract deliverables target date(31/08/2024) |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1erAewuQjYKuSzO2J7M_BGEAM7u-DEnI2&sz=w1000 | https://drive.google.com/file/d/1erAewuQjYKuSzO2J7M_BGEAM7u-DEnI2/view | https://drive.google.com/thumbnail?id=1c3FBPHHZ7t7n-uvjJkQ1bEwKAXm0RkFQ&sz=w1000 | https://drive.google.com/file/d/1c3FBPHHZ7t7n-uvjJkQ1bEwKAXm0RkFQ/view | https://drive.google.com/thumbnail?id=1iggJgkxEIi33_uzKlp_ENRo47YLn90I8&sz=w1000 | https://drive.google.com/file/d/1iggJgkxEIi33_uzKlp_ENRo47YLn90I8/view
2024-08-12 | Madinat Al Riyad-Majlis-P162 | P162 | MJ-13 | 28 | 580 | 608 | Building Permit issued on 23/07/2024 Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024. | Commencement Date 16/07/2024 | 0% | 0% | 0% | Fencing & Signboard Fabrication | 2024-07-30 |  | 2024-07-30 | 2024-08-16 | • Risks / Challenges • Engaging with the authorities regarding the adjacent plot 5 cm impact. to explore the crossing cables if any. • Submission the Advance Payment guarantee, Performance Bond and insurance polices • Resources availability • Safety risk • Shoring Subcontractor appointment • Shelter Special systems appointment • Base line Programme | • Follow up to obtain the required construction NOCs approval. • Finalize staff deployment • Evaluate and appoint the shoring subcontractor • Submission of Engineering log /procurement log especially the long lead items. • Ensure Adherence to safety plan and codes and international standards. • Asses Shelter Special systems suppliers for recommendation and appointment • submission of Baseline program in accordance with the contract. | • submission the baseline program along with construction methodology target date(12/08/2024) • Revise the Project HSE plan summation the and construction environment management plan. target date(12/08/2024) • submission the Advance Payment guarantee, Bonds and insurances target date(15/08/2024) • submission the Pre-Qualifications of shoring Sub-Contractors target date (12/08/2024) • submission the Pre-Qualifications of Piles Sub-Contractors target date (20/08/2024) • Contract agreement target date(25/08/2024) • Contract deliverables target date(31/08/2024) |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1erAewuQjYKuSzO2J7M_BGEAM7u-DEnI2&sz=w1000 | https://drive.google.com/file/d/1erAewuQjYKuSzO2J7M_BGEAM7u-DEnI2/view | https://drive.google.com/thumbnail?id=1c3FBPHHZ7t7n-uvjJkQ1bEwKAXm0RkFQ&sz=w1000 | https://drive.google.com/file/d/1c3FBPHHZ7t7n-uvjJkQ1bEwKAXm0RkFQ/view | https://drive.google.com/thumbnail?id=1iggJgkxEIi33_uzKlp_ENRo47YLn90I8&sz=w1000 | https://drive.google.com/file/d/1iggJgkxEIi33_uzKlp_ENRo47YLn90I8/view
2024-08-12 | Madinat Al Riyad-Majlis-P162 | P162 | MJ-13 | 28 | 580 | 608 | Building Permit issued on 23/07/2024 Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024. | Commencement Date 16/07/2024 | 0% | 0% | 0% | Signboard Installation | 2024-08-03 |  | 2024-08-09 | 2024-08-16 | • Risks / Challenges • Engaging with the authorities regarding the adjacent plot 5 cm impact. to explore the crossing cables if any. • Submission the Advance Payment guarantee, Performance Bond and insurance polices • Resources availability • Safety risk • Shoring Subcontractor appointment • Shelter Special systems appointment • Base line Programme | • Follow up to obtain the required construction NOCs approval. • Finalize staff deployment • Evaluate and appoint the shoring subcontractor • Submission of Engineering log /procurement log especially the long lead items. • Ensure Adherence to safety plan and codes and international standards. • Asses Shelter Special systems suppliers for recommendation and appointment • submission of Baseline program in accordance with the contract. | • submission the baseline program along with construction methodology target date(12/08/2024) • Revise the Project HSE plan summation the and construction environment management plan. target date(12/08/2024) • submission the Advance Payment guarantee, Bonds and insurances target date(15/08/2024) • submission the Pre-Qualifications of shoring Sub-Contractors target date (12/08/2024) • submission the Pre-Qualifications of Piles Sub-Contractors target date (20/08/2024) • Contract agreement target date(25/08/2024) • Contract deliverables target date(31/08/2024) |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1erAewuQjYKuSzO2J7M_BGEAM7u-DEnI2&sz=w1000 | https://drive.google.com/file/d/1erAewuQjYKuSzO2J7M_BGEAM7u-DEnI2/view | https://drive.google.com/thumbnail?id=1c3FBPHHZ7t7n-uvjJkQ1bEwKAXm0RkFQ&sz=w1000 | https://drive.google.com/file/d/1c3FBPHHZ7t7n-uvjJkQ1bEwKAXm0RkFQ/view | https://drive.google.com/thumbnail?id=1iggJgkxEIi33_uzKlp_ENRo47YLn90I8&sz=w1000 | https://drive.google.com/file/d/1iggJgkxEIi33_uzKlp_ENRo47YLn90I8/view
2024-08-12 | Madinat Al Riyad-Majlis-P162 | P162 | MJ-13 | 28 | 580 | 608 | Building Permit issued on 23/07/2024 Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024. | Commencement Date 16/07/2024 | 0% | 0% | 0% | Fencing Installation | 2024-08-03 |  | 2024-08-09 | 2024-08-16 | • Risks / Challenges • Engaging with the authorities regarding the adjacent plot 5 cm impact. to explore the crossing cables if any. • Submission the Advance Payment guarantee, Performance Bond and insurance polices • Resources availability • Safety risk • Shoring Subcontractor appointment • Shelter Special systems appointment • Base line Programme | • Follow up to obtain the required construction NOCs approval. • Finalize staff deployment • Evaluate and appoint the shoring subcontractor • Submission of Engineering log /procurement log especially the long lead items. • Ensure Adherence to safety plan and codes and international standards. • Asses Shelter Special systems suppliers for recommendation and appointment • submission of Baseline program in accordance with the contract. | • submission the baseline program along with construction methodology target date(12/08/2024) • Revise the Project HSE plan summation the and construction environment management plan. target date(12/08/2024) • submission the Advance Payment guarantee, Bonds and insurances target date(15/08/2024) • submission the Pre-Qualifications of shoring Sub-Contractors target date (12/08/2024) • submission the Pre-Qualifications of Piles Sub-Contractors target date (20/08/2024) • Contract agreement target date(25/08/2024) • Contract deliverables target date(31/08/2024) |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1erAewuQjYKuSzO2J7M_BGEAM7u-DEnI2&sz=w1000 | https://drive.google.com/file/d/1erAewuQjYKuSzO2J7M_BGEAM7u-DEnI2/view | https://drive.google.com/thumbnail?id=1c3FBPHHZ7t7n-uvjJkQ1bEwKAXm0RkFQ&sz=w1000 | https://drive.google.com/file/d/1c3FBPHHZ7t7n-uvjJkQ1bEwKAXm0RkFQ/view | https://drive.google.com/thumbnail?id=1iggJgkxEIi33_uzKlp_ENRo47YLn90I8&sz=w1000 | https://drive.google.com/file/d/1iggJgkxEIi33_uzKlp_ENRo47YLn90I8/view
2024-08-12 | Madinat Al Riyad-Majlis-P162 | P162 | MJ-13 | 28 | 580 | 608 | Building Permit issued on 23/07/2024 Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024. | Commencement Date 16/07/2024 | 0% | 0% | 0% | Site offices Fabrication | 2024-08-07 |  | 2024-08-07 | 2024-08-16 | • Risks / Challenges • Engaging with the authorities regarding the adjacent plot 5 cm impact. to explore the crossing cables if any. • Submission the Advance Payment guarantee, Performance Bond and insurance polices • Resources availability • Safety risk • Shoring Subcontractor appointment • Shelter Special systems appointment • Base line Programme | • Follow up to obtain the required construction NOCs approval. • Finalize staff deployment • Evaluate and appoint the shoring subcontractor • Submission of Engineering log /procurement log especially the long lead items. • Ensure Adherence to safety plan and codes and international standards. • Asses Shelter Special systems suppliers for recommendation and appointment • submission of Baseline program in accordance with the contract. | • submission the baseline program along with construction methodology target date(12/08/2024) • Revise the Project HSE plan summation the and construction environment management plan. target date(12/08/2024) • submission the Advance Payment guarantee, Bonds and insurances target date(15/08/2024) • submission the Pre-Qualifications of shoring Sub-Contractors target date (12/08/2024) • submission the Pre-Qualifications of Piles Sub-Contractors target date (20/08/2024) • Contract agreement target date(25/08/2024) • Contract deliverables target date(31/08/2024) |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1erAewuQjYKuSzO2J7M_BGEAM7u-DEnI2&sz=w1000 | https://drive.google.com/file/d/1erAewuQjYKuSzO2J7M_BGEAM7u-DEnI2/view | https://drive.google.com/thumbnail?id=1c3FBPHHZ7t7n-uvjJkQ1bEwKAXm0RkFQ&sz=w1000 | https://drive.google.com/file/d/1c3FBPHHZ7t7n-uvjJkQ1bEwKAXm0RkFQ/view | https://drive.google.com/thumbnail?id=1iggJgkxEIi33_uzKlp_ENRo47YLn90I8&sz=w1000 | https://drive.google.com/file/d/1iggJgkxEIi33_uzKlp_ENRo47YLn90I8/view
2024-08-12 | Madinat Al Riyad-Majlis-P162 | P162 | MJ-13 | 28 | 580 | 608 | Building Permit issued on 23/07/2024 Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024. | Commencement Date 16/07/2024 | 0% | 0% | 0% | Site offices Installation | 2024-08-28 |  | 2024-08-28 | 2024-08-16 | • Risks / Challenges • Engaging with the authorities regarding the adjacent plot 5 cm impact. to explore the crossing cables if any. • Submission the Advance Payment guarantee, Performance Bond and insurance polices • Resources availability • Safety risk • Shoring Subcontractor appointment • Shelter Special systems appointment • Base line Programme | • Follow up to obtain the required construction NOCs approval. • Finalize staff deployment • Evaluate and appoint the shoring subcontractor • Submission of Engineering log /procurement log especially the long lead items. • Ensure Adherence to safety plan and codes and international standards. • Asses Shelter Special systems suppliers for recommendation and appointment • submission of Baseline program in accordance with the contract. | • submission the baseline program along with construction methodology target date(12/08/2024) • Revise the Project HSE plan summation the and construction environment management plan. target date(12/08/2024) • submission the Advance Payment guarantee, Bonds and insurances target date(15/08/2024) • submission the Pre-Qualifications of shoring Sub-Contractors target date (12/08/2024) • submission the Pre-Qualifications of Piles Sub-Contractors target date (20/08/2024) • Contract agreement target date(25/08/2024) • Contract deliverables target date(31/08/2024) |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1erAewuQjYKuSzO2J7M_BGEAM7u-DEnI2&sz=w1000 | https://drive.google.com/file/d/1erAewuQjYKuSzO2J7M_BGEAM7u-DEnI2/view | https://drive.google.com/thumbnail?id=1c3FBPHHZ7t7n-uvjJkQ1bEwKAXm0RkFQ&sz=w1000 | https://drive.google.com/file/d/1c3FBPHHZ7t7n-uvjJkQ1bEwKAXm0RkFQ/view | https://drive.google.com/thumbnail?id=1iggJgkxEIi33_uzKlp_ENRo47YLn90I8&sz=w1000 | https://drive.google.com/file/d/1iggJgkxEIi33_uzKlp_ENRo47YLn90I8/view
2024-08-12 | Madinat Al Riyad-Majlis-P162 | P162 | MJ-13 | 28 | 580 | 608 | Building Permit issued on 23/07/2024 Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024. | Commencement Date 16/07/2024 | 0% | 0% | 0% | Handing Over | 2026-03-15 |  | 2026-03-25 | 2024-08-16 | • Risks / Challenges • Engaging with the authorities regarding the adjacent plot 5 cm impact. to explore the crossing cables if any. • Submission the Advance Payment guarantee, Performance Bond and insurance polices • Resources availability • Safety risk • Shoring Subcontractor appointment • Shelter Special systems appointment • Base line Programme | • Follow up to obtain the required construction NOCs approval. • Finalize staff deployment • Evaluate and appoint the shoring subcontractor • Submission of Engineering log /procurement log especially the long lead items. • Ensure Adherence to safety plan and codes and international standards. • Asses Shelter Special systems suppliers for recommendation and appointment • submission of Baseline program in accordance with the contract. | • submission the baseline program along with construction methodology target date(12/08/2024) • Revise the Project HSE plan summation the and construction environment management plan. target date(12/08/2024) • submission the Advance Payment guarantee, Bonds and insurances target date(15/08/2024) • submission the Pre-Qualifications of shoring Sub-Contractors target date (12/08/2024) • submission the Pre-Qualifications of Piles Sub-Contractors target date (20/08/2024) • Contract agreement target date(25/08/2024) • Contract deliverables target date(31/08/2024) |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1erAewuQjYKuSzO2J7M_BGEAM7u-DEnI2&sz=w1000 | https://drive.google.com/file/d/1erAewuQjYKuSzO2J7M_BGEAM7u-DEnI2/view | https://drive.google.com/thumbnail?id=1c3FBPHHZ7t7n-uvjJkQ1bEwKAXm0RkFQ&sz=w1000 | https://drive.google.com/file/d/1c3FBPHHZ7t7n-uvjJkQ1bEwKAXm0RkFQ/view | https://drive.google.com/thumbnail?id=1iggJgkxEIi33_uzKlp_ENRo47YLn90I8&sz=w1000 | https://drive.google.com/file/d/1iggJgkxEIi33_uzKlp_ENRo47YLn90I8/view
2024-08-12 | Al Shahama-School-P17 | P17 | SC-02 | 219 | 328 | 547 | Annex Building RCC Wall Shutter fixing Upto FF Level in progress – 80% Completed; Concrete 70% completed School Building GF - RCC Wall Rebar fixing 85% Completed | To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. School Construction is ongoing while awaiting final cost agreement with the employer. | 14.64% | 20.06% | 5.42% | Notice to Commence | 2023-09-18 | 2023-09-26 |  | 2024-08-16 | • Risks / Challenges • Bill No.4 – MEP Final Rate Agreement required – 19-Aug-24 (Delaying the MEP Agency mobilization at site, Engineering & Procurement process) • Approval for Remaining Cost plus & Re-measurable Items required – 19-Aug-24 (Hampering the Annex & School building progress) • MEP Long lead items – Materials submittals & Approvals delaying due to Agency not mobilized (Impacted in the critical path) • Addition in Scope (Internal wall + External RCC Wall at School) & changes in construction methodology hindering the progress | • Expedite final rate agreement between parties and accelerate procurement of critical materials. • Obtain timely approvals and expedite procurement of critical materials; Consider expediting procurement processes. • Expedite MEP agency onboarding to initiate material submittals and approvals for long-lead items, and assess the potential benefits of local procurement. • Reassess project scope to identify resource and timeline requirements; Develop a revised project schedule incorporating the new scope and methodology | Annex Building – • Superstructure works – Wall Rebar, Shutter & Concrete pouring up to 1st FL level Shelter Block – • Substructure – Waterproofing & Backfilling works Superstructure - RCC wall to progress GF & 1FL Surface Preparation & Application of CFRP Roof Slab Strengthening works to progress | 78077600 |  | 78077600 | 1576709 |  | 79654309 | 10200000 | 180000 | https://drive.google.com/thumbnail?id=1vEe16r7h-ux1rA7AxiyngNZw8Z8sHH4F&sz=w1000 | https://drive.google.com/file/d/1vEe16r7h-ux1rA7AxiyngNZw8Z8sHH4F/view?usp=drive_link | https://drive.google.com/thumbnail?id=1Id-FrFKnEcbWhvWSxpJ-s5C1Sd5GUsBE&sz=w1000 | https://drive.google.com/file/d/1Id-FrFKnEcbWhvWSxpJ-s5C1Sd5GUsBE/view?usp=drive_link | https://drive.google.com/thumbnail?id=13aoD-D4xVjW7Mpl0_JTNMreYR8d1A9sn&sz=w1000 | https://drive.google.com/file/d/13aoD-D4xVjW7Mpl0_JTNMreYR8d1A9sn/view?usp=drive_link
2024-08-12 | Al Shahama-School-P17 | P17 | SC-02 | 219 | 328 | 547 | Annex Building RCC Wall Shutter fixing Upto FF Level in progress – 80% Completed; Concrete 70% completed School Building GF - RCC Wall Rebar fixing 85% Completed | To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. School Construction is ongoing while awaiting final cost agreement with the employer. | 14.64% | 20.06% | 5.42% | Site Mobilization | 2023-10-21 | 2023-12-06 |  | 2024-08-16 | • Risks / Challenges • Bill No.4 – MEP Final Rate Agreement required – 19-Aug-24 (Delaying the MEP Agency mobilization at site, Engineering & Procurement process) • Approval for Remaining Cost plus & Re-measurable Items required – 19-Aug-24 (Hampering the Annex & School building progress) • MEP Long lead items – Materials submittals & Approvals delaying due to Agency not mobilized (Impacted in the critical path) • Addition in Scope (Internal wall + External RCC Wall at School) & changes in construction methodology hindering the progress | • Expedite final rate agreement between parties and accelerate procurement of critical materials. • Obtain timely approvals and expedite procurement of critical materials; Consider expediting procurement processes. • Expedite MEP agency onboarding to initiate material submittals and approvals for long-lead items, and assess the potential benefits of local procurement. • Reassess project scope to identify resource and timeline requirements; Develop a revised project schedule incorporating the new scope and methodology | Annex Building – • Superstructure works – Wall Rebar, Shutter & Concrete pouring up to 1st FL level Shelter Block – • Substructure – Waterproofing & Backfilling works Superstructure - RCC wall to progress GF & 1FL Surface Preparation & Application of CFRP Roof Slab Strengthening works to progress | 78077600 |  | 78077600 | 1576709 |  | 79654309 | 10200000 | 180000 | https://drive.google.com/thumbnail?id=1vEe16r7h-ux1rA7AxiyngNZw8Z8sHH4F&sz=w1000 | https://drive.google.com/file/d/1vEe16r7h-ux1rA7AxiyngNZw8Z8sHH4F/view?usp=drive_link | https://drive.google.com/thumbnail?id=1Id-FrFKnEcbWhvWSxpJ-s5C1Sd5GUsBE&sz=w1000 | https://drive.google.com/file/d/1Id-FrFKnEcbWhvWSxpJ-s5C1Sd5GUsBE/view?usp=drive_link | https://drive.google.com/thumbnail?id=13aoD-D4xVjW7Mpl0_JTNMreYR8d1A9sn&sz=w1000 | https://drive.google.com/file/d/13aoD-D4xVjW7Mpl0_JTNMreYR8d1A9sn/view?usp=drive_link
2024-08-12 | Al Shahama-School-P17 | P17 | SC-02 | 219 | 328 | 547 | Annex Building RCC Wall Shutter fixing Upto FF Level in progress – 80% Completed; Concrete 70% completed School Building GF - RCC Wall Rebar fixing 85% Completed | To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. School Construction is ongoing while awaiting final cost agreement with the employer. | 14.64% | 20.06% | 5.42% | Building Permit | 2024-05-17 | 2024-05-23 |  | 2024-08-16 | • Risks / Challenges • Bill No.4 – MEP Final Rate Agreement required – 19-Aug-24 (Delaying the MEP Agency mobilization at site, Engineering & Procurement process) • Approval for Remaining Cost plus & Re-measurable Items required – 19-Aug-24 (Hampering the Annex & School building progress) • MEP Long lead items – Materials submittals & Approvals delaying due to Agency not mobilized (Impacted in the critical path) • Addition in Scope (Internal wall + External RCC Wall at School) & changes in construction methodology hindering the progress | • Expedite final rate agreement between parties and accelerate procurement of critical materials. • Obtain timely approvals and expedite procurement of critical materials; Consider expediting procurement processes. • Expedite MEP agency onboarding to initiate material submittals and approvals for long-lead items, and assess the potential benefits of local procurement. • Reassess project scope to identify resource and timeline requirements; Develop a revised project schedule incorporating the new scope and methodology | Annex Building – • Superstructure works – Wall Rebar, Shutter & Concrete pouring up to 1st FL level Shelter Block – • Substructure – Waterproofing & Backfilling works Superstructure - RCC wall to progress GF & 1FL Surface Preparation & Application of CFRP Roof Slab Strengthening works to progress | 78077600 |  | 78077600 | 1576709 |  | 79654309 | 10200000 | 180000 | https://drive.google.com/thumbnail?id=1vEe16r7h-ux1rA7AxiyngNZw8Z8sHH4F&sz=w1000 | https://drive.google.com/file/d/1vEe16r7h-ux1rA7AxiyngNZw8Z8sHH4F/view?usp=drive_link | https://drive.google.com/thumbnail?id=1Id-FrFKnEcbWhvWSxpJ-s5C1Sd5GUsBE&sz=w1000 | https://drive.google.com/file/d/1Id-FrFKnEcbWhvWSxpJ-s5C1Sd5GUsBE/view?usp=drive_link | https://drive.google.com/thumbnail?id=13aoD-D4xVjW7Mpl0_JTNMreYR8d1A9sn&sz=w1000 | https://drive.google.com/file/d/13aoD-D4xVjW7Mpl0_JTNMreYR8d1A9sn/view?usp=drive_link
2024-08-12 | Al Shahama-School-P17 | P17 | SC-02 | 219 | 328 | 547 | Annex Building RCC Wall Shutter fixing Upto FF Level in progress – 80% Completed; Concrete 70% completed School Building GF - RCC Wall Rebar fixing 85% Completed | To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. School Construction is ongoing while awaiting final cost agreement with the employer. | 14.64% | 20.06% | 5.42% | Design Phase | 2024-05-21 | 2024-07-25 |  | 2024-08-16 | • Risks / Challenges • Bill No.4 – MEP Final Rate Agreement required – 19-Aug-24 (Delaying the MEP Agency mobilization at site, Engineering & Procurement process) • Approval for Remaining Cost plus & Re-measurable Items required – 19-Aug-24 (Hampering the Annex & School building progress) • MEP Long lead items – Materials submittals & Approvals delaying due to Agency not mobilized (Impacted in the critical path) • Addition in Scope (Internal wall + External RCC Wall at School) & changes in construction methodology hindering the progress | • Expedite final rate agreement between parties and accelerate procurement of critical materials. • Obtain timely approvals and expedite procurement of critical materials; Consider expediting procurement processes. • Expedite MEP agency onboarding to initiate material submittals and approvals for long-lead items, and assess the potential benefits of local procurement. • Reassess project scope to identify resource and timeline requirements; Develop a revised project schedule incorporating the new scope and methodology | Annex Building – • Superstructure works – Wall Rebar, Shutter & Concrete pouring up to 1st FL level Shelter Block – • Substructure – Waterproofing & Backfilling works Superstructure - RCC wall to progress GF & 1FL Surface Preparation & Application of CFRP Roof Slab Strengthening works to progress | 78077600 |  | 78077600 | 1576709 |  | 79654309 | 10200000 | 180000 | https://drive.google.com/thumbnail?id=1vEe16r7h-ux1rA7AxiyngNZw8Z8sHH4F&sz=w1000 | https://drive.google.com/file/d/1vEe16r7h-ux1rA7AxiyngNZw8Z8sHH4F/view?usp=drive_link | https://drive.google.com/thumbnail?id=1Id-FrFKnEcbWhvWSxpJ-s5C1Sd5GUsBE&sz=w1000 | https://drive.google.com/file/d/1Id-FrFKnEcbWhvWSxpJ-s5C1Sd5GUsBE/view?usp=drive_link | https://drive.google.com/thumbnail?id=13aoD-D4xVjW7Mpl0_JTNMreYR8d1A9sn&sz=w1000 | https://drive.google.com/file/d/13aoD-D4xVjW7Mpl0_JTNMreYR8d1A9sn/view?usp=drive_link
2024-08-12 | Al Shahama-School-P17 | P17 | SC-02 | 219 | 328 | 547 | Annex Building RCC Wall Shutter fixing Upto FF Level in progress – 80% Completed; Concrete 70% completed School Building GF - RCC Wall Rebar fixing 85% Completed | To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. School Construction is ongoing while awaiting final cost agreement with the employer. | 14.64% | 20.06% | 5.42% | Structural Completion | 2024-10-31 |  | 2025-01-09 | 2024-08-16 | • Risks / Challenges • Bill No.4 – MEP Final Rate Agreement required – 19-Aug-24 (Delaying the MEP Agency mobilization at site, Engineering & Procurement process) • Approval for Remaining Cost plus & Re-measurable Items required – 19-Aug-24 (Hampering the Annex & School building progress) • MEP Long lead items – Materials submittals & Approvals delaying due to Agency not mobilized (Impacted in the critical path) • Addition in Scope (Internal wall + External RCC Wall at School) & changes in construction methodology hindering the progress | • Expedite final rate agreement between parties and accelerate procurement of critical materials. • Obtain timely approvals and expedite procurement of critical materials; Consider expediting procurement processes. • Expedite MEP agency onboarding to initiate material submittals and approvals for long-lead items, and assess the potential benefits of local procurement. • Reassess project scope to identify resource and timeline requirements; Develop a revised project schedule incorporating the new scope and methodology | Annex Building – • Superstructure works – Wall Rebar, Shutter & Concrete pouring up to 1st FL level Shelter Block – • Substructure – Waterproofing & Backfilling works Superstructure - RCC wall to progress GF & 1FL Surface Preparation & Application of CFRP Roof Slab Strengthening works to progress | 78077600 |  | 78077600 | 1576709 |  | 79654309 | 10200000 | 180000 | https://drive.google.com/thumbnail?id=1vEe16r7h-ux1rA7AxiyngNZw8Z8sHH4F&sz=w1000 | https://drive.google.com/file/d/1vEe16r7h-ux1rA7AxiyngNZw8Z8sHH4F/view?usp=drive_link | https://drive.google.com/thumbnail?id=1Id-FrFKnEcbWhvWSxpJ-s5C1Sd5GUsBE&sz=w1000 | https://drive.google.com/file/d/1Id-FrFKnEcbWhvWSxpJ-s5C1Sd5GUsBE/view?usp=drive_link | https://drive.google.com/thumbnail?id=13aoD-D4xVjW7Mpl0_JTNMreYR8d1A9sn&sz=w1000 | https://drive.google.com/file/d/13aoD-D4xVjW7Mpl0_JTNMreYR8d1A9sn/view?usp=drive_link
2024-08-12 | Al Shahama-School-P17 | P17 | SC-02 | 219 | 328 | 547 | Annex Building RCC Wall Shutter fixing Upto FF Level in progress – 80% Completed; Concrete 70% completed School Building GF - RCC Wall Rebar fixing 85% Completed | To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. School Construction is ongoing while awaiting final cost agreement with the employer. | 14.64% | 20.06% | 5.42% | MEP & Finishes | 2025-01-25 |  | 2025-05-12 | 2024-08-16 | • Risks / Challenges • Bill No.4 – MEP Final Rate Agreement required – 19-Aug-24 (Delaying the MEP Agency mobilization at site, Engineering & Procurement process) • Approval for Remaining Cost plus & Re-measurable Items required – 19-Aug-24 (Hampering the Annex & School building progress) • MEP Long lead items – Materials submittals & Approvals delaying due to Agency not mobilized (Impacted in the critical path) • Addition in Scope (Internal wall + External RCC Wall at School) & changes in construction methodology hindering the progress | • Expedite final rate agreement between parties and accelerate procurement of critical materials. • Obtain timely approvals and expedite procurement of critical materials; Consider expediting procurement processes. • Expedite MEP agency onboarding to initiate material submittals and approvals for long-lead items, and assess the potential benefits of local procurement. • Reassess project scope to identify resource and timeline requirements; Develop a revised project schedule incorporating the new scope and methodology | Annex Building – • Superstructure works – Wall Rebar, Shutter & Concrete pouring up to 1st FL level Shelter Block – • Substructure – Waterproofing & Backfilling works Superstructure - RCC wall to progress GF & 1FL Surface Preparation & Application of CFRP Roof Slab Strengthening works to progress | 78077600 |  | 78077600 | 1576709 |  | 79654309 | 10200000 | 180000 | https://drive.google.com/thumbnail?id=1vEe16r7h-ux1rA7AxiyngNZw8Z8sHH4F&sz=w1000 | https://drive.google.com/file/d/1vEe16r7h-ux1rA7AxiyngNZw8Z8sHH4F/view?usp=drive_link | https://drive.google.com/thumbnail?id=1Id-FrFKnEcbWhvWSxpJ-s5C1Sd5GUsBE&sz=w1000 | https://drive.google.com/file/d/1Id-FrFKnEcbWhvWSxpJ-s5C1Sd5GUsBE/view?usp=drive_link | https://drive.google.com/thumbnail?id=13aoD-D4xVjW7Mpl0_JTNMreYR8d1A9sn&sz=w1000 | https://drive.google.com/file/d/13aoD-D4xVjW7Mpl0_JTNMreYR8d1A9sn/view?usp=drive_link
2024-08-12 | Al Shahama-School-P17 | P17 | SC-02 | 219 | 328 | 547 | Annex Building RCC Wall Shutter fixing Upto FF Level in progress – 80% Completed; Concrete 70% completed School Building GF - RCC Wall Rebar fixing 85% Completed | To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. School Construction is ongoing while awaiting final cost agreement with the employer. | 14.64% | 20.06% | 5.42% | BCC Inspection | 2025-02-13 |  | 2025-05-22 | 2024-08-16 | • Risks / Challenges • Bill No.4 – MEP Final Rate Agreement required – 19-Aug-24 (Delaying the MEP Agency mobilization at site, Engineering & Procurement process) • Approval for Remaining Cost plus & Re-measurable Items required – 19-Aug-24 (Hampering the Annex & School building progress) • MEP Long lead items – Materials submittals & Approvals delaying due to Agency not mobilized (Impacted in the critical path) • Addition in Scope (Internal wall + External RCC Wall at School) & changes in construction methodology hindering the progress | • Expedite final rate agreement between parties and accelerate procurement of critical materials. • Obtain timely approvals and expedite procurement of critical materials; Consider expediting procurement processes. • Expedite MEP agency onboarding to initiate material submittals and approvals for long-lead items, and assess the potential benefits of local procurement. • Reassess project scope to identify resource and timeline requirements; Develop a revised project schedule incorporating the new scope and methodology | Annex Building – • Superstructure works – Wall Rebar, Shutter & Concrete pouring up to 1st FL level Shelter Block – • Substructure – Waterproofing & Backfilling works Superstructure - RCC wall to progress GF & 1FL Surface Preparation & Application of CFRP Roof Slab Strengthening works to progress | 78077600 |  | 78077600 | 1576709 |  | 79654309 | 10200000 | 180000 | https://drive.google.com/thumbnail?id=1vEe16r7h-ux1rA7AxiyngNZw8Z8sHH4F&sz=w1000 | https://drive.google.com/file/d/1vEe16r7h-ux1rA7AxiyngNZw8Z8sHH4F/view?usp=drive_link | https://drive.google.com/thumbnail?id=1Id-FrFKnEcbWhvWSxpJ-s5C1Sd5GUsBE&sz=w1000 | https://drive.google.com/file/d/1Id-FrFKnEcbWhvWSxpJ-s5C1Sd5GUsBE/view?usp=drive_link | https://drive.google.com/thumbnail?id=13aoD-D4xVjW7Mpl0_JTNMreYR8d1A9sn&sz=w1000 | https://drive.google.com/file/d/13aoD-D4xVjW7Mpl0_JTNMreYR8d1A9sn/view?usp=drive_link
2024-08-12 | Al Shahama-School-P17 | P17 | SC-02 | 219 | 328 | 547 | Annex Building RCC Wall Shutter fixing Upto FF Level in progress – 80% Completed; Concrete 70% completed School Building GF - RCC Wall Rebar fixing 85% Completed | To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. School Construction is ongoing while awaiting final cost agreement with the employer. | 14.64% | 20.06% | 5.42% | BCC Issuance | 2025-03-04 |  | 2025-06-12 | 2024-08-16 | • Risks / Challenges • Bill No.4 – MEP Final Rate Agreement required – 19-Aug-24 (Delaying the MEP Agency mobilization at site, Engineering & Procurement process) • Approval for Remaining Cost plus & Re-measurable Items required – 19-Aug-24 (Hampering the Annex & School building progress) • MEP Long lead items – Materials submittals & Approvals delaying due to Agency not mobilized (Impacted in the critical path) • Addition in Scope (Internal wall + External RCC Wall at School) & changes in construction methodology hindering the progress | • Expedite final rate agreement between parties and accelerate procurement of critical materials. • Obtain timely approvals and expedite procurement of critical materials; Consider expediting procurement processes. • Expedite MEP agency onboarding to initiate material submittals and approvals for long-lead items, and assess the potential benefits of local procurement. • Reassess project scope to identify resource and timeline requirements; Develop a revised project schedule incorporating the new scope and methodology | Annex Building – • Superstructure works – Wall Rebar, Shutter & Concrete pouring up to 1st FL level Shelter Block – • Substructure – Waterproofing & Backfilling works Superstructure - RCC wall to progress GF & 1FL Surface Preparation & Application of CFRP Roof Slab Strengthening works to progress | 78077600 |  | 78077600 | 1576709 |  | 79654309 | 10200000 | 180000 | https://drive.google.com/thumbnail?id=1vEe16r7h-ux1rA7AxiyngNZw8Z8sHH4F&sz=w1000 | https://drive.google.com/file/d/1vEe16r7h-ux1rA7AxiyngNZw8Z8sHH4F/view?usp=drive_link | https://drive.google.com/thumbnail?id=1Id-FrFKnEcbWhvWSxpJ-s5C1Sd5GUsBE&sz=w1000 | https://drive.google.com/file/d/1Id-FrFKnEcbWhvWSxpJ-s5C1Sd5GUsBE/view?usp=drive_link | https://drive.google.com/thumbnail?id=13aoD-D4xVjW7Mpl0_JTNMreYR8d1A9sn&sz=w1000 | https://drive.google.com/file/d/13aoD-D4xVjW7Mpl0_JTNMreYR8d1A9sn/view?usp=drive_link
2024-08-12 | Al Shahama-School-P17 | P17 | SC-02 | 219 | 328 | 547 | Annex Building RCC Wall Shutter fixing Upto FF Level in progress – 80% Completed; Concrete 70% completed School Building GF - RCC Wall Rebar fixing 85% Completed | To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. School Construction is ongoing while awaiting final cost agreement with the employer. | 14.64% | 20.06% | 5.42% | Completion | 2025-03-14 |  | 2025-06-25 | 2024-08-16 | • Risks / Challenges • Bill No.4 – MEP Final Rate Agreement required – 19-Aug-24 (Delaying the MEP Agency mobilization at site, Engineering & Procurement process) • Approval for Remaining Cost plus & Re-measurable Items required – 19-Aug-24 (Hampering the Annex & School building progress) • MEP Long lead items – Materials submittals & Approvals delaying due to Agency not mobilized (Impacted in the critical path) • Addition in Scope (Internal wall + External RCC Wall at School) & changes in construction methodology hindering the progress | • Expedite final rate agreement between parties and accelerate procurement of critical materials. • Obtain timely approvals and expedite procurement of critical materials; Consider expediting procurement processes. • Expedite MEP agency onboarding to initiate material submittals and approvals for long-lead items, and assess the potential benefits of local procurement. • Reassess project scope to identify resource and timeline requirements; Develop a revised project schedule incorporating the new scope and methodology | Annex Building – • Superstructure works – Wall Rebar, Shutter & Concrete pouring up to 1st FL level Shelter Block – • Substructure – Waterproofing & Backfilling works Superstructure - RCC wall to progress GF & 1FL Surface Preparation & Application of CFRP Roof Slab Strengthening works to progress | 78077600 |  | 78077600 | 1576709 |  | 79654309 | 10200000 | 180000 | https://drive.google.com/thumbnail?id=1vEe16r7h-ux1rA7AxiyngNZw8Z8sHH4F&sz=w1000 | https://drive.google.com/file/d/1vEe16r7h-ux1rA7AxiyngNZw8Z8sHH4F/view?usp=drive_link | https://drive.google.com/thumbnail?id=1Id-FrFKnEcbWhvWSxpJ-s5C1Sd5GUsBE&sz=w1000 | https://drive.google.com/file/d/1Id-FrFKnEcbWhvWSxpJ-s5C1Sd5GUsBE/view?usp=drive_link | https://drive.google.com/thumbnail?id=13aoD-D4xVjW7Mpl0_JTNMreYR8d1A9sn&sz=w1000 | https://drive.google.com/file/d/13aoD-D4xVjW7Mpl0_JTNMreYR8d1A9sn/view?usp=drive_link
2024-08-12 | Baniyas-School-P77 | P77 | SC-01 | 159 | 390 | 549 | Annex Building • Backfilling Upto Plinth Level 90% completed; School Building • Foundation Work 100% completed; RCC Plinth Wall Concrete pouring 20% Completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 3.11% | 9.57% | 6.46% | Notice to Commence | 2024-03-05 | 2024-03-05 |  | 2024-08-16 | • Approval for Remaining Cost plus & Re-measurable Items required – 19-Aug-24 (Hampering the Annex & School building progress) • MEP Long lead items – Materials submittals & Approvals | • Obtain timely approvals and expedite procurement of critical materials; Consider expediting procurement processes. • MEP Agency Onboard required at the earliest to initiate the Material submittals/ Approval for Long lead items and order placement | Annex Building • Backfilling Complete & Grade slab works to progress • GF RCC wall works to progress Shelter Block • Substructure –RCC Wall upto Plinth to progress • RCC Wall Rebar Fixing to progress at GF & FF Level • Surface Preparation for CRFP works |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1auczJq74YC7zQtmuh6xlGQH7tRkhMdYG&sz=w1000 | https://drive.google.com/file/d/1auczJq74YC7zQtmuh6xlGQH7tRkhMdYG/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hhxNGrt1RWUdQCNORiATApfV6dbwQHYv&sz=w1000 | https://drive.google.com/file/d/1hhxNGrt1RWUdQCNORiATApfV6dbwQHYv/view?usp=drive_link | https://drive.google.com/thumbnail?id=1C5uHqCyjwEZRMq4L3oZrkNQH8lBZAZfP&sz=w1000 | https://drive.google.com/file/d/1C5uHqCyjwEZRMq4L3oZrkNQH8lBZAZfP/view?usp=drive_link
2024-08-12 | Baniyas-School-P77 | P77 | SC-01 | 159 | 390 | 549 | Annex Building • Backfilling Upto Plinth Level 90% completed; School Building • Foundation Work 100% completed; RCC Plinth Wall Concrete pouring 20% Completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 3.11% | 9.57% | 6.46% | Site Mobilization | 2024-04-09 | 2024-05-18 |  | 2024-08-16 | • Approval for Remaining Cost plus & Re-measurable Items required – 19-Aug-24 (Hampering the Annex & School building progress) • MEP Long lead items – Materials submittals & Approvals | • Obtain timely approvals and expedite procurement of critical materials; Consider expediting procurement processes. • MEP Agency Onboard required at the earliest to initiate the Material submittals/ Approval for Long lead items and order placement | Annex Building • Backfilling Complete & Grade slab works to progress • GF RCC wall works to progress Shelter Block • Substructure –RCC Wall upto Plinth to progress • RCC Wall Rebar Fixing to progress at GF & FF Level • Surface Preparation for CRFP works |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1auczJq74YC7zQtmuh6xlGQH7tRkhMdYG&sz=w1000 | https://drive.google.com/file/d/1auczJq74YC7zQtmuh6xlGQH7tRkhMdYG/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hhxNGrt1RWUdQCNORiATApfV6dbwQHYv&sz=w1000 | https://drive.google.com/file/d/1hhxNGrt1RWUdQCNORiATApfV6dbwQHYv/view?usp=drive_link | https://drive.google.com/thumbnail?id=1C5uHqCyjwEZRMq4L3oZrkNQH8lBZAZfP&sz=w1000 | https://drive.google.com/file/d/1C5uHqCyjwEZRMq4L3oZrkNQH8lBZAZfP/view?usp=drive_link
2024-08-12 | Baniyas-School-P77 | P77 | SC-01 | 159 | 390 | 549 | Annex Building • Backfilling Upto Plinth Level 90% completed; School Building • Foundation Work 100% completed; RCC Plinth Wall Concrete pouring 20% Completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 3.11% | 9.57% | 6.46% | Building Permit | 2024-01-11 | 2024-08-06 |  | 2024-08-16 | • Approval for Remaining Cost plus & Re-measurable Items required – 19-Aug-24 (Hampering the Annex & School building progress) • MEP Long lead items – Materials submittals & Approvals | • Obtain timely approvals and expedite procurement of critical materials; Consider expediting procurement processes. • MEP Agency Onboard required at the earliest to initiate the Material submittals/ Approval for Long lead items and order placement | Annex Building • Backfilling Complete & Grade slab works to progress • GF RCC wall works to progress Shelter Block • Substructure –RCC Wall upto Plinth to progress • RCC Wall Rebar Fixing to progress at GF & FF Level • Surface Preparation for CRFP works |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1auczJq74YC7zQtmuh6xlGQH7tRkhMdYG&sz=w1000 | https://drive.google.com/file/d/1auczJq74YC7zQtmuh6xlGQH7tRkhMdYG/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hhxNGrt1RWUdQCNORiATApfV6dbwQHYv&sz=w1000 | https://drive.google.com/file/d/1hhxNGrt1RWUdQCNORiATApfV6dbwQHYv/view?usp=drive_link | https://drive.google.com/thumbnail?id=1C5uHqCyjwEZRMq4L3oZrkNQH8lBZAZfP&sz=w1000 | https://drive.google.com/file/d/1C5uHqCyjwEZRMq4L3oZrkNQH8lBZAZfP/view?usp=drive_link
2024-08-12 | Baniyas-School-P77 | P77 | SC-01 | 159 | 390 | 549 | Annex Building • Backfilling Upto Plinth Level 90% completed; School Building • Foundation Work 100% completed; RCC Plinth Wall Concrete pouring 20% Completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 3.11% | 9.57% | 6.46% | Design Phase | 2024-11-06 |  | 2024-10-05 | 2024-08-16 | • Approval for Remaining Cost plus & Re-measurable Items required – 19-Aug-24 (Hampering the Annex & School building progress) • MEP Long lead items – Materials submittals & Approvals | • Obtain timely approvals and expedite procurement of critical materials; Consider expediting procurement processes. • MEP Agency Onboard required at the earliest to initiate the Material submittals/ Approval for Long lead items and order placement | Annex Building • Backfilling Complete & Grade slab works to progress • GF RCC wall works to progress Shelter Block • Substructure –RCC Wall upto Plinth to progress • RCC Wall Rebar Fixing to progress at GF & FF Level • Surface Preparation for CRFP works |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1auczJq74YC7zQtmuh6xlGQH7tRkhMdYG&sz=w1000 | https://drive.google.com/file/d/1auczJq74YC7zQtmuh6xlGQH7tRkhMdYG/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hhxNGrt1RWUdQCNORiATApfV6dbwQHYv&sz=w1000 | https://drive.google.com/file/d/1hhxNGrt1RWUdQCNORiATApfV6dbwQHYv/view?usp=drive_link | https://drive.google.com/thumbnail?id=1C5uHqCyjwEZRMq4L3oZrkNQH8lBZAZfP&sz=w1000 | https://drive.google.com/file/d/1C5uHqCyjwEZRMq4L3oZrkNQH8lBZAZfP/view?usp=drive_link
2024-08-12 | Baniyas-School-P77 | P77 | SC-01 | 159 | 390 | 549 | Annex Building • Backfilling Upto Plinth Level 90% completed; School Building • Foundation Work 100% completed; RCC Plinth Wall Concrete pouring 20% Completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 3.11% | 9.57% | 6.46% | Structural Completion | 2025-12-04 |  | 2025-03-12 | 2024-08-16 | • Approval for Remaining Cost plus & Re-measurable Items required – 19-Aug-24 (Hampering the Annex & School building progress) • MEP Long lead items – Materials submittals & Approvals | • Obtain timely approvals and expedite procurement of critical materials; Consider expediting procurement processes. • MEP Agency Onboard required at the earliest to initiate the Material submittals/ Approval for Long lead items and order placement | Annex Building • Backfilling Complete & Grade slab works to progress • GF RCC wall works to progress Shelter Block • Substructure –RCC Wall upto Plinth to progress • RCC Wall Rebar Fixing to progress at GF & FF Level • Surface Preparation for CRFP works |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1auczJq74YC7zQtmuh6xlGQH7tRkhMdYG&sz=w1000 | https://drive.google.com/file/d/1auczJq74YC7zQtmuh6xlGQH7tRkhMdYG/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hhxNGrt1RWUdQCNORiATApfV6dbwQHYv&sz=w1000 | https://drive.google.com/file/d/1hhxNGrt1RWUdQCNORiATApfV6dbwQHYv/view?usp=drive_link | https://drive.google.com/thumbnail?id=1C5uHqCyjwEZRMq4L3oZrkNQH8lBZAZfP&sz=w1000 | https://drive.google.com/file/d/1C5uHqCyjwEZRMq4L3oZrkNQH8lBZAZfP/view?usp=drive_link
2024-08-12 | Baniyas-School-P77 | P77 | SC-01 | 159 | 390 | 549 | Annex Building • Backfilling Upto Plinth Level 90% completed; School Building • Foundation Work 100% completed; RCC Plinth Wall Concrete pouring 20% Completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 3.11% | 9.57% | 6.46% | MEP & Finishes | 2025-07-19 |  | 2025-06-13 | 2024-08-16 | • Approval for Remaining Cost plus & Re-measurable Items required – 19-Aug-24 (Hampering the Annex & School building progress) • MEP Long lead items – Materials submittals & Approvals | • Obtain timely approvals and expedite procurement of critical materials; Consider expediting procurement processes. • MEP Agency Onboard required at the earliest to initiate the Material submittals/ Approval for Long lead items and order placement | Annex Building • Backfilling Complete & Grade slab works to progress • GF RCC wall works to progress Shelter Block • Substructure –RCC Wall upto Plinth to progress • RCC Wall Rebar Fixing to progress at GF & FF Level • Surface Preparation for CRFP works |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1auczJq74YC7zQtmuh6xlGQH7tRkhMdYG&sz=w1000 | https://drive.google.com/file/d/1auczJq74YC7zQtmuh6xlGQH7tRkhMdYG/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hhxNGrt1RWUdQCNORiATApfV6dbwQHYv&sz=w1000 | https://drive.google.com/file/d/1hhxNGrt1RWUdQCNORiATApfV6dbwQHYv/view?usp=drive_link | https://drive.google.com/thumbnail?id=1C5uHqCyjwEZRMq4L3oZrkNQH8lBZAZfP&sz=w1000 | https://drive.google.com/file/d/1C5uHqCyjwEZRMq4L3oZrkNQH8lBZAZfP/view?usp=drive_link
2024-08-12 | Baniyas-School-P77 | P77 | SC-01 | 159 | 390 | 549 | Annex Building • Backfilling Upto Plinth Level 90% completed; School Building • Foundation Work 100% completed; RCC Plinth Wall Concrete pouring 20% Completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 3.11% | 9.57% | 6.46% | BCC Inspection | 2025-08-05 |  | 2025-07-03 | 2024-08-16 | • Approval for Remaining Cost plus & Re-measurable Items required – 19-Aug-24 (Hampering the Annex & School building progress) • MEP Long lead items – Materials submittals & Approvals | • Obtain timely approvals and expedite procurement of critical materials; Consider expediting procurement processes. • MEP Agency Onboard required at the earliest to initiate the Material submittals/ Approval for Long lead items and order placement | Annex Building • Backfilling Complete & Grade slab works to progress • GF RCC wall works to progress Shelter Block • Substructure –RCC Wall upto Plinth to progress • RCC Wall Rebar Fixing to progress at GF & FF Level • Surface Preparation for CRFP works |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1auczJq74YC7zQtmuh6xlGQH7tRkhMdYG&sz=w1000 | https://drive.google.com/file/d/1auczJq74YC7zQtmuh6xlGQH7tRkhMdYG/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hhxNGrt1RWUdQCNORiATApfV6dbwQHYv&sz=w1000 | https://drive.google.com/file/d/1hhxNGrt1RWUdQCNORiATApfV6dbwQHYv/view?usp=drive_link | https://drive.google.com/thumbnail?id=1C5uHqCyjwEZRMq4L3oZrkNQH8lBZAZfP&sz=w1000 | https://drive.google.com/file/d/1C5uHqCyjwEZRMq4L3oZrkNQH8lBZAZfP/view?usp=drive_link
2024-08-12 | Baniyas-School-P77 | P77 | SC-01 | 159 | 390 | 549 | Annex Building • Backfilling Upto Plinth Level 90% completed; School Building • Foundation Work 100% completed; RCC Plinth Wall Concrete pouring 20% Completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 3.11% | 9.57% | 6.46% | BCC Issuance | 2025-08-22 |  | 2025-07-22 | 2024-08-16 | • Approval for Remaining Cost plus & Re-measurable Items required – 19-Aug-24 (Hampering the Annex & School building progress) • MEP Long lead items – Materials submittals & Approvals | • Obtain timely approvals and expedite procurement of critical materials; Consider expediting procurement processes. • MEP Agency Onboard required at the earliest to initiate the Material submittals/ Approval for Long lead items and order placement | Annex Building • Backfilling Complete & Grade slab works to progress • GF RCC wall works to progress Shelter Block • Substructure –RCC Wall upto Plinth to progress • RCC Wall Rebar Fixing to progress at GF & FF Level • Surface Preparation for CRFP works |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1auczJq74YC7zQtmuh6xlGQH7tRkhMdYG&sz=w1000 | https://drive.google.com/file/d/1auczJq74YC7zQtmuh6xlGQH7tRkhMdYG/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hhxNGrt1RWUdQCNORiATApfV6dbwQHYv&sz=w1000 | https://drive.google.com/file/d/1hhxNGrt1RWUdQCNORiATApfV6dbwQHYv/view?usp=drive_link | https://drive.google.com/thumbnail?id=1C5uHqCyjwEZRMq4L3oZrkNQH8lBZAZfP&sz=w1000 | https://drive.google.com/file/d/1C5uHqCyjwEZRMq4L3oZrkNQH8lBZAZfP/view?usp=drive_link
2024-08-12 | Baniyas-School-P77 | P77 | SC-01 | 159 | 390 | 549 | Annex Building • Backfilling Upto Plinth Level 90% completed; School Building • Foundation Work 100% completed; RCC Plinth Wall Concrete pouring 20% Completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 3.11% | 9.57% | 6.46% | Completion | 2025-09-04 |  | 2025-09-04 | 2024-08-16 | • Approval for Remaining Cost plus & Re-measurable Items required – 19-Aug-24 (Hampering the Annex & School building progress) • MEP Long lead items – Materials submittals & Approvals | • Obtain timely approvals and expedite procurement of critical materials; Consider expediting procurement processes. • MEP Agency Onboard required at the earliest to initiate the Material submittals/ Approval for Long lead items and order placement | Annex Building • Backfilling Complete & Grade slab works to progress • GF RCC wall works to progress Shelter Block • Substructure –RCC Wall upto Plinth to progress • RCC Wall Rebar Fixing to progress at GF & FF Level • Surface Preparation for CRFP works |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1auczJq74YC7zQtmuh6xlGQH7tRkhMdYG&sz=w1000 | https://drive.google.com/file/d/1auczJq74YC7zQtmuh6xlGQH7tRkhMdYG/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hhxNGrt1RWUdQCNORiATApfV6dbwQHYv&sz=w1000 | https://drive.google.com/file/d/1hhxNGrt1RWUdQCNORiATApfV6dbwQHYv/view?usp=drive_link | https://drive.google.com/thumbnail?id=1C5uHqCyjwEZRMq4L3oZrkNQH8lBZAZfP&sz=w1000 | https://drive.google.com/file/d/1C5uHqCyjwEZRMq4L3oZrkNQH8lBZAZfP/view?usp=drive_link
2024-08-12 | Al Sarouj-School-P16 | P16 | SC-04 | 219 | 328 | 547 | Annex Building • Backfilling 70% completed; GF RCC wall works to progress School Building • Substructure – Foundation Concrete 95% completed; RCC Wall (upto Plinth) 68% done | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 14.64% | 12.43% | -2.21% | Notice to Commence | 2023-09-18 | 2023-09-26 |  | 2024-08-16 | • Bill No.4 – MEP Final Rate Agreement required – 19-Aug-24 (Delaying the MEP Agency mobilization at site, Engineering & Procurement process) • Approval for Remaining Cost plus & Re-measurable Items required – 19-Aug-24 (Hampering the Annex & School building progress) • MEP Long lead items – Materials submittals & Approvals delaying due to Agency not mobilized (Impacted in the critical path) • Addition in Scope (Internal wall + External RCC Wall at School) & changes in construction methodology hindering the progress | • Expedite final rate agreement between parties and accelerate procurement of critical materials. • Obtain timely approvals and expedite procurement of critical materials; Consider expediting procurement processes. • Expedite MEP agency onboarding to initiate material submittals and approvals for long-lead items, and assess the potential benefits of local procurement. • Reassess project scope to identify resource and timeline requirements; Develop a revised project schedule incorporating the new scope and methodology | Annex Building • Substructure works to complete • Superstructure – RCC Wall works to progress Shelter Block • Substructure – Anchoring to completed • Substructure – Foundation Cast & Existing Structure Strengthening works to progress • GF – Rebar Fixing for Wall to progress • Surface Preparation for CRFP works |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=11xxU2ddfwE6cm1UuPtNg46qi4NQOhg8k&sz=w1000 | https://drive.google.com/file/d/11xxU2ddfwE6cm1UuPtNg46qi4NQOhg8k/view?usp=drive_link | https://drive.google.com/thumbnail?id=1MXyFNwT7lana1d7a1lX-bhotozLGMclA&sz=w1000 | https://drive.google.com/file/d/1MXyFNwT7lana1d7a1lX-bhotozLGMclA/view?usp=drive_link | https://drive.google.com/thumbnail?id=1H0oJ6vgdqHw6dKdkzkTd3-KkxRDPqWbg&sz=w1000 | https://drive.google.com/file/d/1H0oJ6vgdqHw6dKdkzkTd3-KkxRDPqWbg/view?usp=drive_link
2024-08-12 | Al Sarouj-School-P16 | P16 | SC-04 | 219 | 328 | 547 | Annex Building • Backfilling 70% completed; GF RCC wall works to progress School Building • Substructure – Foundation Concrete 95% completed; RCC Wall (upto Plinth) 68% done | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 14.64% | 12.43% | -2.21% | Site Mobilization | 2023-10-21 | 2024-01-06 |  | 2024-08-16 | • Bill No.4 – MEP Final Rate Agreement required – 19-Aug-24 (Delaying the MEP Agency mobilization at site, Engineering & Procurement process) • Approval for Remaining Cost plus & Re-measurable Items required – 19-Aug-24 (Hampering the Annex & School building progress) • MEP Long lead items – Materials submittals & Approvals delaying due to Agency not mobilized (Impacted in the critical path) • Addition in Scope (Internal wall + External RCC Wall at School) & changes in construction methodology hindering the progress | • Expedite final rate agreement between parties and accelerate procurement of critical materials. • Obtain timely approvals and expedite procurement of critical materials; Consider expediting procurement processes. • Expedite MEP agency onboarding to initiate material submittals and approvals for long-lead items, and assess the potential benefits of local procurement. • Reassess project scope to identify resource and timeline requirements; Develop a revised project schedule incorporating the new scope and methodology | Annex Building • Substructure works to complete • Superstructure – RCC Wall works to progress Shelter Block • Substructure – Anchoring to completed • Substructure – Foundation Cast & Existing Structure Strengthening works to progress • GF – Rebar Fixing for Wall to progress • Surface Preparation for CRFP works |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=11xxU2ddfwE6cm1UuPtNg46qi4NQOhg8k&sz=w1000 | https://drive.google.com/file/d/11xxU2ddfwE6cm1UuPtNg46qi4NQOhg8k/view?usp=drive_link | https://drive.google.com/thumbnail?id=1MXyFNwT7lana1d7a1lX-bhotozLGMclA&sz=w1000 | https://drive.google.com/file/d/1MXyFNwT7lana1d7a1lX-bhotozLGMclA/view?usp=drive_link | https://drive.google.com/thumbnail?id=1H0oJ6vgdqHw6dKdkzkTd3-KkxRDPqWbg&sz=w1000 | https://drive.google.com/file/d/1H0oJ6vgdqHw6dKdkzkTd3-KkxRDPqWbg/view?usp=drive_link
2024-08-12 | Al Sarouj-School-P16 | P16 | SC-04 | 219 | 328 | 547 | Annex Building • Backfilling 70% completed; GF RCC wall works to progress School Building • Substructure – Foundation Concrete 95% completed; RCC Wall (upto Plinth) 68% done | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 14.64% | 12.43% | -2.21% | Building Permit | 2024-05-17 | 2024-06-20 |  | 2024-08-16 | • Bill No.4 – MEP Final Rate Agreement required – 19-Aug-24 (Delaying the MEP Agency mobilization at site, Engineering & Procurement process) • Approval for Remaining Cost plus & Re-measurable Items required – 19-Aug-24 (Hampering the Annex & School building progress) • MEP Long lead items – Materials submittals & Approvals delaying due to Agency not mobilized (Impacted in the critical path) • Addition in Scope (Internal wall + External RCC Wall at School) & changes in construction methodology hindering the progress | • Expedite final rate agreement between parties and accelerate procurement of critical materials. • Obtain timely approvals and expedite procurement of critical materials; Consider expediting procurement processes. • Expedite MEP agency onboarding to initiate material submittals and approvals for long-lead items, and assess the potential benefits of local procurement. • Reassess project scope to identify resource and timeline requirements; Develop a revised project schedule incorporating the new scope and methodology | Annex Building • Substructure works to complete • Superstructure – RCC Wall works to progress Shelter Block • Substructure – Anchoring to completed • Substructure – Foundation Cast & Existing Structure Strengthening works to progress • GF – Rebar Fixing for Wall to progress • Surface Preparation for CRFP works |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=11xxU2ddfwE6cm1UuPtNg46qi4NQOhg8k&sz=w1000 | https://drive.google.com/file/d/11xxU2ddfwE6cm1UuPtNg46qi4NQOhg8k/view?usp=drive_link | https://drive.google.com/thumbnail?id=1MXyFNwT7lana1d7a1lX-bhotozLGMclA&sz=w1000 | https://drive.google.com/file/d/1MXyFNwT7lana1d7a1lX-bhotozLGMclA/view?usp=drive_link | https://drive.google.com/thumbnail?id=1H0oJ6vgdqHw6dKdkzkTd3-KkxRDPqWbg&sz=w1000 | https://drive.google.com/file/d/1H0oJ6vgdqHw6dKdkzkTd3-KkxRDPqWbg/view?usp=drive_link
2024-08-12 | Al Sarouj-School-P16 | P16 | SC-04 | 219 | 328 | 547 | Annex Building • Backfilling 70% completed; GF RCC wall works to progress School Building • Substructure – Foundation Concrete 95% completed; RCC Wall (upto Plinth) 68% done | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 14.64% | 12.43% | -2.21% | Design Phase | 2024-05-21 | 2024-08-10 |  | 2024-08-16 | • Bill No.4 – MEP Final Rate Agreement required – 19-Aug-24 (Delaying the MEP Agency mobilization at site, Engineering & Procurement process) • Approval for Remaining Cost plus & Re-measurable Items required – 19-Aug-24 (Hampering the Annex & School building progress) • MEP Long lead items – Materials submittals & Approvals delaying due to Agency not mobilized (Impacted in the critical path) • Addition in Scope (Internal wall + External RCC Wall at School) & changes in construction methodology hindering the progress | • Expedite final rate agreement between parties and accelerate procurement of critical materials. • Obtain timely approvals and expedite procurement of critical materials; Consider expediting procurement processes. • Expedite MEP agency onboarding to initiate material submittals and approvals for long-lead items, and assess the potential benefits of local procurement. • Reassess project scope to identify resource and timeline requirements; Develop a revised project schedule incorporating the new scope and methodology | Annex Building • Substructure works to complete • Superstructure – RCC Wall works to progress Shelter Block • Substructure – Anchoring to completed • Substructure – Foundation Cast & Existing Structure Strengthening works to progress • GF – Rebar Fixing for Wall to progress • Surface Preparation for CRFP works |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=11xxU2ddfwE6cm1UuPtNg46qi4NQOhg8k&sz=w1000 | https://drive.google.com/file/d/11xxU2ddfwE6cm1UuPtNg46qi4NQOhg8k/view?usp=drive_link | https://drive.google.com/thumbnail?id=1MXyFNwT7lana1d7a1lX-bhotozLGMclA&sz=w1000 | https://drive.google.com/file/d/1MXyFNwT7lana1d7a1lX-bhotozLGMclA/view?usp=drive_link | https://drive.google.com/thumbnail?id=1H0oJ6vgdqHw6dKdkzkTd3-KkxRDPqWbg&sz=w1000 | https://drive.google.com/file/d/1H0oJ6vgdqHw6dKdkzkTd3-KkxRDPqWbg/view?usp=drive_link
2024-08-12 | Al Sarouj-School-P16 | P16 | SC-04 | 219 | 328 | 547 | Annex Building • Backfilling 70% completed; GF RCC wall works to progress School Building • Substructure – Foundation Concrete 95% completed; RCC Wall (upto Plinth) 68% done | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 14.64% | 12.43% | -2.21% | Structural Completion | 2024-10-31 |  | 2025-01-23 | 2024-08-16 | • Bill No.4 – MEP Final Rate Agreement required – 19-Aug-24 (Delaying the MEP Agency mobilization at site, Engineering & Procurement process) • Approval for Remaining Cost plus & Re-measurable Items required – 19-Aug-24 (Hampering the Annex & School building progress) • MEP Long lead items – Materials submittals & Approvals delaying due to Agency not mobilized (Impacted in the critical path) • Addition in Scope (Internal wall + External RCC Wall at School) & changes in construction methodology hindering the progress | • Expedite final rate agreement between parties and accelerate procurement of critical materials. • Obtain timely approvals and expedite procurement of critical materials; Consider expediting procurement processes. • Expedite MEP agency onboarding to initiate material submittals and approvals for long-lead items, and assess the potential benefits of local procurement. • Reassess project scope to identify resource and timeline requirements; Develop a revised project schedule incorporating the new scope and methodology | Annex Building • Substructure works to complete • Superstructure – RCC Wall works to progress Shelter Block • Substructure – Anchoring to completed • Substructure – Foundation Cast & Existing Structure Strengthening works to progress • GF – Rebar Fixing for Wall to progress • Surface Preparation for CRFP works |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=11xxU2ddfwE6cm1UuPtNg46qi4NQOhg8k&sz=w1000 | https://drive.google.com/file/d/11xxU2ddfwE6cm1UuPtNg46qi4NQOhg8k/view?usp=drive_link | https://drive.google.com/thumbnail?id=1MXyFNwT7lana1d7a1lX-bhotozLGMclA&sz=w1000 | https://drive.google.com/file/d/1MXyFNwT7lana1d7a1lX-bhotozLGMclA/view?usp=drive_link | https://drive.google.com/thumbnail?id=1H0oJ6vgdqHw6dKdkzkTd3-KkxRDPqWbg&sz=w1000 | https://drive.google.com/file/d/1H0oJ6vgdqHw6dKdkzkTd3-KkxRDPqWbg/view?usp=drive_link
2024-08-12 | Al Sarouj-School-P16 | P16 | SC-04 | 219 | 328 | 547 | Annex Building • Backfilling 70% completed; GF RCC wall works to progress School Building • Substructure – Foundation Concrete 95% completed; RCC Wall (upto Plinth) 68% done | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 14.64% | 12.43% | -2.21% | MEP & Finishes | 2025-01-25 |  | 2025-05-12 | 2024-08-16 | • Bill No.4 – MEP Final Rate Agreement required – 19-Aug-24 (Delaying the MEP Agency mobilization at site, Engineering & Procurement process) • Approval for Remaining Cost plus & Re-measurable Items required – 19-Aug-24 (Hampering the Annex & School building progress) • MEP Long lead items – Materials submittals & Approvals delaying due to Agency not mobilized (Impacted in the critical path) • Addition in Scope (Internal wall + External RCC Wall at School) & changes in construction methodology hindering the progress | • Expedite final rate agreement between parties and accelerate procurement of critical materials. • Obtain timely approvals and expedite procurement of critical materials; Consider expediting procurement processes. • Expedite MEP agency onboarding to initiate material submittals and approvals for long-lead items, and assess the potential benefits of local procurement. • Reassess project scope to identify resource and timeline requirements; Develop a revised project schedule incorporating the new scope and methodology | Annex Building • Substructure works to complete • Superstructure – RCC Wall works to progress Shelter Block • Substructure – Anchoring to completed • Substructure – Foundation Cast & Existing Structure Strengthening works to progress • GF – Rebar Fixing for Wall to progress • Surface Preparation for CRFP works |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=11xxU2ddfwE6cm1UuPtNg46qi4NQOhg8k&sz=w1000 | https://drive.google.com/file/d/11xxU2ddfwE6cm1UuPtNg46qi4NQOhg8k/view?usp=drive_link | https://drive.google.com/thumbnail?id=1MXyFNwT7lana1d7a1lX-bhotozLGMclA&sz=w1000 | https://drive.google.com/file/d/1MXyFNwT7lana1d7a1lX-bhotozLGMclA/view?usp=drive_link | https://drive.google.com/thumbnail?id=1H0oJ6vgdqHw6dKdkzkTd3-KkxRDPqWbg&sz=w1000 | https://drive.google.com/file/d/1H0oJ6vgdqHw6dKdkzkTd3-KkxRDPqWbg/view?usp=drive_link
2024-08-12 | Al Sarouj-School-P16 | P16 | SC-04 | 219 | 328 | 547 | Annex Building • Backfilling 70% completed; GF RCC wall works to progress School Building • Substructure – Foundation Concrete 95% completed; RCC Wall (upto Plinth) 68% done | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 14.64% | 12.43% | -2.21% | BCC Inspection | 2025-02-13 |  | 2025-05-22 | 2024-08-16 | • Bill No.4 – MEP Final Rate Agreement required – 19-Aug-24 (Delaying the MEP Agency mobilization at site, Engineering & Procurement process) • Approval for Remaining Cost plus & Re-measurable Items required – 19-Aug-24 (Hampering the Annex & School building progress) • MEP Long lead items – Materials submittals & Approvals delaying due to Agency not mobilized (Impacted in the critical path) • Addition in Scope (Internal wall + External RCC Wall at School) & changes in construction methodology hindering the progress | • Expedite final rate agreement between parties and accelerate procurement of critical materials. • Obtain timely approvals and expedite procurement of critical materials; Consider expediting procurement processes. • Expedite MEP agency onboarding to initiate material submittals and approvals for long-lead items, and assess the potential benefits of local procurement. • Reassess project scope to identify resource and timeline requirements; Develop a revised project schedule incorporating the new scope and methodology | Annex Building • Substructure works to complete • Superstructure – RCC Wall works to progress Shelter Block • Substructure – Anchoring to completed • Substructure – Foundation Cast & Existing Structure Strengthening works to progress • GF – Rebar Fixing for Wall to progress • Surface Preparation for CRFP works |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=11xxU2ddfwE6cm1UuPtNg46qi4NQOhg8k&sz=w1000 | https://drive.google.com/file/d/11xxU2ddfwE6cm1UuPtNg46qi4NQOhg8k/view?usp=drive_link | https://drive.google.com/thumbnail?id=1MXyFNwT7lana1d7a1lX-bhotozLGMclA&sz=w1000 | https://drive.google.com/file/d/1MXyFNwT7lana1d7a1lX-bhotozLGMclA/view?usp=drive_link | https://drive.google.com/thumbnail?id=1H0oJ6vgdqHw6dKdkzkTd3-KkxRDPqWbg&sz=w1000 | https://drive.google.com/file/d/1H0oJ6vgdqHw6dKdkzkTd3-KkxRDPqWbg/view?usp=drive_link
2024-08-12 | Al Sarouj-School-P16 | P16 | SC-04 | 219 | 328 | 547 | Annex Building • Backfilling 70% completed; GF RCC wall works to progress School Building • Substructure – Foundation Concrete 95% completed; RCC Wall (upto Plinth) 68% done | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 14.64% | 12.43% | -2.21% | BCC Issuance | 2025-03-24 |  | 2025-06-12 | 2024-08-16 | • Bill No.4 – MEP Final Rate Agreement required – 19-Aug-24 (Delaying the MEP Agency mobilization at site, Engineering & Procurement process) • Approval for Remaining Cost plus & Re-measurable Items required – 19-Aug-24 (Hampering the Annex & School building progress) • MEP Long lead items – Materials submittals & Approvals delaying due to Agency not mobilized (Impacted in the critical path) • Addition in Scope (Internal wall + External RCC Wall at School) & changes in construction methodology hindering the progress | • Expedite final rate agreement between parties and accelerate procurement of critical materials. • Obtain timely approvals and expedite procurement of critical materials; Consider expediting procurement processes. • Expedite MEP agency onboarding to initiate material submittals and approvals for long-lead items, and assess the potential benefits of local procurement. • Reassess project scope to identify resource and timeline requirements; Develop a revised project schedule incorporating the new scope and methodology | Annex Building • Substructure works to complete • Superstructure – RCC Wall works to progress Shelter Block • Substructure – Anchoring to completed • Substructure – Foundation Cast & Existing Structure Strengthening works to progress • GF – Rebar Fixing for Wall to progress • Surface Preparation for CRFP works |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=11xxU2ddfwE6cm1UuPtNg46qi4NQOhg8k&sz=w1000 | https://drive.google.com/file/d/11xxU2ddfwE6cm1UuPtNg46qi4NQOhg8k/view?usp=drive_link | https://drive.google.com/thumbnail?id=1MXyFNwT7lana1d7a1lX-bhotozLGMclA&sz=w1000 | https://drive.google.com/file/d/1MXyFNwT7lana1d7a1lX-bhotozLGMclA/view?usp=drive_link | https://drive.google.com/thumbnail?id=1H0oJ6vgdqHw6dKdkzkTd3-KkxRDPqWbg&sz=w1000 | https://drive.google.com/file/d/1H0oJ6vgdqHw6dKdkzkTd3-KkxRDPqWbg/view?usp=drive_link
2024-08-12 | Al Sarouj-School-P16 | P16 | SC-04 | 219 | 328 | 547 | Annex Building • Backfilling 70% completed; GF RCC wall works to progress School Building • Substructure – Foundation Concrete 95% completed; RCC Wall (upto Plinth) 68% done | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 14.64% | 12.43% | -2.21% | Completion | 2025-03-17 |  | 2025-06-25 | 2024-08-16 | • Bill No.4 – MEP Final Rate Agreement required – 19-Aug-24 (Delaying the MEP Agency mobilization at site, Engineering & Procurement process) • Approval for Remaining Cost plus & Re-measurable Items required – 19-Aug-24 (Hampering the Annex & School building progress) • MEP Long lead items – Materials submittals & Approvals delaying due to Agency not mobilized (Impacted in the critical path) • Addition in Scope (Internal wall + External RCC Wall at School) & changes in construction methodology hindering the progress | Annex Building Substructure – Grade Slab & Beam Works to progress Superstructure works – RCC wall up to FF level to progress Shelter Block Substructure –works to complete Superstructure – RCC Wall work to progress upto 1FL Level Surface Preparation for CRFP works to progress Expedite final rate agreement between parties and accelerate procurement of critical materials. • Obtain timely approvals and expedite procurement of critical materials; Consider expediting procurement processes. • Expedite MEP agency onboarding to initiate material submittals and approvals for long-lead items, and assess the potential benefits of local procurement. • Reassess project scope to identify resource and timeline requirements; Develop a revised project schedule incorporating the new scope and methodology | Annex Building • Substructure works to complete • Superstructure – RCC Wall works to progress Shelter Block • Substructure – Anchoring to completed • Substructure – Foundation Cast & Existing Structure Strengthening works to progress • GF – Rebar Fixing for Wall to progress • Surface Preparation for CRFP works |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=11xxU2ddfwE6cm1UuPtNg46qi4NQOhg8k&sz=w1000 | https://drive.google.com/file/d/11xxU2ddfwE6cm1UuPtNg46qi4NQOhg8k/view?usp=drive_link | https://drive.google.com/thumbnail?id=1MXyFNwT7lana1d7a1lX-bhotozLGMclA&sz=w1000 | https://drive.google.com/file/d/1MXyFNwT7lana1d7a1lX-bhotozLGMclA/view?usp=drive_link | https://drive.google.com/thumbnail?id=1H0oJ6vgdqHw6dKdkzkTd3-KkxRDPqWbg&sz=w1000 | https://drive.google.com/file/d/1H0oJ6vgdqHw6dKdkzkTd3-KkxRDPqWbg/view?usp=drive_link
2024-08-12 | Al Sarouj-School-P2 | P2 | SC-03 | 255 | 292 | 547 | Annex Building • Superstructure – Ground Floor RCC Wall Concrete 20% Completed; Rebar Fixing 70% done School Building • RCC Wall Concrete Upto Plinth 83% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 5.21% | 14.1% | 8.89% | Notice to Commence | 2023-11-30 | 2023-11-30 |  | 2024-08-16 | • Bill No.4 – MEP Final Rate Agreement required – 19-Aug-24 (Delaying the MEP Agency mobilization at site, Engineering & Procurement process) • Approval for Remaining Cost plus & Re-measurable Items required – 19-Aug-24 (Hampering the Annex & School building progress) • MEP Long lead items – Materials submittals & Approvals delaying due to Agency not mobilized (Impacted in the critical path) • Addition in Scope (Internal wall + External RCC Wall at School) & changes in construction methodology hindering the progress | • Expedite final rate agreement between parties and accelerate procurement of critical materials. • Obtain timely approvals and expedite procurement of critical materials; Consider expediting procurement processes. • Expedite MEP agency onboarding to initiate material submittals and approvals for long-lead items, and assess the potential benefits of local procurement. • Reassess project scope to identify resource and timeline requirements; Develop a revised project schedule incorporating the new scope and methodology | Annex Building • Substructure – Grade Slab & Beam Works to progress • Superstructure works – RCC wall up to FF level to progress Shelter Block • Substructure –works to complete • Superstructure – RCC Wall work to progress upto 1FL Level • Surface Preparation for CRFP works to progress |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1WyM62m91MyOYiYchDit1EWaKO2dnqPzx&sz=w1000 | https://drive.google.com/file/d/1WyM62m91MyOYiYchDit1EWaKO2dnqPzx/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hp_omkqqkYn1e8mTswZtyA2acgQaNMuO&sz=w1000 | https://drive.google.com/file/d/1hp_omkqqkYn1e8mTswZtyA2acgQaNMuO/view?usp=drive_link | https://drive.google.com/thumbnail?id=1S7XMV5_8waurveisDWugvibu1mQY1cgy&sz=w1000 | https://drive.google.com/file/d/1S7XMV5_8waurveisDWugvibu1mQY1cgy/view?usp=drive_link
2024-08-12 | Al Sarouj-School-P2 | P2 | SC-03 | 255 | 292 | 547 | Annex Building • Superstructure – Ground Floor RCC Wall Concrete 20% Completed; Rebar Fixing 70% done School Building • RCC Wall Concrete Upto Plinth 83% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 5.21% | 14.1% | 8.89% | Site Mobilization | 2024-01-05 | 2024-01-06 |  | 2024-08-16 | • Bill No.4 – MEP Final Rate Agreement required – 19-Aug-24 (Delaying the MEP Agency mobilization at site, Engineering & Procurement process) • Approval for Remaining Cost plus & Re-measurable Items required – 19-Aug-24 (Hampering the Annex & School building progress) • MEP Long lead items – Materials submittals & Approvals delaying due to Agency not mobilized (Impacted in the critical path) • Addition in Scope (Internal wall + External RCC Wall at School) & changes in construction methodology hindering the progress | • Expedite final rate agreement between parties and accelerate procurement of critical materials. • Obtain timely approvals and expedite procurement of critical materials; Consider expediting procurement processes. • Expedite MEP agency onboarding to initiate material submittals and approvals for long-lead items, and assess the potential benefits of local procurement. • Reassess project scope to identify resource and timeline requirements; Develop a revised project schedule incorporating the new scope and methodology | Annex Building • Substructure – Grade Slab & Beam Works to progress • Superstructure works – RCC wall up to FF level to progress Shelter Block • Substructure –works to complete • Superstructure – RCC Wall work to progress upto 1FL Level • Surface Preparation for CRFP works to progress |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1WyM62m91MyOYiYchDit1EWaKO2dnqPzx&sz=w1000 | https://drive.google.com/file/d/1WyM62m91MyOYiYchDit1EWaKO2dnqPzx/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hp_omkqqkYn1e8mTswZtyA2acgQaNMuO&sz=w1000 | https://drive.google.com/file/d/1hp_omkqqkYn1e8mTswZtyA2acgQaNMuO/view?usp=drive_link | https://drive.google.com/thumbnail?id=1S7XMV5_8waurveisDWugvibu1mQY1cgy&sz=w1000 | https://drive.google.com/file/d/1S7XMV5_8waurveisDWugvibu1mQY1cgy/view?usp=drive_link
2024-08-12 | Al Sarouj-School-P2 | P2 | SC-03 | 255 | 292 | 547 | Annex Building • Superstructure – Ground Floor RCC Wall Concrete 20% Completed; Rebar Fixing 70% done School Building • RCC Wall Concrete Upto Plinth 83% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 5.21% | 14.1% | 8.89% | Building Permit | 2024-07-29 | 2024-06-20 |  | 2024-08-16 | • Bill No.4 – MEP Final Rate Agreement required – 19-Aug-24 (Delaying the MEP Agency mobilization at site, Engineering & Procurement process) • Approval for Remaining Cost plus & Re-measurable Items required – 19-Aug-24 (Hampering the Annex & School building progress) • MEP Long lead items – Materials submittals & Approvals delaying due to Agency not mobilized (Impacted in the critical path) • Addition in Scope (Internal wall + External RCC Wall at School) & changes in construction methodology hindering the progress | • Expedite final rate agreement between parties and accelerate procurement of critical materials. • Obtain timely approvals and expedite procurement of critical materials; Consider expediting procurement processes. • Expedite MEP agency onboarding to initiate material submittals and approvals for long-lead items, and assess the potential benefits of local procurement. • Reassess project scope to identify resource and timeline requirements; Develop a revised project schedule incorporating the new scope and methodology | Annex Building • Substructure – Grade Slab & Beam Works to progress • Superstructure works – RCC wall up to FF level to progress Shelter Block • Substructure –works to complete • Superstructure – RCC Wall work to progress upto 1FL Level • Surface Preparation for CRFP works to progress |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1WyM62m91MyOYiYchDit1EWaKO2dnqPzx&sz=w1000 | https://drive.google.com/file/d/1WyM62m91MyOYiYchDit1EWaKO2dnqPzx/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hp_omkqqkYn1e8mTswZtyA2acgQaNMuO&sz=w1000 | https://drive.google.com/file/d/1hp_omkqqkYn1e8mTswZtyA2acgQaNMuO/view?usp=drive_link | https://drive.google.com/thumbnail?id=1S7XMV5_8waurveisDWugvibu1mQY1cgy&sz=w1000 | https://drive.google.com/file/d/1S7XMV5_8waurveisDWugvibu1mQY1cgy/view?usp=drive_link
2024-08-12 | Al Sarouj-School-P2 | P2 | SC-03 | 255 | 292 | 547 | Annex Building • Superstructure – Ground Floor RCC Wall Concrete 20% Completed; Rebar Fixing 70% done School Building • RCC Wall Concrete Upto Plinth 83% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 5.21% | 14.1% | 8.89% | Design Phase | 2024-07-31 | 2024-08-12 |  | 2024-08-16 | • Bill No.4 – MEP Final Rate Agreement required – 19-Aug-24 (Delaying the MEP Agency mobilization at site, Engineering & Procurement process) • Approval for Remaining Cost plus & Re-measurable Items required – 19-Aug-24 (Hampering the Annex & School building progress) • MEP Long lead items – Materials submittals & Approvals delaying due to Agency not mobilized (Impacted in the critical path) • Addition in Scope (Internal wall + External RCC Wall at School) & changes in construction methodology hindering the progress | • Expedite final rate agreement between parties and accelerate procurement of critical materials. • Obtain timely approvals and expedite procurement of critical materials; Consider expediting procurement processes. • Expedite MEP agency onboarding to initiate material submittals and approvals for long-lead items, and assess the potential benefits of local procurement. • Reassess project scope to identify resource and timeline requirements; Develop a revised project schedule incorporating the new scope and methodology | Annex Building • Substructure – Grade Slab & Beam Works to progress • Superstructure works – RCC wall up to FF level to progress Shelter Block • Substructure –works to complete • Superstructure – RCC Wall work to progress upto 1FL Level • Surface Preparation for CRFP works to progress |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1WyM62m91MyOYiYchDit1EWaKO2dnqPzx&sz=w1000 | https://drive.google.com/file/d/1WyM62m91MyOYiYchDit1EWaKO2dnqPzx/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hp_omkqqkYn1e8mTswZtyA2acgQaNMuO&sz=w1000 | https://drive.google.com/file/d/1hp_omkqqkYn1e8mTswZtyA2acgQaNMuO/view?usp=drive_link | https://drive.google.com/thumbnail?id=1S7XMV5_8waurveisDWugvibu1mQY1cgy&sz=w1000 | https://drive.google.com/file/d/1S7XMV5_8waurveisDWugvibu1mQY1cgy/view?usp=drive_link
2024-08-12 | Al Sarouj-School-P2 | P2 | SC-03 | 255 | 292 | 547 | Annex Building • Superstructure – Ground Floor RCC Wall Concrete 20% Completed; Rebar Fixing 70% done School Building • RCC Wall Concrete Upto Plinth 83% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 5.21% | 14.1% | 8.89% | Structural Completion | 2025-01-14 |  | 2025-01-15 | 2024-08-16 | • Bill No.4 – MEP Final Rate Agreement required – 19-Aug-24 (Delaying the MEP Agency mobilization at site, Engineering & Procurement process) • Approval for Remaining Cost plus & Re-measurable Items required – 19-Aug-24 (Hampering the Annex & School building progress) • MEP Long lead items – Materials submittals & Approvals delaying due to Agency not mobilized (Impacted in the critical path) • Addition in Scope (Internal wall + External RCC Wall at School) & changes in construction methodology hindering the progress | • Expedite final rate agreement between parties and accelerate procurement of critical materials. • Obtain timely approvals and expedite procurement of critical materials; Consider expediting procurement processes. • Expedite MEP agency onboarding to initiate material submittals and approvals for long-lead items, and assess the potential benefits of local procurement. • Reassess project scope to identify resource and timeline requirements; Develop a revised project schedule incorporating the new scope and methodology | Annex Building • Substructure – Grade Slab & Beam Works to progress • Superstructure works – RCC wall up to FF level to progress Shelter Block • Substructure –works to complete • Superstructure – RCC Wall work to progress upto 1FL Level • Surface Preparation for CRFP works to progress |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1WyM62m91MyOYiYchDit1EWaKO2dnqPzx&sz=w1000 | https://drive.google.com/file/d/1WyM62m91MyOYiYchDit1EWaKO2dnqPzx/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hp_omkqqkYn1e8mTswZtyA2acgQaNMuO&sz=w1000 | https://drive.google.com/file/d/1hp_omkqqkYn1e8mTswZtyA2acgQaNMuO/view?usp=drive_link | https://drive.google.com/thumbnail?id=1S7XMV5_8waurveisDWugvibu1mQY1cgy&sz=w1000 | https://drive.google.com/file/d/1S7XMV5_8waurveisDWugvibu1mQY1cgy/view?usp=drive_link
2024-08-12 | Al Sarouj-School-P2 | P2 | SC-03 | 255 | 292 | 547 | Annex Building • Superstructure – Ground Floor RCC Wall Concrete 20% Completed; Rebar Fixing 70% done School Building • RCC Wall Concrete Upto Plinth 83% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 5.21% | 14.1% | 8.89% | MEP & Finishes | 2025-04-10 |  | 2025-05-12 | 2024-08-16 | • Bill No.4 – MEP Final Rate Agreement required – 19-Aug-24 (Delaying the MEP Agency mobilization at site, Engineering & Procurement process) • Approval for Remaining Cost plus & Re-measurable Items required – 19-Aug-24 (Hampering the Annex & School building progress) • MEP Long lead items – Materials submittals & Approvals delaying due to Agency not mobilized (Impacted in the critical path) • Addition in Scope (Internal wall + External RCC Wall at School) & changes in construction methodology hindering the progress | • Expedite final rate agreement between parties and accelerate procurement of critical materials. • Obtain timely approvals and expedite procurement of critical materials; Consider expediting procurement processes. • Expedite MEP agency onboarding to initiate material submittals and approvals for long-lead items, and assess the potential benefits of local procurement. • Reassess project scope to identify resource and timeline requirements; Develop a revised project schedule incorporating the new scope and methodology | Annex Building • Substructure – Grade Slab & Beam Works to progress • Superstructure works – RCC wall up to FF level to progress Shelter Block • Substructure –works to complete • Superstructure – RCC Wall work to progress upto 1FL Level • Surface Preparation for CRFP works to progress |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1WyM62m91MyOYiYchDit1EWaKO2dnqPzx&sz=w1000 | https://drive.google.com/file/d/1WyM62m91MyOYiYchDit1EWaKO2dnqPzx/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hp_omkqqkYn1e8mTswZtyA2acgQaNMuO&sz=w1000 | https://drive.google.com/file/d/1hp_omkqqkYn1e8mTswZtyA2acgQaNMuO/view?usp=drive_link | https://drive.google.com/thumbnail?id=1S7XMV5_8waurveisDWugvibu1mQY1cgy&sz=w1000 | https://drive.google.com/file/d/1S7XMV5_8waurveisDWugvibu1mQY1cgy/view?usp=drive_link
2024-08-12 | Al Sarouj-School-P2 | P2 | SC-03 | 255 | 292 | 547 | Annex Building • Superstructure – Ground Floor RCC Wall Concrete 20% Completed; Rebar Fixing 70% done School Building • RCC Wall Concrete Upto Plinth 83% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 5.21% | 14.1% | 8.89% | BCC Inspection | 2025-04-29 |  | 2025-05-22 | 2024-08-16 | • Bill No.4 – MEP Final Rate Agreement required – 19-Aug-24 (Delaying the MEP Agency mobilization at site, Engineering & Procurement process) • Approval for Remaining Cost plus & Re-measurable Items required – 19-Aug-24 (Hampering the Annex & School building progress) • MEP Long lead items – Materials submittals & Approvals delaying due to Agency not mobilized (Impacted in the critical path) • Addition in Scope (Internal wall + External RCC Wall at School) & changes in construction methodology hindering the progress | • Expedite final rate agreement between parties and accelerate procurement of critical materials. • Obtain timely approvals and expedite procurement of critical materials; Consider expediting procurement processes. • Expedite MEP agency onboarding to initiate material submittals and approvals for long-lead items, and assess the potential benefits of local procurement. • Reassess project scope to identify resource and timeline requirements; Develop a revised project schedule incorporating the new scope and methodology | Annex Building • Substructure – Grade Slab & Beam Works to progress • Superstructure works – RCC wall up to FF level to progress Shelter Block • Substructure –works to complete • Superstructure – RCC Wall work to progress upto 1FL Level • Surface Preparation for CRFP works to progress |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1WyM62m91MyOYiYchDit1EWaKO2dnqPzx&sz=w1000 | https://drive.google.com/file/d/1WyM62m91MyOYiYchDit1EWaKO2dnqPzx/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hp_omkqqkYn1e8mTswZtyA2acgQaNMuO&sz=w1000 | https://drive.google.com/file/d/1hp_omkqqkYn1e8mTswZtyA2acgQaNMuO/view?usp=drive_link | https://drive.google.com/thumbnail?id=1S7XMV5_8waurveisDWugvibu1mQY1cgy&sz=w1000 | https://drive.google.com/file/d/1S7XMV5_8waurveisDWugvibu1mQY1cgy/view?usp=drive_link
2024-08-12 | Al Sarouj-School-P2 | P2 | SC-03 | 255 | 292 | 547 | Annex Building • Superstructure – Ground Floor RCC Wall Concrete 20% Completed; Rebar Fixing 70% done School Building • RCC Wall Concrete Upto Plinth 83% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 5.21% | 14.1% | 8.89% | BCC Issuance | 2025-05-16 |  | 2025-06-12 | 2024-08-16 | • Bill No.4 – MEP Final Rate Agreement required – 19-Aug-24 (Delaying the MEP Agency mobilization at site, Engineering & Procurement process) • Approval for Remaining Cost plus & Re-measurable Items required – 19-Aug-24 (Hampering the Annex & School building progress) • MEP Long lead items – Materials submittals & Approvals delaying due to Agency not mobilized (Impacted in the critical path) • Addition in Scope (Internal wall + External RCC Wall at School) & changes in construction methodology hindering the progress | • Expedite final rate agreement between parties and accelerate procurement of critical materials. • Obtain timely approvals and expedite procurement of critical materials; Consider expediting procurement processes. • Expedite MEP agency onboarding to initiate material submittals and approvals for long-lead items, and assess the potential benefits of local procurement. • Reassess project scope to identify resource and timeline requirements; Develop a revised project schedule incorporating the new scope and methodology | Annex Building • Substructure – Grade Slab & Beam Works to progress • Superstructure works – RCC wall up to FF level to progress Shelter Block • Substructure –works to complete • Superstructure – RCC Wall work to progress upto 1FL Level • Surface Preparation for CRFP works to progress |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1WyM62m91MyOYiYchDit1EWaKO2dnqPzx&sz=w1000 | https://drive.google.com/file/d/1WyM62m91MyOYiYchDit1EWaKO2dnqPzx/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hp_omkqqkYn1e8mTswZtyA2acgQaNMuO&sz=w1000 | https://drive.google.com/file/d/1hp_omkqqkYn1e8mTswZtyA2acgQaNMuO/view?usp=drive_link | https://drive.google.com/thumbnail?id=1S7XMV5_8waurveisDWugvibu1mQY1cgy&sz=w1000 | https://drive.google.com/file/d/1S7XMV5_8waurveisDWugvibu1mQY1cgy/view?usp=drive_link
2024-08-12 | Al Sarouj-School-P2 | P2 | SC-03 | 255 | 292 | 547 | Annex Building • Superstructure – Ground Floor RCC Wall Concrete 20% Completed; Rebar Fixing 70% done School Building • RCC Wall Concrete Upto Plinth 83% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 5.21% | 14.1% | 8.89% | Completion | 2025-05-29 |  | 2025-05-29 | 2024-08-16 | • Bill No.4 – MEP Final Rate Agreement required – 19-Aug-24 (Delaying the MEP Agency mobilization at site, Engineering & Procurement process) • Approval for Remaining Cost plus & Re-measurable Items required – 19-Aug-24 (Hampering the Annex & School building progress) • MEP Long lead items – Materials submittals & Approvals delaying due to Agency not mobilized (Impacted in the critical path) • Addition in Scope (Internal wall + External RCC Wall at School) & changes in construction methodology hindering the progress | • Expedite final rate agreement between parties and accelerate procurement of critical materials. • Obtain timely approvals and expedite procurement of critical materials; Consider expediting procurement processes. • Expedite MEP agency onboarding to initiate material submittals and approvals for long-lead items, and assess the potential benefits of local procurement. • Reassess project scope to identify resource and timeline requirements; Develop a revised project schedule incorporating the new scope and methodology | Annex Building • Substructure – Grade Slab & Beam Works to progress • Superstructure works – RCC wall up to FF level to progress Shelter Block • Substructure –works to complete • Superstructure – RCC Wall work to progress upto 1FL Level • Surface Preparation for CRFP works to progress |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1WyM62m91MyOYiYchDit1EWaKO2dnqPzx&sz=w1000 | https://drive.google.com/file/d/1WyM62m91MyOYiYchDit1EWaKO2dnqPzx/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hp_omkqqkYn1e8mTswZtyA2acgQaNMuO&sz=w1000 | https://drive.google.com/file/d/1hp_omkqqkYn1e8mTswZtyA2acgQaNMuO/view?usp=drive_link | https://drive.google.com/thumbnail?id=1S7XMV5_8waurveisDWugvibu1mQY1cgy&sz=w1000 | https://drive.google.com/file/d/1S7XMV5_8waurveisDWugvibu1mQY1cgy/view?usp=drive_link
2024-08-12 | Madinat Zayed-School-P105 | P105 | SC-06 | 219 | 328 | 547 | Annex Building • Superstructure – GF RCC Wall Rebar Fixing 92% Completed; School Building • Substructure –RCC Wall Upto Plinth 30% Done | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 14.83% | 15.04% | 0.21% | Notice to Commence | 2023-09-18 | 2023-09-26 |  | 2024-08-16 | • Bill No.4 – MEP Final Rate Agreement required – 19-Aug-24 (Delaying the MEP Agency mobilization at site, Engineering & Procurement process) • Approval for Remaining Cost plus & Re-measurable Items required – 19-Aug-24 (Hampering the Annex & School building progress) • MEP Long lead items – Materials submittals & Approvals delaying due to Agency not mobilized (Impacted in the critical path) • Addition in Scope (Internal wall + External RCC Wall at School) & changes in construction methodology hindering the progress | • Expedite final rate agreement between parties and accelerate procurement of critical materials. • Obtain timely approvals and expedite procurement of critical materials; Consider expediting procurement processes. • Expedite MEP agency onboarding to initiate material submittals and approvals for long-lead items, and assess the potential benefits of local procurement. • Reassess project scope to identify resource and timeline requirements; Develop a revised project schedule incorporating the new scope and methodology | Annex Building • Substructure – Grade Slab Works to progress • Superstructure works – RCC Wall works upto FF Level Shelter Block – • Substructure – Foundation Cast & Existing Structure Strengthening works to progress • Superstructure - GF & FF Wall to progress • Surface Preparation for CRFP works |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1txs_xJtZSRV3s1r41GM6nzBz3ZapFemu&sz=w1000 | https://drive.google.com/file/d/1txs_xJtZSRV3s1r41GM6nzBz3ZapFemu/view?usp=drive_link | https://drive.google.com/thumbnail?id=1sHpvQ8oEquSNbOS5urjlkBz79EG_gVnn&sz=w1000 | https://drive.google.com/file/d/1sHpvQ8oEquSNbOS5urjlkBz79EG_gVnn/view?usp=drive_link | https://drive.google.com/thumbnail?id=1f-lGcQWt6ANBmjBjmKSpaSIRJHeZxffC&sz=w1000 | https://drive.google.com/file/d/1f-lGcQWt6ANBmjBjmKSpaSIRJHeZxffC/view?usp=drive_link
2024-08-12 | Madinat Zayed-School-P105 | P105 | SC-06 | 219 | 328 | 547 | Annex Building • Superstructure – GF RCC Wall Rebar Fixing 92% Completed; School Building • Substructure –RCC Wall Upto Plinth 30% Done | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 14.83% | 15.04% | 0.21% | Site Mobilization | 2023-10-21 | 2024-01-06 |  | 2024-08-16 | • Bill No.4 – MEP Final Rate Agreement required – 19-Aug-24 (Delaying the MEP Agency mobilization at site, Engineering & Procurement process) • Approval for Remaining Cost plus & Re-measurable Items required – 19-Aug-24 (Hampering the Annex & School building progress) • MEP Long lead items – Materials submittals & Approvals delaying due to Agency not mobilized (Impacted in the critical path) • Addition in Scope (Internal wall + External RCC Wall at School) & changes in construction methodology hindering the progress | • Expedite final rate agreement between parties and accelerate procurement of critical materials. • Obtain timely approvals and expedite procurement of critical materials; Consider expediting procurement processes. • Expedite MEP agency onboarding to initiate material submittals and approvals for long-lead items, and assess the potential benefits of local procurement. • Reassess project scope to identify resource and timeline requirements; Develop a revised project schedule incorporating the new scope and methodology | Annex Building • Substructure – Grade Slab Works to progress • Superstructure works – RCC Wall works upto FF Level Shelter Block – • Substructure – Foundation Cast & Existing Structure Strengthening works to progress • Superstructure - GF & FF Wall to progress • Surface Preparation for CRFP works |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1txs_xJtZSRV3s1r41GM6nzBz3ZapFemu&sz=w1000 | https://drive.google.com/file/d/1txs_xJtZSRV3s1r41GM6nzBz3ZapFemu/view?usp=drive_link | https://drive.google.com/thumbnail?id=1sHpvQ8oEquSNbOS5urjlkBz79EG_gVnn&sz=w1000 | https://drive.google.com/file/d/1sHpvQ8oEquSNbOS5urjlkBz79EG_gVnn/view?usp=drive_link | https://drive.google.com/thumbnail?id=1f-lGcQWt6ANBmjBjmKSpaSIRJHeZxffC&sz=w1000 | https://drive.google.com/file/d/1f-lGcQWt6ANBmjBjmKSpaSIRJHeZxffC/view?usp=drive_link
2024-08-12 | Madinat Zayed-School-P105 | P105 | SC-06 | 219 | 328 | 547 | Annex Building • Superstructure – GF RCC Wall Rebar Fixing 92% Completed; School Building • Substructure –RCC Wall Upto Plinth 30% Done | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 14.83% | 15.04% | 0.21% | Building Permit | 2024-05-17 | 2024-05-23 |  | 2024-08-16 | • Bill No.4 – MEP Final Rate Agreement required – 19-Aug-24 (Delaying the MEP Agency mobilization at site, Engineering & Procurement process) • Approval for Remaining Cost plus & Re-measurable Items required – 19-Aug-24 (Hampering the Annex & School building progress) • MEP Long lead items – Materials submittals & Approvals delaying due to Agency not mobilized (Impacted in the critical path) • Addition in Scope (Internal wall + External RCC Wall at School) & changes in construction methodology hindering the progress | • Expedite final rate agreement between parties and accelerate procurement of critical materials. • Obtain timely approvals and expedite procurement of critical materials; Consider expediting procurement processes. • Expedite MEP agency onboarding to initiate material submittals and approvals for long-lead items, and assess the potential benefits of local procurement. • Reassess project scope to identify resource and timeline requirements; Develop a revised project schedule incorporating the new scope and methodology | Annex Building • Substructure – Grade Slab Works to progress • Superstructure works – RCC Wall works upto FF Level Shelter Block – • Substructure – Foundation Cast & Existing Structure Strengthening works to progress • Superstructure - GF & FF Wall to progress • Surface Preparation for CRFP works |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1txs_xJtZSRV3s1r41GM6nzBz3ZapFemu&sz=w1000 | https://drive.google.com/file/d/1txs_xJtZSRV3s1r41GM6nzBz3ZapFemu/view?usp=drive_link | https://drive.google.com/thumbnail?id=1sHpvQ8oEquSNbOS5urjlkBz79EG_gVnn&sz=w1000 | https://drive.google.com/file/d/1sHpvQ8oEquSNbOS5urjlkBz79EG_gVnn/view?usp=drive_link | https://drive.google.com/thumbnail?id=1f-lGcQWt6ANBmjBjmKSpaSIRJHeZxffC&sz=w1000 | https://drive.google.com/file/d/1f-lGcQWt6ANBmjBjmKSpaSIRJHeZxffC/view?usp=drive_link
2024-08-12 | Madinat Zayed-School-P105 | P105 | SC-06 | 219 | 328 | 547 | Annex Building • Superstructure – GF RCC Wall Rebar Fixing 92% Completed; School Building • Substructure –RCC Wall Upto Plinth 30% Done | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 14.83% | 15.04% | 0.21% | Design Phase | 2024-05-21 | 2024-08-12 |  | 2024-08-16 | • Bill No.4 – MEP Final Rate Agreement required – 19-Aug-24 (Delaying the MEP Agency mobilization at site, Engineering & Procurement process) • Approval for Remaining Cost plus & Re-measurable Items required – 19-Aug-24 (Hampering the Annex & School building progress) • MEP Long lead items – Materials submittals & Approvals delaying due to Agency not mobilized (Impacted in the critical path) • Addition in Scope (Internal wall + External RCC Wall at School) & changes in construction methodology hindering the progress | • Expedite final rate agreement between parties and accelerate procurement of critical materials. • Obtain timely approvals and expedite procurement of critical materials; Consider expediting procurement processes. • Expedite MEP agency onboarding to initiate material submittals and approvals for long-lead items, and assess the potential benefits of local procurement. • Reassess project scope to identify resource and timeline requirements; Develop a revised project schedule incorporating the new scope and methodology | Annex Building • Substructure – Grade Slab Works to progress • Superstructure works – RCC Wall works upto FF Level Shelter Block – • Substructure – Foundation Cast & Existing Structure Strengthening works to progress • Superstructure - GF & FF Wall to progress • Surface Preparation for CRFP works |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1txs_xJtZSRV3s1r41GM6nzBz3ZapFemu&sz=w1000 | https://drive.google.com/file/d/1txs_xJtZSRV3s1r41GM6nzBz3ZapFemu/view?usp=drive_link | https://drive.google.com/thumbnail?id=1sHpvQ8oEquSNbOS5urjlkBz79EG_gVnn&sz=w1000 | https://drive.google.com/file/d/1sHpvQ8oEquSNbOS5urjlkBz79EG_gVnn/view?usp=drive_link | https://drive.google.com/thumbnail?id=1f-lGcQWt6ANBmjBjmKSpaSIRJHeZxffC&sz=w1000 | https://drive.google.com/file/d/1f-lGcQWt6ANBmjBjmKSpaSIRJHeZxffC/view?usp=drive_link
2024-08-12 | Madinat Zayed-School-P105 | P105 | SC-06 | 219 | 328 | 547 | Annex Building • Superstructure – GF RCC Wall Rebar Fixing 92% Completed; School Building • Substructure –RCC Wall Upto Plinth 30% Done | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 14.83% | 15.04% | 0.21% | Structural Completion | 2024-10-31 |  | 2025-01-09 | 2024-08-16 | • Bill No.4 – MEP Final Rate Agreement required – 19-Aug-24 (Delaying the MEP Agency mobilization at site, Engineering & Procurement process) • Approval for Remaining Cost plus & Re-measurable Items required – 19-Aug-24 (Hampering the Annex & School building progress) • MEP Long lead items – Materials submittals & Approvals delaying due to Agency not mobilized (Impacted in the critical path) • Addition in Scope (Internal wall + External RCC Wall at School) & changes in construction methodology hindering the progress | • Expedite final rate agreement between parties and accelerate procurement of critical materials. • Obtain timely approvals and expedite procurement of critical materials; Consider expediting procurement processes. • Expedite MEP agency onboarding to initiate material submittals and approvals for long-lead items, and assess the potential benefits of local procurement. • Reassess project scope to identify resource and timeline requirements; Develop a revised project schedule incorporating the new scope and methodology | Annex Building • Substructure – Grade Slab Works to progress • Superstructure works – RCC Wall works upto FF Level Shelter Block – • Substructure – Foundation Cast & Existing Structure Strengthening works to progress • Superstructure - GF & FF Wall to progress • Surface Preparation for CRFP works |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1txs_xJtZSRV3s1r41GM6nzBz3ZapFemu&sz=w1000 | https://drive.google.com/file/d/1txs_xJtZSRV3s1r41GM6nzBz3ZapFemu/view?usp=drive_link | https://drive.google.com/thumbnail?id=1sHpvQ8oEquSNbOS5urjlkBz79EG_gVnn&sz=w1000 | https://drive.google.com/file/d/1sHpvQ8oEquSNbOS5urjlkBz79EG_gVnn/view?usp=drive_link | https://drive.google.com/thumbnail?id=1f-lGcQWt6ANBmjBjmKSpaSIRJHeZxffC&sz=w1000 | https://drive.google.com/file/d/1f-lGcQWt6ANBmjBjmKSpaSIRJHeZxffC/view?usp=drive_link
2024-08-12 | Madinat Zayed-School-P105 | P105 | SC-06 | 219 | 328 | 547 | Annex Building • Superstructure – GF RCC Wall Rebar Fixing 92% Completed; School Building • Substructure –RCC Wall Upto Plinth 30% Done | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 14.83% | 15.04% | 0.21% | MEP & Finishes | 2025-01-25 |  | 2025-05-12 | 2024-08-16 | • Bill No.4 – MEP Final Rate Agreement required – 19-Aug-24 (Delaying the MEP Agency mobilization at site, Engineering & Procurement process) • Approval for Remaining Cost plus & Re-measurable Items required – 19-Aug-24 (Hampering the Annex & School building progress) • MEP Long lead items – Materials submittals & Approvals delaying due to Agency not mobilized (Impacted in the critical path) • Addition in Scope (Internal wall + External RCC Wall at School) & changes in construction methodology hindering the progress | • Expedite final rate agreement between parties and accelerate procurement of critical materials. • Obtain timely approvals and expedite procurement of critical materials; Consider expediting procurement processes. • Expedite MEP agency onboarding to initiate material submittals and approvals for long-lead items, and assess the potential benefits of local procurement. • Reassess project scope to identify resource and timeline requirements; Develop a revised project schedule incorporating the new scope and methodology | Annex Building • Substructure – Grade Slab Works to progress • Superstructure works – RCC Wall works upto FF Level Shelter Block – • Substructure – Foundation Cast & Existing Structure Strengthening works to progress • Superstructure - GF & FF Wall to progress • Surface Preparation for CRFP works |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1txs_xJtZSRV3s1r41GM6nzBz3ZapFemu&sz=w1000 | https://drive.google.com/file/d/1txs_xJtZSRV3s1r41GM6nzBz3ZapFemu/view?usp=drive_link | https://drive.google.com/thumbnail?id=1sHpvQ8oEquSNbOS5urjlkBz79EG_gVnn&sz=w1000 | https://drive.google.com/file/d/1sHpvQ8oEquSNbOS5urjlkBz79EG_gVnn/view?usp=drive_link | https://drive.google.com/thumbnail?id=1f-lGcQWt6ANBmjBjmKSpaSIRJHeZxffC&sz=w1000 | https://drive.google.com/file/d/1f-lGcQWt6ANBmjBjmKSpaSIRJHeZxffC/view?usp=drive_link
2024-08-12 | Madinat Zayed-School-P105 | P105 | SC-06 | 219 | 328 | 547 | Annex Building • Superstructure – GF RCC Wall Rebar Fixing 92% Completed; School Building • Substructure –RCC Wall Upto Plinth 30% Done | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 14.83% | 15.04% | 0.21% | BCC Inspection | 2025-02-13 |  | 2025-05-22 | 2024-08-16 | • Bill No.4 – MEP Final Rate Agreement required – 19-Aug-24 (Delaying the MEP Agency mobilization at site, Engineering & Procurement process) • Approval for Remaining Cost plus & Re-measurable Items required – 19-Aug-24 (Hampering the Annex & School building progress) • MEP Long lead items – Materials submittals & Approvals delaying due to Agency not mobilized (Impacted in the critical path) • Addition in Scope (Internal wall + External RCC Wall at School) & changes in construction methodology hindering the progress | • Expedite final rate agreement between parties and accelerate procurement of critical materials. • Obtain timely approvals and expedite procurement of critical materials; Consider expediting procurement processes. • Expedite MEP agency onboarding to initiate material submittals and approvals for long-lead items, and assess the potential benefits of local procurement. • Reassess project scope to identify resource and timeline requirements; Develop a revised project schedule incorporating the new scope and methodology | Annex Building • Substructure – Grade Slab Works to progress • Superstructure works – RCC Wall works upto FF Level Shelter Block – • Substructure – Foundation Cast & Existing Structure Strengthening works to progress • Superstructure - GF & FF Wall to progress • Surface Preparation for CRFP works |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1txs_xJtZSRV3s1r41GM6nzBz3ZapFemu&sz=w1000 | https://drive.google.com/file/d/1txs_xJtZSRV3s1r41GM6nzBz3ZapFemu/view?usp=drive_link | https://drive.google.com/thumbnail?id=1sHpvQ8oEquSNbOS5urjlkBz79EG_gVnn&sz=w1000 | https://drive.google.com/file/d/1sHpvQ8oEquSNbOS5urjlkBz79EG_gVnn/view?usp=drive_link | https://drive.google.com/thumbnail?id=1f-lGcQWt6ANBmjBjmKSpaSIRJHeZxffC&sz=w1000 | https://drive.google.com/file/d/1f-lGcQWt6ANBmjBjmKSpaSIRJHeZxffC/view?usp=drive_link
2024-08-12 | Madinat Zayed-School-P105 | P105 | SC-06 | 219 | 328 | 547 | Annex Building • Superstructure – GF RCC Wall Rebar Fixing 92% Completed; School Building • Substructure –RCC Wall Upto Plinth 30% Done | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 14.83% | 15.04% | 0.21% | BCC Issuance | 2025-03-04 |  | 2025-05-12 | 2024-08-16 | • Bill No.4 – MEP Final Rate Agreement required – 19-Aug-24 (Delaying the MEP Agency mobilization at site, Engineering & Procurement process) • Approval for Remaining Cost plus & Re-measurable Items required – 19-Aug-24 (Hampering the Annex & School building progress) • MEP Long lead items – Materials submittals & Approvals delaying due to Agency not mobilized (Impacted in the critical path) • Addition in Scope (Internal wall + External RCC Wall at School) & changes in construction methodology hindering the progress | • Expedite final rate agreement between parties and accelerate procurement of critical materials. • Obtain timely approvals and expedite procurement of critical materials; Consider expediting procurement processes. • Expedite MEP agency onboarding to initiate material submittals and approvals for long-lead items, and assess the potential benefits of local procurement. • Reassess project scope to identify resource and timeline requirements; Develop a revised project schedule incorporating the new scope and methodology | Annex Building • Substructure – Grade Slab Works to progress • Superstructure works – RCC Wall works upto FF Level Shelter Block – • Substructure – Foundation Cast & Existing Structure Strengthening works to progress • Superstructure - GF & FF Wall to progress • Surface Preparation for CRFP works |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1txs_xJtZSRV3s1r41GM6nzBz3ZapFemu&sz=w1000 | https://drive.google.com/file/d/1txs_xJtZSRV3s1r41GM6nzBz3ZapFemu/view?usp=drive_link | https://drive.google.com/thumbnail?id=1sHpvQ8oEquSNbOS5urjlkBz79EG_gVnn&sz=w1000 | https://drive.google.com/file/d/1sHpvQ8oEquSNbOS5urjlkBz79EG_gVnn/view?usp=drive_link | https://drive.google.com/thumbnail?id=1f-lGcQWt6ANBmjBjmKSpaSIRJHeZxffC&sz=w1000 | https://drive.google.com/file/d/1f-lGcQWt6ANBmjBjmKSpaSIRJHeZxffC/view?usp=drive_link
2024-08-12 | Madinat Zayed-School-P105 | P105 | SC-06 | 219 | 328 | 547 | Annex Building • Superstructure – GF RCC Wall Rebar Fixing 92% Completed; School Building • Substructure –RCC Wall Upto Plinth 30% Done | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 14.83% | 15.04% | 0.21% | Completion | 2025-03-17 |  | 2025-06-25 | 2024-08-16 | • Bill No.4 – MEP Final Rate Agreement required – 19-Aug-24 (Delaying the MEP Agency mobilization at site, Engineering & Procurement process) • Approval for Remaining Cost plus & Re-measurable Items required – 19-Aug-24 (Hampering the Annex & School building progress) • MEP Long lead items – Materials submittals & Approvals delaying due to Agency not mobilized (Impacted in the critical path) • Addition in Scope (Internal wall + External RCC Wall at School) & changes in construction methodology hindering the progress | • Expedite final rate agreement between parties and accelerate procurement of critical materials. • Obtain timely approvals and expedite procurement of critical materials; Consider expediting procurement processes. • Expedite MEP agency onboarding to initiate material submittals and approvals for long-lead items, and assess the potential benefits of local procurement. • Reassess project scope to identify resource and timeline requirements; Develop a revised project schedule incorporating the new scope and methodology | Annex Building • Substructure – Grade Slab Works to progress • Superstructure works – RCC Wall works upto FF Level Shelter Block – • Substructure – Foundation Cast & Existing Structure Strengthening works to progress • Superstructure - GF & FF Wall to progress • Surface Preparation for CRFP works |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1txs_xJtZSRV3s1r41GM6nzBz3ZapFemu&sz=w1000 | https://drive.google.com/file/d/1txs_xJtZSRV3s1r41GM6nzBz3ZapFemu/view?usp=drive_link | https://drive.google.com/thumbnail?id=1sHpvQ8oEquSNbOS5urjlkBz79EG_gVnn&sz=w1000 | https://drive.google.com/file/d/1sHpvQ8oEquSNbOS5urjlkBz79EG_gVnn/view?usp=drive_link | https://drive.google.com/thumbnail?id=1f-lGcQWt6ANBmjBjmKSpaSIRJHeZxffC&sz=w1000 | https://drive.google.com/file/d/1f-lGcQWt6ANBmjBjmKSpaSIRJHeZxffC/view?usp=drive_link
2024-08-12 | Madinat Zayed-School-P38 | P38 | SC-07 | 219 | 328 | 547 | Annex Building • GF RCC Wall – Rebar fixing 64% Completed; Wall Concrete 13% Completed School Building • Substructure – GF RCC Wall Rebar Fixing – 32% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 14.83% | 19.35% | 4.52% | Notice to Commence | 2023-09-18 | 2023-09-26 |  | 2024-08-16 | • Bill No.4 – MEP Final Rate Agreement required – 19-Aug-24 (Delaying the MEP Agency mobilization at site, Engineering & Procurement process) • Approval for Remaining Cost plus & Re-measurable Items required – 19-Aug-24 (Hampering the Annex & School building progress) • MEP Long lead items – Materials submittals & Approvals delaying due to Agency not mobilized (Impacted in the critical path) • Addition in Scope (Internal wall + External RCC Wall at School) & changes in construction methodology hindering the progress | • Expedite final rate agreement between parties and accelerate procurement of critical materials. • Obtain timely approvals and expedite procurement of critical materials; Consider expediting procurement processes. • Expedite MEP agency onboarding to initiate material submittals and approvals for long-lead items, and assess the potential benefits of local procurement. • Reassess project scope to identify resource and timeline requirements; Develop a revised project schedule incorporating the new scope and methodology | Annex Building • Superstructure works – RCC Wall works upto FF Level Shelter Block • Substructure – Foundation works to complete GF – RCC Wall works upto 1FL Level to progress Surface Preparation for CRFP works |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=14L_MyL0E1NhkfD2UE0lu92Vn4JYniGzV&sz=w1000 | https://drive.google.com/file/d/14L_MyL0E1NhkfD2UE0lu92Vn4JYniGzV/view?usp=drive_link | https://drive.google.com/thumbnail?id=1ev6SB5Xmz8kTZkmVUzuxOMvRBzuRZDZn&sz=w1000 | https://drive.google.com/file/d/1ev6SB5Xmz8kTZkmVUzuxOMvRBzuRZDZn/view?usp=drive_link | https://drive.google.com/thumbnail?id=16qjAofdO5jTUaZwIB_r0x5yIDWAJWjtC&sz=w1000 | https://drive.google.com/file/d/16qjAofdO5jTUaZwIB_r0x5yIDWAJWjtC/view?usp=drive_link
2024-08-12 | Madinat Zayed-School-P38 | P38 | SC-07 | 219 | 328 | 547 | Annex Building • GF RCC Wall – Rebar fixing 64% Completed; Wall Concrete 13% Completed School Building • Substructure – GF RCC Wall Rebar Fixing – 32% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 14.83% | 19.35% | 4.52% | Site Mobilization | 2023-10-21 | 2024-01-13 |  | 2024-08-16 | • Bill No.4 – MEP Final Rate Agreement required – 19-Aug-24 (Delaying the MEP Agency mobilization at site, Engineering & Procurement process) • Approval for Remaining Cost plus & Re-measurable Items required – 19-Aug-24 (Hampering the Annex & School building progress) • MEP Long lead items – Materials submittals & Approvals delaying due to Agency not mobilized (Impacted in the critical path) • Addition in Scope (Internal wall + External RCC Wall at School) & changes in construction methodology hindering the progress | • Expedite final rate agreement between parties and accelerate procurement of critical materials. • Obtain timely approvals and expedite procurement of critical materials; Consider expediting procurement processes. • Expedite MEP agency onboarding to initiate material submittals and approvals for long-lead items, and assess the potential benefits of local procurement. • Reassess project scope to identify resource and timeline requirements; Develop a revised project schedule incorporating the new scope and methodology | Annex Building • Superstructure works – RCC Wall works upto FF Level Shelter Block • Substructure – Foundation works to complete GF – RCC Wall works upto 1FL Level to progress Surface Preparation for CRFP works |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=14L_MyL0E1NhkfD2UE0lu92Vn4JYniGzV&sz=w1000 | https://drive.google.com/file/d/14L_MyL0E1NhkfD2UE0lu92Vn4JYniGzV/view?usp=drive_link | https://drive.google.com/thumbnail?id=1ev6SB5Xmz8kTZkmVUzuxOMvRBzuRZDZn&sz=w1000 | https://drive.google.com/file/d/1ev6SB5Xmz8kTZkmVUzuxOMvRBzuRZDZn/view?usp=drive_link | https://drive.google.com/thumbnail?id=16qjAofdO5jTUaZwIB_r0x5yIDWAJWjtC&sz=w1000 | https://drive.google.com/file/d/16qjAofdO5jTUaZwIB_r0x5yIDWAJWjtC/view?usp=drive_link
2024-08-12 | Madinat Zayed-School-P38 | P38 | SC-07 | 219 | 328 | 547 | Annex Building • GF RCC Wall – Rebar fixing 64% Completed; Wall Concrete 13% Completed School Building • Substructure – GF RCC Wall Rebar Fixing – 32% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 14.83% | 19.35% | 4.52% | Building Permit | 2024-05-17 | 2024-05-27 |  | 2024-08-16 | • Bill No.4 – MEP Final Rate Agreement required – 19-Aug-24 (Delaying the MEP Agency mobilization at site, Engineering & Procurement process) • Approval for Remaining Cost plus & Re-measurable Items required – 19-Aug-24 (Hampering the Annex & School building progress) • MEP Long lead items – Materials submittals & Approvals delaying due to Agency not mobilized (Impacted in the critical path) • Addition in Scope (Internal wall + External RCC Wall at School) & changes in construction methodology hindering the progress | • Expedite final rate agreement between parties and accelerate procurement of critical materials. • Obtain timely approvals and expedite procurement of critical materials; Consider expediting procurement processes. • Expedite MEP agency onboarding to initiate material submittals and approvals for long-lead items, and assess the potential benefits of local procurement. • Reassess project scope to identify resource and timeline requirements; Develop a revised project schedule incorporating the new scope and methodology | Annex Building • Superstructure works – RCC Wall works upto FF Level Shelter Block • Substructure – Foundation works to complete GF – RCC Wall works upto 1FL Level to progress Surface Preparation for CRFP works |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=14L_MyL0E1NhkfD2UE0lu92Vn4JYniGzV&sz=w1000 | https://drive.google.com/file/d/14L_MyL0E1NhkfD2UE0lu92Vn4JYniGzV/view?usp=drive_link | https://drive.google.com/thumbnail?id=1ev6SB5Xmz8kTZkmVUzuxOMvRBzuRZDZn&sz=w1000 | https://drive.google.com/file/d/1ev6SB5Xmz8kTZkmVUzuxOMvRBzuRZDZn/view?usp=drive_link | https://drive.google.com/thumbnail?id=16qjAofdO5jTUaZwIB_r0x5yIDWAJWjtC&sz=w1000 | https://drive.google.com/file/d/16qjAofdO5jTUaZwIB_r0x5yIDWAJWjtC/view?usp=drive_link
2024-08-12 | Madinat Zayed-School-P38 | P38 | SC-07 | 219 | 328 | 547 | Annex Building • GF RCC Wall – Rebar fixing 64% Completed; Wall Concrete 13% Completed School Building • Substructure – GF RCC Wall Rebar Fixing – 32% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 14.83% | 19.35% | 4.52% | Design Phase | 2024-05-21 | 2024-08-12 |  | 2024-08-16 | • Bill No.4 – MEP Final Rate Agreement required – 19-Aug-24 (Delaying the MEP Agency mobilization at site, Engineering & Procurement process) • Approval for Remaining Cost plus & Re-measurable Items required – 19-Aug-24 (Hampering the Annex & School building progress) • MEP Long lead items – Materials submittals & Approvals delaying due to Agency not mobilized (Impacted in the critical path) • Addition in Scope (Internal wall + External RCC Wall at School) & changes in construction methodology hindering the progress | • Expedite final rate agreement between parties and accelerate procurement of critical materials. • Obtain timely approvals and expedite procurement of critical materials; Consider expediting procurement processes. • Expedite MEP agency onboarding to initiate material submittals and approvals for long-lead items, and assess the potential benefits of local procurement. • Reassess project scope to identify resource and timeline requirements; Develop a revised project schedule incorporating the new scope and methodology | Annex Building • Superstructure works – RCC Wall works upto FF Level Shelter Block • Substructure – Foundation works to complete GF – RCC Wall works upto 1FL Level to progress Surface Preparation for CRFP works |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=14L_MyL0E1NhkfD2UE0lu92Vn4JYniGzV&sz=w1000 | https://drive.google.com/file/d/14L_MyL0E1NhkfD2UE0lu92Vn4JYniGzV/view?usp=drive_link | https://drive.google.com/thumbnail?id=1ev6SB5Xmz8kTZkmVUzuxOMvRBzuRZDZn&sz=w1000 | https://drive.google.com/file/d/1ev6SB5Xmz8kTZkmVUzuxOMvRBzuRZDZn/view?usp=drive_link | https://drive.google.com/thumbnail?id=16qjAofdO5jTUaZwIB_r0x5yIDWAJWjtC&sz=w1000 | https://drive.google.com/file/d/16qjAofdO5jTUaZwIB_r0x5yIDWAJWjtC/view?usp=drive_link
2024-08-12 | Madinat Zayed-School-P38 | P38 | SC-07 | 219 | 328 | 547 | Annex Building • GF RCC Wall – Rebar fixing 64% Completed; Wall Concrete 13% Completed School Building • Substructure – GF RCC Wall Rebar Fixing – 32% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 14.83% | 19.35% | 4.52% | Structural Completion | 2024-10-31 |  | 2025-01-14 | 2024-08-16 | • Bill No.4 – MEP Final Rate Agreement required – 19-Aug-24 (Delaying the MEP Agency mobilization at site, Engineering & Procurement process) • Approval for Remaining Cost plus & Re-measurable Items required – 19-Aug-24 (Hampering the Annex & School building progress) • MEP Long lead items – Materials submittals & Approvals delaying due to Agency not mobilized (Impacted in the critical path) • Addition in Scope (Internal wall + External RCC Wall at School) & changes in construction methodology hindering the progress | • Expedite final rate agreement between parties and accelerate procurement of critical materials. • Obtain timely approvals and expedite procurement of critical materials; Consider expediting procurement processes. • Expedite MEP agency onboarding to initiate material submittals and approvals for long-lead items, and assess the potential benefits of local procurement. • Reassess project scope to identify resource and timeline requirements; Develop a revised project schedule incorporating the new scope and methodology | Annex Building • Superstructure works – RCC Wall works upto FF Level Shelter Block • Substructure – Foundation works to complete GF – RCC Wall works upto 1FL Level to progress Surface Preparation for CRFP works |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=14L_MyL0E1NhkfD2UE0lu92Vn4JYniGzV&sz=w1000 | https://drive.google.com/file/d/14L_MyL0E1NhkfD2UE0lu92Vn4JYniGzV/view?usp=drive_link | https://drive.google.com/thumbnail?id=1ev6SB5Xmz8kTZkmVUzuxOMvRBzuRZDZn&sz=w1000 | https://drive.google.com/file/d/1ev6SB5Xmz8kTZkmVUzuxOMvRBzuRZDZn/view?usp=drive_link | https://drive.google.com/thumbnail?id=16qjAofdO5jTUaZwIB_r0x5yIDWAJWjtC&sz=w1000 | https://drive.google.com/file/d/16qjAofdO5jTUaZwIB_r0x5yIDWAJWjtC/view?usp=drive_link
2024-08-12 | Madinat Zayed-School-P38 | P38 | SC-07 | 219 | 328 | 547 | Annex Building • GF RCC Wall – Rebar fixing 64% Completed; Wall Concrete 13% Completed School Building • Substructure – GF RCC Wall Rebar Fixing – 32% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 14.83% | 19.35% | 4.52% | MEP & Finishes | 2025-01-25 |  | 2025-05-12 | 2024-08-16 | • Bill No.4 – MEP Final Rate Agreement required – 19-Aug-24 (Delaying the MEP Agency mobilization at site, Engineering & Procurement process) • Approval for Remaining Cost plus & Re-measurable Items required – 19-Aug-24 (Hampering the Annex & School building progress) • MEP Long lead items – Materials submittals & Approvals delaying due to Agency not mobilized (Impacted in the critical path) • Addition in Scope (Internal wall + External RCC Wall at School) & changes in construction methodology hindering the progress | • Expedite final rate agreement between parties and accelerate procurement of critical materials. • Obtain timely approvals and expedite procurement of critical materials; Consider expediting procurement processes. • Expedite MEP agency onboarding to initiate material submittals and approvals for long-lead items, and assess the potential benefits of local procurement. • Reassess project scope to identify resource and timeline requirements; Develop a revised project schedule incorporating the new scope and methodology | Annex Building • Superstructure works – RCC Wall works upto FF Level Shelter Block • Substructure – Foundation works to complete GF – RCC Wall works upto 1FL Level to progress Surface Preparation for CRFP works |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=14L_MyL0E1NhkfD2UE0lu92Vn4JYniGzV&sz=w1000 | https://drive.google.com/file/d/14L_MyL0E1NhkfD2UE0lu92Vn4JYniGzV/view?usp=drive_link | https://drive.google.com/thumbnail?id=1ev6SB5Xmz8kTZkmVUzuxOMvRBzuRZDZn&sz=w1000 | https://drive.google.com/file/d/1ev6SB5Xmz8kTZkmVUzuxOMvRBzuRZDZn/view?usp=drive_link | https://drive.google.com/thumbnail?id=16qjAofdO5jTUaZwIB_r0x5yIDWAJWjtC&sz=w1000 | https://drive.google.com/file/d/16qjAofdO5jTUaZwIB_r0x5yIDWAJWjtC/view?usp=drive_link
2024-08-12 | Madinat Zayed-School-P38 | P38 | SC-07 | 219 | 328 | 547 | Annex Building • GF RCC Wall – Rebar fixing 64% Completed; Wall Concrete 13% Completed School Building • Substructure – GF RCC Wall Rebar Fixing – 32% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 14.83% | 19.35% | 4.52% | BCC Inspection | 2025-02-13 |  | 2025-05-22 | 2024-08-16 | • Bill No.4 – MEP Final Rate Agreement required – 19-Aug-24 (Delaying the MEP Agency mobilization at site, Engineering & Procurement process) • Approval for Remaining Cost plus & Re-measurable Items required – 19-Aug-24 (Hampering the Annex & School building progress) • MEP Long lead items – Materials submittals & Approvals delaying due to Agency not mobilized (Impacted in the critical path) • Addition in Scope (Internal wall + External RCC Wall at School) & changes in construction methodology hindering the progress | • Expedite final rate agreement between parties and accelerate procurement of critical materials. • Obtain timely approvals and expedite procurement of critical materials; Consider expediting procurement processes. • Expedite MEP agency onboarding to initiate material submittals and approvals for long-lead items, and assess the potential benefits of local procurement. • Reassess project scope to identify resource and timeline requirements; Develop a revised project schedule incorporating the new scope and methodology | Annex Building • Superstructure works – RCC Wall works upto FF Level Shelter Block • Substructure – Foundation works to complete GF – RCC Wall works upto 1FL Level to progress Surface Preparation for CRFP works |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=14L_MyL0E1NhkfD2UE0lu92Vn4JYniGzV&sz=w1000 | https://drive.google.com/file/d/14L_MyL0E1NhkfD2UE0lu92Vn4JYniGzV/view?usp=drive_link | https://drive.google.com/thumbnail?id=1ev6SB5Xmz8kTZkmVUzuxOMvRBzuRZDZn&sz=w1000 | https://drive.google.com/file/d/1ev6SB5Xmz8kTZkmVUzuxOMvRBzuRZDZn/view?usp=drive_link | https://drive.google.com/thumbnail?id=16qjAofdO5jTUaZwIB_r0x5yIDWAJWjtC&sz=w1000 | https://drive.google.com/file/d/16qjAofdO5jTUaZwIB_r0x5yIDWAJWjtC/view?usp=drive_link
2024-08-12 | Madinat Zayed-School-P38 | P38 | SC-07 | 219 | 328 | 547 | Annex Building • GF RCC Wall – Rebar fixing 64% Completed; Wall Concrete 13% Completed School Building • Substructure – GF RCC Wall Rebar Fixing – 32% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 14.83% | 19.35% | 4.52% | BCC Issuance | 2025-03-04 |  | 2025-06-12 | 2024-08-16 | • Bill No.4 – MEP Final Rate Agreement required – 19-Aug-24 (Delaying the MEP Agency mobilization at site, Engineering & Procurement process) • Approval for Remaining Cost plus & Re-measurable Items required – 19-Aug-24 (Hampering the Annex & School building progress) • MEP Long lead items – Materials submittals & Approvals delaying due to Agency not mobilized (Impacted in the critical path) • Addition in Scope (Internal wall + External RCC Wall at School) & changes in construction methodology hindering the progress | • Expedite final rate agreement between parties and accelerate procurement of critical materials. • Obtain timely approvals and expedite procurement of critical materials; Consider expediting procurement processes. • Expedite MEP agency onboarding to initiate material submittals and approvals for long-lead items, and assess the potential benefits of local procurement. • Reassess project scope to identify resource and timeline requirements; Develop a revised project schedule incorporating the new scope and methodology | Annex Building • Superstructure works – RCC Wall works upto FF Level Shelter Block • Substructure – Foundation works to complete GF – RCC Wall works upto 1FL Level to progress Surface Preparation for CRFP works |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=14L_MyL0E1NhkfD2UE0lu92Vn4JYniGzV&sz=w1000 | https://drive.google.com/file/d/14L_MyL0E1NhkfD2UE0lu92Vn4JYniGzV/view?usp=drive_link | https://drive.google.com/thumbnail?id=1ev6SB5Xmz8kTZkmVUzuxOMvRBzuRZDZn&sz=w1000 | https://drive.google.com/file/d/1ev6SB5Xmz8kTZkmVUzuxOMvRBzuRZDZn/view?usp=drive_link | https://drive.google.com/thumbnail?id=16qjAofdO5jTUaZwIB_r0x5yIDWAJWjtC&sz=w1000 | https://drive.google.com/file/d/16qjAofdO5jTUaZwIB_r0x5yIDWAJWjtC/view?usp=drive_link
2024-08-12 | Madinat Zayed-School-P38 | P38 | SC-07 | 219 | 328 | 547 | Annex Building • GF RCC Wall – Rebar fixing 64% Completed; Wall Concrete 13% Completed School Building • Substructure – GF RCC Wall Rebar Fixing – 32% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 14.83% | 19.35% | 4.52% | Completion | 2025-03-17 |  | 2025-06-25 | 2024-08-16 | • Bill No.4 – MEP Final Rate Agreement required – 19-Aug-24 (Delaying the MEP Agency mobilization at site, Engineering & Procurement process) • Approval for Remaining Cost plus & Re-measurable Items required – 19-Aug-24 (Hampering the Annex & School building progress) • MEP Long lead items – Materials submittals & Approvals delaying due to Agency not mobilized (Impacted in the critical path) • Addition in Scope (Internal wall + External RCC Wall at School) & changes in construction methodology hindering the progress | • Expedite final rate agreement between parties and accelerate procurement of critical materials. • Obtain timely approvals and expedite procurement of critical materials; Consider expediting procurement processes. • Expedite MEP agency onboarding to initiate material submittals and approvals for long-lead items, and assess the potential benefits of local procurement. • Reassess project scope to identify resource and timeline requirements; Develop a revised project schedule incorporating the new scope and methodology | Annex Building • Superstructure works – RCC Wall works upto FF Level Shelter Block • Substructure – Foundation works to complete GF – RCC Wall works upto 1FL Level to progress Surface Preparation for CRFP works |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=14L_MyL0E1NhkfD2UE0lu92Vn4JYniGzV&sz=w1000 | https://drive.google.com/file/d/14L_MyL0E1NhkfD2UE0lu92Vn4JYniGzV/view?usp=drive_link | https://drive.google.com/thumbnail?id=1ev6SB5Xmz8kTZkmVUzuxOMvRBzuRZDZn&sz=w1000 | https://drive.google.com/file/d/1ev6SB5Xmz8kTZkmVUzuxOMvRBzuRZDZn/view?usp=drive_link | https://drive.google.com/thumbnail?id=16qjAofdO5jTUaZwIB_r0x5yIDWAJWjtC&sz=w1000 | https://drive.google.com/file/d/16qjAofdO5jTUaZwIB_r0x5yIDWAJWjtC/view?usp=drive_link
2024-08-12 | Al Sila-School-P43 | P43 | SC-05 | 219 | 328 | 547 | Annex Building • GF - RCC Wall Rebar Fixing 51% completed School Building • RCC Plinth Wall - 30% Completed • GF – RCC Wall Rebar Fixing – 14% Completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 14.64% | 12.67% | -1.973% | Notice to Commence | 2023-09-18 | 2023-09-26 |  | 2024-08-16 | • Bill No.4 – MEP Final Rate Agreement required – 19-Aug-24 (Delaying the MEP Agency mobilization at site, Engineering & Procurement process) • Approval for Remaining Cost plus & Re-measurable Items required – 19-Aug-24 (Hampering the Annex & School building progress) • MEP Long lead items – Materials submittals & Approvals delaying due to Agency not mobilized (Impacted in the critical path) • Addition in Scope (Internal wall + External RCC Wall at School) & changes in construction methodology hindering the progress | • Expedite final rate agreement between parties and accelerate procurement of critical materials. • Obtain timely approvals and expedite procurement of critical materials; Consider expediting procurement processes. • Expedite MEP agency onboarding to initiate material submittals and approvals for long-lead items, and assess the potential benefits of local procurement. • Reassess project scope to identify resource and timeline requirements; Develop a revised project schedule incorporating the new scope and methodology | Annex Building • Substructure – Grade Slab Works • Superstructure works – RCC Wall works upto 1FL Level Shelter Block • Substructure –Foundation Cast & Existing Structure Strengthening works to progress • RCC Plinth Wall & GF Wall Works to progress • Surface Preparation for CRFP works |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1dScaMwmgQ5YIvqUOVMiDsOPUqR2RbhFd&sz=w1000 | https://drive.google.com/file/d/1dScaMwmgQ5YIvqUOVMiDsOPUqR2RbhFd/view?usp=drive_link | https://drive.google.com/thumbnail?id=111CWUZAruPmvLjxfjEfGmVJyVABOAn6H&sz=w1000 | https://drive.google.com/file/d/111CWUZAruPmvLjxfjEfGmVJyVABOAn6H/view?usp=drive_link | https://drive.google.com/thumbnail?id=1V_6F8E7F44jsBtYi6gGMFlkhGRPoCKfO&sz=w1000 | https://drive.google.com/file/d/1V_6F8E7F44jsBtYi6gGMFlkhGRPoCKfO/view?usp=drive_link
2024-08-12 | Al Sila-School-P43 | P43 | SC-05 | 219 | 328 | 547 | Annex Building • GF - RCC Wall Rebar Fixing 51% completed School Building • RCC Plinth Wall - 30% Completed • GF – RCC Wall Rebar Fixing – 14% Completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 14.64% | 12.67% | -1.973% | Site Mobilization | 2023-10-21 | 2024-01-06 |  | 2024-08-16 | • Bill No.4 – MEP Final Rate Agreement required – 19-Aug-24 (Delaying the MEP Agency mobilization at site, Engineering & Procurement process) • Approval for Remaining Cost plus & Re-measurable Items required – 19-Aug-24 (Hampering the Annex & School building progress) • MEP Long lead items – Materials submittals & Approvals delaying due to Agency not mobilized (Impacted in the critical path) • Addition in Scope (Internal wall + External RCC Wall at School) & changes in construction methodology hindering the progress | • Expedite final rate agreement between parties and accelerate procurement of critical materials. • Obtain timely approvals and expedite procurement of critical materials; Consider expediting procurement processes. • Expedite MEP agency onboarding to initiate material submittals and approvals for long-lead items, and assess the potential benefits of local procurement. • Reassess project scope to identify resource and timeline requirements; Develop a revised project schedule incorporating the new scope and methodology | Annex Building • Substructure – Grade Slab Works • Superstructure works – RCC Wall works upto 1FL Level Shelter Block • Substructure –Foundation Cast & Existing Structure Strengthening works to progress • RCC Plinth Wall & GF Wall Works to progress • Surface Preparation for CRFP works |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1dScaMwmgQ5YIvqUOVMiDsOPUqR2RbhFd&sz=w1000 | https://drive.google.com/file/d/1dScaMwmgQ5YIvqUOVMiDsOPUqR2RbhFd/view?usp=drive_link | https://drive.google.com/thumbnail?id=111CWUZAruPmvLjxfjEfGmVJyVABOAn6H&sz=w1000 | https://drive.google.com/file/d/111CWUZAruPmvLjxfjEfGmVJyVABOAn6H/view?usp=drive_link | https://drive.google.com/thumbnail?id=1V_6F8E7F44jsBtYi6gGMFlkhGRPoCKfO&sz=w1000 | https://drive.google.com/file/d/1V_6F8E7F44jsBtYi6gGMFlkhGRPoCKfO/view?usp=drive_link
2024-08-12 | Al Sila-School-P43 | P43 | SC-05 | 219 | 328 | 547 | Annex Building • GF - RCC Wall Rebar Fixing 51% completed School Building • RCC Plinth Wall - 30% Completed • GF – RCC Wall Rebar Fixing – 14% Completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 14.64% | 12.67% | -1.973% | Building Permit | 2024-05-17 | 2024-06-04 |  | 2024-08-16 | • Bill No.4 – MEP Final Rate Agreement required – 19-Aug-24 (Delaying the MEP Agency mobilization at site, Engineering & Procurement process) • Approval for Remaining Cost plus & Re-measurable Items required – 19-Aug-24 (Hampering the Annex & School building progress) • MEP Long lead items – Materials submittals & Approvals delaying due to Agency not mobilized (Impacted in the critical path) • Addition in Scope (Internal wall + External RCC Wall at School) & changes in construction methodology hindering the progress | • Expedite final rate agreement between parties and accelerate procurement of critical materials. • Obtain timely approvals and expedite procurement of critical materials; Consider expediting procurement processes. • Expedite MEP agency onboarding to initiate material submittals and approvals for long-lead items, and assess the potential benefits of local procurement. • Reassess project scope to identify resource and timeline requirements; Develop a revised project schedule incorporating the new scope and methodology | Annex Building • Substructure – Grade Slab Works • Superstructure works – RCC Wall works upto 1FL Level Shelter Block • Substructure –Foundation Cast & Existing Structure Strengthening works to progress • RCC Plinth Wall & GF Wall Works to progress • Surface Preparation for CRFP works |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1dScaMwmgQ5YIvqUOVMiDsOPUqR2RbhFd&sz=w1000 | https://drive.google.com/file/d/1dScaMwmgQ5YIvqUOVMiDsOPUqR2RbhFd/view?usp=drive_link | https://drive.google.com/thumbnail?id=111CWUZAruPmvLjxfjEfGmVJyVABOAn6H&sz=w1000 | https://drive.google.com/file/d/111CWUZAruPmvLjxfjEfGmVJyVABOAn6H/view?usp=drive_link | https://drive.google.com/thumbnail?id=1V_6F8E7F44jsBtYi6gGMFlkhGRPoCKfO&sz=w1000 | https://drive.google.com/file/d/1V_6F8E7F44jsBtYi6gGMFlkhGRPoCKfO/view?usp=drive_link
2024-08-12 | Al Sila-School-P43 | P43 | SC-05 | 219 | 328 | 547 | Annex Building • GF - RCC Wall Rebar Fixing 51% completed School Building • RCC Plinth Wall - 30% Completed • GF – RCC Wall Rebar Fixing – 14% Completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 14.64% | 12.67% | -1.973% | Design Phase | 2024-05-21 | 2024-08-10 |  | 2024-08-16 | • Bill No.4 – MEP Final Rate Agreement required – 19-Aug-24 (Delaying the MEP Agency mobilization at site, Engineering & Procurement process) • Approval for Remaining Cost plus & Re-measurable Items required – 19-Aug-24 (Hampering the Annex & School building progress) • MEP Long lead items – Materials submittals & Approvals delaying due to Agency not mobilized (Impacted in the critical path) • Addition in Scope (Internal wall + External RCC Wall at School) & changes in construction methodology hindering the progress | • Expedite final rate agreement between parties and accelerate procurement of critical materials. • Obtain timely approvals and expedite procurement of critical materials; Consider expediting procurement processes. • Expedite MEP agency onboarding to initiate material submittals and approvals for long-lead items, and assess the potential benefits of local procurement. • Reassess project scope to identify resource and timeline requirements; Develop a revised project schedule incorporating the new scope and methodology | Annex Building • Substructure – Grade Slab Works • Superstructure works – RCC Wall works upto 1FL Level Shelter Block • Substructure –Foundation Cast & Existing Structure Strengthening works to progress • RCC Plinth Wall & GF Wall Works to progress • Surface Preparation for CRFP works |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1dScaMwmgQ5YIvqUOVMiDsOPUqR2RbhFd&sz=w1000 | https://drive.google.com/file/d/1dScaMwmgQ5YIvqUOVMiDsOPUqR2RbhFd/view?usp=drive_link | https://drive.google.com/thumbnail?id=111CWUZAruPmvLjxfjEfGmVJyVABOAn6H&sz=w1000 | https://drive.google.com/file/d/111CWUZAruPmvLjxfjEfGmVJyVABOAn6H/view?usp=drive_link | https://drive.google.com/thumbnail?id=1V_6F8E7F44jsBtYi6gGMFlkhGRPoCKfO&sz=w1000 | https://drive.google.com/file/d/1V_6F8E7F44jsBtYi6gGMFlkhGRPoCKfO/view?usp=drive_link
2024-08-12 | Al Sila-School-P43 | P43 | SC-05 | 219 | 328 | 547 | Annex Building • GF - RCC Wall Rebar Fixing 51% completed School Building • RCC Plinth Wall - 30% Completed • GF – RCC Wall Rebar Fixing – 14% Completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 14.64% | 12.67% | -1.973% | Structural Completion | 2024-10-31 | 2024-01-18 |  | 2024-08-16 | • Bill No.4 – MEP Final Rate Agreement required – 19-Aug-24 (Delaying the MEP Agency mobilization at site, Engineering & Procurement process) • Approval for Remaining Cost plus & Re-measurable Items required – 19-Aug-24 (Hampering the Annex & School building progress) • MEP Long lead items – Materials submittals & Approvals delaying due to Agency not mobilized (Impacted in the critical path) • Addition in Scope (Internal wall + External RCC Wall at School) & changes in construction methodology hindering the progress | • Expedite final rate agreement between parties and accelerate procurement of critical materials. • Obtain timely approvals and expedite procurement of critical materials; Consider expediting procurement processes. • Expedite MEP agency onboarding to initiate material submittals and approvals for long-lead items, and assess the potential benefits of local procurement. • Reassess project scope to identify resource and timeline requirements; Develop a revised project schedule incorporating the new scope and methodology | Annex Building • Substructure – Grade Slab Works • Superstructure works – RCC Wall works upto 1FL Level Shelter Block • Substructure –Foundation Cast & Existing Structure Strengthening works to progress • RCC Plinth Wall & GF Wall Works to progress • Surface Preparation for CRFP works |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1dScaMwmgQ5YIvqUOVMiDsOPUqR2RbhFd&sz=w1000 | https://drive.google.com/file/d/1dScaMwmgQ5YIvqUOVMiDsOPUqR2RbhFd/view?usp=drive_link | https://drive.google.com/thumbnail?id=111CWUZAruPmvLjxfjEfGmVJyVABOAn6H&sz=w1000 | https://drive.google.com/file/d/111CWUZAruPmvLjxfjEfGmVJyVABOAn6H/view?usp=drive_link | https://drive.google.com/thumbnail?id=1V_6F8E7F44jsBtYi6gGMFlkhGRPoCKfO&sz=w1000 | https://drive.google.com/file/d/1V_6F8E7F44jsBtYi6gGMFlkhGRPoCKfO/view?usp=drive_link
2024-08-12 | Al Sila-School-P43 | P43 | SC-05 | 219 | 328 | 547 | Annex Building • GF - RCC Wall Rebar Fixing 51% completed School Building • RCC Plinth Wall - 30% Completed • GF – RCC Wall Rebar Fixing – 14% Completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 14.64% | 12.67% | -1.973% | MEP & Finishes | 2025-01-25 |  | 2025-05-12 | 2024-08-16 | • Bill No.4 – MEP Final Rate Agreement required – 19-Aug-24 (Delaying the MEP Agency mobilization at site, Engineering & Procurement process) • Approval for Remaining Cost plus & Re-measurable Items required – 19-Aug-24 (Hampering the Annex & School building progress) • MEP Long lead items – Materials submittals & Approvals delaying due to Agency not mobilized (Impacted in the critical path) • Addition in Scope (Internal wall + External RCC Wall at School) & changes in construction methodology hindering the progress | • Expedite final rate agreement between parties and accelerate procurement of critical materials. • Obtain timely approvals and expedite procurement of critical materials; Consider expediting procurement processes. • Expedite MEP agency onboarding to initiate material submittals and approvals for long-lead items, and assess the potential benefits of local procurement. • Reassess project scope to identify resource and timeline requirements; Develop a revised project schedule incorporating the new scope and methodology | Annex Building • Substructure – Grade Slab Works • Superstructure works – RCC Wall works upto 1FL Level Shelter Block • Substructure –Foundation Cast & Existing Structure Strengthening works to progress • RCC Plinth Wall & GF Wall Works to progress • Surface Preparation for CRFP works |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1dScaMwmgQ5YIvqUOVMiDsOPUqR2RbhFd&sz=w1000 | https://drive.google.com/file/d/1dScaMwmgQ5YIvqUOVMiDsOPUqR2RbhFd/view?usp=drive_link | https://drive.google.com/thumbnail?id=111CWUZAruPmvLjxfjEfGmVJyVABOAn6H&sz=w1000 | https://drive.google.com/file/d/111CWUZAruPmvLjxfjEfGmVJyVABOAn6H/view?usp=drive_link | https://drive.google.com/thumbnail?id=1V_6F8E7F44jsBtYi6gGMFlkhGRPoCKfO&sz=w1000 | https://drive.google.com/file/d/1V_6F8E7F44jsBtYi6gGMFlkhGRPoCKfO/view?usp=drive_link
2024-08-12 | Al Sila-School-P43 | P43 | SC-05 | 219 | 328 | 547 | Annex Building • GF - RCC Wall Rebar Fixing 51% completed School Building • RCC Plinth Wall - 30% Completed • GF – RCC Wall Rebar Fixing – 14% Completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 14.64% | 12.67% | -1.973% | BCC Inspection | 2025-02-13 |  | 2025-05-22 | 2024-08-16 | • Bill No.4 – MEP Final Rate Agreement required – 19-Aug-24 (Delaying the MEP Agency mobilization at site, Engineering & Procurement process) • Approval for Remaining Cost plus & Re-measurable Items required – 19-Aug-24 (Hampering the Annex & School building progress) • MEP Long lead items – Materials submittals & Approvals delaying due to Agency not mobilized (Impacted in the critical path) • Addition in Scope (Internal wall + External RCC Wall at School) & changes in construction methodology hindering the progress | • Expedite final rate agreement between parties and accelerate procurement of critical materials. • Obtain timely approvals and expedite procurement of critical materials; Consider expediting procurement processes. • Expedite MEP agency onboarding to initiate material submittals and approvals for long-lead items, and assess the potential benefits of local procurement. • Reassess project scope to identify resource and timeline requirements; Develop a revised project schedule incorporating the new scope and methodology | Annex Building • Substructure – Grade Slab Works • Superstructure works – RCC Wall works upto 1FL Level Shelter Block • Substructure –Foundation Cast & Existing Structure Strengthening works to progress • RCC Plinth Wall & GF Wall Works to progress • Surface Preparation for CRFP works |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1dScaMwmgQ5YIvqUOVMiDsOPUqR2RbhFd&sz=w1000 | https://drive.google.com/file/d/1dScaMwmgQ5YIvqUOVMiDsOPUqR2RbhFd/view?usp=drive_link | https://drive.google.com/thumbnail?id=111CWUZAruPmvLjxfjEfGmVJyVABOAn6H&sz=w1000 | https://drive.google.com/file/d/111CWUZAruPmvLjxfjEfGmVJyVABOAn6H/view?usp=drive_link | https://drive.google.com/thumbnail?id=1V_6F8E7F44jsBtYi6gGMFlkhGRPoCKfO&sz=w1000 | https://drive.google.com/file/d/1V_6F8E7F44jsBtYi6gGMFlkhGRPoCKfO/view?usp=drive_link
2024-08-12 | Al Sila-School-P43 | P43 | SC-05 | 219 | 328 | 547 | Annex Building • GF - RCC Wall Rebar Fixing 51% completed School Building • RCC Plinth Wall - 30% Completed • GF – RCC Wall Rebar Fixing – 14% Completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 14.64% | 12.67% | -1.973% | BCC Issuance | 2025-03-04 |  | 2025-06-12 | 2024-08-16 | • Bill No.4 – MEP Final Rate Agreement required – 19-Aug-24 (Delaying the MEP Agency mobilization at site, Engineering & Procurement process) • Approval for Remaining Cost plus & Re-measurable Items required – 19-Aug-24 (Hampering the Annex & School building progress) • MEP Long lead items – Materials submittals & Approvals delaying due to Agency not mobilized (Impacted in the critical path) • Addition in Scope (Internal wall + External RCC Wall at School) & changes in construction methodology hindering the progress | • Expedite final rate agreement between parties and accelerate procurement of critical materials. • Obtain timely approvals and expedite procurement of critical materials; Consider expediting procurement processes. • Expedite MEP agency onboarding to initiate material submittals and approvals for long-lead items, and assess the potential benefits of local procurement. • Reassess project scope to identify resource and timeline requirements; Develop a revised project schedule incorporating the new scope and methodology | Annex Building • Substructure – Grade Slab Works • Superstructure works – RCC Wall works upto 1FL Level Shelter Block • Substructure –Foundation Cast & Existing Structure Strengthening works to progress • RCC Plinth Wall & GF Wall Works to progress • Surface Preparation for CRFP works |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1dScaMwmgQ5YIvqUOVMiDsOPUqR2RbhFd&sz=w1000 | https://drive.google.com/file/d/1dScaMwmgQ5YIvqUOVMiDsOPUqR2RbhFd/view?usp=drive_link | https://drive.google.com/thumbnail?id=111CWUZAruPmvLjxfjEfGmVJyVABOAn6H&sz=w1000 | https://drive.google.com/file/d/111CWUZAruPmvLjxfjEfGmVJyVABOAn6H/view?usp=drive_link | https://drive.google.com/thumbnail?id=1V_6F8E7F44jsBtYi6gGMFlkhGRPoCKfO&sz=w1000 | https://drive.google.com/file/d/1V_6F8E7F44jsBtYi6gGMFlkhGRPoCKfO/view?usp=drive_link
2024-08-12 | Al Sila-School-P43 | P43 | SC-05 | 219 | 328 | 547 | Annex Building • GF - RCC Wall Rebar Fixing 51% completed School Building • RCC Plinth Wall - 30% Completed • GF – RCC Wall Rebar Fixing – 14% Completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 14.64% | 12.67% | -1.973% | Completion | 2025-05-17 |  | 2025-06-25 | 2024-08-16 | • Bill No.4 – MEP Final Rate Agreement required – 19-Aug-24 (Delaying the MEP Agency mobilization at site, Engineering & Procurement process) • Approval for Remaining Cost plus & Re-measurable Items required – 19-Aug-24 (Hampering the Annex & School building progress) • MEP Long lead items – Materials submittals & Approvals delaying due to Agency not mobilized (Impacted in the critical path) • Addition in Scope (Internal wall + External RCC Wall at School) & changes in construction methodology hindering the progress | • Expedite final rate agreement between parties and accelerate procurement of critical materials. • Obtain timely approvals and expedite procurement of critical materials; Consider expediting procurement processes. • Expedite MEP agency onboarding to initiate material submittals and approvals for long-lead items, and assess the potential benefits of local procurement. • Reassess project scope to identify resource and timeline requirements; Develop a revised project schedule incorporating the new scope and methodology | Annex Building • Substructure – Grade Slab Works • Superstructure works – RCC Wall works upto 1FL Level Shelter Block • Substructure –Foundation Cast & Existing Structure Strengthening works to progress • RCC Plinth Wall & GF Wall Works to progress • Surface Preparation for CRFP works |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1dScaMwmgQ5YIvqUOVMiDsOPUqR2RbhFd&sz=w1000 | https://drive.google.com/file/d/1dScaMwmgQ5YIvqUOVMiDsOPUqR2RbhFd/view?usp=drive_link | https://drive.google.com/thumbnail?id=111CWUZAruPmvLjxfjEfGmVJyVABOAn6H&sz=w1000 | https://drive.google.com/file/d/111CWUZAruPmvLjxfjEfGmVJyVABOAn6H/view?usp=drive_link | https://drive.google.com/thumbnail?id=1V_6F8E7F44jsBtYi6gGMFlkhGRPoCKfO&sz=w1000 | https://drive.google.com/file/d/1V_6F8E7F44jsBtYi6gGMFlkhGRPoCKfO/view?usp=drive_link
2024-08-12 | Al Hili-Majlis-10 | 10 | MJ-10 | 14 | 594 | 608 | • Contractor mobilization activities commenced | • Building permit is to be obtained | 0% | 0% | 0% | Notice to Commence | 2024-07-16 | 2024-07-16 |  | 2024-08-16 | • Timely mobilization of key construction staffs and supervision staffs | - | • Onboarding key resources • Submission of baseline plan |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1fHz1NxkdI260HU_cA-zOMox6gaTachXD&sz=w1000 | https://drive.google.com/file/d/1fHz1NxkdI260HU_cA-zOMox6gaTachXD/view?usp=drive_link | https://drive.google.com/thumbnail?id=1fYpQ5poYHYgUA8baZjhriBM5Ln-hQTID&sz=w1000 | https://drive.google.com/file/d/1fYpQ5poYHYgUA8baZjhriBM5Ln-hQTID/view?usp=drive_link | https://drive.google.com/thumbnail?id=1haY8RHl6xd4zLp2freVwagnUjWns8HvA&sz=w1000 | https://drive.google.com/file/d/1haY8RHl6xd4zLp2freVwagnUjWns8HvA/view?usp=drive_link
2024-08-12 | Al Hili-Majlis-10 | 10 | MJ-10 | 14 | 594 | 608 | • Contractor mobilization activities commenced | • Building permit is to be obtained | 0% | 0% | 0% | Building Permit | 2024-07-04 | 2024-07-23 |  | 2024-08-16 | • Timely mobilization of key construction staffs and supervision staffs | - | • Onboarding key resources • Submission of baseline plan |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1fHz1NxkdI260HU_cA-zOMox6gaTachXD&sz=w1000 | https://drive.google.com/file/d/1fHz1NxkdI260HU_cA-zOMox6gaTachXD/view?usp=drive_link | https://drive.google.com/thumbnail?id=1fYpQ5poYHYgUA8baZjhriBM5Ln-hQTID&sz=w1000 | https://drive.google.com/file/d/1fYpQ5poYHYgUA8baZjhriBM5Ln-hQTID/view?usp=drive_link | https://drive.google.com/thumbnail?id=1haY8RHl6xd4zLp2freVwagnUjWns8HvA&sz=w1000 | https://drive.google.com/file/d/1haY8RHl6xd4zLp2freVwagnUjWns8HvA/view?usp=drive_link
2024-08-12 | Al Hili-Majlis-10 | 10 | MJ-10 | 14 | 594 | 608 | • Contractor mobilization activities commenced | • Building permit is to be obtained | 0% | 0% | 0% | Demarcation | 2024-07-26 | 2024-07-26 |  | 2024-08-16 | • Timely mobilization of key construction staffs and supervision staffs | - | • Onboarding key resources • Submission of baseline plan |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1fHz1NxkdI260HU_cA-zOMox6gaTachXD&sz=w1000 | https://drive.google.com/file/d/1fHz1NxkdI260HU_cA-zOMox6gaTachXD/view?usp=drive_link | https://drive.google.com/thumbnail?id=1fYpQ5poYHYgUA8baZjhriBM5Ln-hQTID&sz=w1000 | https://drive.google.com/file/d/1fYpQ5poYHYgUA8baZjhriBM5Ln-hQTID/view?usp=drive_link | https://drive.google.com/thumbnail?id=1haY8RHl6xd4zLp2freVwagnUjWns8HvA&sz=w1000 | https://drive.google.com/file/d/1haY8RHl6xd4zLp2freVwagnUjWns8HvA/view?usp=drive_link
2024-08-12 | Al Hili-Majlis-10 | 10 | MJ-10 | 14 | 594 | 608 | • Contractor mobilization activities commenced | • Building permit is to be obtained | 0% | 0% | 0% | Fencing & Signboard Fabrication | 2024-07-30 |  | 2024-07-30 | 2024-08-16 | • Timely mobilization of key construction staffs and supervision staffs | - | • Onboarding key resources • Submission of baseline plan |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1fHz1NxkdI260HU_cA-zOMox6gaTachXD&sz=w1000 | https://drive.google.com/file/d/1fHz1NxkdI260HU_cA-zOMox6gaTachXD/view?usp=drive_link | https://drive.google.com/thumbnail?id=1fYpQ5poYHYgUA8baZjhriBM5Ln-hQTID&sz=w1000 | https://drive.google.com/file/d/1fYpQ5poYHYgUA8baZjhriBM5Ln-hQTID/view?usp=drive_link | https://drive.google.com/thumbnail?id=1haY8RHl6xd4zLp2freVwagnUjWns8HvA&sz=w1000 | https://drive.google.com/file/d/1haY8RHl6xd4zLp2freVwagnUjWns8HvA/view?usp=drive_link
2024-08-12 | Al Hili-Majlis-10 | 10 | MJ-10 | 14 | 594 | 608 | • Contractor mobilization activities commenced | • Building permit is to be obtained | 0% | 0% | 0% | Signboard Installation | 2024-08-03 |  | 2024-08-03 | 2024-08-16 | • Timely mobilization of key construction staffs and supervision staffs | - | • Onboarding key resources • Submission of baseline plan |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1fHz1NxkdI260HU_cA-zOMox6gaTachXD&sz=w1000 | https://drive.google.com/file/d/1fHz1NxkdI260HU_cA-zOMox6gaTachXD/view?usp=drive_link | https://drive.google.com/thumbnail?id=1fYpQ5poYHYgUA8baZjhriBM5Ln-hQTID&sz=w1000 | https://drive.google.com/file/d/1fYpQ5poYHYgUA8baZjhriBM5Ln-hQTID/view?usp=drive_link | https://drive.google.com/thumbnail?id=1haY8RHl6xd4zLp2freVwagnUjWns8HvA&sz=w1000 | https://drive.google.com/file/d/1haY8RHl6xd4zLp2freVwagnUjWns8HvA/view?usp=drive_link
2024-08-12 | Al Hili-Majlis-10 | 10 | MJ-10 | 14 | 594 | 608 | • Contractor mobilization activities commenced | • Building permit is to be obtained | 0% | 0% | 0% | Fencing Installation | 2024-08-03 |  | 2024-08-03 | 2024-08-16 | • Timely mobilization of key construction staffs and supervision staffs | - | • Onboarding key resources • Submission of baseline plan |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1fHz1NxkdI260HU_cA-zOMox6gaTachXD&sz=w1000 | https://drive.google.com/file/d/1fHz1NxkdI260HU_cA-zOMox6gaTachXD/view?usp=drive_link | https://drive.google.com/thumbnail?id=1fYpQ5poYHYgUA8baZjhriBM5Ln-hQTID&sz=w1000 | https://drive.google.com/file/d/1fYpQ5poYHYgUA8baZjhriBM5Ln-hQTID/view?usp=drive_link | https://drive.google.com/thumbnail?id=1haY8RHl6xd4zLp2freVwagnUjWns8HvA&sz=w1000 | https://drive.google.com/file/d/1haY8RHl6xd4zLp2freVwagnUjWns8HvA/view?usp=drive_link
2024-08-12 | Al Hili-Majlis-10 | 10 | MJ-10 | 14 | 594 | 608 | • Contractor mobilization activities commenced | • Building permit is to be obtained | 0% | 0% | 0% | Site Offices Fabrication | 2024-08-07 |  | 2024-08-07 | 2024-08-16 | • Timely mobilization of key construction staffs and supervision staffs | - | • Onboarding key resources • Submission of baseline plan |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1fHz1NxkdI260HU_cA-zOMox6gaTachXD&sz=w1000 | https://drive.google.com/file/d/1fHz1NxkdI260HU_cA-zOMox6gaTachXD/view?usp=drive_link | https://drive.google.com/thumbnail?id=1fYpQ5poYHYgUA8baZjhriBM5Ln-hQTID&sz=w1000 | https://drive.google.com/file/d/1fYpQ5poYHYgUA8baZjhriBM5Ln-hQTID/view?usp=drive_link | https://drive.google.com/thumbnail?id=1haY8RHl6xd4zLp2freVwagnUjWns8HvA&sz=w1000 | https://drive.google.com/file/d/1haY8RHl6xd4zLp2freVwagnUjWns8HvA/view?usp=drive_link
2024-08-12 | Al Hili-Majlis-10 | 10 | MJ-10 | 14 | 594 | 608 | • Contractor mobilization activities commenced | • Building permit is to be obtained | 0% | 0% | 0% | Site Offices Installation | 2024-08-28 |  | 2024-08-28 | 2024-08-16 | • Timely mobilization of key construction staffs and supervision staffs | - | • Onboarding key resources • Submission of baseline plan |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1fHz1NxkdI260HU_cA-zOMox6gaTachXD&sz=w1000 | https://drive.google.com/file/d/1fHz1NxkdI260HU_cA-zOMox6gaTachXD/view?usp=drive_link | https://drive.google.com/thumbnail?id=1fYpQ5poYHYgUA8baZjhriBM5Ln-hQTID&sz=w1000 | https://drive.google.com/file/d/1fYpQ5poYHYgUA8baZjhriBM5Ln-hQTID/view?usp=drive_link | https://drive.google.com/thumbnail?id=1haY8RHl6xd4zLp2freVwagnUjWns8HvA&sz=w1000 | https://drive.google.com/file/d/1haY8RHl6xd4zLp2freVwagnUjWns8HvA/view?usp=drive_link
2024-08-12 | Al Hili-Majlis-10 | 10 | MJ-10 | 14 | 594 | 608 | • Contractor mobilization activities commenced | • Building permit is to be obtained | 0% | 0% | 0% | Handing Over | 2026-03-15 |  | 2026-03-15 | 2024-08-16 | • Timely mobilization of key construction staffs and supervision staffs | - | • Onboarding key resources • Submission of baseline plan |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1fHz1NxkdI260HU_cA-zOMox6gaTachXD&sz=w1000 | https://drive.google.com/file/d/1fHz1NxkdI260HU_cA-zOMox6gaTachXD/view?usp=drive_link | https://drive.google.com/thumbnail?id=1fYpQ5poYHYgUA8baZjhriBM5Ln-hQTID&sz=w1000 | https://drive.google.com/file/d/1fYpQ5poYHYgUA8baZjhriBM5Ln-hQTID/view?usp=drive_link | https://drive.google.com/thumbnail?id=1haY8RHl6xd4zLp2freVwagnUjWns8HvA&sz=w1000 | https://drive.google.com/file/d/1haY8RHl6xd4zLp2freVwagnUjWns8HvA/view?usp=drive_link
2024-08-12 | Al Tiwayya-Majlis-13 | 13 | MJ-11 | 14 | 594 | 608 | • Contractor mobilization activities commenced | • Building permit is to be obtained | 0% | 0% | 0% | Notice to Commence | 2024-07-16 | 2024-07-16 |  | 2024-08-16 | • Timely mobilization of key construction staffs and supervision staffs | - | • Onboarding key resources • Submission of baseline plan |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1L2I73RPdpxaKO9zAt2EjFURAX7DFTPZb&sz=w1000 | https://drive.google.com/file/d/1L2I73RPdpxaKO9zAt2EjFURAX7DFTPZb/view?usp=drive_link | https://drive.google.com/thumbnail?id=1AGpx0fGJvSUChgQhDonCGIknvfhb1EPL&sz=w1000 | https://drive.google.com/file/d/1AGpx0fGJvSUChgQhDonCGIknvfhb1EPL/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hTpfTQ2NSH26bsU3KzVg6m_V5Q-Tluu1&sz=w1000 | https://drive.google.com/file/d/1hTpfTQ2NSH26bsU3KzVg6m_V5Q-Tluu1/view?usp=drive_link
2024-08-12 | Al Tiwayya-Majlis-13 | 13 | MJ-11 | 14 | 594 | 608 | • Contractor mobilization activities commenced | • Building permit is to be obtained | 0% | 0% | 0% | Building Permit | 2024-07-04 | 2024-07-23 |  | 2024-08-16 | • Timely mobilization of key construction staffs and supervision staffs | - | • Onboarding key resources • Submission of baseline plan |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1L2I73RPdpxaKO9zAt2EjFURAX7DFTPZb&sz=w1000 | https://drive.google.com/file/d/1L2I73RPdpxaKO9zAt2EjFURAX7DFTPZb/view?usp=drive_link | https://drive.google.com/thumbnail?id=1AGpx0fGJvSUChgQhDonCGIknvfhb1EPL&sz=w1000 | https://drive.google.com/file/d/1AGpx0fGJvSUChgQhDonCGIknvfhb1EPL/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hTpfTQ2NSH26bsU3KzVg6m_V5Q-Tluu1&sz=w1000 | https://drive.google.com/file/d/1hTpfTQ2NSH26bsU3KzVg6m_V5Q-Tluu1/view?usp=drive_link
2024-08-12 | Al Tiwayya-Majlis-13 | 13 | MJ-11 | 14 | 594 | 608 | • Contractor mobilization activities commenced | • Building permit is to be obtained | 0% | 0% | 0% | Demarcation | 2024-07-26 | 2024-07-26 |  | 2024-08-16 | • Timely mobilization of key construction staffs and supervision staffs | - | • Onboarding key resources • Submission of baseline plan |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1L2I73RPdpxaKO9zAt2EjFURAX7DFTPZb&sz=w1000 | https://drive.google.com/file/d/1L2I73RPdpxaKO9zAt2EjFURAX7DFTPZb/view?usp=drive_link | https://drive.google.com/thumbnail?id=1AGpx0fGJvSUChgQhDonCGIknvfhb1EPL&sz=w1000 | https://drive.google.com/file/d/1AGpx0fGJvSUChgQhDonCGIknvfhb1EPL/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hTpfTQ2NSH26bsU3KzVg6m_V5Q-Tluu1&sz=w1000 | https://drive.google.com/file/d/1hTpfTQ2NSH26bsU3KzVg6m_V5Q-Tluu1/view?usp=drive_link
2024-08-12 | Al Tiwayya-Majlis-13 | 13 | MJ-11 | 14 | 594 | 608 | • Contractor mobilization activities commenced | • Building permit is to be obtained | 0% | 0% | 0% | Fencing & Signboard Fabrication | 2024-07-30 |  | 2024-07-30 | 2024-08-16 | • Timely mobilization of key construction staffs and supervision staffs | - | • Onboarding key resources • Submission of baseline plan |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1L2I73RPdpxaKO9zAt2EjFURAX7DFTPZb&sz=w1000 | https://drive.google.com/file/d/1L2I73RPdpxaKO9zAt2EjFURAX7DFTPZb/view?usp=drive_link | https://drive.google.com/thumbnail?id=1AGpx0fGJvSUChgQhDonCGIknvfhb1EPL&sz=w1000 | https://drive.google.com/file/d/1AGpx0fGJvSUChgQhDonCGIknvfhb1EPL/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hTpfTQ2NSH26bsU3KzVg6m_V5Q-Tluu1&sz=w1000 | https://drive.google.com/file/d/1hTpfTQ2NSH26bsU3KzVg6m_V5Q-Tluu1/view?usp=drive_link
2024-08-12 | Al Tiwayya-Majlis-13 | 13 | MJ-11 | 14 | 594 | 608 | • Contractor mobilization activities commenced | • Building permit is to be obtained | 0% | 0% | 0% | Signboard Installation | 2024-08-03 |  | 2024-08-03 | 2024-08-16 | • Timely mobilization of key construction staffs and supervision staffs | - | • Onboarding key resources • Submission of baseline plan |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1L2I73RPdpxaKO9zAt2EjFURAX7DFTPZb&sz=w1000 | https://drive.google.com/file/d/1L2I73RPdpxaKO9zAt2EjFURAX7DFTPZb/view?usp=drive_link | https://drive.google.com/thumbnail?id=1AGpx0fGJvSUChgQhDonCGIknvfhb1EPL&sz=w1000 | https://drive.google.com/file/d/1AGpx0fGJvSUChgQhDonCGIknvfhb1EPL/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hTpfTQ2NSH26bsU3KzVg6m_V5Q-Tluu1&sz=w1000 | https://drive.google.com/file/d/1hTpfTQ2NSH26bsU3KzVg6m_V5Q-Tluu1/view?usp=drive_link
2024-08-12 | Al Tiwayya-Majlis-13 | 13 | MJ-11 | 14 | 594 | 608 | • Contractor mobilization activities commenced | • Building permit is to be obtained | 0% | 0% | 0% | Fencing Installation | 2024-08-03 |  | 2024-08-03 | 2024-08-16 | • Timely mobilization of key construction staffs and supervision staffs | - | • Onboarding key resources • Submission of baseline plan |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1L2I73RPdpxaKO9zAt2EjFURAX7DFTPZb&sz=w1000 | https://drive.google.com/file/d/1L2I73RPdpxaKO9zAt2EjFURAX7DFTPZb/view?usp=drive_link | https://drive.google.com/thumbnail?id=1AGpx0fGJvSUChgQhDonCGIknvfhb1EPL&sz=w1000 | https://drive.google.com/file/d/1AGpx0fGJvSUChgQhDonCGIknvfhb1EPL/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hTpfTQ2NSH26bsU3KzVg6m_V5Q-Tluu1&sz=w1000 | https://drive.google.com/file/d/1hTpfTQ2NSH26bsU3KzVg6m_V5Q-Tluu1/view?usp=drive_link
2024-08-12 | Al Tiwayya-Majlis-13 | 13 | MJ-11 | 14 | 594 | 608 | • Contractor mobilization activities commenced | • Building permit is to be obtained | 0% | 0% | 0% | Site Offices Fabrication | 2024-08-07 |  | 2024-08-07 | 2024-08-16 | • Timely mobilization of key construction staffs and supervision staffs | - | • Onboarding key resources • Submission of baseline plan |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1L2I73RPdpxaKO9zAt2EjFURAX7DFTPZb&sz=w1000 | https://drive.google.com/file/d/1L2I73RPdpxaKO9zAt2EjFURAX7DFTPZb/view?usp=drive_link | https://drive.google.com/thumbnail?id=1AGpx0fGJvSUChgQhDonCGIknvfhb1EPL&sz=w1000 | https://drive.google.com/file/d/1AGpx0fGJvSUChgQhDonCGIknvfhb1EPL/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hTpfTQ2NSH26bsU3KzVg6m_V5Q-Tluu1&sz=w1000 | https://drive.google.com/file/d/1hTpfTQ2NSH26bsU3KzVg6m_V5Q-Tluu1/view?usp=drive_link
2024-08-12 | Al Tiwayya-Majlis-13 | 13 | MJ-11 | 14 | 594 | 608 | • Contractor mobilization activities commenced | • Building permit is to be obtained | 0% | 0% | 0% | Site Offices Installation | 2024-08-28 |  | 2024-08-28 | 2024-08-16 | • Timely mobilization of key construction staffs and supervision staffs | - | • Onboarding key resources • Submission of baseline plan |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1L2I73RPdpxaKO9zAt2EjFURAX7DFTPZb&sz=w1000 | https://drive.google.com/file/d/1L2I73RPdpxaKO9zAt2EjFURAX7DFTPZb/view?usp=drive_link | https://drive.google.com/thumbnail?id=1AGpx0fGJvSUChgQhDonCGIknvfhb1EPL&sz=w1000 | https://drive.google.com/file/d/1AGpx0fGJvSUChgQhDonCGIknvfhb1EPL/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hTpfTQ2NSH26bsU3KzVg6m_V5Q-Tluu1&sz=w1000 | https://drive.google.com/file/d/1hTpfTQ2NSH26bsU3KzVg6m_V5Q-Tluu1/view?usp=drive_link
2024-08-12 | Al Tiwayya-Majlis-13 | 13 | MJ-11 | 14 | 594 | 608 | • Contractor mobilization activities commenced | • Building permit is to be obtained | 0% | 0% | 0% | Handing Over | 2026-03-15 |  | 2026-03-15 | 2024-08-16 | • Timely mobilization of key construction staffs and supervision staffs | - | • Onboarding key resources • Submission of baseline plan |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1L2I73RPdpxaKO9zAt2EjFURAX7DFTPZb&sz=w1000 | https://drive.google.com/file/d/1L2I73RPdpxaKO9zAt2EjFURAX7DFTPZb/view?usp=drive_link | https://drive.google.com/thumbnail?id=1AGpx0fGJvSUChgQhDonCGIknvfhb1EPL&sz=w1000 | https://drive.google.com/file/d/1AGpx0fGJvSUChgQhDonCGIknvfhb1EPL/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hTpfTQ2NSH26bsU3KzVg6m_V5Q-Tluu1&sz=w1000 | https://drive.google.com/file/d/1hTpfTQ2NSH26bsU3KzVg6m_V5Q-Tluu1/view?usp=drive_link
2024-08-12 | Al Danah-Car Park-P22 | P22 | CP-05 | 14 | 594 | 608 | • Contractor commenced mobilization activities | • Building permit approval to be obtained | 0% | 0% | 0% | Notice to Commence | 2024-07-16 | 2024-07-16 |  | 2024-08-16 | • Timely mobilization of key construction staffs and supervision staffs • Removal of existing cars in the parking | • Conducting regular interviews and referring candidates for faster selection. • Coordination with ITC and Mawaqif to remove the cars promptly | • Onboarding key resources • Submission of baseline plan |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1BVjBBAXT_96iPy3fp-6ru_uP2gFFD9k5&sz=w1000 | https://drive.google.com/file/d/1BVjBBAXT_96iPy3fp-6ru_uP2gFFD9k5/view?usp=drive_link | https://drive.google.com/thumbnail?id=18JXX9Xdz8u3muQ6ah955dHbx8Mt116y0&sz=w1000 | https://drive.google.com/file/d/18JXX9Xdz8u3muQ6ah955dHbx8Mt116y0/view?usp=drive_link | https://drive.google.com/thumbnail?id=1DniouUoUJ3x7ZuVALbXjnO8pXKv0CDN4&sz=w1000 | https://drive.google.com/file/d/1DniouUoUJ3x7ZuVALbXjnO8pXKv0CDN4/view?usp=drive_link
2024-08-12 | Al Danah-Car Park-P22 | P22 | CP-05 | 14 | 594 | 608 | • Contractor commenced mobilization activities | • Building permit approval to be obtained | 0% | 0% | 0% | Mobilization | 2024-07-27 | 2024-07-27 |  | 2024-08-16 | • Timely mobilization of key construction staffs and supervision staffs • Removal of existing cars in the parking | • Conducting regular interviews and referring candidates for faster selection. • Coordination with ITC and Mawaqif to remove the cars promptly | • Onboarding key resources • Submission of baseline plan |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1BVjBBAXT_96iPy3fp-6ru_uP2gFFD9k5&sz=w1000 | https://drive.google.com/file/d/1BVjBBAXT_96iPy3fp-6ru_uP2gFFD9k5/view?usp=drive_link | https://drive.google.com/thumbnail?id=18JXX9Xdz8u3muQ6ah955dHbx8Mt116y0&sz=w1000 | https://drive.google.com/file/d/18JXX9Xdz8u3muQ6ah955dHbx8Mt116y0/view?usp=drive_link | https://drive.google.com/thumbnail?id=1DniouUoUJ3x7ZuVALbXjnO8pXKv0CDN4&sz=w1000 | https://drive.google.com/file/d/1DniouUoUJ3x7ZuVALbXjnO8pXKv0CDN4/view?usp=drive_link
2024-08-12 | Al Danah-Car Park-P8 | P8 | CP-06 | 14 | 594 | 608 | • Contractor commenced mobilization activities | • Building permit approval to be obtained | 0% | 0% | 0% | Notice to Commence | 2024-07-16 | 2024-07-16 |  | 2024-08-16 | • Timely mobilization of key construction staffs and supervision staffs • Removal of existing cars in the parking | • Conducting regular interviews and referring candidates for faster selection. • Coordination with ITC and Mawaqif to remove the cars promptly | • Onboarding key resources • Submission of baseline plan |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=15hAdSmxMNgF49PWXzt3FyV7tP6RC-DYV&sz=w1000 | https://drive.google.com/file/d/15hAdSmxMNgF49PWXzt3FyV7tP6RC-DYV/view?usp=drive_link | https://drive.google.com/thumbnail?id=1QTt3cnFrYx2jRA1mwDh2HaskxQ_KA9bI&sz=w1000 | https://drive.google.com/file/d/1QTt3cnFrYx2jRA1mwDh2HaskxQ_KA9bI/view?usp=drive_link | https://drive.google.com/thumbnail?id=1Erl7NeY9yDz7jaHgoz9oWN5EzWXacAUi&sz=w1000 | https://drive.google.com/file/d/1Erl7NeY9yDz7jaHgoz9oWN5EzWXacAUi/view?usp=drive_link
2024-08-12 | Al Danah-Car Park-P8 | P8 | CP-06 | 14 | 594 | 608 | • Contractor commenced mobilization activities | • Building permit approval to be obtained | 0% | 0% | 0% | Mobilization | 2024-07-27 | 2024-07-27 |  | 2024-08-16 | • Timely mobilization of key construction staffs and supervision staffs • Removal of existing cars in the parking | • Conducting regular interviews and referring candidates for faster selection. • Coordination with ITC and Mawaqif to remove the cars promptly | • Onboarding key resources • Submission of baseline plan |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=15hAdSmxMNgF49PWXzt3FyV7tP6RC-DYV&sz=w1000 | https://drive.google.com/file/d/15hAdSmxMNgF49PWXzt3FyV7tP6RC-DYV/view?usp=drive_link | https://drive.google.com/thumbnail?id=1QTt3cnFrYx2jRA1mwDh2HaskxQ_KA9bI&sz=w1000 | https://drive.google.com/file/d/1QTt3cnFrYx2jRA1mwDh2HaskxQ_KA9bI/view?usp=drive_link | https://drive.google.com/thumbnail?id=1Erl7NeY9yDz7jaHgoz9oWN5EzWXacAUi&sz=w1000 | https://drive.google.com/file/d/1Erl7NeY9yDz7jaHgoz9oWN5EzWXacAUi/view?usp=drive_link
2024-08-12 | Al Danah-Car Park-P5 | P5 | CP-04 | 14 | 594 | 608 | • Contractor commenced mobilization activities | • Building permit approval to be obtained | 0% | 0% | 0% | Notice to Commence | 2024-07-16 | 2024-07-16 |  | 2024-08-16 | • Timely mobilization of key construction staffs and supervision staffs • Removal of existing cars in the parking | • Conducting regular interviews and referring candidates for faster selection. • Coordination with ITC and Mawaqif to remove the cars promptly | • Onboarding key resources • Submission of baseline plan |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1jy1jKqvPQlXEx88sgsCJn4_Xn9TzTh0g&sz=w1000 | https://drive.google.com/file/d/1jy1jKqvPQlXEx88sgsCJn4_Xn9TzTh0g/view?usp=drive_link | https://drive.google.com/thumbnail?id=1A9cK8swFtcvt3i5pczRoUvEUjnHeKzVL&sz=w1000 | https://drive.google.com/file/d/1A9cK8swFtcvt3i5pczRoUvEUjnHeKzVL/view?usp=drive_link | https://drive.google.com/thumbnail?id=1c_Dwx1T-XSZFsCAQtJWlrkzPzGdVQlbf&sz=w1000 | https://drive.google.com/file/d/1c_Dwx1T-XSZFsCAQtJWlrkzPzGdVQlbf/view?usp=drive_link
2024-08-12 | Al Danah-Car Park-P5 | P5 | CP-04 | 14 | 594 | 608 | • Contractor commenced mobilization activities | • Building permit approval to be obtained | 0% | 0% | 0% | Mobilization | 2024-07-27 | 2024-07-27 |  | 2024-08-16 | • Timely mobilization of key construction staffs and supervision staffs • Removal of existing cars in the parking | • Conducting regular interviews and referring candidates for faster selection. • Coordination with ITC and Mawaqif to remove the cars promptly | • Onboarding key resources • Submission of baseline plan |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1jy1jKqvPQlXEx88sgsCJn4_Xn9TzTh0g&sz=w1000 | https://drive.google.com/file/d/1jy1jKqvPQlXEx88sgsCJn4_Xn9TzTh0g/view?usp=drive_link | https://drive.google.com/thumbnail?id=1A9cK8swFtcvt3i5pczRoUvEUjnHeKzVL&sz=w1000 | https://drive.google.com/file/d/1A9cK8swFtcvt3i5pczRoUvEUjnHeKzVL/view?usp=drive_link | https://drive.google.com/thumbnail?id=1c_Dwx1T-XSZFsCAQtJWlrkzPzGdVQlbf&sz=w1000 | https://drive.google.com/file/d/1c_Dwx1T-XSZFsCAQtJWlrkzPzGdVQlbf/view?usp=drive_link
2024-08-12 | Al Danah-Car Park-P7 | P7 | CP-03 | 14 | 594 | 608 | • Contractor commenced mobilization activities | • Building permit approval to be obtained | 0% | 0% | 0% | Notice to Commence | 2024-07-16 | 2024-07-16 |  | 2024-08-16 | • Timely mobilization of key construction staffs and supervision staffs • Removal of existing cars in the parking | • Conducting regular interviews and referring candidates for faster selection. • Coordination with ITC and Mawaqif to remove the cars promptly | • Onboarding key resources • Submission of baseline plan |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1G0X3ugNeHwTLERFskdq8bubMXXLFcuaw&sz=w1000 | https://drive.google.com/file/d/1G0X3ugNeHwTLERFskdq8bubMXXLFcuaw/view?usp=drive_link | https://drive.google.com/thumbnail?id=1jHGj7XAWagahBHNCKtHr5H5tDQk0bs8B&sz=w1000 | https://drive.google.com/file/d/1jHGj7XAWagahBHNCKtHr5H5tDQk0bs8B/view?usp=drive_link | https://drive.google.com/thumbnail?id=1L3X2HGJwAc7DPG7ILmixFmOZqHkRaHZL&sz=w1000 | https://drive.google.com/file/d/1L3X2HGJwAc7DPG7ILmixFmOZqHkRaHZL/view?usp=drive_link
2024-08-12 | Al Danah-Car Park-P7 | P7 | CP-03 | 14 | 594 | 608 | • Contractor commenced mobilization activities | • Building permit approval to be obtained | 0% | 0% | 0% | Mobilization | 2024-07-27 | 2024-07-27 |  | 2024-08-16 | • Timely mobilization of key construction staffs and supervision staffs • Removal of existing cars in the parking | • Conducting regular interviews and referring candidates for faster selection. • Coordination with ITC and Mawaqif to remove the cars promptly | • Onboarding key resources • Submission of baseline plan |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1G0X3ugNeHwTLERFskdq8bubMXXLFcuaw&sz=w1000 | https://drive.google.com/file/d/1G0X3ugNeHwTLERFskdq8bubMXXLFcuaw/view?usp=drive_link | https://drive.google.com/thumbnail?id=1jHGj7XAWagahBHNCKtHr5H5tDQk0bs8B&sz=w1000 | https://drive.google.com/file/d/1jHGj7XAWagahBHNCKtHr5H5tDQk0bs8B/view?usp=drive_link | https://drive.google.com/thumbnail?id=1L3X2HGJwAc7DPG7ILmixFmOZqHkRaHZL&sz=w1000 | https://drive.google.com/file/d/1L3X2HGJwAc7DPG7ILmixFmOZqHkRaHZL/view?usp=drive_link
2024-08-12 | Saadiyat Island-Majlis-Aldar | Aldar | MJ-17 | 0 | 500 | 500 | • Design Completed • Tender process commenced | • Task order with Aldar to be signed | 0% | 0% | 0% | Design Completed | 2024-07-31 | 2024-07-31 |  | 2024-08-16 | • Timely award of contract by Aldar | • Follow up with Aldar to award the contract. | • Award of Contract • Notice to commence • Mobilization |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1lU4EjoZZIUOHuZTzDR1G531j3Yac1TYp&sz=w1000 | https://drive.google.com/file/d/1lU4EjoZZIUOHuZTzDR1G531j3Yac1TYp/view?usp=drive_link | https://drive.google.com/thumbnail?id=15rDYnSbQ1MxyeaE4lqym4hP9lG005zY8&sz=w1000 | https://drive.google.com/file/d/15rDYnSbQ1MxyeaE4lqym4hP9lG005zY8/view?usp=drive_link | https://drive.google.com/thumbnail?id=1EZXBLH_WJCOWieaYP8wVUSZc7iwtUfUh&sz=w1000 | https://drive.google.com/file/d/1EZXBLH_WJCOWieaYP8wVUSZc7iwtUfUh/view?usp=drive_link
2024-08-12 | Saadiyat Island-Majlis-Aldar | Aldar | MJ-17 | 0 | 500 | 500 | • Design Completed • Tender process commenced | • Task order with Aldar to be signed | 0% | 0% | 0% | Tender Process Completion | 2024-10-31 |  | 2024-10-31 | 2024-08-16 | • Timely award of contract by Aldar | • Follow up with Aldar to award the contract. | • Award of Contract • Notice to commence • Mobilization |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1lU4EjoZZIUOHuZTzDR1G531j3Yac1TYp&sz=w1000 | https://drive.google.com/file/d/1lU4EjoZZIUOHuZTzDR1G531j3Yac1TYp/view?usp=drive_link | https://drive.google.com/thumbnail?id=15rDYnSbQ1MxyeaE4lqym4hP9lG005zY8&sz=w1000 | https://drive.google.com/file/d/15rDYnSbQ1MxyeaE4lqym4hP9lG005zY8/view?usp=drive_link | https://drive.google.com/thumbnail?id=1EZXBLH_WJCOWieaYP8wVUSZc7iwtUfUh&sz=w1000 | https://drive.google.com/file/d/1EZXBLH_WJCOWieaYP8wVUSZc7iwtUfUh/view?usp=drive_link
2024-08-12 | Saadiyat Island-Majlis-Aldar | Aldar | MJ-17 | 0 | 500 | 500 | • Design Completed • Tender process commenced | • Task order with Aldar to be signed | 0% | 0% | 0% | Commencement | 2024-12-31 |  | 2024-12-31 | 2024-08-16 | • Timely award of contract by Aldar | • Follow up with Aldar to award the contract. | • Award of Contract • Notice to commence • Mobilization |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1lU4EjoZZIUOHuZTzDR1G531j3Yac1TYp&sz=w1000 | https://drive.google.com/file/d/1lU4EjoZZIUOHuZTzDR1G531j3Yac1TYp/view?usp=drive_link | https://drive.google.com/thumbnail?id=15rDYnSbQ1MxyeaE4lqym4hP9lG005zY8&sz=w1000 | https://drive.google.com/file/d/15rDYnSbQ1MxyeaE4lqym4hP9lG005zY8/view?usp=drive_link | https://drive.google.com/thumbnail?id=1EZXBLH_WJCOWieaYP8wVUSZc7iwtUfUh&sz=w1000 | https://drive.google.com/file/d/1EZXBLH_WJCOWieaYP8wVUSZc7iwtUfUh/view?usp=drive_link
2024-08-12 | Saadiyat Island-Majlis-Aldar | Aldar | MJ-17 | 0 | 500 | 500 | • Design Completed • Tender process commenced | • Task order with Aldar to be signed | 0% | 0% | 0% | Completion | 2026-12-31 |  | 2026-12-31 | 2024-08-16 | • Timely award of contract by Aldar | • Follow up with Aldar to award the contract. | • Award of Contract • Notice to commence • Mobilization |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1lU4EjoZZIUOHuZTzDR1G531j3Yac1TYp&sz=w1000 | https://drive.google.com/file/d/1lU4EjoZZIUOHuZTzDR1G531j3Yac1TYp/view?usp=drive_link | https://drive.google.com/thumbnail?id=15rDYnSbQ1MxyeaE4lqym4hP9lG005zY8&sz=w1000 | https://drive.google.com/file/d/15rDYnSbQ1MxyeaE4lqym4hP9lG005zY8/view?usp=drive_link | https://drive.google.com/thumbnail?id=1EZXBLH_WJCOWieaYP8wVUSZc7iwtUfUh&sz=w1000 | https://drive.google.com/file/d/1EZXBLH_WJCOWieaYP8wVUSZc7iwtUfUh/view?usp=drive_link
2024-08-12 | Balghaiylam-Majlis-Aldar | Aldar | MJ-18 | 0 | 500 | 500 | • Design Completed • Tender process commenced | • Task order with Aldar to be signed | 0% | 0% | 0% | Design Completion | 2024-07-31 | 2024-07-31 |  | 2024-08-16 | • Timely award of contract by Aldar | • Follow up with Aldar to award the contract. | • Award of Contract • Notice to commence • Mobilization |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1IC8FNC3yghFwIETCJNRQUyEvRizMiEGs&sz=w1000 | https://drive.google.com/file/d/1IC8FNC3yghFwIETCJNRQUyEvRizMiEGs/view?usp=drive_link | https://drive.google.com/thumbnail?id=1bWjnhn8h7JZ3cQnvkpaYRTXauIEl9hqN&sz=w1000 | https://drive.google.com/file/d/1bWjnhn8h7JZ3cQnvkpaYRTXauIEl9hqN/view?usp=drive_link | https://drive.google.com/thumbnail?id=1qAqvXcdebOv4XD9YIwOc1UDjezQgT9A7&sz=w1000 | https://drive.google.com/file/d/1qAqvXcdebOv4XD9YIwOc1UDjezQgT9A7/view?usp=drive_link
2024-08-12 | Balghaiylam-Majlis-Aldar | Aldar | MJ-18 | 0 | 500 | 500 | • Design Completed • Tender process commenced | • Task order with Aldar to be signed | 0% | 0% | 0% | Tender Process Completion | 2024-10-31 |  | 2024-10-31 | 2024-08-16 | • Timely award of contract by Aldar | • Follow up with Aldar to award the contract. | • Award of Contract • Notice to commence • Mobilization |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1IC8FNC3yghFwIETCJNRQUyEvRizMiEGs&sz=w1000 | https://drive.google.com/file/d/1IC8FNC3yghFwIETCJNRQUyEvRizMiEGs/view?usp=drive_link | https://drive.google.com/thumbnail?id=1bWjnhn8h7JZ3cQnvkpaYRTXauIEl9hqN&sz=w1000 | https://drive.google.com/file/d/1bWjnhn8h7JZ3cQnvkpaYRTXauIEl9hqN/view?usp=drive_link | https://drive.google.com/thumbnail?id=1qAqvXcdebOv4XD9YIwOc1UDjezQgT9A7&sz=w1000 | https://drive.google.com/file/d/1qAqvXcdebOv4XD9YIwOc1UDjezQgT9A7/view?usp=drive_link
2024-08-12 | Balghaiylam-Majlis-Aldar | Aldar | MJ-18 | 0 | 500 | 500 | • Design Completed • Tender process commenced | • Task order with Aldar to be signed | 0% | 0% | 0% | Commencement | 2024-12-31 |  | 2024-12-31 | 2024-08-16 | • Timely award of contract by Aldar | • Follow up with Aldar to award the contract. | • Award of Contract • Notice to commence • Mobilization |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1IC8FNC3yghFwIETCJNRQUyEvRizMiEGs&sz=w1000 | https://drive.google.com/file/d/1IC8FNC3yghFwIETCJNRQUyEvRizMiEGs/view?usp=drive_link | https://drive.google.com/thumbnail?id=1bWjnhn8h7JZ3cQnvkpaYRTXauIEl9hqN&sz=w1000 | https://drive.google.com/file/d/1bWjnhn8h7JZ3cQnvkpaYRTXauIEl9hqN/view?usp=drive_link | https://drive.google.com/thumbnail?id=1qAqvXcdebOv4XD9YIwOc1UDjezQgT9A7&sz=w1000 | https://drive.google.com/file/d/1qAqvXcdebOv4XD9YIwOc1UDjezQgT9A7/view?usp=drive_link
2024-08-12 | Balghaiylam-Majlis-Aldar | Aldar | MJ-18 | 0 | 500 | 500 | • Design Completed • Tender process commenced | • Task order with Aldar to be signed | 0% | 0% | 0% | Completion | 2026-12-31 |  | 2026-12-31 | 2024-08-16 | • Timely award of contract by Aldar | • Follow up with Aldar to award the contract. | • Award of Contract • Notice to commence • Mobilization |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1IC8FNC3yghFwIETCJNRQUyEvRizMiEGs&sz=w1000 | https://drive.google.com/file/d/1IC8FNC3yghFwIETCJNRQUyEvRizMiEGs/view?usp=drive_link | https://drive.google.com/thumbnail?id=1bWjnhn8h7JZ3cQnvkpaYRTXauIEl9hqN&sz=w1000 | https://drive.google.com/file/d/1bWjnhn8h7JZ3cQnvkpaYRTXauIEl9hqN/view?usp=drive_link | https://drive.google.com/thumbnail?id=1qAqvXcdebOv4XD9YIwOc1UDjezQgT9A7&sz=w1000 | https://drive.google.com/file/d/1qAqvXcdebOv4XD9YIwOc1UDjezQgT9A7/view?usp=drive_link
2024-08-12 | Al Bateen-Majlis-P1 | P1 | MJ-01 | 600 | 0 | 600 | • Project Completed • Maintenance ongoing | • Detection systems has manufacturer issues that needs to be fixed. | 100% | 100% | 0% | Construction Completion | 2022-07-31 | 2022-07-31 |  |  | • Blast/Gastight Doors has minor leaks • Detection systems are very sensitive leading to faulse alarms | • Carried out pressure testing and identified the doors with leakage and informed contractor to fix it. • Meeting conducted with Environics to fix the issues. | • CCTV and other ICT related elements to be standardized as instructed by CPC |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1QelJzgWu58DSQ-OdyKkGNNTLKOGM973S&sz=w1000 | https://drive.google.com/file/d/1QelJzgWu58DSQ-OdyKkGNNTLKOGM973S/view?usp=drive_link | https://drive.google.com/thumbnail?id=1X6lkb4s2fJhZdoOzi9qO6PCLirHtWBfg&sz=w1000 | https://drive.google.com/file/d/1X6lkb4s2fJhZdoOzi9qO6PCLirHtWBfg/view?usp=drive_link | https://drive.google.com/thumbnail?id=1nPYXb0bT3AaVcs_PIgKdMHAkz4HUPldb&sz=w1000 | https://drive.google.com/file/d/1nPYXb0bT3AaVcs_PIgKdMHAkz4HUPldb/view?usp=drive_link
2024-08-12 | Al Bateen-Majlis-P1 | P1 | MJ-01 | 600 | 0 | 600 | • Project Completed • Maintenance ongoing | • Detection systems has manufacturer issues that needs to be fixed. | 100% | 100% | 0% | Maintenance Ongoing | 2022-10-01 | 2022-10-01 |  |  | • Blast/Gastight Doors has minor leaks • Detection systems are very sensitive leading to faulse alarms | • Carried out pressure testing and identified the doors with leakage and informed contractor to fix it. • Meeting conducted with Environics to fix the issues. | • CCTV and other ICT related elements to be standardized as instructed by CPC |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1QelJzgWu58DSQ-OdyKkGNNTLKOGM973S&sz=w1000 | https://drive.google.com/file/d/1QelJzgWu58DSQ-OdyKkGNNTLKOGM973S/view?usp=drive_link | https://drive.google.com/thumbnail?id=1X6lkb4s2fJhZdoOzi9qO6PCLirHtWBfg&sz=w1000 | https://drive.google.com/file/d/1X6lkb4s2fJhZdoOzi9qO6PCLirHtWBfg/view?usp=drive_link | https://drive.google.com/thumbnail?id=1nPYXb0bT3AaVcs_PIgKdMHAkz4HUPldb&sz=w1000 | https://drive.google.com/file/d/1nPYXb0bT3AaVcs_PIgKdMHAkz4HUPldb/view?usp=drive_link
2024-08-12 | Al Danah-Car Park-P8-E09_02 | P8 | CP-11 | 0 | 0 | 0 | • Design Completed • Tender process commenced | • Pile value engineering to be finalized | 10% | 10% | 0% | Design Coompletion | 2024-08-01 | 2024-08-01 |  |  | • Timely award of contract • Removal of existing cars in the parking • Building permits approvals | • Conducting regular interviews and referring candidates for faster selection. • Coordination with ITC and Mawaqif to remove the cars promptly | • Completion of tender process • Award of contract • Issuing commencement notice • Building permits & construciton permits |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=17qq6Tadw8QG-EBTE_YugsSCYtfMTbldO&sz=w1000 | https://drive.google.com/file/d/17qq6Tadw8QG-EBTE_YugsSCYtfMTbldO/view?usp=drive_link | https://drive.google.com/thumbnail?id=12yh1qsat5zorZubk7_I1WnTJ-HCui9bu&sz=w1000 | https://drive.google.com/file/d/12yh1qsat5zorZubk7_I1WnTJ-HCui9bu/view?usp=drive_link | https://drive.google.com/thumbnail?id=1pHA_6MlFurP9b4-tt7h0DMzqGV0-Tlzo&sz=w1000 | https://drive.google.com/file/d/1pHA_6MlFurP9b4-tt7h0DMzqGV0-Tlzo/view?usp=drive_link
2024-08-12 | Al Danah-Car Park-P8-E09_02 | P8 | CP-11 | 0 | 0 | 0 | • Design Completed • Tender process commenced | • Pile value engineering to be finalized | 10% | 10% | 0% | Tender Process Completion | 2024-11-15 |  | 2024-11-15 |  | • Timely award of contract • Removal of existing cars in the parking • Building permits approvals | • Conducting regular interviews and referring candidates for faster selection. • Coordination with ITC and Mawaqif to remove the cars promptly | • Completion of tender process • Award of contract • Issuing commencement notice • Building permits & construciton permits |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=17qq6Tadw8QG-EBTE_YugsSCYtfMTbldO&sz=w1000 | https://drive.google.com/file/d/17qq6Tadw8QG-EBTE_YugsSCYtfMTbldO/view?usp=drive_link | https://drive.google.com/thumbnail?id=12yh1qsat5zorZubk7_I1WnTJ-HCui9bu&sz=w1000 | https://drive.google.com/file/d/12yh1qsat5zorZubk7_I1WnTJ-HCui9bu/view?usp=drive_link | https://drive.google.com/thumbnail?id=1pHA_6MlFurP9b4-tt7h0DMzqGV0-Tlzo&sz=w1000 | https://drive.google.com/file/d/1pHA_6MlFurP9b4-tt7h0DMzqGV0-Tlzo/view?usp=drive_link
2024-08-12 | Al Danah-Car Park-P8-E09_02 | P8 | CP-11 | 0 | 0 | 0 | • Design Completed • Tender process commenced | • Pile value engineering to be finalized | 10% | 10% | 0% | Construction Completion | 2026-10-31 |  | 2026-10-31 |  | • Timely award of contract • Removal of existing cars in the parking • Building permits approvals | • Conducting regular interviews and referring candidates for faster selection. • Coordination with ITC and Mawaqif to remove the cars promptly | • Completion of tender process • Award of contract • Issuing commencement notice • Building permits & construciton permits |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=17qq6Tadw8QG-EBTE_YugsSCYtfMTbldO&sz=w1000 | https://drive.google.com/file/d/17qq6Tadw8QG-EBTE_YugsSCYtfMTbldO/view?usp=drive_link | https://drive.google.com/thumbnail?id=12yh1qsat5zorZubk7_I1WnTJ-HCui9bu&sz=w1000 | https://drive.google.com/file/d/12yh1qsat5zorZubk7_I1WnTJ-HCui9bu/view?usp=drive_link | https://drive.google.com/thumbnail?id=1pHA_6MlFurP9b4-tt7h0DMzqGV0-Tlzo&sz=w1000 | https://drive.google.com/file/d/1pHA_6MlFurP9b4-tt7h0DMzqGV0-Tlzo/view?usp=drive_link
2024-08-12 | Al Zahiyah-Car Park-TMP7 | TMP7 | CP-10 | 0 | 0 | 0 | • Design Completed • Tender process commenced | • Pile value engineering to be finalized | 10% | 10% | 0% | Design Coompletion | 2024-08-01 | 2024-08-01 |  |  | • Timely award of contract • Removal of existing cars in the parking • Building permits approvals | • Conducting regular interviews and referring candidates for faster selection. • Coordination with ITC and Mawaqif to remove the cars promptly | • Completion of tender process • Award of contract • Issuing commencement notice • Building permits & construciton permits |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1_yC-HE54yXARQXJOTnV7FW3AhPsBP3Sf&sz=w1000 | https://drive.google.com/file/d/1_yC-HE54yXARQXJOTnV7FW3AhPsBP3Sf/view?usp=drive_link | https://drive.google.com/thumbnail?id=1_wgBYwiOTkIPVCE6-tw2TMSEmlcsp4t0&sz=w1000 | https://drive.google.com/file/d/1_wgBYwiOTkIPVCE6-tw2TMSEmlcsp4t0/view?usp=drive_link | https://drive.google.com/thumbnail?id=198ZgTwMgLui1F5kC8xfZILjv0PrDjFb9&sz=w1000 | https://drive.google.com/file/d/198ZgTwMgLui1F5kC8xfZILjv0PrDjFb9/view?usp=drive_link
2024-08-12 | Al Zahiyah-Car Park-TMP7 | TMP7 | CP-10 | 0 | 0 | 0 | • Design Completed • Tender process commenced | • Pile value engineering to be finalized | 10% | 10% | 0% | Tender Process Completion | 2024-11-15 |  | 2024-11-15 |  | • Timely award of contract • Removal of existing cars in the parking • Building permits approvals | • Conducting regular interviews and referring candidates for faster selection. • Coordination with ITC and Mawaqif to remove the cars promptly | • Completion of tender process • Award of contract • Issuing commencement notice • Building permits & construciton permits |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1_yC-HE54yXARQXJOTnV7FW3AhPsBP3Sf&sz=w1000 | https://drive.google.com/file/d/1_yC-HE54yXARQXJOTnV7FW3AhPsBP3Sf/view?usp=drive_link | https://drive.google.com/thumbnail?id=1_wgBYwiOTkIPVCE6-tw2TMSEmlcsp4t0&sz=w1000 | https://drive.google.com/file/d/1_wgBYwiOTkIPVCE6-tw2TMSEmlcsp4t0/view?usp=drive_link | https://drive.google.com/thumbnail?id=198ZgTwMgLui1F5kC8xfZILjv0PrDjFb9&sz=w1000 | https://drive.google.com/file/d/198ZgTwMgLui1F5kC8xfZILjv0PrDjFb9/view?usp=drive_link
2024-08-12 | Al Zahiyah-Car Park-TMP7 | TMP7 | CP-10 | 0 | 0 | 0 | • Design Completed • Tender process commenced | • Pile value engineering to be finalized | 10% | 10% | 0% | Construction Completion | 2026-10-31 |  | 2026-10-31 |  | • Timely award of contract • Removal of existing cars in the parking • Building permits approvals | • Conducting regular interviews and referring candidates for faster selection. • Coordination with ITC and Mawaqif to remove the cars promptly | • Completion of tender process • Award of contract • Issuing commencement notice • Building permits & construciton permits |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1_yC-HE54yXARQXJOTnV7FW3AhPsBP3Sf&sz=w1000 | https://drive.google.com/file/d/1_yC-HE54yXARQXJOTnV7FW3AhPsBP3Sf/view?usp=drive_link | https://drive.google.com/thumbnail?id=1_wgBYwiOTkIPVCE6-tw2TMSEmlcsp4t0&sz=w1000 | https://drive.google.com/file/d/1_wgBYwiOTkIPVCE6-tw2TMSEmlcsp4t0/view?usp=drive_link | https://drive.google.com/thumbnail?id=198ZgTwMgLui1F5kC8xfZILjv0PrDjFb9&sz=w1000 | https://drive.google.com/file/d/198ZgTwMgLui1F5kC8xfZILjv0PrDjFb9/view?usp=drive_link
2024-08-30 | Al Shahama-Majlis-P547 | P547 | MJ-02 | 269 | 329 | 598 | 1-Excavation till Rfat Foundation Completed . 2-Pile head trimming on progress . 3-Pile Head Treatment ongoing . 4-Integrity test piles ongoing . 5-Leveling and compaction ongoing. 6. Raft PCC ongoing. 7-Disposal of Excavated Soil ongoing . 8-Gunting works ongoing . 9- Waterproofing ongoing 9- Dynamic test ongoing. | Substation Relocation. Shoring system from Secant to Continuous. Piles static load test form 8Piles to 5piles . Pile Test from Sonic to TRM . | 45.76% | 34.14% | -11.62% | 1-Notice to Commence ( Contractual Milestone ) | 2023-12-05 | 2023-12-05 |  | 2024-08-30 | 1-Lifting Works ( Unsafe Lifting / Rigging ) Lack of 3rd party Inspection/ Riggers/ and the damaged rigging tackles . 2-Poor Compliance ( Using of Fall Arrest Equipment at heights) 3-Delivery of Long Lead Items ( Chillers & Generator & Air handling Unit ) 4-Delays in response regarding to blast steel doors necessary enquiries/tests /reports /simulations,……..compliance with engineer enquiries as stated via Material submission rev. 04 that that required to be attended to avoid delays in manufacturing processing 5-Contractor anticipation /repeated failed commitments found inaccurate/to be enhanced , and require Contractor action to increase the required resources to achieve anticipated productivity as committed . | 1-Apply the mandatory requirement for lifting equipment as the construction sector - OSHAD 34,.0 Safe lifting and lifting accessories. SF , increase inspection procedure, Implement the control for contractor and subcontractor. 2-Allocate sufficient nos of Fall arrest Equipment, Training and Awareness , Induction , Monitoring and apply the Risk Assessment - refer to OSHAD SF no. 23 W& H . 3-Contractor is requested to keep follow up with supplier /specialist to enable received the goods on time , and without affecting the planned delivery schedule 4-After several reminders to the Contractor , contractor advised during last progress meeting that the door specialist attended to provide the necessary certificates /tests as well , and will be issued to Engineer formally for review , and further action 5-Contractor is requested to secure all the necessary resources that should meet /cover all remaining SOW after study the productivities rate of each equipment /machines to enable provide the accurate dates of mitigation that should be attended upon enquired by Engineer /client | *Completion of Excavate Soil Till Raft Foundation *Completion of Disposal of Excavated Materials *Completion of Site Cleaning and Preparation *Completion of Pile Head Breaking . *Completion of Raft PCC works . *Completion of Steel Reinforcement for Raft Foundation Fabrication and Delivery . * Completion TRM & Dynamic test *Completion of Pile Integrity Test *Start the Screed and Raft R.FT | 85805249.48 | 0 | 85805249.48 | 3799481.4618 | 0 | 89604730.9418 | 17180863.6 | 1117487.2997 | https://drive.google.com/thumbnail?id=1LSdEMIAx0nOnLCMaT-0CJD9nxONTEfbb&sz=w1000 | https://drive.google.com/file/d/1LSdEMIAx0nOnLCMaT-0CJD9nxONTEfbb/view?usp=drive_link | https://drive.google.com/thumbnail?id=1DE97kviXT-3hj-mPkqohYwgjer1eZUEt&sz=w1000 | https://drive.google.com/file/d/1DE97kviXT-3hj-mPkqohYwgjer1eZUEt/view?usp=drive_link | https://drive.google.com/thumbnail?id=1DE97kviXT-3hj-mPkqohYwgjer1eZUEt&sz=w1000 | https://drive.google.com/file/d/1DE97kviXT-3hj-mPkqohYwgjer1eZUEt/view?usp=drive_link
2024-08-30 | Al Shahama-Majlis-P547 | P547 | MJ-02 | 269 | 329 | 598 | 1-Excavation till Rfat Foundation Completed . 2-Pile head trimming on progress . 3-Pile Head Treatment ongoing . 4-Integrity test piles ongoing . 5-Leveling and compaction ongoing. 6. Raft PCC ongoing. 7-Disposal of Excavated Soil ongoing . 8-Gunting works ongoing . 9- Waterproofing ongoing 9- Dynamic test ongoing. | Substation Relocation. Shoring system from Secant to Continuous. Piles static load test form 8Piles to 5piles . Pile Test from Sonic to TRM . | 45.76% | 34.14% | -11.62% | 2-Substructure- Earth work up to Raft Foundation (next Monitiring Milestone) | 2024-07-30 |  | 2024-09-15 | 2024-08-30 | 1-Lifting Works ( Unsafe Lifting / Rigging ) Lack of 3rd party Inspection/ Riggers/ and the damaged rigging tackles . 2-Poor Compliance ( Using of Fall Arrest Equipment at heights) 3-Delivery of Long Lead Items ( Chillers & Generator & Air handling Unit ) 4-Delays in response regarding to blast steel doors necessary enquiries/tests /reports /simulations,……..compliance with engineer enquiries as stated via Material submission rev. 04 that that required to be attended to avoid delays in manufacturing processing 5-Contractor anticipation /repeated failed commitments found inaccurate/to be enhanced , and require Contractor action to increase the required resources to achieve anticipated productivity as committed . | 1-Apply the mandatory requirement for lifting equipment as the construction sector - OSHAD 34,.0 Safe lifting and lifting accessories. SF , increase inspection procedure, Implement the control for contractor and subcontractor. 2-Allocate sufficient nos of Fall arrest Equipment, Training and Awareness , Induction , Monitoring and apply the Risk Assessment - refer to OSHAD SF no. 23 W& H . 3-Contractor is requested to keep follow up with supplier /specialist to enable received the goods on time , and without affecting the planned delivery schedule 4-After several reminders to the Contractor , contractor advised during last progress meeting that the door specialist attended to provide the necessary certificates /tests as well , and will be issued to Engineer formally for review , and further action 5-Contractor is requested to secure all the necessary resources that should meet /cover all remaining SOW after study the productivities rate of each equipment /machines to enable provide the accurate dates of mitigation that should be attended upon enquired by Engineer /client | *Completion of Excavate Soil Till Raft Foundation *Completion of Disposal of Excavated Materials *Completion of Site Cleaning and Preparation *Completion of Pile Head Breaking . *Completion of Raft PCC works . *Completion of Steel Reinforcement for Raft Foundation Fabrication and Delivery . * Completion TRM & Dynamic test *Completion of Pile Integrity Test *Start the Screed and Raft R.FT | 85805249.48 | 0 | 85805249.48 | 3799481.4618 | 0 | 89604730.9418 | 17180863.6 | 1117487.2997 | https://drive.google.com/thumbnail?id=1LSdEMIAx0nOnLCMaT-0CJD9nxONTEfbb&sz=w1000 | https://drive.google.com/file/d/1LSdEMIAx0nOnLCMaT-0CJD9nxONTEfbb/view?usp=drive_link | https://drive.google.com/thumbnail?id=1DE97kviXT-3hj-mPkqohYwgjer1eZUEt&sz=w1000 | https://drive.google.com/file/d/1DE97kviXT-3hj-mPkqohYwgjer1eZUEt/view?usp=drive_link | https://drive.google.com/thumbnail?id=1DE97kviXT-3hj-mPkqohYwgjer1eZUEt&sz=w1000 | https://drive.google.com/file/d/1DE97kviXT-3hj-mPkqohYwgjer1eZUEt/view?usp=drive_link
2024-08-30 | Al Shahama-Majlis-P547 | P547 | MJ-02 | 269 | 329 | 598 | 1-Excavation till Rfat Foundation Completed . 2-Pile head trimming on progress . 3-Pile Head Treatment ongoing . 4-Integrity test piles ongoing . 5-Leveling and compaction ongoing. 6. Raft PCC ongoing. 7-Disposal of Excavated Soil ongoing . 8-Gunting works ongoing . 9- Waterproofing ongoing 9- Dynamic test ongoing. | Substation Relocation. Shoring system from Secant to Continuous. Piles static load test form 8Piles to 5piles . Pile Test from Sonic to TRM . | 45.76% | 34.14% | -11.62% | 3-Superstructure-Basment | 2024-09-04 |  | 2024-11-20 | 2024-08-30 | 1-Lifting Works ( Unsafe Lifting / Rigging ) Lack of 3rd party Inspection/ Riggers/ and the damaged rigging tackles . 2-Poor Compliance ( Using of Fall Arrest Equipment at heights) 3-Delivery of Long Lead Items ( Chillers & Generator & Air handling Unit ) 4-Delays in response regarding to blast steel doors necessary enquiries/tests /reports /simulations,……..compliance with engineer enquiries as stated via Material submission rev. 04 that that required to be attended to avoid delays in manufacturing processing 5-Contractor anticipation /repeated failed commitments found inaccurate/to be enhanced , and require Contractor action to increase the required resources to achieve anticipated productivity as committed . | 1-Apply the mandatory requirement for lifting equipment as the construction sector - OSHAD 34,.0 Safe lifting and lifting accessories. SF , increase inspection procedure, Implement the control for contractor and subcontractor. 2-Allocate sufficient nos of Fall arrest Equipment, Training and Awareness , Induction , Monitoring and apply the Risk Assessment - refer to OSHAD SF no. 23 W& H . 3-Contractor is requested to keep follow up with supplier /specialist to enable received the goods on time , and without affecting the planned delivery schedule 4-After several reminders to the Contractor , contractor advised during last progress meeting that the door specialist attended to provide the necessary certificates /tests as well , and will be issued to Engineer formally for review , and further action 5-Contractor is requested to secure all the necessary resources that should meet /cover all remaining SOW after study the productivities rate of each equipment /machines to enable provide the accurate dates of mitigation that should be attended upon enquired by Engineer /client | *Completion of Excavate Soil Till Raft Foundation *Completion of Disposal of Excavated Materials *Completion of Site Cleaning and Preparation *Completion of Pile Head Breaking . *Completion of Raft PCC works . *Completion of Steel Reinforcement for Raft Foundation Fabrication and Delivery . * Completion TRM & Dynamic test *Completion of Pile Integrity Test *Start the Screed and Raft R.FT | 85805249.48 | 0 | 85805249.48 | 3799481.4618 | 0 | 89604730.9418 | 17180863.6 | 1117487.2997 | https://drive.google.com/thumbnail?id=1LSdEMIAx0nOnLCMaT-0CJD9nxONTEfbb&sz=w1000 | https://drive.google.com/file/d/1LSdEMIAx0nOnLCMaT-0CJD9nxONTEfbb/view?usp=drive_link | https://drive.google.com/thumbnail?id=1DE97kviXT-3hj-mPkqohYwgjer1eZUEt&sz=w1000 | https://drive.google.com/file/d/1DE97kviXT-3hj-mPkqohYwgjer1eZUEt/view?usp=drive_link | https://drive.google.com/thumbnail?id=1DE97kviXT-3hj-mPkqohYwgjer1eZUEt&sz=w1000 | https://drive.google.com/file/d/1DE97kviXT-3hj-mPkqohYwgjer1eZUEt/view?usp=drive_link
2024-08-30 | Al Shahama-Majlis-P547 | P547 | MJ-02 | 269 | 329 | 598 | 1-Excavation till Rfat Foundation Completed . 2-Pile head trimming on progress . 3-Pile Head Treatment ongoing . 4-Integrity test piles ongoing . 5-Leveling and compaction ongoing. 6. Raft PCC ongoing. 7-Disposal of Excavated Soil ongoing . 8-Gunting works ongoing . 9- Waterproofing ongoing 9- Dynamic test ongoing. | Substation Relocation. Shoring system from Secant to Continuous. Piles static load test form 8Piles to 5piles . Pile Test from Sonic to TRM . | 45.76% | 34.14% | -11.62% | 4-Superstructure-Majlis | 2025-07-18 |  | 2025-07-18 | 2024-08-30 | 1-Lifting Works ( Unsafe Lifting / Rigging ) Lack of 3rd party Inspection/ Riggers/ and the damaged rigging tackles . 2-Poor Compliance ( Using of Fall Arrest Equipment at heights) 3-Delivery of Long Lead Items ( Chillers & Generator & Air handling Unit ) 4-Delays in response regarding to blast steel doors necessary enquiries/tests /reports /simulations,……..compliance with engineer enquiries as stated via Material submission rev. 04 that that required to be attended to avoid delays in manufacturing processing 5-Contractor anticipation /repeated failed commitments found inaccurate/to be enhanced , and require Contractor action to increase the required resources to achieve anticipated productivity as committed . | 1-Apply the mandatory requirement for lifting equipment as the construction sector - OSHAD 34,.0 Safe lifting and lifting accessories. SF , increase inspection procedure, Implement the control for contractor and subcontractor. 2-Allocate sufficient nos of Fall arrest Equipment, Training and Awareness , Induction , Monitoring and apply the Risk Assessment - refer to OSHAD SF no. 23 W& H . 3-Contractor is requested to keep follow up with supplier /specialist to enable received the goods on time , and without affecting the planned delivery schedule 4-After several reminders to the Contractor , contractor advised during last progress meeting that the door specialist attended to provide the necessary certificates /tests as well , and will be issued to Engineer formally for review , and further action 5-Contractor is requested to secure all the necessary resources that should meet /cover all remaining SOW after study the productivities rate of each equipment /machines to enable provide the accurate dates of mitigation that should be attended upon enquired by Engineer /client | *Completion of Excavate Soil Till Raft Foundation *Completion of Disposal of Excavated Materials *Completion of Site Cleaning and Preparation *Completion of Pile Head Breaking . *Completion of Raft PCC works . *Completion of Steel Reinforcement for Raft Foundation Fabrication and Delivery . * Completion TRM & Dynamic test *Completion of Pile Integrity Test *Start the Screed and Raft R.FT | 85805249.48 | 0 | 85805249.48 | 3799481.4618 | 0 | 89604730.9418 | 17180863.6 | 1117487.2997 | https://drive.google.com/thumbnail?id=1LSdEMIAx0nOnLCMaT-0CJD9nxONTEfbb&sz=w1000 | https://drive.google.com/file/d/1LSdEMIAx0nOnLCMaT-0CJD9nxONTEfbb/view?usp=drive_link | https://drive.google.com/thumbnail?id=1DE97kviXT-3hj-mPkqohYwgjer1eZUEt&sz=w1000 | https://drive.google.com/file/d/1DE97kviXT-3hj-mPkqohYwgjer1eZUEt/view?usp=drive_link | https://drive.google.com/thumbnail?id=1DE97kviXT-3hj-mPkqohYwgjer1eZUEt&sz=w1000 | https://drive.google.com/file/d/1DE97kviXT-3hj-mPkqohYwgjer1eZUEt/view?usp=drive_link
2024-08-30 | Al Shahama-Majlis-P547 | P547 | MJ-02 | 269 | 329 | 598 | 1-Excavation till Rfat Foundation Completed . 2-Pile head trimming on progress . 3-Pile Head Treatment ongoing . 4-Integrity test piles ongoing . 5-Leveling and compaction ongoing. 6. Raft PCC ongoing. 7-Disposal of Excavated Soil ongoing . 8-Gunting works ongoing . 9- Waterproofing ongoing 9- Dynamic test ongoing. | Substation Relocation. Shoring system from Secant to Continuous. Piles static load test form 8Piles to 5piles . Pile Test from Sonic to TRM . | 45.76% | 34.14% | -11.62% | 5- Majlis - Power | 2025-07-23 |  | 2025-07-23 | 2024-08-30 | 1-Lifting Works ( Unsafe Lifting / Rigging ) Lack of 3rd party Inspection/ Riggers/ and the damaged rigging tackles . 2-Poor Compliance ( Using of Fall Arrest Equipment at heights) 3-Delivery of Long Lead Items ( Chillers & Generator & Air handling Unit ) 4-Delays in response regarding to blast steel doors necessary enquiries/tests /reports /simulations,……..compliance with engineer enquiries as stated via Material submission rev. 04 that that required to be attended to avoid delays in manufacturing processing 5-Contractor anticipation /repeated failed commitments found inaccurate/to be enhanced , and require Contractor action to increase the required resources to achieve anticipated productivity as committed . | 1-Apply the mandatory requirement for lifting equipment as the construction sector - OSHAD 34,.0 Safe lifting and lifting accessories. SF , increase inspection procedure, Implement the control for contractor and subcontractor. 2-Allocate sufficient nos of Fall arrest Equipment, Training and Awareness , Induction , Monitoring and apply the Risk Assessment - refer to OSHAD SF no. 23 W& H . 3-Contractor is requested to keep follow up with supplier /specialist to enable received the goods on time , and without affecting the planned delivery schedule 4-After several reminders to the Contractor , contractor advised during last progress meeting that the door specialist attended to provide the necessary certificates /tests as well , and will be issued to Engineer formally for review , and further action 5-Contractor is requested to secure all the necessary resources that should meet /cover all remaining SOW after study the productivities rate of each equipment /machines to enable provide the accurate dates of mitigation that should be attended upon enquired by Engineer /client | *Completion of Excavate Soil Till Raft Foundation *Completion of Disposal of Excavated Materials *Completion of Site Cleaning and Preparation *Completion of Pile Head Breaking . *Completion of Raft PCC works . *Completion of Steel Reinforcement for Raft Foundation Fabrication and Delivery . * Completion TRM & Dynamic test *Completion of Pile Integrity Test *Start the Screed and Raft R.FT | 85805249.48 | 0 | 85805249.48 | 3799481.4618 | 0 | 89604730.9418 | 17180863.6 | 1117487.2997 | https://drive.google.com/thumbnail?id=1LSdEMIAx0nOnLCMaT-0CJD9nxONTEfbb&sz=w1000 | https://drive.google.com/file/d/1LSdEMIAx0nOnLCMaT-0CJD9nxONTEfbb/view?usp=drive_link | https://drive.google.com/thumbnail?id=1DE97kviXT-3hj-mPkqohYwgjer1eZUEt&sz=w1000 | https://drive.google.com/file/d/1DE97kviXT-3hj-mPkqohYwgjer1eZUEt/view?usp=drive_link | https://drive.google.com/thumbnail?id=1DE97kviXT-3hj-mPkqohYwgjer1eZUEt&sz=w1000 | https://drive.google.com/file/d/1DE97kviXT-3hj-mPkqohYwgjer1eZUEt/view?usp=drive_link
2024-08-30 | Al Shahama-Majlis-P547 | P547 | MJ-02 | 269 | 329 | 598 | 1-Excavation till Rfat Foundation Completed . 2-Pile head trimming on progress . 3-Pile Head Treatment ongoing . 4-Integrity test piles ongoing . 5-Leveling and compaction ongoing. 6. Raft PCC ongoing. 7-Disposal of Excavated Soil ongoing . 8-Gunting works ongoing . 9- Waterproofing ongoing 9- Dynamic test ongoing. | Substation Relocation. Shoring system from Secant to Continuous. Piles static load test form 8Piles to 5piles . Pile Test from Sonic to TRM . | 45.76% | 34.14% | -11.62% | 6- Project Finsh date ( Contractual Milestone ) | 2025-07-30 |  | 2025-07-24 | 2024-08-30 | 1-Lifting Works ( Unsafe Lifting / Rigging ) Lack of 3rd party Inspection/ Riggers/ and the damaged rigging tackles . 2-Poor Compliance ( Using of Fall Arrest Equipment at heights) 3-Delivery of Long Lead Items ( Chillers & Generator & Air handling Unit ) 4-Delays in response regarding to blast steel doors necessary enquiries/tests /reports /simulations,……..compliance with engineer enquiries as stated via Material submission rev. 04 that that required to be attended to avoid delays in manufacturing processing 5-Contractor anticipation /repeated failed commitments found inaccurate/to be enhanced , and require Contractor action to increase the required resources to achieve anticipated productivity as committed . | 1-Apply the mandatory requirement for lifting equipment as the construction sector - OSHAD 34,.0 Safe lifting and lifting accessories. SF , increase inspection procedure, Implement the control for contractor and subcontractor. 2-Allocate sufficient nos of Fall arrest Equipment, Training and Awareness , Induction , Monitoring and apply the Risk Assessment - refer to OSHAD SF no. 23 W& H . 3-Contractor is requested to keep follow up with supplier /specialist to enable received the goods on time , and without affecting the planned delivery schedule 4-After several reminders to the Contractor , contractor advised during last progress meeting that the door specialist attended to provide the necessary certificates /tests as well , and will be issued to Engineer formally for review , and further action 5-Contractor is requested to secure all the necessary resources that should meet /cover all remaining SOW after study the productivities rate of each equipment /machines to enable provide the accurate dates of mitigation that should be attended upon enquired by Engineer /client | *Completion of Excavate Soil Till Raft Foundation *Completion of Disposal of Excavated Materials *Completion of Site Cleaning and Preparation *Completion of Pile Head Breaking . *Completion of Raft PCC works . *Completion of Steel Reinforcement for Raft Foundation Fabrication and Delivery . * Completion TRM & Dynamic test *Completion of Pile Integrity Test *Start the Screed and Raft R.FT | 85805249.48 | 0 | 85805249.48 | 3799481.4618 | 0 | 89604730.9418 | 17180863.6 | 1117487.2997 | https://drive.google.com/thumbnail?id=1LSdEMIAx0nOnLCMaT-0CJD9nxONTEfbb&sz=w1000 | https://drive.google.com/file/d/1LSdEMIAx0nOnLCMaT-0CJD9nxONTEfbb/view?usp=drive_link | https://drive.google.com/thumbnail?id=1DE97kviXT-3hj-mPkqohYwgjer1eZUEt&sz=w1000 | https://drive.google.com/file/d/1DE97kviXT-3hj-mPkqohYwgjer1eZUEt/view?usp=drive_link | https://drive.google.com/thumbnail?id=1DE97kviXT-3hj-mPkqohYwgjer1eZUEt&sz=w1000 | https://drive.google.com/file/d/1DE97kviXT-3hj-mPkqohYwgjer1eZUEt/view?usp=drive_link
2024-08-30 | Mohamed Bin Zayed City -Majlis-P19 | P19 | MJ-03 | 269 | 329 | 598 | *Piles Shoring Completed *Breaking of Shoring Head piles ongoing. -Breaking of Guide wall on going . -Casted of Main Piles on going -Dewatering Installation (8 nos pipes). -Relocation Services ongoing. | As the recommendation from project's Engineer, Engineer have identified the need for an additional construction team by the contractor . | 45.73% | 21.41% | -24.32% | Notice to Commence | 2023-12-05 | 2023-12-05 |  | 2024-08-30 | 1-Lifting Works ( Unsafe Lifting / Rigging ) Lack of 3rd party Inspection/ Riggers/ and the damaged rigging tackles 2-Inadequate Handling and Storage of Compress Gases 3-Delay in work commencement of MBZ project due to delays in response from Contractor end regarding to NOC’s / Utility Relocation. 4-Delays un issuance of Clear affection plan without conditions on 29thMay 2024. 5-Delay in issuance of NOCs for MCC, Strom Water ,and Etisalat 6-The project will require night shift operations. This adjustment is essential to meet project deadlines 7-Contractor anticipation to enable work night shift (24 days ) is still not applicable at this site due to the nature of the required activities that will not be allowed at such sensitive area , and Contractor should increase the resources to enable compensate the above mentioned restriction . 8-Working adjacent to the sensitive building/area , and anticipated restriction regarding to adjacent sensitive building /area 9-Subcontractor continuance breakdown of equipment | 1-Apply the mandatory requirement for lifting equipment as the construction sector - OSHAD 34,.0 Safe lifting and lifting accessories. SF , increase inspection procedure, Implement the control for contractor and subcontractor. 2-Apply the COSHH assessment, Allocate resources for Compress gases requirements , Implement the Risk Assessment 3-Required Noc,s already obtained , and Contractor corrective action is required to allocate additional resources to overcome /compensate the occurred delays 4-After Client support Clear affection plsn issued without any restriction 5-Storm water removed from site properties , and other services already relocated /removed 6-Due to the natur of the MBZ Area noght shify is not possible , however Contractor can compensate the same by allocating additional resources /equipment 7-Contractor notified by the same , and instructed to focus to increase the required resources to expedite the progress 8-Contractor currently liasing with Authorities to enable have special permit from ADM /levant Authorities to increase working time as possible 9-Contractor conduct several meetings with Piling subcontractor to secure /replace all existing equipment that are in bad condition to be replaced by other equipment that can continue piing work without stoppage that currently continuance breakdown /in bad condition | Relocation Services. -Complete the Main Piles. -Complete the Guide wall and shoring pile head breaking. -Start of Capping Beams and Struts activities | 78195477.46 | 0 | 78195477.46 | 3462518.5382 | 0 | 81657995.9982 | 4774958.11 | 1018381.2003 | https://drive.google.com/thumbnail?id=1-uqOeguQnsVTKjN4CUm_DKAjRsf3GvNl&sz=w1000 | https://drive.google.com/file/d/1-uqOeguQnsVTKjN4CUm_DKAjRsf3GvNl/view?usp=drive_link | https://drive.google.com/thumbnail?id=1eSxlhhtsJOyik_7Sfm5xJHDz0O_y42HO&sz=w1000 | https://drive.google.com/file/d/1eSxlhhtsJOyik_7Sfm5xJHDz0O_y42HO/view?usp=drive_link | https://drive.google.com/thumbnail?id=1mdyrvDZwnHDAJR9GoBxTgVEGuoFOKVP7&sz=w1000 | https://drive.google.com/file/d/1mdyrvDZwnHDAJR9GoBxTgVEGuoFOKVP7/view?usp=drive_link
2024-08-30 | Mohamed Bin Zayed City -Majlis-P19 | P19 | MJ-03 | 269 | 329 | 598 | *Piles Shoring Completed *Breaking of Shoring Head piles ongoing. -Breaking of Guide wall on going . -Casted of Main Piles on going -Dewatering Installation (8 nos pipes). -Relocation Services ongoing. | As the recommendation from project's Engineer, Engineer have identified the need for an additional construction team by the contractor . | 45.73% | 21.41% | -24.32% | Complation Mainpiles (next Monitiring Milestone) | 2024-07-30 |  | 2024-09-20 | 2024-08-30 | 1-Lifting Works ( Unsafe Lifting / Rigging ) Lack of 3rd party Inspection/ Riggers/ and the damaged rigging tackles 2-Inadequate Handling and Storage of Compress Gases 3-Delay in work commencement of MBZ project due to delays in response from Contractor end regarding to NOC’s / Utility Relocation. 4-Delays un issuance of Clear affection plan without conditions on 29thMay 2024. 5-Delay in issuance of NOCs for MCC, Strom Water ,and Etisalat 6-The project will require night shift operations. This adjustment is essential to meet project deadlines 7-Contractor anticipation to enable work night shift (24 days ) is still not applicable at this site due to the nature of the required activities that will not be allowed at such sensitive area , and Contractor should increase the resources to enable compensate the above mentioned restriction . 8-Working adjacent to the sensitive building/area , and anticipated restriction regarding to adjacent sensitive building /area 9-Subcontractor continuance breakdown of equipment | 1-Apply the mandatory requirement for lifting equipment as the construction sector - OSHAD 34,.0 Safe lifting and lifting accessories. SF , increase inspection procedure, Implement the control for contractor and subcontractor. 2-Apply the COSHH assessment, Allocate resources for Compress gases requirements , Implement the Risk Assessment 3-Required Noc,s already obtained , and Contractor corrective action is required to allocate additional resources to overcome /compensate the occurred delays 4-After Client support Clear affection plsn issued without any restriction 5-Storm water removed from site properties , and other services already relocated /removed 6-Due to the natur of the MBZ Area noght shify is not possible , however Contractor can compensate the same by allocating additional resources /equipment 7-Contractor notified by the same , and instructed to focus to increase the required resources to expedite the progress 8-Contractor currently liasing with Authorities to enable have special permit from ADM /levant Authorities to increase working time as possible 9-Contractor conduct several meetings with Piling subcontractor to secure /replace all existing equipment that are in bad condition to be replaced by other equipment that can continue piing work without stoppage that currently continuance breakdown /in bad condition | Relocation Services. -Complete the Main Piles. -Complete the Guide wall and shoring pile head breaking. -Start of Capping Beams and Struts activities | 78195477.46 | 0 | 78195477.46 | 3462518.5382 | 0 | 81657995.9982 | 4774958.11 | 1018381.2003 | https://drive.google.com/thumbnail?id=1-uqOeguQnsVTKjN4CUm_DKAjRsf3GvNl&sz=w1000 | https://drive.google.com/file/d/1-uqOeguQnsVTKjN4CUm_DKAjRsf3GvNl/view?usp=drive_link | https://drive.google.com/thumbnail?id=1eSxlhhtsJOyik_7Sfm5xJHDz0O_y42HO&sz=w1000 | https://drive.google.com/file/d/1eSxlhhtsJOyik_7Sfm5xJHDz0O_y42HO/view?usp=drive_link | https://drive.google.com/thumbnail?id=1mdyrvDZwnHDAJR9GoBxTgVEGuoFOKVP7&sz=w1000 | https://drive.google.com/file/d/1mdyrvDZwnHDAJR9GoBxTgVEGuoFOKVP7/view?usp=drive_link
2024-08-30 | Mohamed Bin Zayed City -Majlis-P19 | P19 | MJ-03 | 269 | 329 | 598 | *Piles Shoring Completed *Breaking of Shoring Head piles ongoing. -Breaking of Guide wall on going . -Casted of Main Piles on going -Dewatering Installation (8 nos pipes). -Relocation Services ongoing. | As the recommendation from project's Engineer, Engineer have identified the need for an additional construction team by the contractor . | 45.73% | 21.41% | -24.32% | Superstructure-Basment | 2025-07-19 |  | 2025-11-20 | 2024-08-30 | 1-Lifting Works ( Unsafe Lifting / Rigging ) Lack of 3rd party Inspection/ Riggers/ and the damaged rigging tackles 2-Inadequate Handling and Storage of Compress Gases 3-Delay in work commencement of MBZ project due to delays in response from Contractor end regarding to NOC’s / Utility Relocation. 4-Delays un issuance of Clear affection plan without conditions on 29thMay 2024. 5-Delay in issuance of NOCs for MCC, Strom Water ,and Etisalat 6-The project will require night shift operations. This adjustment is essential to meet project deadlines 7-Contractor anticipation to enable work night shift (24 days ) is still not applicable at this site due to the nature of the required activities that will not be allowed at such sensitive area , and Contractor should increase the resources to enable compensate the above mentioned restriction . 8-Working adjacent to the sensitive building/area , and anticipated restriction regarding to adjacent sensitive building /area 9-Subcontractor continuance breakdown of equipment | 1-Apply the mandatory requirement for lifting equipment as the construction sector - OSHAD 34,.0 Safe lifting and lifting accessories. SF , increase inspection procedure, Implement the control for contractor and subcontractor. 2-Apply the COSHH assessment, Allocate resources for Compress gases requirements , Implement the Risk Assessment 3-Required Noc,s already obtained , and Contractor corrective action is required to allocate additional resources to overcome /compensate the occurred delays 4-After Client support Clear affection plsn issued without any restriction 5-Storm water removed from site properties , and other services already relocated /removed 6-Due to the natur of the MBZ Area noght shify is not possible , however Contractor can compensate the same by allocating additional resources /equipment 7-Contractor notified by the same , and instructed to focus to increase the required resources to expedite the progress 8-Contractor currently liasing with Authorities to enable have special permit from ADM /levant Authorities to increase working time as possible 9-Contractor conduct several meetings with Piling subcontractor to secure /replace all existing equipment that are in bad condition to be replaced by other equipment that can continue piing work without stoppage that currently continuance breakdown /in bad condition | Relocation Services. -Complete the Main Piles. -Complete the Guide wall and shoring pile head breaking. -Start of Capping Beams and Struts activities | 78195477.46 | 0 | 78195477.46 | 3462518.5382 | 0 | 81657995.9982 | 4774958.11 | 1018381.2003 | https://drive.google.com/thumbnail?id=1-uqOeguQnsVTKjN4CUm_DKAjRsf3GvNl&sz=w1000 | https://drive.google.com/file/d/1-uqOeguQnsVTKjN4CUm_DKAjRsf3GvNl/view?usp=drive_link | https://drive.google.com/thumbnail?id=1eSxlhhtsJOyik_7Sfm5xJHDz0O_y42HO&sz=w1000 | https://drive.google.com/file/d/1eSxlhhtsJOyik_7Sfm5xJHDz0O_y42HO/view?usp=drive_link | https://drive.google.com/thumbnail?id=1mdyrvDZwnHDAJR9GoBxTgVEGuoFOKVP7&sz=w1000 | https://drive.google.com/file/d/1mdyrvDZwnHDAJR9GoBxTgVEGuoFOKVP7/view?usp=drive_link
2024-08-30 | Mohamed Bin Zayed City -Majlis-P19 | P19 | MJ-03 | 269 | 329 | 598 | *Piles Shoring Completed *Breaking of Shoring Head piles ongoing. -Breaking of Guide wall on going . -Casted of Main Piles on going -Dewatering Installation (8 nos pipes). -Relocation Services ongoing. | As the recommendation from project's Engineer, Engineer have identified the need for an additional construction team by the contractor . | 45.73% | 21.41% | -24.32% | Superstructure-Majlis | 2025-07-24 |  | 2025-12-20 | 2024-08-30 | 1-Lifting Works ( Unsafe Lifting / Rigging ) Lack of 3rd party Inspection/ Riggers/ and the damaged rigging tackles 2-Inadequate Handling and Storage of Compress Gases 3-Delay in work commencement of MBZ project due to delays in response from Contractor end regarding to NOC’s / Utility Relocation. 4-Delays un issuance of Clear affection plan without conditions on 29thMay 2024. 5-Delay in issuance of NOCs for MCC, Strom Water ,and Etisalat 6-The project will require night shift operations. This adjustment is essential to meet project deadlines 7-Contractor anticipation to enable work night shift (24 days ) is still not applicable at this site due to the nature of the required activities that will not be allowed at such sensitive area , and Contractor should increase the resources to enable compensate the above mentioned restriction . 8-Working adjacent to the sensitive building/area , and anticipated restriction regarding to adjacent sensitive building /area 9-Subcontractor continuance breakdown of equipment | 1-Apply the mandatory requirement for lifting equipment as the construction sector - OSHAD 34,.0 Safe lifting and lifting accessories. SF , increase inspection procedure, Implement the control for contractor and subcontractor. 2-Apply the COSHH assessment, Allocate resources for Compress gases requirements , Implement the Risk Assessment 3-Required Noc,s already obtained , and Contractor corrective action is required to allocate additional resources to overcome /compensate the occurred delays 4-After Client support Clear affection plsn issued without any restriction 5-Storm water removed from site properties , and other services already relocated /removed 6-Due to the natur of the MBZ Area noght shify is not possible , however Contractor can compensate the same by allocating additional resources /equipment 7-Contractor notified by the same , and instructed to focus to increase the required resources to expedite the progress 8-Contractor currently liasing with Authorities to enable have special permit from ADM /levant Authorities to increase working time as possible 9-Contractor conduct several meetings with Piling subcontractor to secure /replace all existing equipment that are in bad condition to be replaced by other equipment that can continue piing work without stoppage that currently continuance breakdown /in bad condition | Relocation Services. -Complete the Main Piles. -Complete the Guide wall and shoring pile head breaking. -Start of Capping Beams and Struts activities | 78195477.46 | 0 | 78195477.46 | 3462518.5382 | 0 | 81657995.9982 | 4774958.11 | 1018381.2003 | https://drive.google.com/thumbnail?id=1-uqOeguQnsVTKjN4CUm_DKAjRsf3GvNl&sz=w1000 | https://drive.google.com/file/d/1-uqOeguQnsVTKjN4CUm_DKAjRsf3GvNl/view?usp=drive_link | https://drive.google.com/thumbnail?id=1eSxlhhtsJOyik_7Sfm5xJHDz0O_y42HO&sz=w1000 | https://drive.google.com/file/d/1eSxlhhtsJOyik_7Sfm5xJHDz0O_y42HO/view?usp=drive_link | https://drive.google.com/thumbnail?id=1mdyrvDZwnHDAJR9GoBxTgVEGuoFOKVP7&sz=w1000 | https://drive.google.com/file/d/1mdyrvDZwnHDAJR9GoBxTgVEGuoFOKVP7/view?usp=drive_link
2024-08-30 | Mohamed Bin Zayed City -Majlis-P19 | P19 | MJ-03 | 269 | 329 | 598 | *Piles Shoring Completed *Breaking of Shoring Head piles ongoing. -Breaking of Guide wall on going . -Casted of Main Piles on going -Dewatering Installation (8 nos pipes). -Relocation Services ongoing. | As the recommendation from project's Engineer, Engineer have identified the need for an additional construction team by the contractor . | 45.73% | 21.41% | -24.32% | Majlis - Power | 2025-07-24 |  | 2025-12-20 | 2024-08-30 | 1-Lifting Works ( Unsafe Lifting / Rigging ) Lack of 3rd party Inspection/ Riggers/ and the damaged rigging tackles 2-Inadequate Handling and Storage of Compress Gases 3-Delay in work commencement of MBZ project due to delays in response from Contractor end regarding to NOC’s / Utility Relocation. 4-Delays un issuance of Clear affection plan without conditions on 29thMay 2024. 5-Delay in issuance of NOCs for MCC, Strom Water ,and Etisalat 6-The project will require night shift operations. This adjustment is essential to meet project deadlines 7-Contractor anticipation to enable work night shift (24 days ) is still not applicable at this site due to the nature of the required activities that will not be allowed at such sensitive area , and Contractor should increase the resources to enable compensate the above mentioned restriction . 8-Working adjacent to the sensitive building/area , and anticipated restriction regarding to adjacent sensitive building /area 9-Subcontractor continuance breakdown of equipment | 1-Apply the mandatory requirement for lifting equipment as the construction sector - OSHAD 34,.0 Safe lifting and lifting accessories. SF , increase inspection procedure, Implement the control for contractor and subcontractor. 2-Apply the COSHH assessment, Allocate resources for Compress gases requirements , Implement the Risk Assessment 3-Required Noc,s already obtained , and Contractor corrective action is required to allocate additional resources to overcome /compensate the occurred delays 4-After Client support Clear affection plsn issued without any restriction 5-Storm water removed from site properties , and other services already relocated /removed 6-Due to the natur of the MBZ Area noght shify is not possible , however Contractor can compensate the same by allocating additional resources /equipment 7-Contractor notified by the same , and instructed to focus to increase the required resources to expedite the progress 8-Contractor currently liasing with Authorities to enable have special permit from ADM /levant Authorities to increase working time as possible 9-Contractor conduct several meetings with Piling subcontractor to secure /replace all existing equipment that are in bad condition to be replaced by other equipment that can continue piing work without stoppage that currently continuance breakdown /in bad condition | Relocation Services. -Complete the Main Piles. -Complete the Guide wall and shoring pile head breaking. -Start of Capping Beams and Struts activities | 78195477.46 | 0 | 78195477.46 | 3462518.5382 | 0 | 81657995.9982 | 4774958.11 | 1018381.2003 | https://drive.google.com/thumbnail?id=1-uqOeguQnsVTKjN4CUm_DKAjRsf3GvNl&sz=w1000 | https://drive.google.com/file/d/1-uqOeguQnsVTKjN4CUm_DKAjRsf3GvNl/view?usp=drive_link | https://drive.google.com/thumbnail?id=1eSxlhhtsJOyik_7Sfm5xJHDz0O_y42HO&sz=w1000 | https://drive.google.com/file/d/1eSxlhhtsJOyik_7Sfm5xJHDz0O_y42HO/view?usp=drive_link | https://drive.google.com/thumbnail?id=1mdyrvDZwnHDAJR9GoBxTgVEGuoFOKVP7&sz=w1000 | https://drive.google.com/file/d/1mdyrvDZwnHDAJR9GoBxTgVEGuoFOKVP7/view?usp=drive_link
2024-08-30 | Mohamed Bin Zayed City -Majlis-P19 | P19 | MJ-03 | 269 | 329 | 598 | *Piles Shoring Completed *Breaking of Shoring Head piles ongoing. -Breaking of Guide wall on going . -Casted of Main Piles on going -Dewatering Installation (8 nos pipes). -Relocation Services ongoing. | As the recommendation from project's Engineer, Engineer have identified the need for an additional construction team by the contractor . | 45.73% | 21.41% | -24.32% | Project Finsh date ( Contractual Milestone ) | 2025-07-24 |  | 2025-12-24 | 2024-08-30 | 1-Lifting Works ( Unsafe Lifting / Rigging ) Lack of 3rd party Inspection/ Riggers/ and the damaged rigging tackles 2-Inadequate Handling and Storage of Compress Gases 3-Delay in work commencement of MBZ project due to delays in response from Contractor end regarding to NOC’s / Utility Relocation. 4-Delays un issuance of Clear affection plan without conditions on 29thMay 2024. 5-Delay in issuance of NOCs for MCC, Strom Water ,and Etisalat 6-The project will require night shift operations. This adjustment is essential to meet project deadlines 7-Contractor anticipation to enable work night shift (24 days ) is still not applicable at this site due to the nature of the required activities that will not be allowed at such sensitive area , and Contractor should increase the resources to enable compensate the above mentioned restriction . 8-Working adjacent to the sensitive building/area , and anticipated restriction regarding to adjacent sensitive building /area 9-Subcontractor continuance breakdown of equipment | 1-Apply the mandatory requirement for lifting equipment as the construction sector - OSHAD 34,.0 Safe lifting and lifting accessories. SF , increase inspection procedure, Implement the control for contractor and subcontractor. 2-Apply the COSHH assessment, Allocate resources for Compress gases requirements , Implement the Risk Assessment 3-Required Noc,s already obtained , and Contractor corrective action is required to allocate additional resources to overcome /compensate the occurred delays 4-After Client support Clear affection plsn issued without any restriction 5-Storm water removed from site properties , and other services already relocated /removed 6-Due to the natur of the MBZ Area noght shify is not possible , however Contractor can compensate the same by allocating additional resources /equipment 7-Contractor notified by the same , and instructed to focus to increase the required resources to expedite the progress 8-Contractor currently liasing with Authorities to enable have special permit from ADM /levant Authorities to increase working time as possible 9-Contractor conduct several meetings with Piling subcontractor to secure /replace all existing equipment that are in bad condition to be replaced by other equipment that can continue piing work without stoppage that currently continuance breakdown /in bad condition | Relocation Services. -Complete the Main Piles. -Complete the Guide wall and shoring pile head breaking. -Start of Capping Beams and Struts activities | 78195477.46 | 0 | 78195477.46 | 3462518.5382 | 0 | 81657995.9982 | 4774958.11 | 1018381.2003 | https://drive.google.com/thumbnail?id=1-uqOeguQnsVTKjN4CUm_DKAjRsf3GvNl&sz=w1000 | https://drive.google.com/file/d/1-uqOeguQnsVTKjN4CUm_DKAjRsf3GvNl/view?usp=drive_link | https://drive.google.com/thumbnail?id=1eSxlhhtsJOyik_7Sfm5xJHDz0O_y42HO&sz=w1000 | https://drive.google.com/file/d/1eSxlhhtsJOyik_7Sfm5xJHDz0O_y42HO/view?usp=drive_link | https://drive.google.com/thumbnail?id=1mdyrvDZwnHDAJR9GoBxTgVEGuoFOKVP7&sz=w1000 | https://drive.google.com/file/d/1mdyrvDZwnHDAJR9GoBxTgVEGuoFOKVP7/view?usp=drive_link
2024-08-30 | Al Shahama-Majlis-P547 | P547 | MJ-02 | 276 | 322 | 598 | 1-Excavation till Rfat Foundation Completed . 2-Pile head trimming on progress . 3-Pile Head Treatment ongoing . 4-Integrity test piles ongoing . 5-Leveling and compaction ongoing. 6. Raft PCC ongoing. 7-Disposal of Excavated Soil ongoing . 8-Gunting works ongoing . 9- Waterproofing ongoing 9- Dynamic test ongoing. 10-TRM test ongoing . | Substation Relocation. Shoring system from Secant to Continuous. Reduce the number of Piles static load test form 8Piles to 5piles . Pile Test from Sonic to TRM . | 46.11% | 36.8% | -9.31% | 1-Notice to Commence ( Contractual Milestone ) | 2023-12-05 | 2023-12-05 |  | 2024-09-05 | 1-Lifting Works ( Unsafe Lifting / Rigging ) Lack of 3rd party Inspection/ Riggers/ and the damaged rigging tackles . 2-Poor Compliance ( Using of Fall Arrest Equipment at heights) 3-Delivery of Long Lead Items ( Chillers & Generator & Air handling Unit ) 4-Delays in response regarding to blast steel doors necessary enquiries/tests /reports /simulations,……..compliance with engineer enquiries as stated via Material submission rev. 04 that that required to be attended to avoid delays in manufacturing processing 5-Contractor anticipation /repeated failed commitments found inaccurate/to be enhanced , and require Contractor action to increase the required resources to achieve anticipated productivity as committed . | 1-Apply the mandatory requirement for lifting equipment as the construction sector - OSHAD 34,.0 Safe lifting and lifting accessories. SF , increase inspection procedure, Implement the control for contractor and subcontractor. 2-Allocate sufficient nos of Fall arrest Equipment, Training and Awareness , Induction , Monitoring and apply the Risk Assessment - refer to OSHAD SF no. 23 W& H . 3-Contractor is requested to keep follow up with supplier /specialist to enable received the goods on time , and without affecting the planned delivery schedule 4-After several reminders to the Contractor , contractor advised during last progress meeting that the door specialist attended to provide the necessary certificates /tests as well , and will be issued to Engineer formally for review , and further action 5-Contractor is requested to secure all the necessary resources that should meet /cover all remaining SOW after study the productivities rate of each equipment /machines to enable provide the accurate dates of mitigation that should be attended upon enquired by Engineer /client | *Completion of Excavate Soil Till Raft Foundation *Completion of Disposal of Excavated Materials *Completion of Site Cleaning and Preparation *Completion of Pile Head Breaking . *Completion of Raft PCC works . *Completion of Steel Reinforcement for Raft Foundation Fabrication and Delivery . * Completion TRM & Dynamic test *Completion of Pile Integrity Test *Completion the Screed and Raft R.FT *Completion of Raft Steel works . * Start of Starter bar for columns and walls | 85805249.48 | 0 | 85805249.48 | 3799480.4618 | 0 | 89604729.9418 | 17180863.6 | 1117486.2997 | https://drive.google.com/thumbnail?id=1HbIMSG327H4IroIIbzG-UoNFRHW9d4tq&sz=w1000 | https://drive.google.com/file/d/1HbIMSG327H4IroIIbzG-UoNFRHW9d4tq/view?usp=drive_link | https://drive.google.com/thumbnail?id=1j2tLIzNNUoZkZ243oPB10Uwaw2b3_A58&sz=w1000 | https://drive.google.com/file/d/1j2tLIzNNUoZkZ243oPB10Uwaw2b3_A58/view?usp=drive_link | https://drive.google.com/thumbnail?id=1j2tLIzNNUoZkZ243oPB10Uwaw2b3_A58&sz=w1000 | https://drive.google.com/file/d/1j2tLIzNNUoZkZ243oPB10Uwaw2b3_A58/view?usp=drive_link
2024-08-30 | Al Shahama-Majlis-P547 | P547 | MJ-02 | 276 | 322 | 598 | 1-Excavation till Rfat Foundation Completed . 2-Pile head trimming on progress . 3-Pile Head Treatment ongoing . 4-Integrity test piles ongoing . 5-Leveling and compaction ongoing. 6. Raft PCC ongoing. 7-Disposal of Excavated Soil ongoing . 8-Gunting works ongoing . 9- Waterproofing ongoing 9- Dynamic test ongoing. | Substation Relocation. Shoring system from Secant to Continuous. Piles static load test form 8Piles to 5piles . Pile Test from Sonic to TRM . | 46.11% | 36.8% | -9.31% | 2-Substructure- Earth work up to Raft Foundation (next Monitiring Milestone) | 2024-07-30 |  | 2024-09-20 | 2024-09-05 | 1-Lifting Works ( Unsafe Lifting / Rigging ) Lack of 3rd party Inspection/ Riggers/ and the damaged rigging tackles . 2-Poor Compliance ( Using of Fall Arrest Equipment at heights) 3-Delivery of Long Lead Items ( Chillers & Generator & Air handling Unit ) 4-Delays in response regarding to blast steel doors necessary enquiries/tests /reports /simulations,……..compliance with engineer enquiries as stated via Material submission rev. 04 that that required to be attended to avoid delays in manufacturing processing 5-Contractor anticipation /repeated failed commitments found inaccurate/to be enhanced , and require Contractor action to increase the required resources to achieve anticipated productivity as committed . | 1-Apply the mandatory requirement for lifting equipment as the construction sector - OSHAD 34,.0 Safe lifting and lifting accessories. SF , increase inspection procedure, Implement the control for contractor and subcontractor. 2-Allocate sufficient nos of Fall arrest Equipment, Training and Awareness , Induction , Monitoring and apply the Risk Assessment - refer to OSHAD SF no. 23 W& H . 3-Contractor is requested to keep follow up with supplier /specialist to enable received the goods on time , and without affecting the planned delivery schedule 4-After several reminders to the Contractor , contractor advised during last progress meeting that the door specialist attended to provide the necessary certificates /tests as well , and will be issued to Engineer formally for review , and further action 5-Contractor is requested to secure all the necessary resources that should meet /cover all remaining SOW after study the productivities rate of each equipment /machines to enable provide the accurate dates of mitigation that should be attended upon enquired by Engineer /client | *Completion of Excavate Soil Till Raft Foundation *Completion of Disposal of Excavated Materials *Completion of Site Cleaning and Preparation *Completion of Pile Head Breaking . *Completion of Raft PCC works . *Completion of Steel Reinforcement for Raft Foundation Fabrication and Delivery . * Completion TRM & Dynamic test *Completion of Pile Integrity Test *Completion the Screed and Raft R.FT *Completion of Raft Steel works . * Start of Starter bar for columns and walls | 85805249.48 | 0 | 85805249.48 | 3799481.4618 | 0 | 89604730.9418 | 17180863.6 | 1117487.2997 | https://drive.google.com/thumbnail?id=1HbIMSG327H4IroIIbzG-UoNFRHW9d4tq&sz=w1000 | https://drive.google.com/file/d/1HbIMSG327H4IroIIbzG-UoNFRHW9d4tq/view?usp=drive_link | https://drive.google.com/thumbnail?id=1j2tLIzNNUoZkZ243oPB10Uwaw2b3_A58&sz=w1000 | https://drive.google.com/file/d/1j2tLIzNNUoZkZ243oPB10Uwaw2b3_A58/view?usp=drive_link | https://drive.google.com/thumbnail?id=1j2tLIzNNUoZkZ243oPB10Uwaw2b3_A58&sz=w1000 | https://drive.google.com/file/d/1j2tLIzNNUoZkZ243oPB10Uwaw2b3_A58/view?usp=drive_link
2024-08-30 | Al Shahama-Majlis-P547 | P547 | MJ-02 | 276 | 322 | 598 | 1-Excavation till Rfat Foundation Completed . 2-Pile head trimming on progress . 3-Pile Head Treatment ongoing . 4-Integrity test piles ongoing . 5-Leveling and compaction ongoing. 6. Raft PCC ongoing. 7-Disposal of Excavated Soil ongoing . 8-Gunting works ongoing . 9- Waterproofing ongoing 9- Dynamic test ongoing. 10-TRM test ongoing . | Substation Relocation. Shoring system from Secant to Continuous. Piles static load test form 8Piles to 5piles . Pile Test from Sonic to TRM . | 46.11% | 36.8% | -9.31% | 3-Superstructure-Basment | 2024-09-04 |  | 2024-11-20 | 2024-09-05 | 1-Lifting Works ( Unsafe Lifting / Rigging ) Lack of 3rd party Inspection/ Riggers/ and the damaged rigging tackles . 2-Poor Compliance ( Using of Fall Arrest Equipment at heights) 3-Delivery of Long Lead Items ( Chillers & Generator & Air handling Unit ) 4-Delays in response regarding to blast steel doors necessary enquiries/tests /reports /simulations,……..compliance with engineer enquiries as stated via Material submission rev. 04 that that required to be attended to avoid delays in manufacturing processing 5-Contractor anticipation /repeated failed commitments found inaccurate/to be enhanced , and require Contractor action to increase the required resources to achieve anticipated productivity as committed . | 1-Apply the mandatory requirement for lifting equipment as the construction sector - OSHAD 34,.0 Safe lifting and lifting accessories. SF , increase inspection procedure, Implement the control for contractor and subcontractor. 2-Allocate sufficient nos of Fall arrest Equipment, Training and Awareness , Induction , Monitoring and apply the Risk Assessment - refer to OSHAD SF no. 23 W& H . 3-Contractor is requested to keep follow up with supplier /specialist to enable received the goods on time , and without affecting the planned delivery schedule 4-After several reminders to the Contractor , contractor advised during last progress meeting that the door specialist attended to provide the necessary certificates /tests as well , and will be issued to Engineer formally for review , and further action 5-Contractor is requested to secure all the necessary resources that should meet /cover all remaining SOW after study the productivities rate of each equipment /machines to enable provide the accurate dates of mitigation that should be attended upon enquired by Engineer /client | *Completion of Excavate Soil Till Raft Foundation *Completion of Disposal of Excavated Materials *Completion of Site Cleaning and Preparation *Completion of Pile Head Breaking . *Completion of Raft PCC works . *Completion of Steel Reinforcement for Raft Foundation Fabrication and Delivery . * Completion TRM & Dynamic test *Completion of Pile Integrity Test *Completion the Screed and Raft R.FT *Completion of Raft Steel works . * Start of Starter bar for columns and walls | 85805249.48 | 0 | 85805249.48 | 3799481.4618 | 0 | 89604730.9418 | 17180863.6 | 1117487.2997 | https://drive.google.com/thumbnail?id=1HbIMSG327H4IroIIbzG-UoNFRHW9d4tq&sz=w1000 | https://drive.google.com/file/d/1HbIMSG327H4IroIIbzG-UoNFRHW9d4tq/view?usp=drive_link | https://drive.google.com/thumbnail?id=1j2tLIzNNUoZkZ243oPB10Uwaw2b3_A58&sz=w1000 | https://drive.google.com/file/d/1j2tLIzNNUoZkZ243oPB10Uwaw2b3_A58/view?usp=drive_link | https://drive.google.com/thumbnail?id=1j2tLIzNNUoZkZ243oPB10Uwaw2b3_A58&sz=w1000 | https://drive.google.com/file/d/1j2tLIzNNUoZkZ243oPB10Uwaw2b3_A58/view?usp=drive_link
2024-08-30 | Al Shahama-Majlis-P547 | P547 | MJ-02 | 276 | 322 | 598 | 1-Excavation till Rfat Foundation Completed . 2-Pile head trimming on progress . 3-Pile Head Treatment ongoing . 4-Integrity test piles ongoing . 5-Leveling and compaction ongoing. 6. Raft PCC ongoing. 7-Disposal of Excavated Soil ongoing . 8-Gunting works ongoing . 9- Waterproofing ongoing 9- Dynamic test ongoing. 10-TRM test ongoing . | Substation Relocation. Shoring system from Secant to Continuous. Piles static load test form 8Piles to 5piles . Pile Test from Sonic to TRM . | 46.11% | 36.8% | -9.31% | 4-Superstructure-Majlis | 2025-07-18 |  | 2025-07-18 | 2024-09-05 | 1-Lifting Works ( Unsafe Lifting / Rigging ) Lack of 3rd party Inspection/ Riggers/ and the damaged rigging tackles . 2-Poor Compliance ( Using of Fall Arrest Equipment at heights) 3-Delivery of Long Lead Items ( Chillers & Generator & Air handling Unit ) 4-Delays in response regarding to blast steel doors necessary enquiries/tests /reports /simulations,……..compliance with engineer enquiries as stated via Material submission rev. 04 that that required to be attended to avoid delays in manufacturing processing 5-Contractor anticipation /repeated failed commitments found inaccurate/to be enhanced , and require Contractor action to increase the required resources to achieve anticipated productivity as committed . | 1-Apply the mandatory requirement for lifting equipment as the construction sector - OSHAD 34,.0 Safe lifting and lifting accessories. SF , increase inspection procedure, Implement the control for contractor and subcontractor. 2-Allocate sufficient nos of Fall arrest Equipment, Training and Awareness , Induction , Monitoring and apply the Risk Assessment - refer to OSHAD SF no. 23 W& H . 3-Contractor is requested to keep follow up with supplier /specialist to enable received the goods on time , and without affecting the planned delivery schedule 4-After several reminders to the Contractor , contractor advised during last progress meeting that the door specialist attended to provide the necessary certificates /tests as well , and will be issued to Engineer formally for review , and further action 5-Contractor is requested to secure all the necessary resources that should meet /cover all remaining SOW after study the productivities rate of each equipment /machines to enable provide the accurate dates of mitigation that should be attended upon enquired by Engineer /client | *Completion of Excavate Soil Till Raft Foundation *Completion of Disposal of Excavated Materials *Completion of Site Cleaning and Preparation *Completion of Pile Head Breaking . *Completion of Raft PCC works . *Completion of Steel Reinforcement for Raft Foundation Fabrication and Delivery . * Completion TRM & Dynamic test *Completion of Pile Integrity Test *Completion the Screed and Raft R.FT *Completion of Raft Steel works . * Start of Starter bar for columns and walls | 85805249.48 | 0 | 85805249.48 | 3799481.4618 | 0 | 89604730.9418 | 17180863.6 | 1117487.2997 | https://drive.google.com/thumbnail?id=1HbIMSG327H4IroIIbzG-UoNFRHW9d4tq&sz=w1000 | https://drive.google.com/file/d/1HbIMSG327H4IroIIbzG-UoNFRHW9d4tq/view?usp=drive_link | https://drive.google.com/thumbnail?id=1j2tLIzNNUoZkZ243oPB10Uwaw2b3_A58&sz=w1000 | https://drive.google.com/file/d/1j2tLIzNNUoZkZ243oPB10Uwaw2b3_A58/view?usp=drive_link | https://drive.google.com/thumbnail?id=1j2tLIzNNUoZkZ243oPB10Uwaw2b3_A58&sz=w1000 | https://drive.google.com/file/d/1j2tLIzNNUoZkZ243oPB10Uwaw2b3_A58/view?usp=drive_link
2024-08-30 | Al Shahama-Majlis-P547 | P547 | MJ-02 | 276 | 322 | 598 | 1-Excavation till Rfat Foundation Completed . 2-Pile head trimming on progress . 3-Pile Head Treatment ongoing . 4-Integrity test piles ongoing . 5-Leveling and compaction ongoing. 6. Raft PCC ongoing. 7-Disposal of Excavated Soil ongoing . 8-Gunting works ongoing . 9- Waterproofing ongoing 9- Dynamic test ongoing. 10-TRM test ongoing . | Substation Relocation. Shoring system from Secant to Continuous. Piles static load test form 8Piles to 5piles . Pile Test from Sonic to TRM . | 46.11% | 36.8% | -9.31% | 5- Majlis - Power | 2025-07-23 |  | 2025-07-23 | 2024-09-05 | 1-Lifting Works ( Unsafe Lifting / Rigging ) Lack of 3rd party Inspection/ Riggers/ and the damaged rigging tackles . 2-Poor Compliance ( Using of Fall Arrest Equipment at heights) 3-Delivery of Long Lead Items ( Chillers & Generator & Air handling Unit ) 4-Delays in response regarding to blast steel doors necessary enquiries/tests /reports /simulations,……..compliance with engineer enquiries as stated via Material submission rev. 04 that that required to be attended to avoid delays in manufacturing processing 5-Contractor anticipation /repeated failed commitments found inaccurate/to be enhanced , and require Contractor action to increase the required resources to achieve anticipated productivity as committed . | 1-Apply the mandatory requirement for lifting equipment as the construction sector - OSHAD 34,.0 Safe lifting and lifting accessories. SF , increase inspection procedure, Implement the control for contractor and subcontractor. 2-Allocate sufficient nos of Fall arrest Equipment, Training and Awareness , Induction , Monitoring and apply the Risk Assessment - refer to OSHAD SF no. 23 W& H . 3-Contractor is requested to keep follow up with supplier /specialist to enable received the goods on time , and without affecting the planned delivery schedule 4-After several reminders to the Contractor , contractor advised during last progress meeting that the door specialist attended to provide the necessary certificates /tests as well , and will be issued to Engineer formally for review , and further action 5-Contractor is requested to secure all the necessary resources that should meet /cover all remaining SOW after study the productivities rate of each equipment /machines to enable provide the accurate dates of mitigation that should be attended upon enquired by Engineer /client | *Completion of Excavate Soil Till Raft Foundation *Completion of Disposal of Excavated Materials *Completion of Site Cleaning and Preparation *Completion of Pile Head Breaking . *Completion of Raft PCC works . *Completion of Steel Reinforcement for Raft Foundation Fabrication and Delivery . * Completion TRM & Dynamic test *Completion of Pile Integrity Test *Start the Screed and Raft R.FT | 85805249.48 | 0 | 85805249.48 | 3799481.4618 | 0 | 89604730.9418 | 17180863.6 | 1117487.2997 | https://drive.google.com/thumbnail?id=1HbIMSG327H4IroIIbzG-UoNFRHW9d4tq&sz=w1000 | https://drive.google.com/file/d/1HbIMSG327H4IroIIbzG-UoNFRHW9d4tq/view?usp=drive_link | https://drive.google.com/thumbnail?id=1j2tLIzNNUoZkZ243oPB10Uwaw2b3_A58&sz=w1000 | https://drive.google.com/file/d/1j2tLIzNNUoZkZ243oPB10Uwaw2b3_A58/view?usp=drive_link | https://drive.google.com/thumbnail?id=1j2tLIzNNUoZkZ243oPB10Uwaw2b3_A58&sz=w1000 | https://drive.google.com/file/d/1j2tLIzNNUoZkZ243oPB10Uwaw2b3_A58/view?usp=drive_link
2024-08-30 | Al Shahama-Majlis-P547 | P547 | MJ-02 | 276 | 322 | 598 | 1-Excavation till Rfat Foundation Completed . 2-Pile head trimming on progress . 3-Pile Head Treatment ongoing . 4-Integrity test piles ongoing . 5-Leveling and compaction ongoing. 6. Raft PCC ongoing. 7-Disposal of Excavated Soil ongoing . 8-Gunting works ongoing . 9- Waterproofing ongoing 9- Dynamic test ongoing. 10-TRM test ongoing . | Substation Relocation. Shoring system from Secant to Continuous. Piles static load test form 8Piles to 5piles . Pile Test from Sonic to TRM . | 46.11% | 36.8% | -9.31% | 6- Project Finsh date ( Contractual Milestone ) | 2025-07-30 |  | 2025-07-24 | 2024-09-05 | 1-Lifting Works ( Unsafe Lifting / Rigging ) Lack of 3rd party Inspection/ Riggers/ and the damaged rigging tackles . 2-Poor Compliance ( Using of Fall Arrest Equipment at heights) 3-Delivery of Long Lead Items ( Chillers & Generator & Air handling Unit ) 4-Delays in response regarding to blast steel doors necessary enquiries/tests /reports /simulations,……..compliance with engineer enquiries as stated via Material submission rev. 04 that that required to be attended to avoid delays in manufacturing processing 5-Contractor anticipation /repeated failed commitments found inaccurate/to be enhanced , and require Contractor action to increase the required resources to achieve anticipated productivity as committed . | 1-Apply the mandatory requirement for lifting equipment as the construction sector - OSHAD 34,.0 Safe lifting and lifting accessories. SF , increase inspection procedure, Implement the control for contractor and subcontractor. 2-Allocate sufficient nos of Fall arrest Equipment, Training and Awareness , Induction , Monitoring and apply the Risk Assessment - refer to OSHAD SF no. 23 W& H . 3-Contractor is requested to keep follow up with supplier /specialist to enable received the goods on time , and without affecting the planned delivery schedule 4-After several reminders to the Contractor , contractor advised during last progress meeting that the door specialist attended to provide the necessary certificates /tests as well , and will be issued to Engineer formally for review , and further action 5-Contractor is requested to secure all the necessary resources that should meet /cover all remaining SOW after study the productivities rate of each equipment /machines to enable provide the accurate dates of mitigation that should be attended upon enquired by Engineer /client | *Completion of Excavate Soil Till Raft Foundation *Completion of Disposal of Excavated Materials *Completion of Site Cleaning and Preparation *Completion of Pile Head Breaking . *Completion of Raft PCC works . *Completion of Steel Reinforcement for Raft Foundation Fabrication and Delivery . * Completion TRM & Dynamic test *Completion of Pile Integrity Test *Start the Screed and Raft R.FT | 85805249.48 | 0 | 85805249.48 | 3799481.4618 | 0 | 89604730.9418 | 17180863.6 | 1117487.2997 | https://drive.google.com/thumbnail?id=1HbIMSG327H4IroIIbzG-UoNFRHW9d4tq&sz=w1000 | https://drive.google.com/file/d/1HbIMSG327H4IroIIbzG-UoNFRHW9d4tq/view?usp=drive_link | https://drive.google.com/thumbnail?id=1j2tLIzNNUoZkZ243oPB10Uwaw2b3_A58&sz=w1000 | https://drive.google.com/file/d/1j2tLIzNNUoZkZ243oPB10Uwaw2b3_A58/view?usp=drive_link | https://drive.google.com/thumbnail?id=1j2tLIzNNUoZkZ243oPB10Uwaw2b3_A58&sz=w1000 | https://drive.google.com/file/d/1j2tLIzNNUoZkZ243oPB10Uwaw2b3_A58/view?usp=drive_link
2024-08-30 | Mohamed Bin Zayed City -Majlis-P19 | P19 | MJ-03 | 276 | 322 | 598 | *Piles Shoring Completed *Breaking of Shoring Head piles ongoing. -Breaking of Guide wall on going . -Casted of Main Piles on going -Dewatering Installation ongoing -Relocation Services ongoing. | As the recommendation from project's Engineer, Engineer have identified the need for an additional construction team by the contractor . | 45.35% | 23% | -22.35% | Notice to Commence | 2023-12-05 | 2023-12-05 |  | 2024-09-05 | 1-Lifting Works ( Unsafe Lifting / Rigging ) Lack of 3rd party Inspection/ Riggers/ and the damaged rigging tackles 2-Inadequate Handling and Storage of Compress Gases 3-Delay in work commencement of MBZ project due to delays in response from Contractor end regarding to NOC’s / Utility Relocation. 4-Delays un issuance of Clear affection plan without conditions on 29thMay 2024. 5-Delay in issuance of NOCs for MCC, Strom Water ,and Etisalat 6-The project will require night shift operations. This adjustment is essential to meet project deadlines 7-Contractor anticipation to enable work night shift (24 days ) is still not applicable at this site due to the nature of the required activities that will not be allowed at such sensitive area , and Contractor should increase the resources to enable compensate the above mentioned restriction . 8-Working adjacent to the sensitive building/area , and anticipated restriction regarding to adjacent sensitive building /area 9-Subcontractor continuance breakdown of equipment | 1-Apply the mandatory requirement for lifting equipment as the construction sector - OSHAD 34,.0 Safe lifting and lifting accessories. SF , increase inspection procedure, Implement the control for contractor and subcontractor. 2-Apply the COSHH assessment, Allocate resources for Compress gases requirements , Implement the Risk Assessment 3-Required Noc,s already obtained , and Contractor corrective action is required to allocate additional resources to overcome /compensate the occurred delays 4-After Client support Clear affection plsn issued without any restriction 5-Storm water removed from site properties , and other services already relocated /removed 6-Due to the natur of the MBZ Area noght shify is not possible , however Contractor can compensate the same by allocating additional resources /equipment 7-Contractor notified by the same , and instructed to focus to increase the required resources to expedite the progress 8-Contractor currently liasing with Authorities to enable have special permit from ADM /levant Authorities to increase working time as possible 9-Contractor conduct several meetings with Piling subcontractor to secure /replace all existing equipment that are in bad condition to be replaced by other equipment that can continue piing work without stoppage that currently continuance breakdown /in bad condition | Relocation Services. -Complete the Main Piles. -Complete the Guide wall and shoring pile head breaking. -Start of Capping Beams and Struts activities | 78195477.46 | 0 | 78195477.46 | 3462517.5382 | 0 | 81657994.9982 | 4774958.11 | 1018380.2003 | https://drive.google.com/thumbnail?id=1d7EUl2nVrW2pVWhjsLWPCnuUAtvGF_0w&sz=w1000 | https://drive.google.com/file/d/1d7EUl2nVrW2pVWhjsLWPCnuUAtvGF_0w/view?usp=drive_link | https://drive.google.com/thumbnail?id=1Mz-UnKO6rFVDA_Sts8kV4Nb6AFgcY8xZ&sz=w1000 | https://drive.google.com/file/d/1Mz-UnKO6rFVDA_Sts8kV4Nb6AFgcY8xZ/view?usp=drive_link | https://drive.google.com/thumbnail?id=1ISoQA3fZJl3c0SFy1tNoIXbnwnuAAjGb&sz=w1000 | https://drive.google.com/file/d/1ISoQA3fZJl3c0SFy1tNoIXbnwnuAAjGb/view?usp=drive_link
2024-08-30 | Mohamed Bin Zayed City -Majlis-P19 | P19 | MJ-03 | 276 | 322 | 598 | *Piles Shoring Completed *Breaking of Shoring Head piles ongoing. -Breaking of Guide wall on going . -Casted of Main Piles on going -Dewatering Installation (8 nos pipes). -Relocation Services ongoing. | As the recommendation from project's Engineer, Engineer have identified the need for an additional construction team by the contractor . | 45.35% | 23% | -22.35% | Complation Mainpiles | 2024-07-30 |  | 2024-09-20 | 2024-09-05 | 1-Lifting Works ( Unsafe Lifting / Rigging ) Lack of 3rd party Inspection/ Riggers/ and the damaged rigging tackles 2-Inadequate Handling and Storage of Compress Gases 3-Delay in work commencement of MBZ project due to delays in response from Contractor end regarding to NOC’s / Utility Relocation. 4-Delays un issuance of Clear affection plan without conditions on 29thMay 2024. 5-Delay in issuance of NOCs for MCC, Strom Water ,and Etisalat 6-The project will require night shift operations. This adjustment is essential to meet project deadlines 7-Contractor anticipation to enable work night shift (24 days ) is still not applicable at this site due to the nature of the required activities that will not be allowed at such sensitive area , and Contractor should increase the resources to enable compensate the above mentioned restriction . 8-Working adjacent to the sensitive building/area , and anticipated restriction regarding to adjacent sensitive building /area 9-Subcontractor continuance breakdown of equipment | 1-Apply the mandatory requirement for lifting equipment as the construction sector - OSHAD 34,.0 Safe lifting and lifting accessories. SF , increase inspection procedure, Implement the control for contractor and subcontractor. 2-Apply the COSHH assessment, Allocate resources for Compress gases requirements , Implement the Risk Assessment 3-Required Noc,s already obtained , and Contractor corrective action is required to allocate additional resources to overcome /compensate the occurred delays 4-After Client support Clear affection plsn issued without any restriction 5-Storm water removed from site properties , and other services already relocated /removed 6-Due to the natur of the MBZ Area noght shify is not possible , however Contractor can compensate the same by allocating additional resources /equipment 7-Contractor notified by the same , and instructed to focus to increase the required resources to expedite the progress 8-Contractor currently liasing with Authorities to enable have special permit from ADM /levant Authorities to increase working time as possible 9-Contractor conduct several meetings with Piling subcontractor to secure /replace all existing equipment that are in bad condition to be replaced by other equipment that can continue piing work without stoppage that currently continuance breakdown /in bad condition | Relocation Services. -Complete the Main Piles. -Complete the Guide wall and shoring pile head breaking. -Start of Capping Beams and Struts activities | 78195477.46 | 0 | 78195477.46 | 3462518.5382 | 0 | 81657995.9982 | 4774958.11 | 1018381.2003 | https://drive.google.com/thumbnail?id=1d7EUl2nVrW2pVWhjsLWPCnuUAtvGF_0w&sz=w1000 | https://drive.google.com/file/d/1d7EUl2nVrW2pVWhjsLWPCnuUAtvGF_0w/view?usp=drive_link | https://drive.google.com/thumbnail?id=1Mz-UnKO6rFVDA_Sts8kV4Nb6AFgcY8xZ&sz=w1000 | https://drive.google.com/file/d/1Mz-UnKO6rFVDA_Sts8kV4Nb6AFgcY8xZ/view?usp=drive_link | https://drive.google.com/thumbnail?id=1ISoQA3fZJl3c0SFy1tNoIXbnwnuAAjGb&sz=w1000 | https://drive.google.com/file/d/1ISoQA3fZJl3c0SFy1tNoIXbnwnuAAjGb/view?usp=drive_link
2024-08-30 | Mohamed Bin Zayed City -Majlis-P19 | P19 | MJ-03 | 276 | 322 | 598 | *Piles Shoring Completed *Breaking of Shoring Head piles ongoing. -Breaking of Guide wall on going . -Casted of Main Piles on going -Dewatering Installation onging -Relocation Services ongoing. | As the recommendation from project's Engineer, Engineer have identified the need for an additional construction team by the contractor . | 45.35% | 23% | -22.35% | Superstructure-Basment | 2025-07-19 |  | 2025-11-20 | 2024-09-05 | 1-Lifting Works ( Unsafe Lifting / Rigging ) Lack of 3rd party Inspection/ Riggers/ and the damaged rigging tackles 2-Inadequate Handling and Storage of Compress Gases 3-Delay in work commencement of MBZ project due to delays in response from Contractor end regarding to NOC’s / Utility Relocation. 4-Delays un issuance of Clear affection plan without conditions on 29thMay 2024. 5-Delay in issuance of NOCs for MCC, Strom Water ,and Etisalat 6-The project will require night shift operations. This adjustment is essential to meet project deadlines 7-Contractor anticipation to enable work night shift (24 days ) is still not applicable at this site due to the nature of the required activities that will not be allowed at such sensitive area , and Contractor should increase the resources to enable compensate the above mentioned restriction . 8-Working adjacent to the sensitive building/area , and anticipated restriction regarding to adjacent sensitive building /area 9-Subcontractor continuance breakdown of equipment | 1-Apply the mandatory requirement for lifting equipment as the construction sector - OSHAD 34,.0 Safe lifting and lifting accessories. SF , increase inspection procedure, Implement the control for contractor and subcontractor. 2-Apply the COSHH assessment, Allocate resources for Compress gases requirements , Implement the Risk Assessment 3-Required Noc,s already obtained , and Contractor corrective action is required to allocate additional resources to overcome /compensate the occurred delays 4-After Client support Clear affection plsn issued without any restriction 5-Storm water removed from site properties , and other services already relocated /removed 6-Due to the natur of the MBZ Area noght shify is not possible , however Contractor can compensate the same by allocating additional resources /equipment 7-Contractor notified by the same , and instructed to focus to increase the required resources to expedite the progress 8-Contractor currently liasing with Authorities to enable have special permit from ADM /levant Authorities to increase working time as possible 9-Contractor conduct several meetings with Piling subcontractor to secure /replace all existing equipment that are in bad condition to be replaced by other equipment that can continue piing work without stoppage that currently continuance breakdown /in bad condition | Relocation Services. -Complete the Main Piles. -Complete the Guide wall and shoring pile head breaking. -Start of Capping Beams and Struts activities | 78195477.46 | 0 | 78195477.46 | 3462518.5382 | 0 | 81657995.9982 | 4774958.11 | 1018381.2003 | https://drive.google.com/thumbnail?id=1d7EUl2nVrW2pVWhjsLWPCnuUAtvGF_0w&sz=w1000 | https://drive.google.com/file/d/1d7EUl2nVrW2pVWhjsLWPCnuUAtvGF_0w/view?usp=drive_link | https://drive.google.com/thumbnail?id=1Mz-UnKO6rFVDA_Sts8kV4Nb6AFgcY8xZ&sz=w1000 | https://drive.google.com/file/d/1Mz-UnKO6rFVDA_Sts8kV4Nb6AFgcY8xZ/view?usp=drive_link | https://drive.google.com/thumbnail?id=1ISoQA3fZJl3c0SFy1tNoIXbnwnuAAjGb&sz=w1000 | https://drive.google.com/file/d/1ISoQA3fZJl3c0SFy1tNoIXbnwnuAAjGb/view?usp=drive_link
2024-08-30 | Mohamed Bin Zayed City -Majlis-P19 | P19 | MJ-03 | 276 | 322 | 598 | *Piles Shoring Completed *Breaking of Shoring Head piles ongoing. -Breaking of Guide wall on going . -Casted of Main Piles on going -Dewatering Installation ongoing -Relocation Services ongoing. | As the recommendation from project's Engineer, Engineer have identified the need for an additional construction team by the contractor . | 45.35% | 23% | -22.35% | Superstructure-Majlis | 2025-07-24 |  | 2025-12-20 | 2024-09-05 | 1-Lifting Works ( Unsafe Lifting / Rigging ) Lack of 3rd party Inspection/ Riggers/ and the damaged rigging tackles 2-Inadequate Handling and Storage of Compress Gases 3-Delay in work commencement of MBZ project due to delays in response from Contractor end regarding to NOC’s / Utility Relocation. 4-Delays un issuance of Clear affection plan without conditions on 29thMay 2024. 5-Delay in issuance of NOCs for MCC, Strom Water ,and Etisalat 6-The project will require night shift operations. This adjustment is essential to meet project deadlines 7-Contractor anticipation to enable work night shift (24 days ) is still not applicable at this site due to the nature of the required activities that will not be allowed at such sensitive area , and Contractor should increase the resources to enable compensate the above mentioned restriction . 8-Working adjacent to the sensitive building/area , and anticipated restriction regarding to adjacent sensitive building /area 9-Subcontractor continuance breakdown of equipment | 1-Apply the mandatory requirement for lifting equipment as the construction sector - OSHAD 34,.0 Safe lifting and lifting accessories. SF , increase inspection procedure, Implement the control for contractor and subcontractor. 2-Apply the COSHH assessment, Allocate resources for Compress gases requirements , Implement the Risk Assessment 3-Required Noc,s already obtained , and Contractor corrective action is required to allocate additional resources to overcome /compensate the occurred delays 4-After Client support Clear affection plsn issued without any restriction 5-Storm water removed from site properties , and other services already relocated /removed 6-Due to the natur of the MBZ Area noght shify is not possible , however Contractor can compensate the same by allocating additional resources /equipment 7-Contractor notified by the same , and instructed to focus to increase the required resources to expedite the progress 8-Contractor currently liasing with Authorities to enable have special permit from ADM /levant Authorities to increase working time as possible 9-Contractor conduct several meetings with Piling subcontractor to secure /replace all existing equipment that are in bad condition to be replaced by other equipment that can continue piing work without stoppage that currently continuance breakdown /in bad condition | Relocation Services. -Complete the Main Piles. -Complete the Guide wall and shoring pile head breaking. -Start of Capping Beams and Struts activities | 78195477.46 | 0 | 78195477.46 | 3462518.5382 | 0 | 81657995.9982 | 4774958.11 | 1018381.2003 | https://drive.google.com/thumbnail?id=1d7EUl2nVrW2pVWhjsLWPCnuUAtvGF_0w&sz=w1000 | https://drive.google.com/file/d/1d7EUl2nVrW2pVWhjsLWPCnuUAtvGF_0w/view?usp=drive_link | https://drive.google.com/thumbnail?id=1Mz-UnKO6rFVDA_Sts8kV4Nb6AFgcY8xZ&sz=w1000 | https://drive.google.com/file/d/1Mz-UnKO6rFVDA_Sts8kV4Nb6AFgcY8xZ/view?usp=drive_link | https://drive.google.com/thumbnail?id=1ISoQA3fZJl3c0SFy1tNoIXbnwnuAAjGb&sz=w1000 | https://drive.google.com/file/d/1ISoQA3fZJl3c0SFy1tNoIXbnwnuAAjGb/view?usp=drive_link
2024-08-30 | Mohamed Bin Zayed City -Majlis-P19 | P19 | MJ-03 | 276 | 322 | 598 | *Piles Shoring Completed *Breaking of Shoring Head piles ongoing. -Breaking of Guide wall on going . -Casted of Main Piles on going -Dewatering Installation ongoing -Relocation Services ongoing. | As the recommendation from project's Engineer, Engineer have identified the need for an additional construction team by the contractor . | 45.35% | 23% | -22.35% | Majlis - Power | 2025-07-24 |  | 2025-12-20 | 2024-09-05 | 1-Lifting Works ( Unsafe Lifting / Rigging ) Lack of 3rd party Inspection/ Riggers/ and the damaged rigging tackles 2-Inadequate Handling and Storage of Compress Gases 3-Delay in work commencement of MBZ project due to delays in response from Contractor end regarding to NOC’s / Utility Relocation. 4-Delays un issuance of Clear affection plan without conditions on 29thMay 2024. 5-Delay in issuance of NOCs for MCC, Strom Water ,and Etisalat 6-The project will require night shift operations. This adjustment is essential to meet project deadlines 7-Contractor anticipation to enable work night shift (24 days ) is still not applicable at this site due to the nature of the required activities that will not be allowed at such sensitive area , and Contractor should increase the resources to enable compensate the above mentioned restriction . 8-Working adjacent to the sensitive building/area , and anticipated restriction regarding to adjacent sensitive building /area 9-Subcontractor continuance breakdown of equipment | 1-Apply the mandatory requirement for lifting equipment as the construction sector - OSHAD 34,.0 Safe lifting and lifting accessories. SF , increase inspection procedure, Implement the control for contractor and subcontractor. 2-Apply the COSHH assessment, Allocate resources for Compress gases requirements , Implement the Risk Assessment 3-Required Noc,s already obtained , and Contractor corrective action is required to allocate additional resources to overcome /compensate the occurred delays 4-After Client support Clear affection plsn issued without any restriction 5-Storm water removed from site properties , and other services already relocated /removed 6-Due to the natur of the MBZ Area noght shify is not possible , however Contractor can compensate the same by allocating additional resources /equipment 7-Contractor notified by the same , and instructed to focus to increase the required resources to expedite the progress 8-Contractor currently liasing with Authorities to enable have special permit from ADM /levant Authorities to increase working time as possible 9-Contractor conduct several meetings with Piling subcontractor to secure /replace all existing equipment that are in bad condition to be replaced by other equipment that can continue piing work without stoppage that currently continuance breakdown /in bad condition | Relocation Services. -Complete the Main Piles. -Complete the Guide wall and shoring pile head breaking. -Start of Capping Beams and Struts activities | 78195477.46 | 0 | 78195477.46 | 3462518.5382 | 0 | 81657995.9982 | 4774958.11 | 1018381.2003 | https://drive.google.com/thumbnail?id=1d7EUl2nVrW2pVWhjsLWPCnuUAtvGF_0w&sz=w1000 | https://drive.google.com/file/d/1d7EUl2nVrW2pVWhjsLWPCnuUAtvGF_0w/view?usp=drive_link | https://drive.google.com/thumbnail?id=1Mz-UnKO6rFVDA_Sts8kV4Nb6AFgcY8xZ&sz=w1000 | https://drive.google.com/file/d/1Mz-UnKO6rFVDA_Sts8kV4Nb6AFgcY8xZ/view?usp=drive_link | https://drive.google.com/thumbnail?id=1ISoQA3fZJl3c0SFy1tNoIXbnwnuAAjGb&sz=w1000 | https://drive.google.com/file/d/1ISoQA3fZJl3c0SFy1tNoIXbnwnuAAjGb/view?usp=drive_link
2024-08-30 | Mohamed Bin Zayed City -Majlis-P19 | P19 | MJ-03 | 276 | 322 | 598 | *Piles Shoring Completed *Breaking of Shoring Head piles ongoing. -Breaking of Guide wall on going . -Casted of Main Piles on going -Dewatering Installation ongoing -Relocation Services ongoing. | As the recommendation from project's Engineer, Engineer have identified the need for an additional construction team by the contractor . | 45.35% | 23% | -22.35% | Project Finsh date | 2025-07-24 |  | 2025-12-24 | 2024-09-05 | 1-Lifting Works ( Unsafe Lifting / Rigging ) Lack of 3rd party Inspection/ Riggers/ and the damaged rigging tackles 2-Inadequate Handling and Storage of Compress Gases 3-Delay in work commencement of MBZ project due to delays in response from Contractor end regarding to NOC’s / Utility Relocation. 4-Delays un issuance of Clear affection plan without conditions on 29thMay 2024. 5-Delay in issuance of NOCs for MCC, Strom Water ,and Etisalat 6-The project will require night shift operations. This adjustment is essential to meet project deadlines 7-Contractor anticipation to enable work night shift (24 days ) is still not applicable at this site due to the nature of the required activities that will not be allowed at such sensitive area , and Contractor should increase the resources to enable compensate the above mentioned restriction . 8-Working adjacent to the sensitive building/area , and anticipated restriction regarding to adjacent sensitive building /area 9-Subcontractor continuance breakdown of equipment | 1-Apply the mandatory requirement for lifting equipment as the construction sector - OSHAD 34,.0 Safe lifting and lifting accessories. SF , increase inspection procedure, Implement the control for contractor and subcontractor. 2-Apply the COSHH assessment, Allocate resources for Compress gases requirements , Implement the Risk Assessment 3-Required Noc,s already obtained , and Contractor corrective action is required to allocate additional resources to overcome /compensate the occurred delays 4-After Client support Clear affection plsn issued without any restriction 5-Storm water removed from site properties , and other services already relocated /removed 6-Due to the natur of the MBZ Area noght shify is not possible , however Contractor can compensate the same by allocating additional resources /equipment 7-Contractor notified by the same , and instructed to focus to increase the required resources to expedite the progress 8-Contractor currently liasing with Authorities to enable have special permit from ADM /levant Authorities to increase working time as possible 9-Contractor conduct several meetings with Piling subcontractor to secure /replace all existing equipment that are in bad condition to be replaced by other equipment that can continue piing work without stoppage that currently continuance breakdown /in bad condition | Relocation Services. -Complete the Main Piles. -Complete the Guide wall and shoring pile head breaking. -Start of Capping Beams and Struts activities | 78195477.46 | 0 | 78195477.46 | 3462518.5382 | 0 | 81657995.9982 | 4774958.11 | 1018381.2003 | https://drive.google.com/thumbnail?id=1d7EUl2nVrW2pVWhjsLWPCnuUAtvGF_0w&sz=w1000 | https://drive.google.com/file/d/1d7EUl2nVrW2pVWhjsLWPCnuUAtvGF_0w/view?usp=drive_link | https://drive.google.com/thumbnail?id=1Mz-UnKO6rFVDA_Sts8kV4Nb6AFgcY8xZ&sz=w1000 | https://drive.google.com/file/d/1Mz-UnKO6rFVDA_Sts8kV4Nb6AFgcY8xZ/view?usp=drive_link | https://drive.google.com/thumbnail?id=1ISoQA3fZJl3c0SFy1tNoIXbnwnuAAjGb&sz=w1000 | https://drive.google.com/file/d/1ISoQA3fZJl3c0SFy1tNoIXbnwnuAAjGb/view?usp=drive_link
2024-08-30 | Madinat Al Riyad-Majlis-P3 | P3 | MJ-08 | 46 | 747 | 793 | Contractor Site Office Works In Progress. Temporary Power, Water, Sanitation For Contractor Site Office In Progress. Consultant Site Office Furniture Selected By Engineer & LPO in Process. | *IFC drawings will be issued by next week all buildings. *The contractor has submitted the Project Baseline (BL), Revise &Resubmit | 0% | 0% | 0% | Project Commencement | 2024-07-23 | 2024-07-23 |  | 2024-09-06 | Issuance of IFC drawings to Contractor. Under Process expected early approval. | Although the IFC drawing is not yet available, AIC is supporting the contractor proactively to start the engineering and procurement phases.” | •PQ for Dewatering, Waterproofing •Material Submittal for Cement(SRC & OPC),Polythene Sheet 1000 Guage, Concrete Cover Blocks, Concrete Solid Blocks,Hollow Blocks & Thermal Blocks •Shop drawings calculation & submission for shoring works – by Specialist(14 days from receipt of IFC drawings) •Concrete Mix Design Submittal for SRC(C65) & Substructure(C65) •Concrete Mix Design Submittal for Gunite | 117010730 |  | 117010730 | 3645800 | 0 | 120656530 |  |  | https://drive.google.com/thumbnail?id=1l032NhkgI8VXW1YdwE6IVXJ95axS_1_N&sz=w1000 | https://drive.google.com/file/d/1l032NhkgI8VXW1YdwE6IVXJ95axS_1_N/view?usp=drive_link | https://drive.google.com/thumbnail?id=1iRpGkfGlUpy_9sZc0sYjyX4pKKrv-yKh&sz=w1000 | https://drive.google.com/file/d/1iRpGkfGlUpy_9sZc0sYjyX4pKKrv-yKh/view?usp=drive_link | https://drive.google.com/thumbnail?id=1XZELMJDN7oiWnhqZnzMAEUGGr7oqakya&sz=w1000 | https://drive.google.com/file/d/1XZELMJDN7oiWnhqZnzMAEUGGr7oqakya/view?usp=drive_link
2024-08-30 | Madinat Al Riyad-Majlis-P3 | P3 | MJ-08 | 46 | 747 | 793 | Contractor Site Office Works In Progress. Temporary Power, Water, Sanitation For Contractor Site Office In Progress. Consultant Site Office Furniture Selected By Engineer & LPO in Process. | *IFC drawings will be issued by next week all buildings. *The contractor has submitted the Project Baseline (BL), Revise &Resubmit | 0% | 0% | 0% | Construction Permit & NOC | 2024-08-15 | 2024-08-15 |  | 2024-09-06 | Issuance of IFC drawings to Contractor. Under Process expected early approval. | Although the IFC drawing is not yet available, AIC is supporting the contractor proactively to start the engineering and procurement phases.” | •PQ for Dewatering, Waterproofing •Material Submittal for Cement(SRC & OPC),Polythene Sheet 1000 Guage, Concrete Cover Blocks, Concrete Solid Blocks,Hollow Blocks & Thermal Blocks •Shop drawings calculation & submission for shoring works – by Specialist(14 days from receipt of IFC drawings) •Concrete Mix Design Submittal for SRC(C65) & Substructure(C65) •Concrete Mix Design Submittal for Gunite | 117010730 |  | 117010730 | 3645800 | 0 | 120656530 |  |  | https://drive.google.com/thumbnail?id=1l032NhkgI8VXW1YdwE6IVXJ95axS_1_N&sz=w1000 | https://drive.google.com/file/d/1l032NhkgI8VXW1YdwE6IVXJ95axS_1_N/view?usp=drive_link | https://drive.google.com/thumbnail?id=1iRpGkfGlUpy_9sZc0sYjyX4pKKrv-yKh&sz=w1000 | https://drive.google.com/file/d/1iRpGkfGlUpy_9sZc0sYjyX4pKKrv-yKh/view?usp=drive_link | https://drive.google.com/thumbnail?id=1XZELMJDN7oiWnhqZnzMAEUGGr7oqakya&sz=w1000 | https://drive.google.com/file/d/1XZELMJDN7oiWnhqZnzMAEUGGr7oqakya/view?usp=drive_link
2024-08-30 | Madinat Al Riyad-Majlis-P3 | P3 | MJ-08 | 46 | 747 | 793 | Contractor Site Office Works In Progress. Temporary Power, Water, Sanitation For Contractor Site Office In Progress. Consultant Site Office Furniture Selected By Engineer & LPO in Process. | *IFC drawings will be issued by next week all buildings. *The contractor has submitted the Project Baseline (BL), Revise &Resubmit | 0% | 0% | 0% | Site Moblization | 2024-09-23 |  | 2024-09-23 | 2024-09-06 | Issuance of IFC drawings to Contractor. Under Process expected early approval. | Although the IFC drawing is not yet available, AIC is supporting the contractor proactively to start the engineering and procurement phases.” | •PQ for Dewatering, Waterproofing •Material Submittal for Cement(SRC & OPC),Polythene Sheet 1000 Guage, Concrete Cover Blocks, Concrete Solid Blocks,Hollow Blocks & Thermal Blocks •Shop drawings calculation & submission for shoring works – by Specialist(14 days from receipt of IFC drawings) •Concrete Mix Design Submittal for SRC(C65) & Substructure(C65) •Concrete Mix Design Submittal for Gunite | 117010730 |  | 117010730 | 3645800 | 0 | 120656530 |  |  | https://drive.google.com/thumbnail?id=1l032NhkgI8VXW1YdwE6IVXJ95axS_1_N&sz=w1000 | https://drive.google.com/file/d/1l032NhkgI8VXW1YdwE6IVXJ95axS_1_N/view?usp=drive_link | https://drive.google.com/thumbnail?id=1iRpGkfGlUpy_9sZc0sYjyX4pKKrv-yKh&sz=w1000 | https://drive.google.com/file/d/1iRpGkfGlUpy_9sZc0sYjyX4pKKrv-yKh/view?usp=drive_link | https://drive.google.com/thumbnail?id=1XZELMJDN7oiWnhqZnzMAEUGGr7oqakya&sz=w1000 | https://drive.google.com/file/d/1XZELMJDN7oiWnhqZnzMAEUGGr7oqakya/view?usp=drive_link
2024-08-30 | Madinat Al Riyad-Majlis-P3 | P3 | MJ-08 | 46 | 747 | 793 | Contractor Site Office Works In Progress. Temporary Power, Water, Sanitation For Contractor Site Office In Progress. Consultant Site Office Furniture Selected By Engineer & LPO in Process. | *IFC drawings will be issued by next week all buildings. *The contractor has submitted the Project Baseline (BL), Revise &Resubmit | 0% | 0% | 0% | Engineering Works | 2026-01-31 |  | 2026-01-31 | 2024-09-06 | Issuance of IFC drawings to Contractor. Under Process expected early approval. | Although the IFC drawing is not yet available, AIC is supporting the contractor proactively to start the engineering and procurement phases.” | •PQ for Dewatering, Waterproofing •Material Submittal for Cement(SRC & OPC),Polythene Sheet 1000 Guage, Concrete Cover Blocks, Concrete Solid Blocks,Hollow Blocks & Thermal Blocks •Shop drawings calculation & submission for shoring works – by Specialist(14 days from receipt of IFC drawings) •Concrete Mix Design Submittal for SRC(C65) & Substructure(C65) •Concrete Mix Design Submittal for Gunite | 117010730 |  | 117010730 | 3645800 | 0 | 120656530 |  |  | https://drive.google.com/thumbnail?id=1l032NhkgI8VXW1YdwE6IVXJ95axS_1_N&sz=w1000 | https://drive.google.com/file/d/1l032NhkgI8VXW1YdwE6IVXJ95axS_1_N/view?usp=drive_link | https://drive.google.com/thumbnail?id=1iRpGkfGlUpy_9sZc0sYjyX4pKKrv-yKh&sz=w1000 | https://drive.google.com/file/d/1iRpGkfGlUpy_9sZc0sYjyX4pKKrv-yKh/view?usp=drive_link | https://drive.google.com/thumbnail?id=1XZELMJDN7oiWnhqZnzMAEUGGr7oqakya&sz=w1000 | https://drive.google.com/file/d/1XZELMJDN7oiWnhqZnzMAEUGGr7oqakya/view?usp=drive_link
2024-08-30 | Madinat Al Riyad-Majlis-P3 | P3 | MJ-08 | 46 | 747 | 793 | Contractor Site Office Works In Progress. Temporary Power, Water, Sanitation For Contractor Site Office In Progress. Consultant Site Office Furniture Selected By Engineer & LPO in Process. | *IFC drawings will be issued by next week all buildings. *The contractor has submitted the Project Baseline (BL), Revise &Resubmit | 0% | 0% | 0% | Construction of Shelter | 2026-09-15 |  | 2026-09-15 | 2024-09-06 | Issuance of IFC drawings to Contractor. Under Process expected early approval. | Although the IFC drawing is not yet available, AIC is supporting the contractor proactively to start the engineering and procurement phases.” | •PQ for Dewatering, Waterproofing •Material Submittal for Cement(SRC & OPC),Polythene Sheet 1000 Guage, Concrete Cover Blocks, Concrete Solid Blocks,Hollow Blocks & Thermal Blocks •Shop drawings calculation & submission for shoring works – by Specialist(14 days from receipt of IFC drawings) •Concrete Mix Design Submittal for SRC(C65) & Substructure(C65) •Concrete Mix Design Submittal for Gunite | 117010730 |  | 117010730 | 3645800 | 0 | 120656530 |  |  | https://drive.google.com/thumbnail?id=1l032NhkgI8VXW1YdwE6IVXJ95axS_1_N&sz=w1000 | https://drive.google.com/file/d/1l032NhkgI8VXW1YdwE6IVXJ95axS_1_N/view?usp=drive_link | https://drive.google.com/thumbnail?id=1iRpGkfGlUpy_9sZc0sYjyX4pKKrv-yKh&sz=w1000 | https://drive.google.com/file/d/1iRpGkfGlUpy_9sZc0sYjyX4pKKrv-yKh/view?usp=drive_link | https://drive.google.com/thumbnail?id=1XZELMJDN7oiWnhqZnzMAEUGGr7oqakya&sz=w1000 | https://drive.google.com/file/d/1XZELMJDN7oiWnhqZnzMAEUGGr7oqakya/view?usp=drive_link
2024-08-30 | Madinat Al Riyad-Majlis-P3 | P3 | MJ-08 | 46 | 747 | 793 | Contractor Site Office Works In Progress. Temporary Power, Water, Sanitation For Contractor Site Office In Progress. Consultant Site Office Furniture Selected By Engineer & LPO in Process. | *IFC drawings will be issued by next week all buildings. *The contractor has submitted the Project Baseline (BL), Revise &Resubmit | 0% | 0% | 0% | Construction of Majlis | 2024-07-27 |  | 2024-07-27 | 2024-09-06 | Issuance of IFC drawings to Contractor. Under Process expected early approval. | Although the IFC drawing is not yet available, AIC is supporting the contractor proactively to start the engineering and procurement phases.” | •PQ for Dewatering, Waterproofing •Material Submittal for Cement(SRC & OPC),Polythene Sheet 1000 Guage, Concrete Cover Blocks, Concrete Solid Blocks,Hollow Blocks & Thermal Blocks •Shop drawings calculation & submission for shoring works – by Specialist(14 days from receipt of IFC drawings) •Concrete Mix Design Submittal for SRC(C65) & Substructure(C65) •Concrete Mix Design Submittal for Gunite | 117010730 |  | 117010730 | 3645800 | 0 | 120656530 |  |  | https://drive.google.com/thumbnail?id=1l032NhkgI8VXW1YdwE6IVXJ95axS_1_N&sz=w1000 | https://drive.google.com/file/d/1l032NhkgI8VXW1YdwE6IVXJ95axS_1_N/view?usp=drive_link | https://drive.google.com/thumbnail?id=1iRpGkfGlUpy_9sZc0sYjyX4pKKrv-yKh&sz=w1000 | https://drive.google.com/file/d/1iRpGkfGlUpy_9sZc0sYjyX4pKKrv-yKh/view?usp=drive_link | https://drive.google.com/thumbnail?id=1XZELMJDN7oiWnhqZnzMAEUGGr7oqakya&sz=w1000 | https://drive.google.com/file/d/1XZELMJDN7oiWnhqZnzMAEUGGr7oqakya/view?usp=drive_link
2024-08-30 | Madinat Al Riyad-Majlis-P3 | P3 | MJ-08 | 46 | 747 | 793 | Contractor Site Office Works In Progress. Temporary Power, Water, Sanitation For Contractor Site Office In Progress. Consultant Site Office Furniture Selected By Engineer & LPO in Process. | *IFC drawings will be issued by next week all buildings. *The contractor has submitted the Project Baseline (BL), Revise &Resubmit | 0% | 0% | 0% | Construction of Pump Room | 2026-11-02 |  | 2026-11-02 | 2024-09-06 | Issuance of IFC drawings to Contractor. Under Process expected early approval. | Although the IFC drawing is not yet available, AIC is supporting the contractor proactively to start the engineering and procurement phases.” | •PQ for Dewatering, Waterproofing •Material Submittal for Cement(SRC & OPC),Polythene Sheet 1000 Guage, Concrete Cover Blocks, Concrete Solid Blocks,Hollow Blocks & Thermal Blocks •Shop drawings calculation & submission for shoring works – by Specialist(14 days from receipt of IFC drawings) •Concrete Mix Design Submittal for SRC(C65) & Substructure(C65) •Concrete Mix Design Submittal for Gunite | 117010730 |  | 117010730 | 3645800 | 0 | 120656530 |  |  | https://drive.google.com/thumbnail?id=1l032NhkgI8VXW1YdwE6IVXJ95axS_1_N&sz=w1000 | https://drive.google.com/file/d/1l032NhkgI8VXW1YdwE6IVXJ95axS_1_N/view?usp=drive_link | https://drive.google.com/thumbnail?id=1iRpGkfGlUpy_9sZc0sYjyX4pKKrv-yKh&sz=w1000 | https://drive.google.com/file/d/1iRpGkfGlUpy_9sZc0sYjyX4pKKrv-yKh/view?usp=drive_link | https://drive.google.com/thumbnail?id=1XZELMJDN7oiWnhqZnzMAEUGGr7oqakya&sz=w1000 | https://drive.google.com/file/d/1XZELMJDN7oiWnhqZnzMAEUGGr7oqakya/view?usp=drive_link
2024-08-30 | Madinat Al Riyad-Majlis-P3 | P3 | MJ-08 | 46 | 747 | 793 | Contractor Site Office Works In Progress. Temporary Power, Water, Sanitation For Contractor Site Office In Progress. Consultant Site Office Furniture Selected By Engineer & LPO in Process. | *IFC drawings will be issued by next week all buildings. *The contractor has submitted the Project Baseline (BL), Revise &Resubmit | 0% | 0% | 0% | Construction of Substation | 2025-05-12 |  | 2025-05-12 | 2024-09-06 | Issuance of IFC drawings to Contractor. Under Process expected early approval. | Although the IFC drawing is not yet available, AIC is supporting the contractor proactively to start the engineering and procurement phases.” | •PQ for Dewatering, Waterproofing •Material Submittal for Cement(SRC & OPC),Polythene Sheet 1000 Guage, Concrete Cover Blocks, Concrete Solid Blocks,Hollow Blocks & Thermal Blocks •Shop drawings calculation & submission for shoring works – by Specialist(14 days from receipt of IFC drawings) •Concrete Mix Design Submittal for SRC(C65) & Substructure(C65) •Concrete Mix Design Submittal for Gunite | 117010730 |  | 117010730 | 3645800 | 0 | 120656530 |  |  | https://drive.google.com/thumbnail?id=1l032NhkgI8VXW1YdwE6IVXJ95axS_1_N&sz=w1000 | https://drive.google.com/file/d/1l032NhkgI8VXW1YdwE6IVXJ95axS_1_N/view?usp=drive_link | https://drive.google.com/thumbnail?id=1iRpGkfGlUpy_9sZc0sYjyX4pKKrv-yKh&sz=w1000 | https://drive.google.com/file/d/1iRpGkfGlUpy_9sZc0sYjyX4pKKrv-yKh/view?usp=drive_link | https://drive.google.com/thumbnail?id=1XZELMJDN7oiWnhqZnzMAEUGGr7oqakya&sz=w1000 | https://drive.google.com/file/d/1XZELMJDN7oiWnhqZnzMAEUGGr7oqakya/view?usp=drive_link
2024-08-30 | Madinat Al Riyad-Majlis-P3 | P3 | MJ-08 | 46 | 747 | 793 | Contractor Site Office Works In Progress. Temporary Power, Water, Sanitation For Contractor Site Office In Progress. Consultant Site Office Furniture Selected By Engineer & LPO in Process. | *IFC drawings will be issued by next week all buildings. *The contractor has submitted the Project Baseline (BL), Revise &Resubmit | 0% | 0% | 0% | External Works | 2026-04-14 |  | 2026-04-14 | 2024-09-06 | Issuance of IFC drawings to Contractor. Under Process expected early approval. | Although the IFC drawing is not yet available, AIC is supporting the contractor proactively to start the engineering and procurement phases.” | •PQ for Dewatering, Waterproofing •Material Submittal for Cement(SRC & OPC),Polythene Sheet 1000 Guage, Concrete Cover Blocks, Concrete Solid Blocks,Hollow Blocks & Thermal Blocks •Shop drawings calculation & submission for shoring works – by Specialist(14 days from receipt of IFC drawings) •Concrete Mix Design Submittal for SRC(C65) & Substructure(C65) •Concrete Mix Design Submittal for Gunite | 117010730 |  | 117010730 | 3645800 | 0 | 120656530 |  |  | https://drive.google.com/thumbnail?id=1l032NhkgI8VXW1YdwE6IVXJ95axS_1_N&sz=w1000 | https://drive.google.com/file/d/1l032NhkgI8VXW1YdwE6IVXJ95axS_1_N/view?usp=drive_link | https://drive.google.com/thumbnail?id=1iRpGkfGlUpy_9sZc0sYjyX4pKKrv-yKh&sz=w1000 | https://drive.google.com/file/d/1iRpGkfGlUpy_9sZc0sYjyX4pKKrv-yKh/view?usp=drive_link | https://drive.google.com/thumbnail?id=1XZELMJDN7oiWnhqZnzMAEUGGr7oqakya&sz=w1000 | https://drive.google.com/file/d/1XZELMJDN7oiWnhqZnzMAEUGGr7oqakya/view?usp=drive_link
2024-08-30 | Madinat Al Riyad-Majlis-P3 | P3 | MJ-08 | 46 | 747 | 793 | Contractor Site Office Works In Progress. Temporary Power, Water, Sanitation For Contractor Site Office In Progress. Consultant Site Office Furniture Selected By Engineer & LPO in Process. | *IFC drawings will be issued by next week all buildings. *The contractor has submitted the Project Baseline (BL), Revise &Resubmit | 0% | 0% | 0% | Testing & Commissioning | 2026-09-21 |  | 2026-09-21 | 2024-09-06 | Issuance of IFC drawings to Contractor. Under Process expected early approval. | Although the IFC drawing is not yet available, AIC is supporting the contractor proactively to start the engineering and procurement phases.” | •PQ for Dewatering, Waterproofing •Material Submittal for Cement(SRC & OPC),Polythene Sheet 1000 Guage, Concrete Cover Blocks, Concrete Solid Blocks,Hollow Blocks & Thermal Blocks •Shop drawings calculation & submission for shoring works – by Specialist(14 days from receipt of IFC drawings) •Concrete Mix Design Submittal for SRC(C65) & Substructure(C65) •Concrete Mix Design Submittal for Gunite | 117010730 |  | 117010730 | 3645800 | 0 | 120656530 |  |  | https://drive.google.com/thumbnail?id=1l032NhkgI8VXW1YdwE6IVXJ95axS_1_N&sz=w1000 | https://drive.google.com/file/d/1l032NhkgI8VXW1YdwE6IVXJ95axS_1_N/view?usp=drive_link | https://drive.google.com/thumbnail?id=1iRpGkfGlUpy_9sZc0sYjyX4pKKrv-yKh&sz=w1000 | https://drive.google.com/file/d/1iRpGkfGlUpy_9sZc0sYjyX4pKKrv-yKh/view?usp=drive_link | https://drive.google.com/thumbnail?id=1XZELMJDN7oiWnhqZnzMAEUGGr7oqakya&sz=w1000 | https://drive.google.com/file/d/1XZELMJDN7oiWnhqZnzMAEUGGr7oqakya/view?usp=drive_link
2024-08-30 | Madinat Al Riyad-Majlis-P3 | P3 | MJ-08 | 46 | 747 | 793 | Contractor Site Office Works In Progress. Temporary Power, Water, Sanitation For Contractor Site Office In Progress. Consultant Site Office Furniture Selected By Engineer & LPO in Process. | *IFC drawings will be issued by next week all buildings. *The contractor has submitted the Project Baseline (BL), Revise &Resubmit | 0% | 0% | 0% | Authorities Approvals | 2026-10-09 |  | 2026-10-09 | 2024-09-06 | Issuance of IFC drawings to Contractor. Under Process expected early approval. | Although the IFC drawing is not yet available, AIC is supporting the contractor proactively to start the engineering and procurement phases.” | •PQ for Dewatering, Waterproofing •Material Submittal for Cement(SRC & OPC),Polythene Sheet 1000 Guage, Concrete Cover Blocks, Concrete Solid Blocks,Hollow Blocks & Thermal Blocks •Shop drawings calculation & submission for shoring works – by Specialist(14 days from receipt of IFC drawings) •Concrete Mix Design Submittal for SRC(C65) & Substructure(C65) •Concrete Mix Design Submittal for Gunite | 117010730 |  | 117010730 | 3645800 | 0 | 120656530 |  |  | https://drive.google.com/thumbnail?id=1l032NhkgI8VXW1YdwE6IVXJ95axS_1_N&sz=w1000 | https://drive.google.com/file/d/1l032NhkgI8VXW1YdwE6IVXJ95axS_1_N/view?usp=drive_link | https://drive.google.com/thumbnail?id=1iRpGkfGlUpy_9sZc0sYjyX4pKKrv-yKh&sz=w1000 | https://drive.google.com/file/d/1iRpGkfGlUpy_9sZc0sYjyX4pKKrv-yKh/view?usp=drive_link | https://drive.google.com/thumbnail?id=1XZELMJDN7oiWnhqZnzMAEUGGr7oqakya&sz=w1000 | https://drive.google.com/file/d/1XZELMJDN7oiWnhqZnzMAEUGGr7oqakya/view?usp=drive_link
2024-08-30 | Madinat Al Riyad-Majlis-P3 | P3 | MJ-08 | 46 | 747 | 793 | Contractor Site Office Works In Progress. Temporary Power, Water, Sanitation For Contractor Site Office In Progress. Consultant Site Office Furniture Selected By Engineer & LPO in Process. | *IFC drawings will be issued by next week all buildings. *The contractor has submitted the Project Baseline (BL), Revise &Resubmit | 0% | 0% | 0% | Substantial Completion | 2026-09-23 |  | 2026-09-23 | 2024-09-06 | Issuance of IFC drawings to Contractor. Under Process expected early approval. | Although the IFC drawing is not yet available, AIC is supporting the contractor proactively to start the engineering and procurement phases.” | •PQ for Dewatering, Waterproofing •Material Submittal for Cement(SRC & OPC),Polythene Sheet 1000 Guage, Concrete Cover Blocks, Concrete Solid Blocks,Hollow Blocks & Thermal Blocks •Shop drawings calculation & submission for shoring works – by Specialist(14 days from receipt of IFC drawings) •Concrete Mix Design Submittal for SRC(C65) & Substructure(C65) •Concrete Mix Design Submittal for Gunite | 117010730 |  | 117010730 | 3645800 | 0 | 120656530 |  |  | https://drive.google.com/thumbnail?id=1l032NhkgI8VXW1YdwE6IVXJ95axS_1_N&sz=w1000 | https://drive.google.com/file/d/1l032NhkgI8VXW1YdwE6IVXJ95axS_1_N/view?usp=drive_link | https://drive.google.com/thumbnail?id=1iRpGkfGlUpy_9sZc0sYjyX4pKKrv-yKh&sz=w1000 | https://drive.google.com/file/d/1iRpGkfGlUpy_9sZc0sYjyX4pKKrv-yKh/view?usp=drive_link | https://drive.google.com/thumbnail?id=1XZELMJDN7oiWnhqZnzMAEUGGr7oqakya&sz=w1000 | https://drive.google.com/file/d/1XZELMJDN7oiWnhqZnzMAEUGGr7oqakya/view?usp=drive_link
2024-08-30 | Al Shamkhah-Majlis-P6 | P6 | MJ-09 | 46 | 747 | 793 | Fencing Installation Completed on 20 Aug 24. Soil Investagation Testing Lab completed on 27 Aug 24. Drinking Water Area for Labors completed on 29 Aug 24. M/s Emirates Steel Rebar Supplier Prequalification approved on 27 Aug 24. Prequalification for Anti termite of M/s Terminex Pest Control Services Submitted on 30 Aug 24 | *IFC drawings will be issued by next week all buildings. *The contractor has submitted the Project Baseline (BL), Revise &Resubmit | 0% | 0% | 0% | Project Commencement | 2024-07-23 | 2024-07-23 |  | 2024-09-06 | Issuance of IFC drawings to Contractor. Under Process expected early approval. | Although the IFC drawing is not yet available, AIC is supporting the contractor proactively to start the engineering and procurement phases.” | •PQ for Dewatering, Waterproofing •Material Submittal for Cement(SRC & OPC),Polythene Sheet 1000 Guage, Concrete Cover Blocks, Concrete Solid Blocks,Hollow Blocks & Thermal Blocks •Shop drawings calculation & submission for shoring works – by Specialist(14 days from receipt of IFC drawings) •Concrete Mix Design Submittal for SRC(C65) & Substructure(C65) •Concrete Mix Design Submittal for Gunite | 356759501 |  | 356759501 | 3645800 | 0 | 360405301 |  |  | https://drive.google.com/thumbnail?id=1CGnDxWakVhMcyf3ArpxC0Xg8NB2NJ04m&sz=w1000 | https://drive.google.com/file/d/1CGnDxWakVhMcyf3ArpxC0Xg8NB2NJ04m/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hmXY9RLSychgJTsAJz7iOoJsrTTIp1VT&sz=w1000 | https://drive.google.com/file/d/1hmXY9RLSychgJTsAJz7iOoJsrTTIp1VT/view?usp=drive_link | https://drive.google.com/thumbnail?id=1E_lw9TkbspjWKBlfCTRgy2po44C1TCJP&sz=w1000 | https://drive.google.com/file/d/1E_lw9TkbspjWKBlfCTRgy2po44C1TCJP/view?usp=drive_link
2024-08-30 | Al Shamkhah-Majlis-P6 | P6 | MJ-09 | 46 | 747 | 793 | Fencing Installation Completed on 20 Aug 24. Soil Investagation Testing Lab completed on 27 Aug 24. Drinking Water Area for Labors completed on 29 Aug 24. M/s Emirates Steel Rebar Supplier Prequalification approved on 27 Aug 24. Prequalification for Anti termite of M/s Terminex Pest Control Services Submitted on 30 Aug 24 | *IFC drawings will be issued by next week all buildings. *The contractor has submitted the Project Baseline (BL), Revise &Resubmit | 0% | 0% | 0% | Construction Permit & NOC | 2024-08-15 | 2024-06-08 |  | 2024-09-06 | Issuance of IFC drawings to Contractor. Under Process expected early approval. | Although the IFC drawing is not yet available, AIC is supporting the contractor proactively to start the engineering and procurement phases.” | •PQ for Dewatering, Waterproofing •Material Submittal for Cement(SRC & OPC),Polythene Sheet 1000 Guage, Concrete Cover Blocks, Concrete Solid Blocks,Hollow Blocks & Thermal Blocks •Shop drawings calculation & submission for shoring works – by Specialist(14 days from receipt of IFC drawings) •Concrete Mix Design Submittal for SRC(C65) & Substructure(C65) •Concrete Mix Design Submittal for Gunite | 356759501 |  | 356759501 | 3645800 | 0 | 360405301 |  |  | https://drive.google.com/thumbnail?id=1CGnDxWakVhMcyf3ArpxC0Xg8NB2NJ04m&sz=w1000 | https://drive.google.com/file/d/1CGnDxWakVhMcyf3ArpxC0Xg8NB2NJ04m/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hmXY9RLSychgJTsAJz7iOoJsrTTIp1VT&sz=w1000 | https://drive.google.com/file/d/1hmXY9RLSychgJTsAJz7iOoJsrTTIp1VT/view?usp=drive_link | https://drive.google.com/thumbnail?id=1E_lw9TkbspjWKBlfCTRgy2po44C1TCJP&sz=w1000 | https://drive.google.com/file/d/1E_lw9TkbspjWKBlfCTRgy2po44C1TCJP/view?usp=drive_link
2024-08-30 | Al Shamkhah-Majlis-P6 | P6 | MJ-09 | 46 | 747 | 793 | Fencing Installation Completed on 20 Aug 24. Soil Investagation Testing Lab completed on 27 Aug 24. Drinking Water Area for Labors completed on 29 Aug 24. M/s Emirates Steel Rebar Supplier Prequalification approved on 27 Aug 24. Prequalification for Anti termite of M/s Terminex Pest Control Services Submitted on 30 Aug 24 | *IFC drawings will be issued by next week all buildings. *The contractor has submitted the Project Baseline (BL), Revise &Resubmit | 0% | 0% | 0% | Site Moblization | 2026-09-23 |  | 2026-09-23 | 2024-09-06 | Issuance of IFC drawings to Contractor. Under Process expected early approval. | Although the IFC drawing is not yet available, AIC is supporting the contractor proactively to start the engineering and procurement phases.” | •PQ for Dewatering, Waterproofing •Material Submittal for Cement(SRC & OPC),Polythene Sheet 1000 Guage, Concrete Cover Blocks, Concrete Solid Blocks,Hollow Blocks & Thermal Blocks •Shop drawings calculation & submission for shoring works – by Specialist(14 days from receipt of IFC drawings) •Concrete Mix Design Submittal for SRC(C65) & Substructure(C65) •Concrete Mix Design Submittal for Gunite | 356759501 |  | 356759501 | 3645800 | 0 | 360405301 |  |  | https://drive.google.com/thumbnail?id=1CGnDxWakVhMcyf3ArpxC0Xg8NB2NJ04m&sz=w1000 | https://drive.google.com/file/d/1CGnDxWakVhMcyf3ArpxC0Xg8NB2NJ04m/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hmXY9RLSychgJTsAJz7iOoJsrTTIp1VT&sz=w1000 | https://drive.google.com/file/d/1hmXY9RLSychgJTsAJz7iOoJsrTTIp1VT/view?usp=drive_link | https://drive.google.com/thumbnail?id=1E_lw9TkbspjWKBlfCTRgy2po44C1TCJP&sz=w1000 | https://drive.google.com/file/d/1E_lw9TkbspjWKBlfCTRgy2po44C1TCJP/view?usp=drive_link
2024-08-30 | Al Shamkhah-Majlis-P6 | P6 | MJ-09 | 46 | 747 | 793 | Fencing Installation Completed on 20 Aug 24. Soil Investagation Testing Lab completed on 27 Aug 24. Drinking Water Area for Labors completed on 29 Aug 24. M/s Emirates Steel Rebar Supplier Prequalification approved on 27 Aug 24. Prequalification for Anti termite of M/s Terminex Pest Control Services Submitted on 30 Aug 24 | *IFC drawings will be issued by next week all buildings. *The contractor has submitted the Project Baseline (BL), Revise &Resubmit | 0% | 0% | 0% | Engineering Works | 2026-01-31 |  | 2026-01-31 | 2024-09-06 | Issuance of IFC drawings to Contractor. Under Process expected early approval. | Although the IFC drawing is not yet available, AIC is supporting the contractor proactively to start the engineering and procurement phases.” | •PQ for Dewatering, Waterproofing •Material Submittal for Cement(SRC & OPC),Polythene Sheet 1000 Guage, Concrete Cover Blocks, Concrete Solid Blocks,Hollow Blocks & Thermal Blocks •Shop drawings calculation & submission for shoring works – by Specialist(14 days from receipt of IFC drawings) •Concrete Mix Design Submittal for SRC(C65) & Substructure(C65) •Concrete Mix Design Submittal for Gunite | 356759501 |  | 356759501 | 3645800 | 0 | 360405301 |  |  | https://drive.google.com/thumbnail?id=1CGnDxWakVhMcyf3ArpxC0Xg8NB2NJ04m&sz=w1000 | https://drive.google.com/file/d/1CGnDxWakVhMcyf3ArpxC0Xg8NB2NJ04m/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hmXY9RLSychgJTsAJz7iOoJsrTTIp1VT&sz=w1000 | https://drive.google.com/file/d/1hmXY9RLSychgJTsAJz7iOoJsrTTIp1VT/view?usp=drive_link | https://drive.google.com/thumbnail?id=1E_lw9TkbspjWKBlfCTRgy2po44C1TCJP&sz=w1000 | https://drive.google.com/file/d/1E_lw9TkbspjWKBlfCTRgy2po44C1TCJP/view?usp=drive_link
2024-08-30 | Al Shamkhah-Majlis-P6 | P6 | MJ-09 | 46 | 747 | 793 | Fencing Installation Completed on 20 Aug 24. Soil Investagation Testing Lab completed on 27 Aug 24. Drinking Water Area for Labors completed on 29 Aug 24. M/s Emirates Steel Rebar Supplier Prequalification approved on 27 Aug 24. Prequalification for Anti termite of M/s Terminex Pest Control Services Submitted on 30 Aug 24 | *IFC drawings will be issued by next week all buildings. *The contractor has submitted the Project Baseline (BL), Revise &Resubmit | 0% | 0% | 0% | Shelter Construction | 2026-09-15 |  | 2026-09-15 | 2024-09-06 | Issuance of IFC drawings to Contractor. Under Process expected early approval. | Although the IFC drawing is not yet available, AIC is supporting the contractor proactively to start the engineering and procurement phases.” | •PQ for Dewatering, Waterproofing •Material Submittal for Cement(SRC & OPC),Polythene Sheet 1000 Guage, Concrete Cover Blocks, Concrete Solid Blocks,Hollow Blocks & Thermal Blocks •Shop drawings calculation & submission for shoring works – by Specialist(14 days from receipt of IFC drawings) •Concrete Mix Design Submittal for SRC(C65) & Substructure(C65) •Concrete Mix Design Submittal for Gunite | 356759501 |  | 356759501 | 3645800 | 0 | 360405301 |  |  | https://drive.google.com/thumbnail?id=1CGnDxWakVhMcyf3ArpxC0Xg8NB2NJ04m&sz=w1000 | https://drive.google.com/file/d/1CGnDxWakVhMcyf3ArpxC0Xg8NB2NJ04m/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hmXY9RLSychgJTsAJz7iOoJsrTTIp1VT&sz=w1000 | https://drive.google.com/file/d/1hmXY9RLSychgJTsAJz7iOoJsrTTIp1VT/view?usp=drive_link | https://drive.google.com/thumbnail?id=1E_lw9TkbspjWKBlfCTRgy2po44C1TCJP&sz=w1000 | https://drive.google.com/file/d/1E_lw9TkbspjWKBlfCTRgy2po44C1TCJP/view?usp=drive_link
2024-08-30 | Al Shamkhah-Majlis-P6 | P6 | MJ-09 | 46 | 747 | 793 | Fencing Installation Completed on 20 Aug 24. Soil Investagation Testing Lab completed on 27 Aug 24. Drinking Water Area for Labors completed on 29 Aug 24. M/s Emirates Steel Rebar Supplier Prequalification approved on 27 Aug 24. Prequalification for Anti termite of M/s Terminex Pest Control Services Submitted on 30 Aug 24 | *IFC drawings will be issued by next week all buildings. *The contractor has submitted the Project Baseline (BL), Revise &Resubmit | 0% | 0% | 0% | Mosque Constuction | 2026-03-09 |  | 2026-03-09 | 2024-09-06 | Issuance of IFC drawings to Contractor. Under Process expected early approval. | Although the IFC drawing is not yet available, AIC is supporting the contractor proactively to start the engineering and procurement phases.” | •PQ for Dewatering, Waterproofing •Material Submittal for Cement(SRC & OPC),Polythene Sheet 1000 Guage, Concrete Cover Blocks, Concrete Solid Blocks,Hollow Blocks & Thermal Blocks •Shop drawings calculation & submission for shoring works – by Specialist(14 days from receipt of IFC drawings) •Concrete Mix Design Submittal for SRC(C65) & Substructure(C65) •Concrete Mix Design Submittal for Gunite | 356759501 |  | 356759501 | 3645800 | 0 | 360405301 |  |  | https://drive.google.com/thumbnail?id=1CGnDxWakVhMcyf3ArpxC0Xg8NB2NJ04m&sz=w1000 | https://drive.google.com/file/d/1CGnDxWakVhMcyf3ArpxC0Xg8NB2NJ04m/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hmXY9RLSychgJTsAJz7iOoJsrTTIp1VT&sz=w1000 | https://drive.google.com/file/d/1hmXY9RLSychgJTsAJz7iOoJsrTTIp1VT/view?usp=drive_link | https://drive.google.com/thumbnail?id=1E_lw9TkbspjWKBlfCTRgy2po44C1TCJP&sz=w1000 | https://drive.google.com/file/d/1E_lw9TkbspjWKBlfCTRgy2po44C1TCJP/view?usp=drive_link
2024-08-30 | Al Shamkhah-Majlis-P6 | P6 | MJ-09 | 46 | 747 | 793 | Fencing Installation Completed on 20 Aug 24. Soil Investagation Testing Lab completed on 27 Aug 24. Drinking Water Area for Labors completed on 29 Aug 24. M/s Emirates Steel Rebar Supplier Prequalification approved on 27 Aug 24. Prequalification for Anti termite of M/s Terminex Pest Control Services Submitted on 30 Aug 24 | *IFC drawings will be issued by next week all buildings. *The contractor has submitted the Project Baseline (BL), Revise &Resubmit | 0% | 0% | 0% | Majlis Construction | 2026-07-09 |  | 2026-07-09 | 2024-09-06 | Issuance of IFC drawings to Contractor. Under Process expected early approval. | Although the IFC drawing is not yet available, AIC is supporting the contractor proactively to start the engineering and procurement phases.” | •PQ for Dewatering, Waterproofing •Material Submittal for Cement(SRC & OPC),Polythene Sheet 1000 Guage, Concrete Cover Blocks, Concrete Solid Blocks,Hollow Blocks & Thermal Blocks •Shop drawings calculation & submission for shoring works – by Specialist(14 days from receipt of IFC drawings) •Concrete Mix Design Submittal for SRC(C65) & Substructure(C65) •Concrete Mix Design Submittal for Gunite | 356759501 |  | 356759501 | 3645800 | 0 | 360405301 |  |  | https://drive.google.com/thumbnail?id=1CGnDxWakVhMcyf3ArpxC0Xg8NB2NJ04m&sz=w1000 | https://drive.google.com/file/d/1CGnDxWakVhMcyf3ArpxC0Xg8NB2NJ04m/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hmXY9RLSychgJTsAJz7iOoJsrTTIp1VT&sz=w1000 | https://drive.google.com/file/d/1hmXY9RLSychgJTsAJz7iOoJsrTTIp1VT/view?usp=drive_link | https://drive.google.com/thumbnail?id=1E_lw9TkbspjWKBlfCTRgy2po44C1TCJP&sz=w1000 | https://drive.google.com/file/d/1E_lw9TkbspjWKBlfCTRgy2po44C1TCJP/view?usp=drive_link
2024-08-30 | Al Shamkhah-Majlis-P6 | P6 | MJ-09 | 46 | 747 | 793 | Fencing Installation Completed on 20 Aug 24. Soil Investagation Testing Lab completed on 27 Aug 24. Drinking Water Area for Labors completed on 29 Aug 24. M/s Emirates Steel Rebar Supplier Prequalification approved on 27 Aug 24. Prequalification for Anti termite of M/s Terminex Pest Control Services Submitted on 30 Aug 24 | *IFC drawings will be issued by next week all buildings. *The contractor has submitted the Project Baseline (BL), Revise &Resubmit | 0% | 0% | 0% | Ablution Construction | 2026-01-09 |  | 2026-01-09 | 2024-09-06 | Issuance of IFC drawings to Contractor. Under Process expected early approval. | Although the IFC drawing is not yet available, AIC is supporting the contractor proactively to start the engineering and procurement phases.” | •PQ for Dewatering, Waterproofing •Material Submittal for Cement(SRC & OPC),Polythene Sheet 1000 Guage, Concrete Cover Blocks, Concrete Solid Blocks,Hollow Blocks & Thermal Blocks •Shop drawings calculation & submission for shoring works – by Specialist(14 days from receipt of IFC drawings) •Concrete Mix Design Submittal for SRC(C65) & Substructure(C65) •Concrete Mix Design Submittal for Gunite | 356759501 |  | 356759501 | 3645800 | 0 | 360405301 |  |  | https://drive.google.com/thumbnail?id=1CGnDxWakVhMcyf3ArpxC0Xg8NB2NJ04m&sz=w1000 | https://drive.google.com/file/d/1CGnDxWakVhMcyf3ArpxC0Xg8NB2NJ04m/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hmXY9RLSychgJTsAJz7iOoJsrTTIp1VT&sz=w1000 | https://drive.google.com/file/d/1hmXY9RLSychgJTsAJz7iOoJsrTTIp1VT/view?usp=drive_link | https://drive.google.com/thumbnail?id=1E_lw9TkbspjWKBlfCTRgy2po44C1TCJP&sz=w1000 | https://drive.google.com/file/d/1E_lw9TkbspjWKBlfCTRgy2po44C1TCJP/view?usp=drive_link
2024-08-30 | Al Shamkhah-Majlis-P6 | P6 | MJ-09 | 46 | 747 | 793 | Fencing Installation Completed on 20 Aug 24. Soil Investagation Testing Lab completed on 27 Aug 24. Drinking Water Area for Labors completed on 29 Aug 24. M/s Emirates Steel Rebar Supplier Prequalification approved on 27 Aug 24. Prequalification for Anti termite of M/s Terminex Pest Control Services Submitted on 30 Aug 24 | *IFC drawings will be issued by next week all buildings. *The contractor has submitted the Project Baseline (BL), Revise &Resubmit | 0% | 0% | 0% | Imam House Construction | 2026-07-22 |  | 2026-07-22 | 2024-09-06 | Issuance of IFC drawings to Contractor. Under Process expected early approval. | Although the IFC drawing is not yet available, AIC is supporting the contractor proactively to start the engineering and procurement phases.” | •PQ for Dewatering, Waterproofing •Material Submittal for Cement(SRC & OPC),Polythene Sheet 1000 Guage, Concrete Cover Blocks, Concrete Solid Blocks,Hollow Blocks & Thermal Blocks •Shop drawings calculation & submission for shoring works – by Specialist(14 days from receipt of IFC drawings) •Concrete Mix Design Submittal for SRC(C65) & Substructure(C65) •Concrete Mix Design Submittal for Gunite | 356759501 |  | 356759501 | 3645800 | 0 | 360405301 |  |  | https://drive.google.com/thumbnail?id=1CGnDxWakVhMcyf3ArpxC0Xg8NB2NJ04m&sz=w1000 | https://drive.google.com/file/d/1CGnDxWakVhMcyf3ArpxC0Xg8NB2NJ04m/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hmXY9RLSychgJTsAJz7iOoJsrTTIp1VT&sz=w1000 | https://drive.google.com/file/d/1hmXY9RLSychgJTsAJz7iOoJsrTTIp1VT/view?usp=drive_link | https://drive.google.com/thumbnail?id=1E_lw9TkbspjWKBlfCTRgy2po44C1TCJP&sz=w1000 | https://drive.google.com/file/d/1E_lw9TkbspjWKBlfCTRgy2po44C1TCJP/view?usp=drive_link
2024-08-30 | Al Shamkhah-Majlis-P6 | P6 | MJ-09 | 46 | 747 | 793 | Fencing Installation Completed on 20 Aug 24. Soil Investagation Testing Lab completed on 27 Aug 24. Drinking Water Area for Labors completed on 29 Aug 24. M/s Emirates Steel Rebar Supplier Prequalification approved on 27 Aug 24. Prequalification for Anti termite of M/s Terminex Pest Control Services Submitted on 30 Aug 24 | *IFC drawings will be issued by next week all buildings. *The contractor has submitted the Project Baseline (BL), Revise &Resubmit | 0% | 0% | 0% | Pump Room Construction | 2026-07-31 |  | 2026-07-31 | 2024-09-06 | Issuance of IFC drawings to Contractor. Under Process expected early approval. | Although the IFC drawing is not yet available, AIC is supporting the contractor proactively to start the engineering and procurement phases.” | •PQ for Dewatering, Waterproofing •Material Submittal for Cement(SRC & OPC),Polythene Sheet 1000 Guage, Concrete Cover Blocks, Concrete Solid Blocks,Hollow Blocks & Thermal Blocks •Shop drawings calculation & submission for shoring works – by Specialist(14 days from receipt of IFC drawings) •Concrete Mix Design Submittal for SRC(C65) & Substructure(C65) •Concrete Mix Design Submittal for Gunite | 356759501 |  | 356759501 | 3645800 | 0 | 360405301 |  |  | https://drive.google.com/thumbnail?id=1CGnDxWakVhMcyf3ArpxC0Xg8NB2NJ04m&sz=w1000 | https://drive.google.com/file/d/1CGnDxWakVhMcyf3ArpxC0Xg8NB2NJ04m/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hmXY9RLSychgJTsAJz7iOoJsrTTIp1VT&sz=w1000 | https://drive.google.com/file/d/1hmXY9RLSychgJTsAJz7iOoJsrTTIp1VT/view?usp=drive_link | https://drive.google.com/thumbnail?id=1E_lw9TkbspjWKBlfCTRgy2po44C1TCJP&sz=w1000 | https://drive.google.com/file/d/1E_lw9TkbspjWKBlfCTRgy2po44C1TCJP/view?usp=drive_link
2024-08-30 | Al Shamkhah-Majlis-P6 | P6 | MJ-09 | 46 | 747 | 793 | Fencing Installation Completed on 20 Aug 24. Soil Investagation Testing Lab completed on 27 Aug 24. Drinking Water Area for Labors completed on 29 Aug 24. M/s Emirates Steel Rebar Supplier Prequalification approved on 27 Aug 24. Prequalification for Anti termite of M/s Terminex Pest Control Services Submitted on 30 Aug 24 | *IFC drawings will be issued by next week all buildings. *The contractor has submitted the Project Baseline (BL), Revise &Resubmit | 0% | 0% | 0% | Sub Station Construction | 2025-05-12 |  | 2025-05-12 | 2024-09-06 | Issuance of IFC drawings to Contractor. Under Process expected early approval. | Although the IFC drawing is not yet available, AIC is supporting the contractor proactively to start the engineering and procurement phases.” | •PQ for Dewatering, Waterproofing •Material Submittal for Cement(SRC & OPC),Polythene Sheet 1000 Guage, Concrete Cover Blocks, Concrete Solid Blocks,Hollow Blocks & Thermal Blocks •Shop drawings calculation & submission for shoring works – by Specialist(14 days from receipt of IFC drawings) •Concrete Mix Design Submittal for SRC(C65) & Substructure(C65) •Concrete Mix Design Submittal for Gunite | 356759501 |  | 356759501 | 3645800 | 0 | 360405301 |  |  | https://drive.google.com/thumbnail?id=1CGnDxWakVhMcyf3ArpxC0Xg8NB2NJ04m&sz=w1000 | https://drive.google.com/file/d/1CGnDxWakVhMcyf3ArpxC0Xg8NB2NJ04m/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hmXY9RLSychgJTsAJz7iOoJsrTTIp1VT&sz=w1000 | https://drive.google.com/file/d/1hmXY9RLSychgJTsAJz7iOoJsrTTIp1VT/view?usp=drive_link | https://drive.google.com/thumbnail?id=1E_lw9TkbspjWKBlfCTRgy2po44C1TCJP&sz=w1000 | https://drive.google.com/file/d/1E_lw9TkbspjWKBlfCTRgy2po44C1TCJP/view?usp=drive_link
2024-08-30 | Al Shamkhah-Majlis-P6 | P6 | MJ-09 | 46 | 747 | 793 | Fencing Installation Completed on 20 Aug 24. Soil Investagation Testing Lab completed on 27 Aug 24. Drinking Water Area for Labors completed on 29 Aug 24. M/s Emirates Steel Rebar Supplier Prequalification approved on 27 Aug 24. Prequalification for Anti termite of M/s Terminex Pest Control Services Submitted on 30 Aug 24 | *IFC drawings will be issued by next week all buildings. *The contractor has submitted the Project Baseline (BL), Revise &Resubmit | 0% | 0% | 0% | External Works | 2026-04-14 |  | 2026-04-14 | 2024-09-06 | Issuance of IFC drawings to Contractor. Under Process expected early approval. | Although the IFC drawing is not yet available, AIC is supporting the contractor proactively to start the engineering and procurement phases.” | •PQ for Dewatering, Waterproofing •Material Submittal for Cement(SRC & OPC),Polythene Sheet 1000 Guage, Concrete Cover Blocks, Concrete Solid Blocks,Hollow Blocks & Thermal Blocks •Shop drawings calculation & submission for shoring works – by Specialist(14 days from receipt of IFC drawings) •Concrete Mix Design Submittal for SRC(C65) & Substructure(C65) •Concrete Mix Design Submittal for Gunite | 356759501 |  | 356759501 | 3645800 | 0 | 360405301 |  |  | https://drive.google.com/thumbnail?id=1CGnDxWakVhMcyf3ArpxC0Xg8NB2NJ04m&sz=w1000 | https://drive.google.com/file/d/1CGnDxWakVhMcyf3ArpxC0Xg8NB2NJ04m/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hmXY9RLSychgJTsAJz7iOoJsrTTIp1VT&sz=w1000 | https://drive.google.com/file/d/1hmXY9RLSychgJTsAJz7iOoJsrTTIp1VT/view?usp=drive_link | https://drive.google.com/thumbnail?id=1E_lw9TkbspjWKBlfCTRgy2po44C1TCJP&sz=w1000 | https://drive.google.com/file/d/1E_lw9TkbspjWKBlfCTRgy2po44C1TCJP/view?usp=drive_link
2024-08-30 | Al Shamkhah-Majlis-P6 | P6 | MJ-09 | 46 | 747 | 793 | Fencing Installation Completed on 20 Aug 24. Soil Investagation Testing Lab completed on 27 Aug 24. Drinking Water Area for Labors completed on 29 Aug 24. M/s Emirates Steel Rebar Supplier Prequalification approved on 27 Aug 24. Prequalification for Anti termite of M/s Terminex Pest Control Services Submitted on 30 Aug 24 | *IFC drawings will be issued by next week all buildings. *The contractor has submitted the Project Baseline (BL), Revise &Resubmit | 0% | 0% | 0% | Testing & Commissioning | 2026-09-21 |  | 2026-09-21 | 2024-09-06 | Issuance of IFC drawings to Contractor. Under Process expected early approval. | Although the IFC drawing is not yet available, AIC is supporting the contractor proactively to start the engineering and procurement phases.” | •PQ for Dewatering, Waterproofing •Material Submittal for Cement(SRC & OPC),Polythene Sheet 1000 Guage, Concrete Cover Blocks, Concrete Solid Blocks,Hollow Blocks & Thermal Blocks •Shop drawings calculation & submission for shoring works – by Specialist(14 days from receipt of IFC drawings) •Concrete Mix Design Submittal for SRC(C65) & Substructure(C65) •Concrete Mix Design Submittal for Gunite | 356759501 |  | 356759501 | 3645800 | 0 | 360405301 |  |  | https://drive.google.com/thumbnail?id=1CGnDxWakVhMcyf3ArpxC0Xg8NB2NJ04m&sz=w1000 | https://drive.google.com/file/d/1CGnDxWakVhMcyf3ArpxC0Xg8NB2NJ04m/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hmXY9RLSychgJTsAJz7iOoJsrTTIp1VT&sz=w1000 | https://drive.google.com/file/d/1hmXY9RLSychgJTsAJz7iOoJsrTTIp1VT/view?usp=drive_link | https://drive.google.com/thumbnail?id=1E_lw9TkbspjWKBlfCTRgy2po44C1TCJP&sz=w1000 | https://drive.google.com/file/d/1E_lw9TkbspjWKBlfCTRgy2po44C1TCJP/view?usp=drive_link
2024-08-30 | Al Shamkhah-Majlis-P6 | P6 | MJ-09 | 46 | 747 | 793 | Fencing Installation Completed on 20 Aug 24. Soil Investagation Testing Lab completed on 27 Aug 24. Drinking Water Area for Labors completed on 29 Aug 24. M/s Emirates Steel Rebar Supplier Prequalification approved on 27 Aug 24. Prequalification for Anti termite of M/s Terminex Pest Control Services Submitted on 30 Aug 24 | *IFC drawings will be issued by next week all buildings. *The contractor has submitted the Project Baseline (BL), Revise &Resubmit | 0% | 0% | 0% | Authorities Approvals | 2026-10-09 |  | 2026-10-09 | 2024-09-06 | Issuance of IFC drawings to Contractor. Under Process expected early approval. | Although the IFC drawing is not yet available, AIC is supporting the contractor proactively to start the engineering and procurement phases.” | •PQ for Dewatering, Waterproofing •Material Submittal for Cement(SRC & OPC),Polythene Sheet 1000 Guage, Concrete Cover Blocks, Concrete Solid Blocks,Hollow Blocks & Thermal Blocks •Shop drawings calculation & submission for shoring works – by Specialist(14 days from receipt of IFC drawings) •Concrete Mix Design Submittal for SRC(C65) & Substructure(C65) •Concrete Mix Design Submittal for Gunite | 356759501 |  | 356759501 | 3645800 | 0 | 360405301 |  |  | https://drive.google.com/thumbnail?id=1CGnDxWakVhMcyf3ArpxC0Xg8NB2NJ04m&sz=w1000 | https://drive.google.com/file/d/1CGnDxWakVhMcyf3ArpxC0Xg8NB2NJ04m/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hmXY9RLSychgJTsAJz7iOoJsrTTIp1VT&sz=w1000 | https://drive.google.com/file/d/1hmXY9RLSychgJTsAJz7iOoJsrTTIp1VT/view?usp=drive_link | https://drive.google.com/thumbnail?id=1E_lw9TkbspjWKBlfCTRgy2po44C1TCJP&sz=w1000 | https://drive.google.com/file/d/1E_lw9TkbspjWKBlfCTRgy2po44C1TCJP/view?usp=drive_link
2024-08-30 | Al Shamkhah-Majlis-P6 | P6 | MJ-09 | 46 | 747 | 793 | Fencing Installation Completed on 20 Aug 24. Soil Investagation Testing Lab completed on 27 Aug 24. Drinking Water Area for Labors completed on 29 Aug 24. M/s Emirates Steel Rebar Supplier Prequalification approved on 27 Aug 24. Prequalification for Anti termite of M/s Terminex Pest Control Services Submitted on 30 Aug 24 | *IFC drawings will be issued by next week all buildings. *The contractor has submitted the Project Baseline (BL), Revise &Resubmit | 0% | 0% | 0% | Substantial Completion | 2026-09-23 |  | 2026-09-23 | 2024-09-06 | Issuance of IFC drawings to Contractor. Under Process expected early approval. | Although the IFC drawing is not yet available, AIC is supporting the contractor proactively to start the engineering and procurement phases.” | •PQ for Dewatering, Waterproofing •Material Submittal for Cement(SRC & OPC),Polythene Sheet 1000 Guage, Concrete Cover Blocks, Concrete Solid Blocks,Hollow Blocks & Thermal Blocks •Shop drawings calculation & submission for shoring works – by Specialist(14 days from receipt of IFC drawings) •Concrete Mix Design Submittal for SRC(C65) & Substructure(C65) •Concrete Mix Design Submittal for Gunite | 356759501 |  | 356759501 | 3645800 | 0 | 360405301 |  |  | https://drive.google.com/thumbnail?id=1CGnDxWakVhMcyf3ArpxC0Xg8NB2NJ04m&sz=w1000 | https://drive.google.com/file/d/1CGnDxWakVhMcyf3ArpxC0Xg8NB2NJ04m/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hmXY9RLSychgJTsAJz7iOoJsrTTIp1VT&sz=w1000 | https://drive.google.com/file/d/1hmXY9RLSychgJTsAJz7iOoJsrTTIp1VT/view?usp=drive_link | https://drive.google.com/thumbnail?id=1E_lw9TkbspjWKBlfCTRgy2po44C1TCJP&sz=w1000 | https://drive.google.com/file/d/1E_lw9TkbspjWKBlfCTRgy2po44C1TCJP/view?usp=drive_link
2024-08-30 | Baniyas-Majlis-P13 | P13 | MJ-05 | 96 | 634 | 730 | • Shoring guide wall Completed. • Secant piles Completed. • AWQAF approved Mosque Design. • ADDC accepted protection of existing FH/ water pipeline. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. & PS diversion of existing utilities at Plot P1. • Mosque design assigned to APG. | 6.98% | 7.6% | 0.62% | Commencement Date | 2024-06-03 | 2024-06-03 |  | 2024-09-06 | • Permeant piling start, in line with new optimized pile design Note that as per baseline rev 02 the piles for raft will start on 28-Sep-2024 • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • Appoint specialist for diversion of existing fire hydrant at Plot P1 (Mosque), to avoid delay in building permit issuance. • ADM approval for shelter design (if any) | • Expedite MAK revised submission. • Workshop meetings held with MAK & bidders to expedite bidders proposals re-submission. • sevene review & endorsement. • ADM review started on 04 Sep.2024 & in process for structural package. | • Casting of Capping Beam • Starting of Raft piles | 130388712.65 | 0 | 130388712.65 | 4662507.03 | 0 | 135051219.68 | 13053810 |  | https://drive.google.com/thumbnail?id=1zxbs_azC4N6-X3OZD0Sz6VP6Xjewm9-8&sz=w1000 | https://drive.google.com/file/d/1zxbs_azC4N6-X3OZD0Sz6VP6Xjewm9-8/view | https://drive.google.com/thumbnail?id=1tQyDFiR7dq4GijMcq4Q92uVh9nI1y4mw&sz=w1000 | https://drive.google.com/file/d/1tQyDFiR7dq4GijMcq4Q92uVh9nI1y4mw/view | https://drive.google.com/thumbnail?id=1KD8Xfrs6ZPDDeNsgaKv-b1oJyOORtcmH&sz=w1000 | https://drive.google.com/file/d/1KD8Xfrs6ZPDDeNsgaKv-b1oJyOORtcmH/view
2024-08-30 | Baniyas-Majlis-P13 | P13 | MJ-05 | 96 | 634 | 730 | • Shoring guide wall Completed. • Secant piles Completed. • AWQAF approved Mosque Design. • ADDC accepted protection of existing FH/ water pipeline. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. & PS diversion of existing utilities at Plot P1. • Mosque design assigned to APG. | 6.98% | 7.6% | 0.62% | Construction Permit | 2024-06-12 | 2024-05-22 |  | 2024-09-06 | • Permeant piling start, in line with new optimized pile design Note that as per baseline rev 02 the piles for raft will start on 28-Sep-2024 • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • Appoint specialist for diversion of existing fire hydrant at Plot P1 (Mosque), to avoid delay in building permit issuance. • ADM approval for shelter design (if any) | • Expedite MAK revised submission. • Workshop meetings held with MAK & bidders to expedite bidders proposals re-submission. • sevene review & endorsement. • ADM review started on 04 Sep.2024 & in process for structural package. | • Casting of Capping Beam • Starting of Raft piles | 130388712.65 | 0 | 130388712.65 | 4662507.03 | 0 | 135051219.68 | 13053810 |  | https://drive.google.com/thumbnail?id=1zxbs_azC4N6-X3OZD0Sz6VP6Xjewm9-8&sz=w1000 | https://drive.google.com/file/d/1zxbs_azC4N6-X3OZD0Sz6VP6Xjewm9-8/view | https://drive.google.com/thumbnail?id=1tQyDFiR7dq4GijMcq4Q92uVh9nI1y4mw&sz=w1000 | https://drive.google.com/file/d/1tQyDFiR7dq4GijMcq4Q92uVh9nI1y4mw/view | https://drive.google.com/thumbnail?id=1KD8Xfrs6ZPDDeNsgaKv-b1oJyOORtcmH&sz=w1000 | https://drive.google.com/file/d/1KD8Xfrs6ZPDDeNsgaKv-b1oJyOORtcmH/view
2024-08-30 | Baniyas-Majlis-P13 | P13 | MJ-05 | 96 | 634 | 730 | • Shoring guide wall Completed. • Secant piles Completed. • AWQAF approved Mosque Design. • ADDC accepted protection of existing FH/ water pipeline. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. & PS diversion of existing utilities at Plot P1. • Mosque design assigned to APG. | 6.98% | 7.6% | 0.62% | Site Mobilization | 2024-07-10 | 2024-08-08 | 2024-08-08 | 2024-09-06 | • Permeant piling start, in line with new optimized pile design Note that as per baseline rev 02 the piles for raft will start on 28-Sep-2024 • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • Appoint specialist for diversion of existing fire hydrant at Plot P1 (Mosque), to avoid delay in building permit issuance. • ADM approval for shelter design (if any) | • Expedite MAK revised submission. • Workshop meetings held with MAK & bidders to expedite bidders proposals re-submission. • sevene review & endorsement. • ADM review started on 04 Sep.2024 & in process for structural package. | • Casting of Capping Beam • Starting of Raft piles | 130388712.65 | 0 | 130388712.65 | 4662507.03 | 0 | 135051219.68 | 13053810 |  | https://drive.google.com/thumbnail?id=1zxbs_azC4N6-X3OZD0Sz6VP6Xjewm9-8&sz=w1000 | https://drive.google.com/file/d/1zxbs_azC4N6-X3OZD0Sz6VP6Xjewm9-8/view | https://drive.google.com/thumbnail?id=1tQyDFiR7dq4GijMcq4Q92uVh9nI1y4mw&sz=w1000 | https://drive.google.com/file/d/1tQyDFiR7dq4GijMcq4Q92uVh9nI1y4mw/view | https://drive.google.com/thumbnail?id=1KD8Xfrs6ZPDDeNsgaKv-b1oJyOORtcmH&sz=w1000 | https://drive.google.com/file/d/1KD8Xfrs6ZPDDeNsgaKv-b1oJyOORtcmH/view
2024-08-30 | Baniyas-Majlis-P13 | P13 | MJ-05 | 96 | 634 | 730 | • Shoring guide wall Completed. • Secant piles Completed. • AWQAF approved Mosque Design. • ADDC accepted protection of existing FH/ water pipeline. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. & PS diversion of existing utilities at Plot P1. • Mosque design assigned to APG. | 6.98% | 7.6% | 0.62% | Shoring Drilling & Casting | 2024-09-28 |  | 2024-09-28 | 2024-09-06 | • Permeant piling start, in line with new optimized pile design Note that as per baseline rev 02 the piles for raft will start on 28-Sep-2024 • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • Appoint specialist for diversion of existing fire hydrant at Plot P1 (Mosque), to avoid delay in building permit issuance. • ADM approval for shelter design (if any) | • Expedite MAK revised submission. • Workshop meetings held with MAK & bidders to expedite bidders proposals re-submission. • sevene review & endorsement. • ADM review started on 04 Sep.2024 & in process for structural package. | • Casting of Capping Beam • Starting of Raft piles | 130388712.65 | 0 | 130388712.65 | 4662507.03 | 0 | 135051219.68 | 13053810 |  | https://drive.google.com/thumbnail?id=1zxbs_azC4N6-X3OZD0Sz6VP6Xjewm9-8&sz=w1000 | https://drive.google.com/file/d/1zxbs_azC4N6-X3OZD0Sz6VP6Xjewm9-8/view | https://drive.google.com/thumbnail?id=1tQyDFiR7dq4GijMcq4Q92uVh9nI1y4mw&sz=w1000 | https://drive.google.com/file/d/1tQyDFiR7dq4GijMcq4Q92uVh9nI1y4mw/view | https://drive.google.com/thumbnail?id=1KD8Xfrs6ZPDDeNsgaKv-b1oJyOORtcmH&sz=w1000 | https://drive.google.com/file/d/1KD8Xfrs6ZPDDeNsgaKv-b1oJyOORtcmH/view
2024-08-30 | Baniyas-Majlis-P13 | P13 | MJ-05 | 96 | 634 | 730 | • Shoring guide wall Completed. • Secant piles Completed. • AWQAF approved Mosque Design. • ADDC accepted protection of existing FH/ water pipeline. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. & PS diversion of existing utilities at Plot P1. • Mosque design assigned to APG. | 6.98% | 7.6% | 0.62% | Piling Drilling & Casting | 2024-11-29 |  | 2024-11-29 | 2024-09-06 | • Permeant piling start, in line with new optimized pile design Note that as per baseline rev 02 the piles for raft will start on 28-Sep-2024 • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • Appoint specialist for diversion of existing fire hydrant at Plot P1 (Mosque), to avoid delay in building permit issuance. • ADM approval for shelter design (if any) | • Expedite MAK revised submission. • Workshop meetings held with MAK & bidders to expedite bidders proposals re-submission. • sevene review & endorsement. • ADM review started on 04 Sep.2024 & in process for structural package. | • Casting of Capping Beam • Starting of Raft piles | 130388712.65 | 0 | 130388712.65 | 4662507.03 | 0 | 135051219.68 | 13053810 |  | https://drive.google.com/thumbnail?id=1zxbs_azC4N6-X3OZD0Sz6VP6Xjewm9-8&sz=w1000 | https://drive.google.com/file/d/1zxbs_azC4N6-X3OZD0Sz6VP6Xjewm9-8/view | https://drive.google.com/thumbnail?id=1tQyDFiR7dq4GijMcq4Q92uVh9nI1y4mw&sz=w1000 | https://drive.google.com/file/d/1tQyDFiR7dq4GijMcq4Q92uVh9nI1y4mw/view | https://drive.google.com/thumbnail?id=1KD8Xfrs6ZPDDeNsgaKv-b1oJyOORtcmH&sz=w1000 | https://drive.google.com/file/d/1KD8Xfrs6ZPDDeNsgaKv-b1oJyOORtcmH/view
2024-08-30 | Baniyas-Majlis-P13 | P13 | MJ-05 | 96 | 634 | 730 | • Shoring guide wall Completed. • Secant piles Completed. • AWQAF approved Mosque Design. • ADDC accepted protection of existing FH/ water pipeline. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. & PS diversion of existing utilities at Plot P1. • Mosque design assigned to APG. | 6.98% | 7.6% | 0.62% | Excavation | 2025-02-12 |  | 2025-02-12 | 2024-09-06 | • Permeant piling start, in line with new optimized pile design Note that as per baseline rev 02 the piles for raft will start on 28-Sep-2024 • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • Appoint specialist for diversion of existing fire hydrant at Plot P1 (Mosque), to avoid delay in building permit issuance. • ADM approval for shelter design (if any) | • Expedite MAK revised submission. • Workshop meetings held with MAK & bidders to expedite bidders proposals re-submission. • sevene review & endorsement. • ADM review started on 04 Sep.2024 & in process for structural package. | • Casting of Capping Beam • Starting of Raft piles | 130388712.65 | 0 | 130388712.65 | 4662507.03 | 0 | 135051219.68 | 13053810 |  | https://drive.google.com/thumbnail?id=1zxbs_azC4N6-X3OZD0Sz6VP6Xjewm9-8&sz=w1000 | https://drive.google.com/file/d/1zxbs_azC4N6-X3OZD0Sz6VP6Xjewm9-8/view | https://drive.google.com/thumbnail?id=1tQyDFiR7dq4GijMcq4Q92uVh9nI1y4mw&sz=w1000 | https://drive.google.com/file/d/1tQyDFiR7dq4GijMcq4Q92uVh9nI1y4mw/view | https://drive.google.com/thumbnail?id=1KD8Xfrs6ZPDDeNsgaKv-b1oJyOORtcmH&sz=w1000 | https://drive.google.com/file/d/1KD8Xfrs6ZPDDeNsgaKv-b1oJyOORtcmH/view
2024-08-30 | Baniyas-Majlis-P13 | P13 | MJ-05 | 96 | 634 | 730 | • Shoring guide wall Completed. • Secant piles Completed. • AWQAF approved Mosque Design. • ADDC accepted protection of existing FH/ water pipeline. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. & PS diversion of existing utilities at Plot P1. • Mosque design assigned to APG. | 6.98% | 7.6% | 0.62% | Substructure | 2025-07-20 |  | 2025-07-20 | 2024-09-06 | • Permeant piling start, in line with new optimized pile design Note that as per baseline rev 02 the piles for raft will start on 28-Sep-2024 • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • Appoint specialist for diversion of existing fire hydrant at Plot P1 (Mosque), to avoid delay in building permit issuance. • ADM approval for shelter design (if any) | • Expedite MAK revised submission. • Workshop meetings held with MAK & bidders to expedite bidders proposals re-submission. • sevene review & endorsement. • ADM review started on 04 Sep.2024 & in process for structural package. | • Casting of Capping Beam • Starting of Raft piles | 130388712.65 | 0 | 130388712.65 | 4662507.03 | 0 | 135051219.68 | 13053810 |  | https://drive.google.com/thumbnail?id=1zxbs_azC4N6-X3OZD0Sz6VP6Xjewm9-8&sz=w1000 | https://drive.google.com/file/d/1zxbs_azC4N6-X3OZD0Sz6VP6Xjewm9-8/view | https://drive.google.com/thumbnail?id=1tQyDFiR7dq4GijMcq4Q92uVh9nI1y4mw&sz=w1000 | https://drive.google.com/file/d/1tQyDFiR7dq4GijMcq4Q92uVh9nI1y4mw/view | https://drive.google.com/thumbnail?id=1KD8Xfrs6ZPDDeNsgaKv-b1oJyOORtcmH&sz=w1000 | https://drive.google.com/file/d/1KD8Xfrs6ZPDDeNsgaKv-b1oJyOORtcmH/view
2024-08-30 | Baniyas-Majlis-P13 | P13 | MJ-05 | 96 | 634 | 730 | • Shoring guide wall Completed. • Secant piles Completed. • AWQAF approved Mosque Design. • ADDC accepted protection of existing FH/ water pipeline. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. & PS diversion of existing utilities at Plot P1. • Mosque design assigned to APG. | 6.98% | 7.6% | 0.62% | Superstructure | 2025-11-06 |  | 2025-11-06 | 2024-09-06 | • Permeant piling start, in line with new optimized pile design Note that as per baseline rev 02 the piles for raft will start on 28-Sep-2024 • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • Appoint specialist for diversion of existing fire hydrant at Plot P1 (Mosque), to avoid delay in building permit issuance. • ADM approval for shelter design (if any) | • Expedite MAK revised submission. • Workshop meetings held with MAK & bidders to expedite bidders proposals re-submission. • sevene review & endorsement. • ADM review started on 04 Sep.2024 & in process for structural package. | • Casting of Capping Beam • Starting of Raft piles | 130388712.65 | 0 | 130388712.65 | 4662507.03 | 0 | 135051219.68 | 13053810 |  | https://drive.google.com/thumbnail?id=1zxbs_azC4N6-X3OZD0Sz6VP6Xjewm9-8&sz=w1000 | https://drive.google.com/file/d/1zxbs_azC4N6-X3OZD0Sz6VP6Xjewm9-8/view | https://drive.google.com/thumbnail?id=1tQyDFiR7dq4GijMcq4Q92uVh9nI1y4mw&sz=w1000 | https://drive.google.com/file/d/1tQyDFiR7dq4GijMcq4Q92uVh9nI1y4mw/view | https://drive.google.com/thumbnail?id=1KD8Xfrs6ZPDDeNsgaKv-b1oJyOORtcmH&sz=w1000 | https://drive.google.com/file/d/1KD8Xfrs6ZPDDeNsgaKv-b1oJyOORtcmH/view
2024-08-30 | Baniyas-Majlis-P13 | P13 | MJ-05 | 96 | 634 | 730 | • Shoring guide wall Completed. • Secant piles Completed. • AWQAF approved Mosque Design. • ADDC accepted protection of existing FH/ water pipeline. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. & PS diversion of existing utilities at Plot P1. • Mosque design assigned to APG. | 6.98% | 7.6% | 0.62% | MEP & Finishes | 2026-05-08 |  | 2026-05-08 | 2024-09-06 | • Permeant piling start, in line with new optimized pile design Note that as per baseline rev 02 the piles for raft will start on 28-Sep-2024 • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • Appoint specialist for diversion of existing fire hydrant at Plot P1 (Mosque), to avoid delay in building permit issuance. • ADM approval for shelter design (if any) | • Expedite MAK revised submission. • Workshop meetings held with MAK & bidders to expedite bidders proposals re-submission. • sevene review & endorsement. • ADM review started on 04 Sep.2024 & in process for structural package. | • Casting of Capping Beam • Starting of Raft piles | 130388712.65 | 0 | 130388712.65 | 4662507.03 | 0 | 135051219.68 | 13053810 |  | https://drive.google.com/thumbnail?id=1zxbs_azC4N6-X3OZD0Sz6VP6Xjewm9-8&sz=w1000 | https://drive.google.com/file/d/1zxbs_azC4N6-X3OZD0Sz6VP6Xjewm9-8/view | https://drive.google.com/thumbnail?id=1tQyDFiR7dq4GijMcq4Q92uVh9nI1y4mw&sz=w1000 | https://drive.google.com/file/d/1tQyDFiR7dq4GijMcq4Q92uVh9nI1y4mw/view | https://drive.google.com/thumbnail?id=1KD8Xfrs6ZPDDeNsgaKv-b1oJyOORtcmH&sz=w1000 | https://drive.google.com/file/d/1KD8Xfrs6ZPDDeNsgaKv-b1oJyOORtcmH/view
2024-08-30 | Baniyas-Majlis-P13 | P13 | MJ-05 | 96 | 634 | 730 | • Shoring guide wall Completed. • Secant piles Completed. • AWQAF approved Mosque Design. • ADDC accepted protection of existing FH/ water pipeline. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. & PS diversion of existing utilities at Plot P1. • Mosque design assigned to APG. | 6.98% | 7.6% | 0.62% | Authorities NOCs/BCC | 2026-05-22 |  | 2026-05-22 | 2024-09-06 | • Permeant piling start, in line with new optimized pile design Note that as per baseline rev 02 the piles for raft will start on 28-Sep-2024 • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • Appoint specialist for diversion of existing fire hydrant at Plot P1 (Mosque), to avoid delay in building permit issuance. • ADM approval for shelter design (if any) | • Expedite MAK revised submission. • Workshop meetings held with MAK & bidders to expedite bidders proposals re-submission. • sevene review & endorsement. • ADM review started on 04 Sep.2024 & in process for structural package. | • Casting of Capping Beam • Starting of Raft piles | 130388712.65 | 0 | 130388712.65 | 4662507.03 | 0 | 135051219.68 | 13053810 |  | https://drive.google.com/thumbnail?id=1zxbs_azC4N6-X3OZD0Sz6VP6Xjewm9-8&sz=w1000 | https://drive.google.com/file/d/1zxbs_azC4N6-X3OZD0Sz6VP6Xjewm9-8/view | https://drive.google.com/thumbnail?id=1tQyDFiR7dq4GijMcq4Q92uVh9nI1y4mw&sz=w1000 | https://drive.google.com/file/d/1tQyDFiR7dq4GijMcq4Q92uVh9nI1y4mw/view | https://drive.google.com/thumbnail?id=1KD8Xfrs6ZPDDeNsgaKv-b1oJyOORtcmH&sz=w1000 | https://drive.google.com/file/d/1KD8Xfrs6ZPDDeNsgaKv-b1oJyOORtcmH/view
2024-08-30 | Baniyas-Majlis-P13 | P13 | MJ-05 | 96 | 634 | 730 | • Shoring guide wall Completed. • Secant piles Completed. • AWQAF approved Mosque Design. • ADDC accepted protection of existing FH/ water pipeline. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. & PS diversion of existing utilities at Plot P1. • Mosque design assigned to APG. | 6.98% | 7.6% | 0.62% | External Works | 2026-06-01 |  | 2026-06-01 | 2024-09-06 | • Permeant piling start, in line with new optimized pile design Note that as per baseline rev 02 the piles for raft will start on 28-Sep-2024 • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • Appoint specialist for diversion of existing fire hydrant at Plot P1 (Mosque), to avoid delay in building permit issuance. • ADM approval for shelter design (if any) | • Expedite MAK revised submission. • Workshop meetings held with MAK & bidders to expedite bidders proposals re-submission. • sevene review & endorsement. • ADM review started on 04 Sep.2024 & in process for structural package. | • Casting of Capping Beam • Starting of Raft piles | 130388712.65 | 0 | 130388712.65 | 4662507.03 | 0 | 135051219.68 | 13053810 |  | https://drive.google.com/thumbnail?id=1zxbs_azC4N6-X3OZD0Sz6VP6Xjewm9-8&sz=w1000 | https://drive.google.com/file/d/1zxbs_azC4N6-X3OZD0Sz6VP6Xjewm9-8/view | https://drive.google.com/thumbnail?id=1tQyDFiR7dq4GijMcq4Q92uVh9nI1y4mw&sz=w1000 | https://drive.google.com/file/d/1tQyDFiR7dq4GijMcq4Q92uVh9nI1y4mw/view | https://drive.google.com/thumbnail?id=1KD8Xfrs6ZPDDeNsgaKv-b1oJyOORtcmH&sz=w1000 | https://drive.google.com/file/d/1KD8Xfrs6ZPDDeNsgaKv-b1oJyOORtcmH/view
2024-08-30 | Baniyas-Majlis-P13 | P13 | MJ-05 | 96 | 634 | 730 | • Shoring guide wall Completed. • Secant piles Completed. • AWQAF approved Mosque Design. • ADDC accepted protection of existing FH/ water pipeline. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. & PS diversion of existing utilities at Plot P1. • Mosque design assigned to APG. | 6.98% | 7.6% | 0.62% | Testing & Commissioning | 2026-06-02 |  | 2026-06-02 | 2024-09-06 | • Permeant piling start, in line with new optimized pile design Note that as per baseline rev 02 the piles for raft will start on 28-Sep-2024 • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • Appoint specialist for diversion of existing fire hydrant at Plot P1 (Mosque), to avoid delay in building permit issuance. • ADM approval for shelter design (if any) | • Expedite MAK revised submission. • Workshop meetings held with MAK & bidders to expedite bidders proposals re-submission. • sevene review & endorsement. • ADM review started on 04 Sep.2024 & in process for structural package. | • Casting of Capping Beam • Starting of Raft piles | 130388712.65 | 0 | 130388712.65 | 4662507.03 | 0 | 135051219.68 | 13053810 |  | https://drive.google.com/thumbnail?id=1zxbs_azC4N6-X3OZD0Sz6VP6Xjewm9-8&sz=w1000 | https://drive.google.com/file/d/1zxbs_azC4N6-X3OZD0Sz6VP6Xjewm9-8/view | https://drive.google.com/thumbnail?id=1tQyDFiR7dq4GijMcq4Q92uVh9nI1y4mw&sz=w1000 | https://drive.google.com/file/d/1tQyDFiR7dq4GijMcq4Q92uVh9nI1y4mw/view | https://drive.google.com/thumbnail?id=1KD8Xfrs6ZPDDeNsgaKv-b1oJyOORtcmH&sz=w1000 | https://drive.google.com/file/d/1KD8Xfrs6ZPDDeNsgaKv-b1oJyOORtcmH/view
2024-08-30 | Baniyas-Majlis-P13 | P13 | MJ-05 | 96 | 634 | 730 | • Shoring guide wall Completed. • Secant piles Completed. • AWQAF approved Mosque Design. • ADDC accepted protection of existing FH/ water pipeline. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. & PS diversion of existing utilities at Plot P1. • Mosque design assigned to APG. | 6.98% | 7.6% | 0.62% | Substantial Completion | 2026-06-02 |  | 2026-06-02 | 2024-09-06 | • Permeant piling start, in line with new optimized pile design Note that as per baseline rev 02 the piles for raft will start on 28-Sep-2024 • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • Appoint specialist for diversion of existing fire hydrant at Plot P1 (Mosque), to avoid delay in building permit issuance. • ADM approval for shelter design (if any) | • Expedite MAK revised submission. • Workshop meetings held with MAK & bidders to expedite bidders proposals re-submission. • sevene review & endorsement. • ADM review started on 04 Sep.2024 & in process for structural package. | • Casting of Capping Beam • Starting of Raft piles | 130388712.65 | 0 | 130388712.65 | 4662507.03 | 0 | 135051219.68 | 13053810 |  | https://drive.google.com/thumbnail?id=1_9wvDD0xzarupnO-MkGQjPWkgNEleRMr&sz=w1000 | https://drive.google.com/file/d/1_9wvDD0xzarupnO-MkGQjPWkgNEleRMr/view | https://drive.google.com/thumbnail?id=1rhCvHfKmw2WQRnaHsokOte7r7Nl3uIJy&sz=w1000 | https://drive.google.com/file/d/1rhCvHfKmw2WQRnaHsokOte7r7Nl3uIJy/view | https://drive.google.com/thumbnail?id=1XM56ViSsm-28H781ilJpgfRH-h3HxQCr&sz=w1000 | https://drive.google.com/file/d/1XM56ViSsm-28H781ilJpgfRH-h3HxQCr/view
2024-08-30 | Zayed City-Majlis-P17 | P17 | MJ-04 | 96 | 634 | 730 | • Shoring guide Completed • Shoring pilling in progress. • Site office utilities connection in progress. • Welfare facilities in progress | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. | 8.08% | 8.59% | 0.51% | Commencement Date | 2024-06-03 | 2024-06-03 |  | 2024-09-06 | • Permeant piling start, in line with new optimized pile design Note that as per baseline rev 02 the piles for raft will start on 28-Sep-2024 • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval for shelter design (if any) | • Expedite MAK revised submission. • Workshop meetings held with MAK & bidders to expedite bidders proposals re-submission • ADM review started on 04 Sep.2024 & in process for structural package. | • Casting of Secant Piles • Casting of Capping beam • Starting of Raft Piles. | 130388712.65 | 0 | 130388712.65 | 4662507.03 | 0 | 135051219.68 | 13053810 |  | https://drive.google.com/thumbnail?id=1_9wvDD0xzarupnO-MkGQjPWkgNEleRMr&sz=w1000 | https://drive.google.com/file/d/1_9wvDD0xzarupnO-MkGQjPWkgNEleRMr/view | https://drive.google.com/thumbnail?id=1rhCvHfKmw2WQRnaHsokOte7r7Nl3uIJy&sz=w1000 | https://drive.google.com/file/d/1rhCvHfKmw2WQRnaHsokOte7r7Nl3uIJy/view | https://drive.google.com/thumbnail?id=1XM56ViSsm-28H781ilJpgfRH-h3HxQCr&sz=w1000 | https://drive.google.com/file/d/1XM56ViSsm-28H781ilJpgfRH-h3HxQCr/view
2024-08-30 | Zayed City-Majlis-P17 | P17 | MJ-04 | 96 | 634 | 730 | • Shoring guide Completed • Shoring pilling in progress. • Site office utilities connection in progress. • Welfare facilities in progress | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. | 8.08% | 8.59% | 0.51% | Construction Permit | 2024-06-12 | 2024-05-27 |  | 2024-09-06 | • Permeant piling start, in line with new optimized pile design Note that as per baseline rev 02 the piles for raft will start on 28-Sep-2024 • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval for shelter design (if any) | • Expedite MAK revised submission. • Workshop meetings held with MAK & bidders to expedite bidders proposals re-submission • ADM review started on 04 Sep.2024 & in process for structural package. | • Casting of Secant Piles • Casting of Capping beam • Starting of Raft Piles. | 106953287.35 | 0 | 106953287.35 | 3824490.97 | 0 | 110777778.32 | 10680390 |  | https://drive.google.com/thumbnail?id=1_9wvDD0xzarupnO-MkGQjPWkgNEleRMr&sz=w1000 | https://drive.google.com/file/d/1_9wvDD0xzarupnO-MkGQjPWkgNEleRMr/view | https://drive.google.com/thumbnail?id=1rhCvHfKmw2WQRnaHsokOte7r7Nl3uIJy&sz=w1000 | https://drive.google.com/file/d/1rhCvHfKmw2WQRnaHsokOte7r7Nl3uIJy/view | https://drive.google.com/thumbnail?id=1XM56ViSsm-28H781ilJpgfRH-h3HxQCr&sz=w1000 | https://drive.google.com/file/d/1XM56ViSsm-28H781ilJpgfRH-h3HxQCr/view
2024-08-30 | Zayed City-Majlis-P17 | P17 | MJ-04 | 96 | 634 | 730 | • Shoring guide Completed • Shoring pilling in progress. • Site office utilities connection in progress. • Welfare facilities in progress | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. | 8.08% | 8.59% | 0.51% | Site Mobilization | 2024-07-10 | 2024-08-15 | 2024-08-15 | 2024-09-06 | • Permeant piling start, in line with new optimized pile design Note that as per baseline rev 02 the piles for raft will start on 28-Sep-2024 • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval for shelter design (if any) | • Expedite MAK revised submission. • Workshop meetings held with MAK & bidders to expedite bidders proposals re-submission • ADM review started on 04 Sep.2024 & in process for structural package. | • Casting of Secant Piles • Casting of Capping beam • Starting of Raft Piles. | 106953287.35 | 0 | 106953287.35 | 3824490.97 | 0 | 110777778.32 | 10680390 |  | https://drive.google.com/thumbnail?id=1_9wvDD0xzarupnO-MkGQjPWkgNEleRMr&sz=w1000 | https://drive.google.com/file/d/1_9wvDD0xzarupnO-MkGQjPWkgNEleRMr/view | https://drive.google.com/thumbnail?id=1rhCvHfKmw2WQRnaHsokOte7r7Nl3uIJy&sz=w1000 | https://drive.google.com/file/d/1rhCvHfKmw2WQRnaHsokOte7r7Nl3uIJy/view | https://drive.google.com/thumbnail?id=1XM56ViSsm-28H781ilJpgfRH-h3HxQCr&sz=w1000 | https://drive.google.com/file/d/1XM56ViSsm-28H781ilJpgfRH-h3HxQCr/view
2024-08-30 | Zayed City-Majlis-P17 | P17 | MJ-04 | 96 | 634 | 730 | • Shoring guide Completed • Shoring pilling in progress. • Site office utilities connection in progress. • Welfare facilities in progress | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. | 8.08% | 8.59% | 0.51% | Shoring Drilling & Casting | 2024-09-30 |  | 2024-09-30 | 2024-09-06 | • Permeant piling start, in line with new optimized pile design Note that as per baseline rev 02 the piles for raft will start on 28-Sep-2024 • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval for shelter design (if any) | • Expedite MAK revised submission. • Workshop meetings held with MAK & bidders to expedite bidders proposals re-submission • ADM review started on 04 Sep.2024 & in process for structural package. | • Casting of Secant Piles • Casting of Capping beam • Starting of Raft Piles. | 106953287.35 | 0 | 106953287.35 | 3824490.97 | 0 | 110777778.32 | 10680390 |  | https://drive.google.com/thumbnail?id=1_9wvDD0xzarupnO-MkGQjPWkgNEleRMr&sz=w1000 | https://drive.google.com/file/d/1_9wvDD0xzarupnO-MkGQjPWkgNEleRMr/view | https://drive.google.com/thumbnail?id=1rhCvHfKmw2WQRnaHsokOte7r7Nl3uIJy&sz=w1000 | https://drive.google.com/file/d/1rhCvHfKmw2WQRnaHsokOte7r7Nl3uIJy/view | https://drive.google.com/thumbnail?id=1XM56ViSsm-28H781ilJpgfRH-h3HxQCr&sz=w1000 | https://drive.google.com/file/d/1XM56ViSsm-28H781ilJpgfRH-h3HxQCr/view
2024-08-30 | Zayed City-Majlis-P17 | P17 | MJ-04 | 96 | 634 | 730 | • Shoring guide Completed • Shoring pilling in progress. • Site office utilities connection in progress. • Welfare facilities in progress | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. | 8.08% | 8.59% | 0.51% | Piling Drilling & Casting | 2024-11-30 |  | 2024-11-30 | 2024-09-06 | • Permeant piling start, in line with new optimized pile design Note that as per baseline rev 02 the piles for raft will start on 28-Sep-2024 • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval for shelter design (if any) | • Expedite MAK revised submission. • Workshop meetings held with MAK & bidders to expedite bidders proposals re-submission • ADM review started on 04 Sep.2024 & in process for structural package. | • Casting of Secant Piles • Casting of Capping beam • Starting of Raft Piles. | 106953287.35 | 0 | 106953287.35 | 3824490.97 | 0 | 110777778.32 | 10680390 |  | https://drive.google.com/thumbnail?id=1_9wvDD0xzarupnO-MkGQjPWkgNEleRMr&sz=w1000 | https://drive.google.com/file/d/1_9wvDD0xzarupnO-MkGQjPWkgNEleRMr/view | https://drive.google.com/thumbnail?id=1rhCvHfKmw2WQRnaHsokOte7r7Nl3uIJy&sz=w1000 | https://drive.google.com/file/d/1rhCvHfKmw2WQRnaHsokOte7r7Nl3uIJy/view | https://drive.google.com/thumbnail?id=1XM56ViSsm-28H781ilJpgfRH-h3HxQCr&sz=w1000 | https://drive.google.com/file/d/1XM56ViSsm-28H781ilJpgfRH-h3HxQCr/view
2024-08-30 | Zayed City-Majlis-P17 | P17 | MJ-04 | 96 | 634 | 730 | • Shoring guide Completed • Shoring pilling in progress. • Site office utilities connection in progress. • Welfare facilities in progress | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. | 8.08% | 8.59% | 0.51% | Excavation | 2025-02-13 |  | 2025-02-13 | 2024-09-06 | • Permeant piling start, in line with new optimized pile design Note that as per baseline rev 02 the piles for raft will start on 28-Sep-2024 • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval for shelter design (if any) | • Expedite MAK revised submission. • Workshop meetings held with MAK & bidders to expedite bidders proposals re-submission • ADM review started on 04 Sep.2024 & in process for structural package. | • Casting of Secant Piles • Casting of Capping beam • Starting of Raft Piles. | 106953287.35 | 0 | 106953287.35 | 3824490.97 | 0 | 110777778.32 | 10680390 |  | https://drive.google.com/thumbnail?id=1_9wvDD0xzarupnO-MkGQjPWkgNEleRMr&sz=w1000 | https://drive.google.com/file/d/1_9wvDD0xzarupnO-MkGQjPWkgNEleRMr/view | https://drive.google.com/thumbnail?id=1rhCvHfKmw2WQRnaHsokOte7r7Nl3uIJy&sz=w1000 | https://drive.google.com/file/d/1rhCvHfKmw2WQRnaHsokOte7r7Nl3uIJy/view | https://drive.google.com/thumbnail?id=1XM56ViSsm-28H781ilJpgfRH-h3HxQCr&sz=w1000 | https://drive.google.com/file/d/1XM56ViSsm-28H781ilJpgfRH-h3HxQCr/view
2024-08-30 | Zayed City-Majlis-P17 | P17 | MJ-04 | 96 | 634 | 730 | • Shoring guide Completed • Shoring pilling in progress. • Site office utilities connection in progress. • Welfare facilities in progress | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. | 8.08% | 8.59% | 0.51% | Substructure | 2025-07-20 |  | 2025-07-20 | 2024-09-06 | • Permeant piling start, in line with new optimized pile design Note that as per baseline rev 02 the piles for raft will start on 28-Sep-2024 • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval for shelter design (if any) | • Expedite MAK revised submission. • Workshop meetings held with MAK & bidders to expedite bidders proposals re-submission • ADM review started on 04 Sep.2024 & in process for structural package. | • Casting of Secant Piles • Casting of Capping beam • Starting of Raft Piles. | 106953287.35 | 0 | 106953287.35 | 3824490.97 | 0 | 110777778.32 | 10680390 |  | https://drive.google.com/thumbnail?id=1_9wvDD0xzarupnO-MkGQjPWkgNEleRMr&sz=w1000 | https://drive.google.com/file/d/1_9wvDD0xzarupnO-MkGQjPWkgNEleRMr/view | https://drive.google.com/thumbnail?id=1rhCvHfKmw2WQRnaHsokOte7r7Nl3uIJy&sz=w1000 | https://drive.google.com/file/d/1rhCvHfKmw2WQRnaHsokOte7r7Nl3uIJy/view | https://drive.google.com/thumbnail?id=1XM56ViSsm-28H781ilJpgfRH-h3HxQCr&sz=w1000 | https://drive.google.com/file/d/1XM56ViSsm-28H781ilJpgfRH-h3HxQCr/view
2024-08-30 | Zayed City-Majlis-P17 | P17 | MJ-04 | 96 | 634 | 730 | • Shoring guide Completed • Shoring pilling in progress. • Site office utilities connection in progress. • Welfare facilities in progress | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. | 8.08% | 8.59% | 0.51% | Superstructure | 2025-11-13 |  | 2025-11-13 | 2024-09-06 | • Permeant piling start, in line with new optimized pile design Note that as per baseline rev 02 the piles for raft will start on 28-Sep-2024 • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval for shelter design (if any) | • Expedite MAK revised submission. • Workshop meetings held with MAK & bidders to expedite bidders proposals re-submission • ADM review started on 04 Sep.2024 & in process for structural package. | • Casting of Secant Piles • Casting of Capping beam • Starting of Raft Piles. | 106953287.35 | 0 | 106953287.35 | 3824490.97 | 0 | 110777778.32 | 10680390 |  | https://drive.google.com/thumbnail?id=1_9wvDD0xzarupnO-MkGQjPWkgNEleRMr&sz=w1000 | https://drive.google.com/file/d/1_9wvDD0xzarupnO-MkGQjPWkgNEleRMr/view | https://drive.google.com/thumbnail?id=1rhCvHfKmw2WQRnaHsokOte7r7Nl3uIJy&sz=w1000 | https://drive.google.com/file/d/1rhCvHfKmw2WQRnaHsokOte7r7Nl3uIJy/view | https://drive.google.com/thumbnail?id=1XM56ViSsm-28H781ilJpgfRH-h3HxQCr&sz=w1000 | https://drive.google.com/file/d/1XM56ViSsm-28H781ilJpgfRH-h3HxQCr/view
2024-08-30 | Zayed City-Majlis-P17 | P17 | MJ-04 | 96 | 634 | 730 | • Shoring guide Completed • Shoring pilling in progress. • Site office utilities connection in progress. • Welfare facilities in progress | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. | 8.08% | 8.59% | 0.51% | MEP & Finishes | 2026-05-08 |  | 2026-05-08 | 2024-09-06 | • Permeant piling start, in line with new optimized pile design Note that as per baseline rev 02 the piles for raft will start on 28-Sep-2024 • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval for shelter design (if any) | • Expedite MAK revised submission. • Workshop meetings held with MAK & bidders to expedite bidders proposals re-submission • ADM review started on 04 Sep.2024 & in process for structural package. | • Casting of Secant Piles • Casting of Capping beam • Starting of Raft Piles. | 106953287.35 | 0 | 106953287.35 | 3824490.97 | 0 | 110777778.32 | 10680390 |  | https://drive.google.com/thumbnail?id=1_9wvDD0xzarupnO-MkGQjPWkgNEleRMr&sz=w1000 | https://drive.google.com/file/d/1_9wvDD0xzarupnO-MkGQjPWkgNEleRMr/view | https://drive.google.com/thumbnail?id=1rhCvHfKmw2WQRnaHsokOte7r7Nl3uIJy&sz=w1000 | https://drive.google.com/file/d/1rhCvHfKmw2WQRnaHsokOte7r7Nl3uIJy/view | https://drive.google.com/thumbnail?id=1XM56ViSsm-28H781ilJpgfRH-h3HxQCr&sz=w1000 | https://drive.google.com/file/d/1XM56ViSsm-28H781ilJpgfRH-h3HxQCr/view
2024-08-30 | Zayed City-Majlis-P17 | P17 | MJ-04 | 96 | 634 | 730 | • Shoring guide Completed • Shoring pilling in progress. • Site office utilities connection in progress. • Welfare facilities in progress | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. | 8.08% | 8.59% | 0.51% | Authorities NOCs/BCC | 2026-05-29 |  | 2026-05-29 | 2024-09-06 | • Permeant piling start, in line with new optimized pile design Note that as per baseline rev 02 the piles for raft will start on 28-Sep-2024 • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval for shelter design (if any) | • Expedite MAK revised submission. • Workshop meetings held with MAK & bidders to expedite bidders proposals re-submission • ADM review started on 04 Sep.2024 & in process for structural package. | • Casting of Secant Piles • Casting of Capping beam • Starting of Raft Piles. | 106953287.35 | 0 | 106953287.35 | 3824490.97 | 0 | 110777778.32 | 10680390 |  | https://drive.google.com/thumbnail?id=1_9wvDD0xzarupnO-MkGQjPWkgNEleRMr&sz=w1000 | https://drive.google.com/file/d/1_9wvDD0xzarupnO-MkGQjPWkgNEleRMr/view | https://drive.google.com/thumbnail?id=1rhCvHfKmw2WQRnaHsokOte7r7Nl3uIJy&sz=w1000 | https://drive.google.com/file/d/1rhCvHfKmw2WQRnaHsokOte7r7Nl3uIJy/view | https://drive.google.com/thumbnail?id=1XM56ViSsm-28H781ilJpgfRH-h3HxQCr&sz=w1000 | https://drive.google.com/file/d/1XM56ViSsm-28H781ilJpgfRH-h3HxQCr/view
2024-08-30 | Zayed City-Majlis-P17 | P17 | MJ-04 | 96 | 634 | 730 | • Shoring guide Completed • Shoring pilling in progress. • Site office utilities connection in progress. • Welfare facilities in progress | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. | 8.08% | 8.59% | 0.51% | External Works | 2026-06-02 |  | 2026-06-02 | 2024-09-06 | • Permeant piling start, in line with new optimized pile design Note that as per baseline rev 02 the piles for raft will start on 28-Sep-2024 • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval for shelter design (if any) | • Expedite MAK revised submission. • Workshop meetings held with MAK & bidders to expedite bidders proposals re-submission • ADM review started on 04 Sep.2024 & in process for structural package. | • Casting of Secant Piles • Casting of Capping beam • Starting of Raft Piles. | 106953287.35 | 0 | 106953287.35 | 3824490.97 | 0 | 110777778.32 | 10680390 |  | https://drive.google.com/thumbnail?id=1_9wvDD0xzarupnO-MkGQjPWkgNEleRMr&sz=w1000 | https://drive.google.com/file/d/1_9wvDD0xzarupnO-MkGQjPWkgNEleRMr/view | https://drive.google.com/thumbnail?id=1rhCvHfKmw2WQRnaHsokOte7r7Nl3uIJy&sz=w1000 | https://drive.google.com/file/d/1rhCvHfKmw2WQRnaHsokOte7r7Nl3uIJy/view | https://drive.google.com/thumbnail?id=1XM56ViSsm-28H781ilJpgfRH-h3HxQCr&sz=w1000 | https://drive.google.com/file/d/1XM56ViSsm-28H781ilJpgfRH-h3HxQCr/view
2024-08-30 | Zayed City-Majlis-P17 | P17 | MJ-04 | 96 | 634 | 730 | • Shoring guide Completed • Shoring pilling in progress. • Site office utilities connection in progress. • Welfare facilities in progress | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. | 8.08% | 8.59% | 0.51% | Testing & Commissioning | 2026-06-02 |  | 2026-06-02 | 2024-09-06 | • Permeant piling start, in line with new optimized pile design Note that as per baseline rev 02 the piles for raft will start on 28-Sep-2024 • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval for shelter design (if any) | • Expedite MAK revised submission. • Workshop meetings held with MAK & bidders to expedite bidders proposals re-submission • ADM review started on 04 Sep.2024 & in process for structural package. | • Casting of Secant Piles • Casting of Capping beam • Starting of Raft Piles. | 106953287.35 | 0 | 106953287.35 | 3824490.97 | 0 | 110777778.32 | 10680390 |  | https://drive.google.com/thumbnail?id=1_9wvDD0xzarupnO-MkGQjPWkgNEleRMr&sz=w1000 | https://drive.google.com/file/d/1_9wvDD0xzarupnO-MkGQjPWkgNEleRMr/view | https://drive.google.com/thumbnail?id=1rhCvHfKmw2WQRnaHsokOte7r7Nl3uIJy&sz=w1000 | https://drive.google.com/file/d/1rhCvHfKmw2WQRnaHsokOte7r7Nl3uIJy/view | https://drive.google.com/thumbnail?id=1XM56ViSsm-28H781ilJpgfRH-h3HxQCr&sz=w1000 | https://drive.google.com/file/d/1XM56ViSsm-28H781ilJpgfRH-h3HxQCr/view
2024-08-30 | Zayed City-Majlis-P17 | P17 | MJ-04 | 96 | 634 | 730 | • Shoring guide Completed • Shoring pilling in progress. • Site office utilities connection in progress. • Welfare facilities in progress | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. | 8.08% | 8.59% | 0.51% | Substantial Completion | 2026-06-02 |  | 2026-06-02 | 2024-09-06 | • Permeant piling start, in line with new optimized pile design Note that as per baseline rev 02 the piles for raft will start on 28-Sep-2024 • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval for shelter design (if any) | • Expedite MAK revised submission. • Workshop meetings held with MAK & bidders to expedite bidders proposals re-submission • ADM review started on 04 Sep.2024 & in process for structural package. | • Casting of Secant Piles • Casting of Capping beam • Starting of Raft Piles. | 106953287.35 | 0 | 106953287.35 | 3824490.97 | 0 | 110777778.32 | 10680390 |  | https://drive.google.com/thumbnail?id=1_9wvDD0xzarupnO-MkGQjPWkgNEleRMr&sz=w1000 | https://drive.google.com/file/d/1_9wvDD0xzarupnO-MkGQjPWkgNEleRMr/view | https://drive.google.com/thumbnail?id=1rhCvHfKmw2WQRnaHsokOte7r7Nl3uIJy&sz=w1000 | https://drive.google.com/file/d/1rhCvHfKmw2WQRnaHsokOte7r7Nl3uIJy/view | https://drive.google.com/thumbnail?id=1XM56ViSsm-28H781ilJpgfRH-h3HxQCr&sz=w1000 | https://drive.google.com/file/d/1XM56ViSsm-28H781ilJpgfRH-h3HxQCr/view
2024-08-30 | Mohamed Bin Zayed City-Majlis-P2 | P2 | MJ-12 | 53 | 555 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.38% | 1.31% | -0.07% | Commencement Date |  |  |  | 2024-09-06 | • Engaging with the authorities regarding the adjacent plot 5 cm impact. to explore the crossing cables if any. • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Safety risk •Shoring /Piling work Subcontractor appointment • Shelter Special systems subcontractor appointment • MEP Subcontractor appointment •Contract documents & IFC submission | • Follow up to obtain the required construction NOCs approval. • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Comply with saftey plan • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Finalize contract documents and issue the IFC drawings. | • Mobilizing the team for shoring works | 116841278.4538 | 0 | 116841278.4538 | 3229333.33 | 0 | 120070611.7838 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1TkkF924YYfv_46cDxUoc3DW_cdMcch42&sz=w1000 | https://drive.google.com/file/d/1TkkF924YYfv_46cDxUoc3DW_cdMcch42/view | https://drive.google.com/thumbnail?id=12FCTiQHROItKTuE1paH0D-F5NmHrtpx8&sz=w1000 | https://drive.google.com/file/d/12FCTiQHROItKTuE1paH0D-F5NmHrtpx8/view | https://drive.google.com/thumbnail?id=1y-Ocgzn3Ss07_HRVm38HZw507xBX9Q3K&sz=w1000 | https://drive.google.com/file/d/1y-Ocgzn3Ss07_HRVm38HZw507xBX9Q3K/view
2024-08-30 | Mohamed Bin Zayed City-Majlis-P2 | P2 | MJ-12 | 53 | 555 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.38% | 1.31% | -0.07% | Construction Permit |  |  |  | 2024-09-06 | • Engaging with the authorities regarding the adjacent plot 5 cm impact. to explore the crossing cables if any. • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Safety risk •Shoring /Piling work Subcontractor appointment • Shelter Special systems subcontractor appointment • MEP Subcontractor appointment •Contract documents & IFC submission | • Follow up to obtain the required construction NOCs approval. • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Comply with saftey plan • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Finalize contract documents and issue the IFC drawings. | • Mobilizing the team for shoring works | 116841278.4538 | 0 | 116841278.4538 | 3229333.33 | 0 | 120070611.7838 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1TkkF924YYfv_46cDxUoc3DW_cdMcch42&sz=w1000 | https://drive.google.com/file/d/1TkkF924YYfv_46cDxUoc3DW_cdMcch42/view | https://drive.google.com/thumbnail?id=12FCTiQHROItKTuE1paH0D-F5NmHrtpx8&sz=w1000 | https://drive.google.com/file/d/12FCTiQHROItKTuE1paH0D-F5NmHrtpx8/view | https://drive.google.com/thumbnail?id=1y-Ocgzn3Ss07_HRVm38HZw507xBX9Q3K&sz=w1000 | https://drive.google.com/file/d/1y-Ocgzn3Ss07_HRVm38HZw507xBX9Q3K/view
2024-08-30 | Mohamed Bin Zayed City-Majlis-P2 | P2 | MJ-12 | 53 | 555 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.38% | 1.31% | -0.07% | Site Mobilization |  |  |  | 2024-09-06 | • Engaging with the authorities regarding the adjacent plot 5 cm impact. to explore the crossing cables if any. • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Safety risk •Shoring /Piling work Subcontractor appointment • Shelter Special systems subcontractor appointment • MEP Subcontractor appointment •Contract documents & IFC submission | • Follow up to obtain the required construction NOCs approval. • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Comply with saftey plan • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Finalize contract documents and issue the IFC drawings. | • Mobilizing the team for shoring works | 116841278.4538 | 0 | 116841278.4538 | 3229333.33 | 0 | 120070611.7838 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1TkkF924YYfv_46cDxUoc3DW_cdMcch42&sz=w1000 | https://drive.google.com/file/d/1TkkF924YYfv_46cDxUoc3DW_cdMcch42/view | https://drive.google.com/thumbnail?id=12FCTiQHROItKTuE1paH0D-F5NmHrtpx8&sz=w1000 | https://drive.google.com/file/d/12FCTiQHROItKTuE1paH0D-F5NmHrtpx8/view | https://drive.google.com/thumbnail?id=1y-Ocgzn3Ss07_HRVm38HZw507xBX9Q3K&sz=w1000 | https://drive.google.com/file/d/1y-Ocgzn3Ss07_HRVm38HZw507xBX9Q3K/view
2024-08-30 | Mohamed Bin Zayed City-Majlis-P2 | P2 | MJ-12 | 53 | 555 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.38% | 1.31% | -0.07% | Shoring Drilling & Casting |  |  |  | 2024-09-06 | • Engaging with the authorities regarding the adjacent plot 5 cm impact. to explore the crossing cables if any. • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Safety risk •Shoring /Piling work Subcontractor appointment • Shelter Special systems subcontractor appointment • MEP Subcontractor appointment •Contract documents & IFC submission | • Follow up to obtain the required construction NOCs approval. • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Comply with saftey plan • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Finalize contract documents and issue the IFC drawings. | • Mobilizing the team for shoring works | 116841278.4538 | 0 | 116841278.4538 | 3229333.33 | 0 | 120070611.7838 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1TkkF924YYfv_46cDxUoc3DW_cdMcch42&sz=w1000 | https://drive.google.com/file/d/1TkkF924YYfv_46cDxUoc3DW_cdMcch42/view | https://drive.google.com/thumbnail?id=12FCTiQHROItKTuE1paH0D-F5NmHrtpx8&sz=w1000 | https://drive.google.com/file/d/12FCTiQHROItKTuE1paH0D-F5NmHrtpx8/view | https://drive.google.com/thumbnail?id=1y-Ocgzn3Ss07_HRVm38HZw507xBX9Q3K&sz=w1000 | https://drive.google.com/file/d/1y-Ocgzn3Ss07_HRVm38HZw507xBX9Q3K/view
2024-08-30 | Mohamed Bin Zayed City-Majlis-P2 | P2 | MJ-12 | 53 | 555 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.38% | 1.31% | -0.07% | Piling Drilling & Casting |  |  |  | 2024-09-06 | • Engaging with the authorities regarding the adjacent plot 5 cm impact. to explore the crossing cables if any. • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Safety risk •Shoring /Piling work Subcontractor appointment • Shelter Special systems subcontractor appointment • MEP Subcontractor appointment •Contract documents & IFC submission | • Follow up to obtain the required construction NOCs approval. • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Comply with saftey plan • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Finalize contract documents and issue the IFC drawings. | • Mobilizing the team for shoring works | 116841278.4538 | 0 | 116841278.4538 | 3229333.33 | 0 | 120070611.7838 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1TkkF924YYfv_46cDxUoc3DW_cdMcch42&sz=w1000 | https://drive.google.com/file/d/1TkkF924YYfv_46cDxUoc3DW_cdMcch42/view | https://drive.google.com/thumbnail?id=12FCTiQHROItKTuE1paH0D-F5NmHrtpx8&sz=w1000 | https://drive.google.com/file/d/12FCTiQHROItKTuE1paH0D-F5NmHrtpx8/view | https://drive.google.com/thumbnail?id=1y-Ocgzn3Ss07_HRVm38HZw507xBX9Q3K&sz=w1000 | https://drive.google.com/file/d/1y-Ocgzn3Ss07_HRVm38HZw507xBX9Q3K/view
2024-08-30 | Mohamed Bin Zayed City-Majlis-P2 | P2 | MJ-12 | 53 | 555 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.38% | 1.31% | -0.07% | Excavation |  |  |  | 2024-09-06 | • Engaging with the authorities regarding the adjacent plot 5 cm impact. to explore the crossing cables if any. • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Safety risk •Shoring /Piling work Subcontractor appointment • Shelter Special systems subcontractor appointment • MEP Subcontractor appointment •Contract documents & IFC submission | • Follow up to obtain the required construction NOCs approval. • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Comply with saftey plan • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Finalize contract documents and issue the IFC drawings. | • Mobilizing the team for shoring works | 116841278.4538 | 0 | 116841278.4538 | 3229333.33 | 0 | 120070611.7838 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1TkkF924YYfv_46cDxUoc3DW_cdMcch42&sz=w1000 | https://drive.google.com/file/d/1TkkF924YYfv_46cDxUoc3DW_cdMcch42/view | https://drive.google.com/thumbnail?id=12FCTiQHROItKTuE1paH0D-F5NmHrtpx8&sz=w1000 | https://drive.google.com/file/d/12FCTiQHROItKTuE1paH0D-F5NmHrtpx8/view | https://drive.google.com/thumbnail?id=1y-Ocgzn3Ss07_HRVm38HZw507xBX9Q3K&sz=w1000 | https://drive.google.com/file/d/1y-Ocgzn3Ss07_HRVm38HZw507xBX9Q3K/view
2024-08-30 | Mohamed Bin Zayed City-Majlis-P2 | P2 | MJ-12 | 53 | 555 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.38% | 1.31% | -0.07% | Substructure |  |  |  | 2024-09-06 | • Engaging with the authorities regarding the adjacent plot 5 cm impact. to explore the crossing cables if any. • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Safety risk •Shoring /Piling work Subcontractor appointment • Shelter Special systems subcontractor appointment • MEP Subcontractor appointment •Contract documents & IFC submission | • Follow up to obtain the required construction NOCs approval. • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Comply with saftey plan • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Finalize contract documents and issue the IFC drawings. | • Mobilizing the team for shoring works | 116841278.4538 | 0 | 116841278.4538 | 3229333.33 | 0 | 120070611.7838 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1TkkF924YYfv_46cDxUoc3DW_cdMcch42&sz=w1000 | https://drive.google.com/file/d/1TkkF924YYfv_46cDxUoc3DW_cdMcch42/view | https://drive.google.com/thumbnail?id=12FCTiQHROItKTuE1paH0D-F5NmHrtpx8&sz=w1000 | https://drive.google.com/file/d/12FCTiQHROItKTuE1paH0D-F5NmHrtpx8/view | https://drive.google.com/thumbnail?id=1y-Ocgzn3Ss07_HRVm38HZw507xBX9Q3K&sz=w1000 | https://drive.google.com/file/d/1y-Ocgzn3Ss07_HRVm38HZw507xBX9Q3K/view
2024-08-30 | Mohamed Bin Zayed City-Majlis-P2 | P2 | MJ-12 | 53 | 555 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.38% | 1.31% | -0.07% | Superstructure |  |  |  | 2024-09-06 | • Engaging with the authorities regarding the adjacent plot 5 cm impact. to explore the crossing cables if any. • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Safety risk •Shoring /Piling work Subcontractor appointment • Shelter Special systems subcontractor appointment • MEP Subcontractor appointment •Contract documents & IFC submission | • Follow up to obtain the required construction NOCs approval. • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Comply with saftey plan • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Finalize contract documents and issue the IFC drawings. | • Mobilizing the team for shoring works | 116841278.4538 | 0 | 116841278.4538 | 3229333.33 | 0 | 120070611.7838 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1TkkF924YYfv_46cDxUoc3DW_cdMcch42&sz=w1000 | https://drive.google.com/file/d/1TkkF924YYfv_46cDxUoc3DW_cdMcch42/view | https://drive.google.com/thumbnail?id=12FCTiQHROItKTuE1paH0D-F5NmHrtpx8&sz=w1000 | https://drive.google.com/file/d/12FCTiQHROItKTuE1paH0D-F5NmHrtpx8/view | https://drive.google.com/thumbnail?id=1y-Ocgzn3Ss07_HRVm38HZw507xBX9Q3K&sz=w1000 | https://drive.google.com/file/d/1y-Ocgzn3Ss07_HRVm38HZw507xBX9Q3K/view
2024-08-30 | Mohamed Bin Zayed City-Majlis-P2 | P2 | MJ-12 | 53 | 555 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.38% | 1.31% | -0.07% | MEP & Finishes |  |  |  | 2024-09-06 | • Engaging with the authorities regarding the adjacent plot 5 cm impact. to explore the crossing cables if any. • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Safety risk •Shoring /Piling work Subcontractor appointment • Shelter Special systems subcontractor appointment • MEP Subcontractor appointment •Contract documents & IFC submission | • Follow up to obtain the required construction NOCs approval. • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Comply with saftey plan • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Finalize contract documents and issue the IFC drawings. | • Mobilizing the team for shoring works | 116841278.4538 | 0 | 116841278.4538 | 3229333.33 | 0 | 120070611.7838 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1TkkF924YYfv_46cDxUoc3DW_cdMcch42&sz=w1000 | https://drive.google.com/file/d/1TkkF924YYfv_46cDxUoc3DW_cdMcch42/view | https://drive.google.com/thumbnail?id=12FCTiQHROItKTuE1paH0D-F5NmHrtpx8&sz=w1000 | https://drive.google.com/file/d/12FCTiQHROItKTuE1paH0D-F5NmHrtpx8/view | https://drive.google.com/thumbnail?id=1y-Ocgzn3Ss07_HRVm38HZw507xBX9Q3K&sz=w1000 | https://drive.google.com/file/d/1y-Ocgzn3Ss07_HRVm38HZw507xBX9Q3K/view
2024-08-30 | Mohamed Bin Zayed City-Majlis-P2 | P2 | MJ-12 | 53 | 555 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.38% | 1.31% | -0.07% | Authorities NOCs/BCC |  |  |  | 2024-09-06 | • Engaging with the authorities regarding the adjacent plot 5 cm impact. to explore the crossing cables if any. • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Safety risk •Shoring /Piling work Subcontractor appointment • Shelter Special systems subcontractor appointment • MEP Subcontractor appointment •Contract documents & IFC submission | • Follow up to obtain the required construction NOCs approval. • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Comply with saftey plan • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Finalize contract documents and issue the IFC drawings. | • Mobilizing the team for shoring works | 116841278.4538 | 0 | 116841278.4538 | 3229333.33 | 0 | 120070611.7838 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1TkkF924YYfv_46cDxUoc3DW_cdMcch42&sz=w1000 | https://drive.google.com/file/d/1TkkF924YYfv_46cDxUoc3DW_cdMcch42/view | https://drive.google.com/thumbnail?id=12FCTiQHROItKTuE1paH0D-F5NmHrtpx8&sz=w1000 | https://drive.google.com/file/d/12FCTiQHROItKTuE1paH0D-F5NmHrtpx8/view | https://drive.google.com/thumbnail?id=1y-Ocgzn3Ss07_HRVm38HZw507xBX9Q3K&sz=w1000 | https://drive.google.com/file/d/1y-Ocgzn3Ss07_HRVm38HZw507xBX9Q3K/view
2024-08-30 | Mohamed Bin Zayed City-Majlis-P2 | P2 | MJ-12 | 53 | 555 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.38% | 1.31% | -0.07% | External Works |  |  |  | 2024-09-06 | • Engaging with the authorities regarding the adjacent plot 5 cm impact. to explore the crossing cables if any. • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Safety risk •Shoring /Piling work Subcontractor appointment • Shelter Special systems subcontractor appointment • MEP Subcontractor appointment •Contract documents & IFC submission | • Follow up to obtain the required construction NOCs approval. • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Comply with saftey plan • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Finalize contract documents and issue the IFC drawings. | • Mobilizing the team for shoring works | 116841278.4538 | 0 | 116841278.4538 | 3229333.33 | 0 | 120070611.7838 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1TkkF924YYfv_46cDxUoc3DW_cdMcch42&sz=w1000 | https://drive.google.com/file/d/1TkkF924YYfv_46cDxUoc3DW_cdMcch42/view | https://drive.google.com/thumbnail?id=12FCTiQHROItKTuE1paH0D-F5NmHrtpx8&sz=w1000 | https://drive.google.com/file/d/12FCTiQHROItKTuE1paH0D-F5NmHrtpx8/view | https://drive.google.com/thumbnail?id=1y-Ocgzn3Ss07_HRVm38HZw507xBX9Q3K&sz=w1000 | https://drive.google.com/file/d/1y-Ocgzn3Ss07_HRVm38HZw507xBX9Q3K/view
2024-08-30 | Mohamed Bin Zayed City-Majlis-P2 | P2 | MJ-12 | 53 | 555 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.38% | 1.31% | -0.07% | Testing & Commissioning |  |  |  | 2024-09-06 | • Engaging with the authorities regarding the adjacent plot 5 cm impact. to explore the crossing cables if any. • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Safety risk •Shoring /Piling work Subcontractor appointment • Shelter Special systems subcontractor appointment • MEP Subcontractor appointment •Contract documents & IFC submission | • Follow up to obtain the required construction NOCs approval. • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Comply with saftey plan • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Finalize contract documents and issue the IFC drawings. | • Mobilizing the team for shoring works | 116841278.4538 | 0 | 116841278.4538 | 3229333.33 | 0 | 120070611.7838 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1TkkF924YYfv_46cDxUoc3DW_cdMcch42&sz=w1000 | https://drive.google.com/file/d/1TkkF924YYfv_46cDxUoc3DW_cdMcch42/view | https://drive.google.com/thumbnail?id=12FCTiQHROItKTuE1paH0D-F5NmHrtpx8&sz=w1000 | https://drive.google.com/file/d/12FCTiQHROItKTuE1paH0D-F5NmHrtpx8/view | https://drive.google.com/thumbnail?id=1y-Ocgzn3Ss07_HRVm38HZw507xBX9Q3K&sz=w1000 | https://drive.google.com/file/d/1y-Ocgzn3Ss07_HRVm38HZw507xBX9Q3K/view
2024-08-30 | Mohamed Bin Zayed City-Majlis-P2 | P2 | MJ-12 | 53 | 555 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.38% | 1.31% | -0.07% | Substantial Completion |  |  |  | 2024-09-06 | • Engaging with the authorities regarding the adjacent plot 5 cm impact. to explore the crossing cables if any. • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Safety risk •Shoring /Piling work Subcontractor appointment • Shelter Special systems subcontractor appointment • MEP Subcontractor appointment •Contract documents & IFC submission | • Follow up to obtain the required construction NOCs approval. • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Comply with saftey plan • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Finalize contract documents and issue the IFC drawings. | • Mobilizing the team for shoring works | 116841278.4538 | 0 | 116841278.4538 | 3229333.33 | 0 | 120070611.7838 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1TkkF924YYfv_46cDxUoc3DW_cdMcch42&sz=w1000 | https://drive.google.com/file/d/1TkkF924YYfv_46cDxUoc3DW_cdMcch42/view | https://drive.google.com/thumbnail?id=12FCTiQHROItKTuE1paH0D-F5NmHrtpx8&sz=w1000 | https://drive.google.com/file/d/12FCTiQHROItKTuE1paH0D-F5NmHrtpx8/view | https://drive.google.com/thumbnail?id=1y-Ocgzn3Ss07_HRVm38HZw507xBX9Q3K&sz=w1000 | https://drive.google.com/file/d/1y-Ocgzn3Ss07_HRVm38HZw507xBX9Q3K/view
2024-08-30 | Madinat Al Riyad-Majlis-P162 | P162 | MJ-13 | 53 | 555 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.38% | 1.31% | -0.07% | Commencement Date |  |  |  | 2024-09-06 | • Engaging with the authorities regarding the adjacent plot 5 cm impact. to explore the crossing cables if any. • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Safety risk •Shoring /Piling work Subcontractor appointment • Shelter Special systems subcontractor appointment • MEP Subcontractor appointment •Contract documents & IFC submission | • Follow up to obtain the required construction NOCs approval. • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Comply with saftey plan • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Finalize contract documents and issue the IFC drawings. | • Mobilizing the team for shoring works | 98073241.5243 | 0 | 98073241.5243 | 3229333.33 | 0 | 101302574.8543 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1YYboHNgsShFzYyBHMkUoSzib7zJkM_P6&sz=w1000 | https://drive.google.com/file/d/1YYboHNgsShFzYyBHMkUoSzib7zJkM_P6/view | https://drive.google.com/thumbnail?id=1jRWn6nkUc6PyzKFIrav2bztHDn61jQYs&sz=w1000 | https://drive.google.com/file/d/1jRWn6nkUc6PyzKFIrav2bztHDn61jQYs/view | https://drive.google.com/thumbnail?id=1iBr6b26MBv3-qs2HfZPBv-_SZMciRoSv&sz=w1000 | https://drive.google.com/file/d/1iBr6b26MBv3-qs2HfZPBv-_SZMciRoSv/view
2024-08-30 | Madinat Al Riyad-Majlis-P162 | P162 | MJ-13 | 53 | 555 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.38% | 1.31% | -0.07% | Construction Permit |  |  |  | 2024-09-06 | • Engaging with the authorities regarding the adjacent plot 5 cm impact. to explore the crossing cables if any. • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Safety risk •Shoring /Piling work Subcontractor appointment • Shelter Special systems subcontractor appointment • MEP Subcontractor appointment •Contract documents & IFC submission | • Follow up to obtain the required construction NOCs approval. • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Comply with saftey plan • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Finalize contract documents and issue the IFC drawings. | • Mobilizing the team for shoring works | 98073241.5243 | 0 | 98073241.5243 | 3229333.33 | 0 | 101302574.8543 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1YYboHNgsShFzYyBHMkUoSzib7zJkM_P6&sz=w1000 | https://drive.google.com/file/d/1YYboHNgsShFzYyBHMkUoSzib7zJkM_P6/view | https://drive.google.com/thumbnail?id=1jRWn6nkUc6PyzKFIrav2bztHDn61jQYs&sz=w1000 | https://drive.google.com/file/d/1jRWn6nkUc6PyzKFIrav2bztHDn61jQYs/view | https://drive.google.com/thumbnail?id=1iBr6b26MBv3-qs2HfZPBv-_SZMciRoSv&sz=w1000 | https://drive.google.com/file/d/1iBr6b26MBv3-qs2HfZPBv-_SZMciRoSv/view
2024-08-30 | Madinat Al Riyad-Majlis-P162 | P162 | MJ-13 | 53 | 555 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.38% | 1.31% | -0.07% | Site Mobilization |  |  |  | 2024-09-06 | • Engaging with the authorities regarding the adjacent plot 5 cm impact. to explore the crossing cables if any. • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Safety risk •Shoring /Piling work Subcontractor appointment • Shelter Special systems subcontractor appointment • MEP Subcontractor appointment •Contract documents & IFC submission | • Follow up to obtain the required construction NOCs approval. • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Comply with saftey plan • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Finalize contract documents and issue the IFC drawings. | • Mobilizing the team for shoring works | 98073241.5243 | 0 | 98073241.5243 | 3229333.33 | 0 | 101302574.8543 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1YYboHNgsShFzYyBHMkUoSzib7zJkM_P6&sz=w1000 | https://drive.google.com/file/d/1YYboHNgsShFzYyBHMkUoSzib7zJkM_P6/view | https://drive.google.com/thumbnail?id=1jRWn6nkUc6PyzKFIrav2bztHDn61jQYs&sz=w1000 | https://drive.google.com/file/d/1jRWn6nkUc6PyzKFIrav2bztHDn61jQYs/view | https://drive.google.com/thumbnail?id=1iBr6b26MBv3-qs2HfZPBv-_SZMciRoSv&sz=w1000 | https://drive.google.com/file/d/1iBr6b26MBv3-qs2HfZPBv-_SZMciRoSv/view
2024-08-30 | Madinat Al Riyad-Majlis-P162 | P162 | MJ-13 | 53 | 555 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.38% | 1.31% | -0.07% | Shoring Drilling & Casting |  |  |  | 2024-09-06 | • Engaging with the authorities regarding the adjacent plot 5 cm impact. to explore the crossing cables if any. • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Safety risk •Shoring /Piling work Subcontractor appointment • Shelter Special systems subcontractor appointment • MEP Subcontractor appointment •Contract documents & IFC submission | • Follow up to obtain the required construction NOCs approval. • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Comply with saftey plan • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Finalize contract documents and issue the IFC drawings. | • Mobilizing the team for shoring works | 98073241.5243 | 0 | 98073241.5243 | 3229333.33 | 0 | 101302574.8543 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1YYboHNgsShFzYyBHMkUoSzib7zJkM_P6&sz=w1000 | https://drive.google.com/file/d/1YYboHNgsShFzYyBHMkUoSzib7zJkM_P6/view | https://drive.google.com/thumbnail?id=1jRWn6nkUc6PyzKFIrav2bztHDn61jQYs&sz=w1000 | https://drive.google.com/file/d/1jRWn6nkUc6PyzKFIrav2bztHDn61jQYs/view | https://drive.google.com/thumbnail?id=1iBr6b26MBv3-qs2HfZPBv-_SZMciRoSv&sz=w1000 | https://drive.google.com/file/d/1iBr6b26MBv3-qs2HfZPBv-_SZMciRoSv/view
2024-08-30 | Madinat Al Riyad-Majlis-P162 | P162 | MJ-13 | 53 | 555 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.38% | 1.31% | -0.07% | Piling Drilling & Casting |  |  |  | 2024-09-06 | • Engaging with the authorities regarding the adjacent plot 5 cm impact. to explore the crossing cables if any. • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Safety risk •Shoring /Piling work Subcontractor appointment • Shelter Special systems subcontractor appointment • MEP Subcontractor appointment •Contract documents & IFC submission | • Follow up to obtain the required construction NOCs approval. • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Comply with saftey plan • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Finalize contract documents and issue the IFC drawings. | • Mobilizing the team for shoring works | 98073241.5243 | 0 | 98073241.5243 | 3229333.33 | 0 | 101302574.8543 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1YYboHNgsShFzYyBHMkUoSzib7zJkM_P6&sz=w1000 | https://drive.google.com/file/d/1YYboHNgsShFzYyBHMkUoSzib7zJkM_P6/view | https://drive.google.com/thumbnail?id=1jRWn6nkUc6PyzKFIrav2bztHDn61jQYs&sz=w1000 | https://drive.google.com/file/d/1jRWn6nkUc6PyzKFIrav2bztHDn61jQYs/view | https://drive.google.com/thumbnail?id=1iBr6b26MBv3-qs2HfZPBv-_SZMciRoSv&sz=w1000 | https://drive.google.com/file/d/1iBr6b26MBv3-qs2HfZPBv-_SZMciRoSv/view
2024-08-30 | Madinat Al Riyad-Majlis-P162 | P162 | MJ-13 | 53 | 555 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.38% | 1.31% | -0.07% | Excavation |  |  |  | 2024-09-06 | • Engaging with the authorities regarding the adjacent plot 5 cm impact. to explore the crossing cables if any. • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Safety risk •Shoring /Piling work Subcontractor appointment • Shelter Special systems subcontractor appointment • MEP Subcontractor appointment •Contract documents & IFC submission | • Follow up to obtain the required construction NOCs approval. • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Comply with saftey plan • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Finalize contract documents and issue the IFC drawings. | • Mobilizing the team for shoring works | 98073241.5243 | 0 | 98073241.5243 | 3229333.33 | 0 | 101302574.8543 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1YYboHNgsShFzYyBHMkUoSzib7zJkM_P6&sz=w1000 | https://drive.google.com/file/d/1YYboHNgsShFzYyBHMkUoSzib7zJkM_P6/view | https://drive.google.com/thumbnail?id=1jRWn6nkUc6PyzKFIrav2bztHDn61jQYs&sz=w1000 | https://drive.google.com/file/d/1jRWn6nkUc6PyzKFIrav2bztHDn61jQYs/view | https://drive.google.com/thumbnail?id=1iBr6b26MBv3-qs2HfZPBv-_SZMciRoSv&sz=w1000 | https://drive.google.com/file/d/1iBr6b26MBv3-qs2HfZPBv-_SZMciRoSv/view
2024-08-30 | Madinat Al Riyad-Majlis-P162 | P162 | MJ-13 | 53 | 555 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.38% | 1.31% | -0.07% | Substructure |  |  |  | 2024-09-06 | • Engaging with the authorities regarding the adjacent plot 5 cm impact. to explore the crossing cables if any. • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Safety risk •Shoring /Piling work Subcontractor appointment • Shelter Special systems subcontractor appointment • MEP Subcontractor appointment •Contract documents & IFC submission | • Follow up to obtain the required construction NOCs approval. • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Comply with saftey plan • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Finalize contract documents and issue the IFC drawings. | • Mobilizing the team for shoring works | 98073241.5243 | 0 | 98073241.5243 | 3229333.33 | 0 | 101302574.8543 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1YYboHNgsShFzYyBHMkUoSzib7zJkM_P6&sz=w1000 | https://drive.google.com/file/d/1YYboHNgsShFzYyBHMkUoSzib7zJkM_P6/view | https://drive.google.com/thumbnail?id=1jRWn6nkUc6PyzKFIrav2bztHDn61jQYs&sz=w1000 | https://drive.google.com/file/d/1jRWn6nkUc6PyzKFIrav2bztHDn61jQYs/view | https://drive.google.com/thumbnail?id=1iBr6b26MBv3-qs2HfZPBv-_SZMciRoSv&sz=w1000 | https://drive.google.com/file/d/1iBr6b26MBv3-qs2HfZPBv-_SZMciRoSv/view
2024-08-30 | Madinat Al Riyad-Majlis-P162 | P162 | MJ-13 | 53 | 555 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.38% | 1.31% | -0.07% | Superstructure |  |  |  | 2024-09-06 | • Engaging with the authorities regarding the adjacent plot 5 cm impact. to explore the crossing cables if any. • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Safety risk •Shoring /Piling work Subcontractor appointment • Shelter Special systems subcontractor appointment • MEP Subcontractor appointment •Contract documents & IFC submission | • Follow up to obtain the required construction NOCs approval. • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Comply with saftey plan • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Finalize contract documents and issue the IFC drawings. | • Mobilizing the team for shoring works | 98073241.5243 | 0 | 98073241.5243 | 3229333.33 | 0 | 101302574.8543 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1YYboHNgsShFzYyBHMkUoSzib7zJkM_P6&sz=w1000 | https://drive.google.com/file/d/1YYboHNgsShFzYyBHMkUoSzib7zJkM_P6/view | https://drive.google.com/thumbnail?id=1jRWn6nkUc6PyzKFIrav2bztHDn61jQYs&sz=w1000 | https://drive.google.com/file/d/1jRWn6nkUc6PyzKFIrav2bztHDn61jQYs/view | https://drive.google.com/thumbnail?id=1iBr6b26MBv3-qs2HfZPBv-_SZMciRoSv&sz=w1000 | https://drive.google.com/file/d/1iBr6b26MBv3-qs2HfZPBv-_SZMciRoSv/view
2024-08-30 | Madinat Al Riyad-Majlis-P162 | P162 | MJ-13 | 53 | 555 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.38% | 1.31% | -0.07% | MEP & Finishes |  |  |  | 2024-09-06 | • Engaging with the authorities regarding the adjacent plot 5 cm impact. to explore the crossing cables if any. • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Safety risk •Shoring /Piling work Subcontractor appointment • Shelter Special systems subcontractor appointment • MEP Subcontractor appointment •Contract documents & IFC submission | • Follow up to obtain the required construction NOCs approval. • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Comply with saftey plan • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Finalize contract documents and issue the IFC drawings. | • Mobilizing the team for shoring works | 98073241.5243 | 0 | 98073241.5243 | 3229333.33 | 0 | 101302574.8543 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1YYboHNgsShFzYyBHMkUoSzib7zJkM_P6&sz=w1000 | https://drive.google.com/file/d/1YYboHNgsShFzYyBHMkUoSzib7zJkM_P6/view | https://drive.google.com/thumbnail?id=1jRWn6nkUc6PyzKFIrav2bztHDn61jQYs&sz=w1000 | https://drive.google.com/file/d/1jRWn6nkUc6PyzKFIrav2bztHDn61jQYs/view | https://drive.google.com/thumbnail?id=1iBr6b26MBv3-qs2HfZPBv-_SZMciRoSv&sz=w1000 | https://drive.google.com/file/d/1iBr6b26MBv3-qs2HfZPBv-_SZMciRoSv/view
2024-08-30 | Madinat Al Riyad-Majlis-P162 | P162 | MJ-13 | 53 | 555 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.38% | 1.31% | -0.07% | Authorities NOCs/BCC |  |  |  | 2024-09-06 | • Engaging with the authorities regarding the adjacent plot 5 cm impact. to explore the crossing cables if any. • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Safety risk •Shoring /Piling work Subcontractor appointment • Shelter Special systems subcontractor appointment • MEP Subcontractor appointment •Contract documents & IFC submission | • Follow up to obtain the required construction NOCs approval. • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Comply with saftey plan • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Finalize contract documents and issue the IFC drawings. | • Mobilizing the team for shoring works | 98073241.5243 | 0 | 98073241.5243 | 3229333.33 | 0 | 101302574.8543 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1YYboHNgsShFzYyBHMkUoSzib7zJkM_P6&sz=w1000 | https://drive.google.com/file/d/1YYboHNgsShFzYyBHMkUoSzib7zJkM_P6/view | https://drive.google.com/thumbnail?id=1jRWn6nkUc6PyzKFIrav2bztHDn61jQYs&sz=w1000 | https://drive.google.com/file/d/1jRWn6nkUc6PyzKFIrav2bztHDn61jQYs/view | https://drive.google.com/thumbnail?id=1iBr6b26MBv3-qs2HfZPBv-_SZMciRoSv&sz=w1000 | https://drive.google.com/file/d/1iBr6b26MBv3-qs2HfZPBv-_SZMciRoSv/view
2024-08-30 | Madinat Al Riyad-Majlis-P162 | P162 | MJ-13 | 53 | 555 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.38% | 1.31% | -0.07% | External Works |  |  |  | 2024-09-06 | • Engaging with the authorities regarding the adjacent plot 5 cm impact. to explore the crossing cables if any. • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Safety risk •Shoring /Piling work Subcontractor appointment • Shelter Special systems subcontractor appointment • MEP Subcontractor appointment •Contract documents & IFC submission | • Follow up to obtain the required construction NOCs approval. • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Comply with saftey plan • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Finalize contract documents and issue the IFC drawings. | • Mobilizing the team for shoring works | 98073241.5243 | 0 | 98073241.5243 | 3229333.33 | 0 | 101302574.8543 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1YYboHNgsShFzYyBHMkUoSzib7zJkM_P6&sz=w1000 | https://drive.google.com/file/d/1YYboHNgsShFzYyBHMkUoSzib7zJkM_P6/view | https://drive.google.com/thumbnail?id=1jRWn6nkUc6PyzKFIrav2bztHDn61jQYs&sz=w1000 | https://drive.google.com/file/d/1jRWn6nkUc6PyzKFIrav2bztHDn61jQYs/view | https://drive.google.com/thumbnail?id=1iBr6b26MBv3-qs2HfZPBv-_SZMciRoSv&sz=w1000 | https://drive.google.com/file/d/1iBr6b26MBv3-qs2HfZPBv-_SZMciRoSv/view
2024-08-30 | Madinat Al Riyad-Majlis-P162 | P162 | MJ-13 | 53 | 555 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.38% | 1.31% | -0.07% | Testing & Commissioning |  |  |  | 2024-09-06 | • Engaging with the authorities regarding the adjacent plot 5 cm impact. to explore the crossing cables if any. • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Safety risk •Shoring /Piling work Subcontractor appointment • Shelter Special systems subcontractor appointment • MEP Subcontractor appointment •Contract documents & IFC submission | • Follow up to obtain the required construction NOCs approval. • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Comply with saftey plan • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Finalize contract documents and issue the IFC drawings. | • Mobilizing the team for shoring works | 98073241.5243 | 0 | 98073241.5243 | 3229333.33 | 0 | 101302574.8543 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1YYboHNgsShFzYyBHMkUoSzib7zJkM_P6&sz=w1000 | https://drive.google.com/file/d/1YYboHNgsShFzYyBHMkUoSzib7zJkM_P6/view | https://drive.google.com/thumbnail?id=1jRWn6nkUc6PyzKFIrav2bztHDn61jQYs&sz=w1000 | https://drive.google.com/file/d/1jRWn6nkUc6PyzKFIrav2bztHDn61jQYs/view | https://drive.google.com/thumbnail?id=1iBr6b26MBv3-qs2HfZPBv-_SZMciRoSv&sz=w1000 | https://drive.google.com/file/d/1iBr6b26MBv3-qs2HfZPBv-_SZMciRoSv/view
2024-08-30 | Madinat Al Riyad-Majlis-P162 | P162 | MJ-13 | 53 | 555 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.38% | 1.31% | -0.07% | Substantial Completion |  |  |  | 2024-09-06 | • Engaging with the authorities regarding the adjacent plot 5 cm impact. to explore the crossing cables if any. • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Safety risk •Shoring /Piling work Subcontractor appointment • Shelter Special systems subcontractor appointment • MEP Subcontractor appointment •Contract documents & IFC submission | • Follow up to obtain the required construction NOCs approval. • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Comply with saftey plan • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Finalize contract documents and issue the IFC drawings. | • Mobilizing the team for shoring works | 98073241.5243 | 0 | 98073241.5243 | 3229333.33 | 0 | 101302574.8543 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1YYboHNgsShFzYyBHMkUoSzib7zJkM_P6&sz=w1000 | https://drive.google.com/file/d/1YYboHNgsShFzYyBHMkUoSzib7zJkM_P6/view | https://drive.google.com/thumbnail?id=1jRWn6nkUc6PyzKFIrav2bztHDn61jQYs&sz=w1000 | https://drive.google.com/file/d/1jRWn6nkUc6PyzKFIrav2bztHDn61jQYs/view | https://drive.google.com/thumbnail?id=1iBr6b26MBv3-qs2HfZPBv-_SZMciRoSv&sz=w1000 | https://drive.google.com/file/d/1iBr6b26MBv3-qs2HfZPBv-_SZMciRoSv/view
2024-08-30 | Al Samhah-Majlis-P206 | P206 | MJ-14 | 53 | 555 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.38% | 1.31% | -0.07% | Commencement Date |  |  |  | 2024-09-06 | • Engaging with the authorities regarding the adjacent plot 5 cm impact. to explore the crossing cables if any. • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Safety risk •Shoring /Piling work Subcontractor appointment • Shelter Special systems subcontractor appointment • MEP Subcontractor appointment •Contract documents & IFC submission | • Follow up to obtain the required construction NOCs approval. • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Comply with saftey plan • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Finalize contract documents and issue the IFC drawings. | • Mobilizing the team for shoring works | 110585480.0219 | 0 | 110585480.0219 | 3229333.33 | 0 | 113814813.3519 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1q4cCVCNG__x2eJpAiRLTqR7FTiIzCqW_&sz=w1000 | https://drive.google.com/file/d/1q4cCVCNG__x2eJpAiRLTqR7FTiIzCqW_/view | https://drive.google.com/thumbnail?id=1sNkCfgGH2JR4MdY6bX8EU8QPo1fhVgeJ&sz=w1000 | https://drive.google.com/file/d/1sNkCfgGH2JR4MdY6bX8EU8QPo1fhVgeJ/view | https://drive.google.com/thumbnail?id=1pVsRJ1dyo2hYWyHHI4kWWKMR6i84lDfX&sz=w1000 | https://drive.google.com/file/d/1pVsRJ1dyo2hYWyHHI4kWWKMR6i84lDfX/view?usp=sharing
2024-08-30 | Al Samhah-Majlis-P206 | P206 | MJ-14 | 53 | 555 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.38% | 1.31% | -0.07% | Construction Permit |  |  |  | 2024-09-06 | • Engaging with the authorities regarding the adjacent plot 5 cm impact. to explore the crossing cables if any. • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Safety risk •Shoring /Piling work Subcontractor appointment • Shelter Special systems subcontractor appointment • MEP Subcontractor appointment •Contract documents & IFC submission | • Follow up to obtain the required construction NOCs approval. • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Comply with saftey plan • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Finalize contract documents and issue the IFC drawings. | • Mobilizing the team for shoring works | 110585480.0219 | 0 | 110585480.0219 | 3229333.33 | 0 | 113814813.3519 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1q4cCVCNG__x2eJpAiRLTqR7FTiIzCqW_&sz=w1000 | https://drive.google.com/file/d/1q4cCVCNG__x2eJpAiRLTqR7FTiIzCqW_/view | https://drive.google.com/thumbnail?id=1sNkCfgGH2JR4MdY6bX8EU8QPo1fhVgeJ&sz=w1000 | https://drive.google.com/file/d/1sNkCfgGH2JR4MdY6bX8EU8QPo1fhVgeJ/view | https://drive.google.com/thumbnail?id=1pVsRJ1dyo2hYWyHHI4kWWKMR6i84lDfX&sz=w1000 | https://drive.google.com/file/d/1pVsRJ1dyo2hYWyHHI4kWWKMR6i84lDfX/view?usp=sharing
2024-08-30 | Al Samhah-Majlis-P206 | P206 | MJ-14 | 53 | 555 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.38% | 1.31% | -0.07% | Site Mobilization |  |  |  | 2024-09-06 | • Engaging with the authorities regarding the adjacent plot 5 cm impact. to explore the crossing cables if any. • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Safety risk •Shoring /Piling work Subcontractor appointment • Shelter Special systems subcontractor appointment • MEP Subcontractor appointment •Contract documents & IFC submission | • Follow up to obtain the required construction NOCs approval. • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Comply with saftey plan • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Finalize contract documents and issue the IFC drawings. | • Mobilizing the team for shoring works | 110585480.0219 | 0 | 110585480.0219 | 3229333.33 | 0 | 113814813.3519 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1q4cCVCNG__x2eJpAiRLTqR7FTiIzCqW_&sz=w1000 | https://drive.google.com/file/d/1q4cCVCNG__x2eJpAiRLTqR7FTiIzCqW_/view | https://drive.google.com/thumbnail?id=1sNkCfgGH2JR4MdY6bX8EU8QPo1fhVgeJ&sz=w1000 | https://drive.google.com/file/d/1sNkCfgGH2JR4MdY6bX8EU8QPo1fhVgeJ/view | https://drive.google.com/thumbnail?id=1pVsRJ1dyo2hYWyHHI4kWWKMR6i84lDfX&sz=w1000 | https://drive.google.com/file/d/1pVsRJ1dyo2hYWyHHI4kWWKMR6i84lDfX/view?usp=sharing
2024-08-30 | Al Samhah-Majlis-P206 | P206 | MJ-14 | 53 | 555 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.38% | 1.31% | -0.07% | Shoring Drilling & Casting |  |  |  | 2024-09-06 | • Engaging with the authorities regarding the adjacent plot 5 cm impact. to explore the crossing cables if any. • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Safety risk •Shoring /Piling work Subcontractor appointment • Shelter Special systems subcontractor appointment • MEP Subcontractor appointment •Contract documents & IFC submission | • Follow up to obtain the required construction NOCs approval. • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Comply with saftey plan • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Finalize contract documents and issue the IFC drawings. | • Mobilizing the team for shoring works | 110585480.0219 | 0 | 110585480.0219 | 3229333.33 | 0 | 113814813.3519 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1q4cCVCNG__x2eJpAiRLTqR7FTiIzCqW_&sz=w1000 | https://drive.google.com/file/d/1q4cCVCNG__x2eJpAiRLTqR7FTiIzCqW_/view | https://drive.google.com/thumbnail?id=1sNkCfgGH2JR4MdY6bX8EU8QPo1fhVgeJ&sz=w1000 | https://drive.google.com/file/d/1sNkCfgGH2JR4MdY6bX8EU8QPo1fhVgeJ/view | https://drive.google.com/thumbnail?id=1pVsRJ1dyo2hYWyHHI4kWWKMR6i84lDfX&sz=w1000 | https://drive.google.com/file/d/1pVsRJ1dyo2hYWyHHI4kWWKMR6i84lDfX/view?usp=sharing
2024-08-30 | Al Samhah-Majlis-P206 | P206 | MJ-14 | 53 | 555 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.38% | 1.31% | -0.07% | Piling Drilling & Casting |  |  |  | 2024-09-06 | • Engaging with the authorities regarding the adjacent plot 5 cm impact. to explore the crossing cables if any. • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Safety risk •Shoring /Piling work Subcontractor appointment • Shelter Special systems subcontractor appointment • MEP Subcontractor appointment •Contract documents & IFC submission | • Follow up to obtain the required construction NOCs approval. • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Comply with saftey plan • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Finalize contract documents and issue the IFC drawings. | • Mobilizing the team for shoring works | 110585480.0219 | 0 | 110585480.0219 | 3229333.33 | 0 | 113814813.3519 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1q4cCVCNG__x2eJpAiRLTqR7FTiIzCqW_&sz=w1000 | https://drive.google.com/file/d/1q4cCVCNG__x2eJpAiRLTqR7FTiIzCqW_/view | https://drive.google.com/thumbnail?id=1sNkCfgGH2JR4MdY6bX8EU8QPo1fhVgeJ&sz=w1000 | https://drive.google.com/file/d/1sNkCfgGH2JR4MdY6bX8EU8QPo1fhVgeJ/view | https://drive.google.com/thumbnail?id=1pVsRJ1dyo2hYWyHHI4kWWKMR6i84lDfX&sz=w1000 | https://drive.google.com/file/d/1pVsRJ1dyo2hYWyHHI4kWWKMR6i84lDfX/view?usp=sharing
2024-08-30 | Al Samhah-Majlis-P206 | P206 | MJ-14 | 53 | 555 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.38% | 1.31% | -0.07% | Excavation |  |  |  | 2024-09-06 | • Engaging with the authorities regarding the adjacent plot 5 cm impact. to explore the crossing cables if any. • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Safety risk •Shoring /Piling work Subcontractor appointment • Shelter Special systems subcontractor appointment • MEP Subcontractor appointment •Contract documents & IFC submission | • Follow up to obtain the required construction NOCs approval. • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Comply with saftey plan • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Finalize contract documents and issue the IFC drawings. | • Mobilizing the team for shoring works | 110585480.0219 | 0 | 110585480.0219 | 3229333.33 | 0 | 113814813.3519 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1q4cCVCNG__x2eJpAiRLTqR7FTiIzCqW_&sz=w1000 | https://drive.google.com/file/d/1q4cCVCNG__x2eJpAiRLTqR7FTiIzCqW_/view | https://drive.google.com/thumbnail?id=1sNkCfgGH2JR4MdY6bX8EU8QPo1fhVgeJ&sz=w1000 | https://drive.google.com/file/d/1sNkCfgGH2JR4MdY6bX8EU8QPo1fhVgeJ/view | https://drive.google.com/thumbnail?id=1pVsRJ1dyo2hYWyHHI4kWWKMR6i84lDfX&sz=w1000 | https://drive.google.com/file/d/1pVsRJ1dyo2hYWyHHI4kWWKMR6i84lDfX/view?usp=sharing
2024-08-30 | Al Samhah-Majlis-P206 | P206 | MJ-14 | 53 | 555 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.38% | 1.31% | -0.07% | Substructure |  |  |  | 2024-09-06 | • Engaging with the authorities regarding the adjacent plot 5 cm impact. to explore the crossing cables if any. • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Safety risk •Shoring /Piling work Subcontractor appointment • Shelter Special systems subcontractor appointment • MEP Subcontractor appointment •Contract documents & IFC submission | • Follow up to obtain the required construction NOCs approval. • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Comply with saftey plan • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Finalize contract documents and issue the IFC drawings. | • Mobilizing the team for shoring works | 110585480.0219 | 0 | 110585480.0219 | 3229333.33 | 0 | 113814813.3519 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1q4cCVCNG__x2eJpAiRLTqR7FTiIzCqW_&sz=w1000 | https://drive.google.com/file/d/1q4cCVCNG__x2eJpAiRLTqR7FTiIzCqW_/view | https://drive.google.com/thumbnail?id=1sNkCfgGH2JR4MdY6bX8EU8QPo1fhVgeJ&sz=w1000 | https://drive.google.com/file/d/1sNkCfgGH2JR4MdY6bX8EU8QPo1fhVgeJ/view | https://drive.google.com/thumbnail?id=1pVsRJ1dyo2hYWyHHI4kWWKMR6i84lDfX&sz=w1000 | https://drive.google.com/file/d/1pVsRJ1dyo2hYWyHHI4kWWKMR6i84lDfX/view?usp=sharing
2024-08-30 | Al Samhah-Majlis-P206 | P206 | MJ-14 | 53 | 555 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.38% | 1.31% | -0.07% | Superstructure |  |  |  | 2024-09-06 | • Engaging with the authorities regarding the adjacent plot 5 cm impact. to explore the crossing cables if any. • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Safety risk •Shoring /Piling work Subcontractor appointment • Shelter Special systems subcontractor appointment • MEP Subcontractor appointment •Contract documents & IFC submission | • Follow up to obtain the required construction NOCs approval. • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Comply with saftey plan • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Finalize contract documents and issue the IFC drawings. | • Mobilizing the team for shoring works | 110585480.0219 | 0 | 110585480.0219 | 3229333.33 | 0 | 113814813.3519 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1q4cCVCNG__x2eJpAiRLTqR7FTiIzCqW_&sz=w1000 | https://drive.google.com/file/d/1q4cCVCNG__x2eJpAiRLTqR7FTiIzCqW_/view | https://drive.google.com/thumbnail?id=1sNkCfgGH2JR4MdY6bX8EU8QPo1fhVgeJ&sz=w1000 | https://drive.google.com/file/d/1sNkCfgGH2JR4MdY6bX8EU8QPo1fhVgeJ/view | https://drive.google.com/thumbnail?id=1pVsRJ1dyo2hYWyHHI4kWWKMR6i84lDfX&sz=w1000 | https://drive.google.com/file/d/1pVsRJ1dyo2hYWyHHI4kWWKMR6i84lDfX/view?usp=sharing
2024-08-30 | Al Samhah-Majlis-P206 | P206 | MJ-14 | 53 | 555 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.38% | 1.31% | -0.07% | MEP & Finishes |  |  |  | 2024-09-06 | • Engaging with the authorities regarding the adjacent plot 5 cm impact. to explore the crossing cables if any. • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Safety risk •Shoring /Piling work Subcontractor appointment • Shelter Special systems subcontractor appointment • MEP Subcontractor appointment •Contract documents & IFC submission | • Follow up to obtain the required construction NOCs approval. • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Comply with saftey plan • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Finalize contract documents and issue the IFC drawings. | • Mobilizing the team for shoring works | 110585480.0219 | 0 | 110585480.0219 | 3229333.33 | 0 | 113814813.3519 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1q4cCVCNG__x2eJpAiRLTqR7FTiIzCqW_&sz=w1000 | https://drive.google.com/file/d/1q4cCVCNG__x2eJpAiRLTqR7FTiIzCqW_/view | https://drive.google.com/thumbnail?id=1sNkCfgGH2JR4MdY6bX8EU8QPo1fhVgeJ&sz=w1000 | https://drive.google.com/file/d/1sNkCfgGH2JR4MdY6bX8EU8QPo1fhVgeJ/view | https://drive.google.com/thumbnail?id=1pVsRJ1dyo2hYWyHHI4kWWKMR6i84lDfX&sz=w1000 | https://drive.google.com/file/d/1pVsRJ1dyo2hYWyHHI4kWWKMR6i84lDfX/view?usp=sharing
2024-08-30 | Al Samhah-Majlis-P206 | P206 | MJ-14 | 53 | 555 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.38% | 1.31% | -0.07% | Authorities NOCs/BCC |  |  |  | 2024-09-06 | • Engaging with the authorities regarding the adjacent plot 5 cm impact. to explore the crossing cables if any. • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Safety risk •Shoring /Piling work Subcontractor appointment • Shelter Special systems subcontractor appointment • MEP Subcontractor appointment •Contract documents & IFC submission | • Follow up to obtain the required construction NOCs approval. • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Comply with saftey plan • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Finalize contract documents and issue the IFC drawings. | • Mobilizing the team for shoring works | 110585480.0219 | 0 | 110585480.0219 | 3229333.33 | 0 | 113814813.3519 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1q4cCVCNG__x2eJpAiRLTqR7FTiIzCqW_&sz=w1000 | https://drive.google.com/file/d/1q4cCVCNG__x2eJpAiRLTqR7FTiIzCqW_/view | https://drive.google.com/thumbnail?id=1sNkCfgGH2JR4MdY6bX8EU8QPo1fhVgeJ&sz=w1000 | https://drive.google.com/file/d/1sNkCfgGH2JR4MdY6bX8EU8QPo1fhVgeJ/view | https://drive.google.com/thumbnail?id=1pVsRJ1dyo2hYWyHHI4kWWKMR6i84lDfX&sz=w1000 | https://drive.google.com/file/d/1pVsRJ1dyo2hYWyHHI4kWWKMR6i84lDfX/view?usp=sharing
2024-08-30 | Al Samhah-Majlis-P206 | P206 | MJ-14 | 53 | 555 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.38% | 1.31% | -0.07% | External Works |  |  |  | 2024-09-06 | • Engaging with the authorities regarding the adjacent plot 5 cm impact. to explore the crossing cables if any. • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Safety risk •Shoring /Piling work Subcontractor appointment • Shelter Special systems subcontractor appointment • MEP Subcontractor appointment •Contract documents & IFC submission | • Follow up to obtain the required construction NOCs approval. • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Comply with saftey plan • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Finalize contract documents and issue the IFC drawings. | • Mobilizing the team for shoring works | 110585480.0219 | 0 | 110585480.0219 | 3229333.33 | 0 | 113814813.3519 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1q4cCVCNG__x2eJpAiRLTqR7FTiIzCqW_&sz=w1000 | https://drive.google.com/file/d/1q4cCVCNG__x2eJpAiRLTqR7FTiIzCqW_/view | https://drive.google.com/thumbnail?id=1sNkCfgGH2JR4MdY6bX8EU8QPo1fhVgeJ&sz=w1000 | https://drive.google.com/file/d/1sNkCfgGH2JR4MdY6bX8EU8QPo1fhVgeJ/view | https://drive.google.com/thumbnail?id=1pVsRJ1dyo2hYWyHHI4kWWKMR6i84lDfX&sz=w1000 | https://drive.google.com/file/d/1pVsRJ1dyo2hYWyHHI4kWWKMR6i84lDfX/view?usp=sharing
2024-08-30 | Al Samhah-Majlis-P206 | P206 | MJ-14 | 53 | 555 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.38% | 1.31% | -0.07% | Testing & Commissioning |  |  |  | 2024-09-06 | • Engaging with the authorities regarding the adjacent plot 5 cm impact. to explore the crossing cables if any. • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Safety risk •Shoring /Piling work Subcontractor appointment • Shelter Special systems subcontractor appointment • MEP Subcontractor appointment •Contract documents & IFC submission | • Follow up to obtain the required construction NOCs approval. • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Comply with saftey plan • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Finalize contract documents and issue the IFC drawings. | • Mobilizing the team for shoring works | 110585480.0219 | 0 | 110585480.0219 | 3229333.33 | 0 | 113814813.3519 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1q4cCVCNG__x2eJpAiRLTqR7FTiIzCqW_&sz=w1000 | https://drive.google.com/file/d/1q4cCVCNG__x2eJpAiRLTqR7FTiIzCqW_/view | https://drive.google.com/thumbnail?id=1sNkCfgGH2JR4MdY6bX8EU8QPo1fhVgeJ&sz=w1000 | https://drive.google.com/file/d/1sNkCfgGH2JR4MdY6bX8EU8QPo1fhVgeJ/view | https://drive.google.com/thumbnail?id=1pVsRJ1dyo2hYWyHHI4kWWKMR6i84lDfX&sz=w1000 | https://drive.google.com/file/d/1pVsRJ1dyo2hYWyHHI4kWWKMR6i84lDfX/view?usp=sharing
2024-08-30 | Al Samhah-Majlis-P206 | P206 | MJ-14 | 53 | 555 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.38% | 1.31% | -0.07% | Substantial Completion |  |  |  | 2024-09-06 | • Engaging with the authorities regarding the adjacent plot 5 cm impact. to explore the crossing cables if any. • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Safety risk •Shoring /Piling work Subcontractor appointment • Shelter Special systems subcontractor appointment • MEP Subcontractor appointment •Contract documents & IFC submission | • Follow up to obtain the required construction NOCs approval. • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Comply with saftey plan • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Finalize contract documents and issue the IFC drawings. | • Mobilizing the team for shoring works | 110585480.0219 | 0 | 110585480.0219 | 3229333.33 | 0 | 113814813.3519 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1q4cCVCNG__x2eJpAiRLTqR7FTiIzCqW_&sz=w1000 | https://drive.google.com/file/d/1q4cCVCNG__x2eJpAiRLTqR7FTiIzCqW_/view | https://drive.google.com/thumbnail?id=1sNkCfgGH2JR4MdY6bX8EU8QPo1fhVgeJ&sz=w1000 | https://drive.google.com/file/d/1sNkCfgGH2JR4MdY6bX8EU8QPo1fhVgeJ/view | https://drive.google.com/thumbnail?id=1pVsRJ1dyo2hYWyHHI4kWWKMR6i84lDfX&sz=w1000 | https://drive.google.com/file/d/1pVsRJ1dyo2hYWyHHI4kWWKMR6i84lDfX/view?usp=sharing
2024-08-30 | Baniyas-School-P77 | P77 | SC-01 | 179 | 370 | 549 | • Annex Building - GF Rebar fixing – 26% Completed; Concrete 5% Completed • School Building - RCC Plinth Wall Concrete pouring 90% Completed; GF Rebar Fixing 42% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 3.59% | 14.53% | 10.94% | Notice to Commence | 2024-03-05 | 2024-03-05 |  | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Backfilling Complete & Grade slab works to progress • Annex Building - GF RCC wall works to progress • Shelter Block - Substructure –RCC Wall upto Plinth to progress. • Shelter Block - RCC Wall Rebar Fixing to progress at GF & FF Level • Shelter Block - Surface Preparation for CRFP works | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 7682838.19 | 180000 | https://drive.google.com/thumbnail?id=1UDZ3DSBMcsK5rQzLJk4M0--CngCzKop9&sz=w1000 | https://drive.google.com/file/d/1UDZ3DSBMcsK5rQzLJk4M0--CngCzKop9/view?usp=drive_link | https://drive.google.com/thumbnail?id=1bYy1Ayup9OPnx4Ey4guSJ9WrktD4_Ot6&sz=w1000 | https://drive.google.com/file/d/1bYy1Ayup9OPnx4Ey4guSJ9WrktD4_Ot6/view?usp=drive_link | https://drive.google.com/thumbnail?id=1dMX3W21nvBkM9WPZUIo18OVNIoRxyreY&sz=w1000 | https://drive.google.com/file/d/1dMX3W21nvBkM9WPZUIo18OVNIoRxyreY/view?usp=drive_link
2024-08-30 | Baniyas-School-P77 | P77 | SC-01 | 179 | 370 | 549 | • Annex Building - GF Rebar fixing – 26% Completed; Concrete 5% Completed • School Building - RCC Plinth Wall Concrete pouring 90% Completed; GF Rebar Fixing 42% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 3.59% | 14.53% | 10.94% | Site Mobilization | 2024-04-09 | 2024-05-18 |  | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Backfilling Complete & Grade slab works to progress • Annex Building - GF RCC wall works to progress • Shelter Block - Substructure –RCC Wall upto Plinth to progress. • Shelter Block - RCC Wall Rebar Fixing to progress at GF & FF Level • Shelter Block - Surface Preparation for CRFP works | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 7682838.19 | 180000 | https://drive.google.com/thumbnail?id=1UDZ3DSBMcsK5rQzLJk4M0--CngCzKop9&sz=w1000 | https://drive.google.com/file/d/1UDZ3DSBMcsK5rQzLJk4M0--CngCzKop9/view?usp=drive_link | https://drive.google.com/thumbnail?id=1bYy1Ayup9OPnx4Ey4guSJ9WrktD4_Ot6&sz=w1000 | https://drive.google.com/file/d/1bYy1Ayup9OPnx4Ey4guSJ9WrktD4_Ot6/view?usp=drive_link | https://drive.google.com/thumbnail?id=1dMX3W21nvBkM9WPZUIo18OVNIoRxyreY&sz=w1000 | https://drive.google.com/file/d/1dMX3W21nvBkM9WPZUIo18OVNIoRxyreY/view?usp=drive_link
2024-08-30 | Baniyas-School-P77 | P77 | SC-01 | 179 | 370 | 549 | • Annex Building - GF Rebar fixing – 26% Completed; Concrete 5% Completed • School Building - RCC Plinth Wall Concrete pouring 90% Completed; GF Rebar Fixing 42% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 3.59% | 14.53% | 10.94% | Building Permit | 2024-11-01 | 2024-08-06 |  | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Backfilling Complete & Grade slab works to progress • Annex Building - GF RCC wall works to progress • Shelter Block - Substructure –RCC Wall upto Plinth to progress. • Shelter Block - RCC Wall Rebar Fixing to progress at GF & FF Level • Shelter Block - Surface Preparation for CRFP works | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 7682838.19 | 180000 | https://drive.google.com/thumbnail?id=1UDZ3DSBMcsK5rQzLJk4M0--CngCzKop9&sz=w1000 | https://drive.google.com/file/d/1UDZ3DSBMcsK5rQzLJk4M0--CngCzKop9/view?usp=drive_link | https://drive.google.com/thumbnail?id=1bYy1Ayup9OPnx4Ey4guSJ9WrktD4_Ot6&sz=w1000 | https://drive.google.com/file/d/1bYy1Ayup9OPnx4Ey4guSJ9WrktD4_Ot6/view?usp=drive_link | https://drive.google.com/thumbnail?id=1dMX3W21nvBkM9WPZUIo18OVNIoRxyreY&sz=w1000 | https://drive.google.com/file/d/1dMX3W21nvBkM9WPZUIo18OVNIoRxyreY/view?usp=drive_link
2024-08-30 | Baniyas-School-P77 | P77 | SC-01 | 179 | 370 | 549 | • Annex Building - GF Rebar fixing – 26% Completed; Concrete 5% Completed • School Building - RCC Plinth Wall Concrete pouring 90% Completed; GF Rebar Fixing 42% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 3.59% | 14.53% | 10.94% | School Substructure | 2025-01-21 |  | 2024-09-13 | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Backfilling Complete & Grade slab works to progress • Annex Building - GF RCC wall works to progress • Shelter Block - Substructure –RCC Wall upto Plinth to progress. • Shelter Block - RCC Wall Rebar Fixing to progress at GF & FF Level • Shelter Block - Surface Preparation for CRFP works | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 7682838.19 | 180000 | https://drive.google.com/thumbnail?id=1UDZ3DSBMcsK5rQzLJk4M0--CngCzKop9&sz=w1000 | https://drive.google.com/file/d/1UDZ3DSBMcsK5rQzLJk4M0--CngCzKop9/view?usp=drive_link | https://drive.google.com/thumbnail?id=1bYy1Ayup9OPnx4Ey4guSJ9WrktD4_Ot6&sz=w1000 | https://drive.google.com/file/d/1bYy1Ayup9OPnx4Ey4guSJ9WrktD4_Ot6/view?usp=drive_link | https://drive.google.com/thumbnail?id=1dMX3W21nvBkM9WPZUIo18OVNIoRxyreY&sz=w1000 | https://drive.google.com/file/d/1dMX3W21nvBkM9WPZUIo18OVNIoRxyreY/view?usp=drive_link
2024-08-30 | Baniyas-School-P77 | P77 | SC-01 | 179 | 377 | 556 | • Annex Building - GF Rebar fixing – 26% Completed; Concrete 5% Completed • School Building - RCC Plinth Wall Concrete pouring 90% Completed; GF Rebar Fixing 42% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 3.59% | 14.53% | 10.94% | School Superstructure | 2025-04-28 |  | 2024-10-15 | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Backfilling Complete & Grade slab works to progress • Annex Building - GF RCC wall works to progress • Shelter Block - Substructure –RCC Wall upto Plinth to progress. • Shelter Block - RCC Wall Rebar Fixing to progress at GF & FF Level • Shelter Block - Surface Preparation for CRFP works | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 7682838.19 | 180000 | https://drive.google.com/thumbnail?id=1UDZ3DSBMcsK5rQzLJk4M0--CngCzKop9&sz=w1000 | https://drive.google.com/file/d/1UDZ3DSBMcsK5rQzLJk4M0--CngCzKop9/view?usp=drive_link | https://drive.google.com/thumbnail?id=1bYy1Ayup9OPnx4Ey4guSJ9WrktD4_Ot6&sz=w1000 | https://drive.google.com/file/d/1bYy1Ayup9OPnx4Ey4guSJ9WrktD4_Ot6/view?usp=drive_link | https://drive.google.com/thumbnail?id=1dMX3W21nvBkM9WPZUIo18OVNIoRxyreY&sz=w1000 | https://drive.google.com/file/d/1dMX3W21nvBkM9WPZUIo18OVNIoRxyreY/view?usp=drive_link
2024-08-30 | Baniyas-School-P77 | P77 | SC-01 | 179 | 377 | 556 | • Annex Building - GF Rebar fixing – 26% Completed; Concrete 5% Completed • School Building - RCC Plinth Wall Concrete pouring 90% Completed; GF Rebar Fixing 42% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 3.59% | 14.53% | 10.94% | Annex Substructure | 2025-01-22 | 2024-08-17 |  | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Backfilling Complete & Grade slab works to progress • Annex Building - GF RCC wall works to progress • Shelter Block - Substructure –RCC Wall upto Plinth to progress. • Shelter Block - RCC Wall Rebar Fixing to progress at GF & FF Level • Shelter Block - Surface Preparation for CRFP works | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 7682838.19 | 180000 | https://drive.google.com/thumbnail?id=1UDZ3DSBMcsK5rQzLJk4M0--CngCzKop9&sz=w1000 | https://drive.google.com/file/d/1UDZ3DSBMcsK5rQzLJk4M0--CngCzKop9/view?usp=drive_link | https://drive.google.com/thumbnail?id=1bYy1Ayup9OPnx4Ey4guSJ9WrktD4_Ot6&sz=w1000 | https://drive.google.com/file/d/1bYy1Ayup9OPnx4Ey4guSJ9WrktD4_Ot6/view?usp=drive_link | https://drive.google.com/thumbnail?id=1dMX3W21nvBkM9WPZUIo18OVNIoRxyreY&sz=w1000 | https://drive.google.com/file/d/1dMX3W21nvBkM9WPZUIo18OVNIoRxyreY/view?usp=drive_link
2024-08-30 | Baniyas-School-P77 | P77 | SC-01 | 179 | 377 | 556 | • Annex Building - GF Rebar fixing – 26% Completed; Concrete 5% Completed • School Building - RCC Plinth Wall Concrete pouring 90% Completed; GF Rebar Fixing 42% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 3.59% | 14.53% | 10.94% | Annex Superstructure | 2025-04-21 |  | 2025-01-15 | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Backfilling Complete & Grade slab works to progress • Annex Building - GF RCC wall works to progress • Shelter Block - Substructure –RCC Wall upto Plinth to progress. • Shelter Block - RCC Wall Rebar Fixing to progress at GF & FF Level • Shelter Block - Surface Preparation for CRFP works | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 7682838.19 | 180000 | https://drive.google.com/thumbnail?id=1UDZ3DSBMcsK5rQzLJk4M0--CngCzKop9&sz=w1000 | https://drive.google.com/file/d/1UDZ3DSBMcsK5rQzLJk4M0--CngCzKop9/view?usp=drive_link | https://drive.google.com/thumbnail?id=1bYy1Ayup9OPnx4Ey4guSJ9WrktD4_Ot6&sz=w1000 | https://drive.google.com/file/d/1bYy1Ayup9OPnx4Ey4guSJ9WrktD4_Ot6/view?usp=drive_link | https://drive.google.com/thumbnail?id=1dMX3W21nvBkM9WPZUIo18OVNIoRxyreY&sz=w1000 | https://drive.google.com/file/d/1dMX3W21nvBkM9WPZUIo18OVNIoRxyreY/view?usp=drive_link
2024-08-30 | Baniyas-School-P77 | P77 | SC-01 | 179 | 377 | 556 | • Annex Building - GF Rebar fixing – 26% Completed; Concrete 5% Completed • School Building - RCC Plinth Wall Concrete pouring 90% Completed; GF Rebar Fixing 42% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 3.59% | 14.53% | 10.94% | MEP & Finishes | 2025-07-19 |  | 2025-05-31 | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Backfilling Complete & Grade slab works to progress • Annex Building - GF RCC wall works to progress • Shelter Block - Substructure –RCC Wall upto Plinth to progress. • Shelter Block - RCC Wall Rebar Fixing to progress at GF & FF Level • Shelter Block - Surface Preparation for CRFP works | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 7682838.19 | 180000 | https://drive.google.com/thumbnail?id=1UDZ3DSBMcsK5rQzLJk4M0--CngCzKop9&sz=w1000 | https://drive.google.com/file/d/1UDZ3DSBMcsK5rQzLJk4M0--CngCzKop9/view?usp=drive_link | https://drive.google.com/thumbnail?id=1bYy1Ayup9OPnx4Ey4guSJ9WrktD4_Ot6&sz=w1000 | https://drive.google.com/file/d/1bYy1Ayup9OPnx4Ey4guSJ9WrktD4_Ot6/view?usp=drive_link | https://drive.google.com/thumbnail?id=1dMX3W21nvBkM9WPZUIo18OVNIoRxyreY&sz=w1000 | https://drive.google.com/file/d/1dMX3W21nvBkM9WPZUIo18OVNIoRxyreY/view?usp=drive_link
2024-08-30 | Baniyas-School-P77 | P77 | SC-01 | 179 | 377 | 556 | • Annex Building - GF Rebar fixing – 26% Completed; Concrete 5% Completed • School Building - RCC Plinth Wall Concrete pouring 90% Completed; GF Rebar Fixing 42% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 3.59% | 14.53% | 10.94% | BCC Inspection | 2025-08-05 |  | 2025-06-14 | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Backfilling Complete & Grade slab works to progress • Annex Building - GF RCC wall works to progress • Shelter Block - Substructure –RCC Wall upto Plinth to progress. • Shelter Block - RCC Wall Rebar Fixing to progress at GF & FF Level • Shelter Block - Surface Preparation for CRFP works | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 7682838.19 | 180000 | https://drive.google.com/thumbnail?id=1UDZ3DSBMcsK5rQzLJk4M0--CngCzKop9&sz=w1000 | https://drive.google.com/file/d/1UDZ3DSBMcsK5rQzLJk4M0--CngCzKop9/view?usp=drive_link | https://drive.google.com/thumbnail?id=1bYy1Ayup9OPnx4Ey4guSJ9WrktD4_Ot6&sz=w1000 | https://drive.google.com/file/d/1bYy1Ayup9OPnx4Ey4guSJ9WrktD4_Ot6/view?usp=drive_link | https://drive.google.com/thumbnail?id=1dMX3W21nvBkM9WPZUIo18OVNIoRxyreY&sz=w1000 | https://drive.google.com/file/d/1dMX3W21nvBkM9WPZUIo18OVNIoRxyreY/view?usp=drive_link
2024-08-30 | Baniyas-School-P77 | P77 | SC-01 | 179 | 377 | 556 | • Annex Building - GF Rebar fixing – 26% Completed; Concrete 5% Completed • School Building - RCC Plinth Wall Concrete pouring 90% Completed; GF Rebar Fixing 42% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 3.59% | 14.53% | 10.94% | BCC Issuance | 2025-08-22 |  | 2025-07-22 | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Backfilling Complete & Grade slab works to progress • Annex Building - GF RCC wall works to progress • Shelter Block - Substructure –RCC Wall upto Plinth to progress. • Shelter Block - RCC Wall Rebar Fixing to progress at GF & FF Level • Shelter Block - Surface Preparation for CRFP works | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 7682838.19 | 180000 | https://drive.google.com/thumbnail?id=1UDZ3DSBMcsK5rQzLJk4M0--CngCzKop9&sz=w1000 | https://drive.google.com/file/d/1UDZ3DSBMcsK5rQzLJk4M0--CngCzKop9/view?usp=drive_link | https://drive.google.com/thumbnail?id=1bYy1Ayup9OPnx4Ey4guSJ9WrktD4_Ot6&sz=w1000 | https://drive.google.com/file/d/1bYy1Ayup9OPnx4Ey4guSJ9WrktD4_Ot6/view?usp=drive_link | https://drive.google.com/thumbnail?id=1dMX3W21nvBkM9WPZUIo18OVNIoRxyreY&sz=w1000 | https://drive.google.com/file/d/1dMX3W21nvBkM9WPZUIo18OVNIoRxyreY/view?usp=drive_link
2024-08-30 | Baniyas-School-P77 | P77 | SC-01 | 179 | 377 | 556 | • Annex Building - GF Rebar fixing – 26% Completed; Concrete 5% Completed • School Building - RCC Plinth Wall Concrete pouring 90% Completed; GF Rebar Fixing 42% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 3.59% | 14.53% | 10.94% | Completion | 2025-09-04 |  | 2025-08-04 | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Backfilling Complete & Grade slab works to progress • Annex Building - GF RCC wall works to progress • Shelter Block - Substructure –RCC Wall upto Plinth to progress. • Shelter Block - RCC Wall Rebar Fixing to progress at GF & FF Level • Shelter Block - Surface Preparation for CRFP works | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 7682838.19 | 180000 | https://drive.google.com/thumbnail?id=1UDZ3DSBMcsK5rQzLJk4M0--CngCzKop9&sz=w1000 | https://drive.google.com/file/d/1UDZ3DSBMcsK5rQzLJk4M0--CngCzKop9/view?usp=drive_link | https://drive.google.com/thumbnail?id=1bYy1Ayup9OPnx4Ey4guSJ9WrktD4_Ot6&sz=w1000 | https://drive.google.com/file/d/1bYy1Ayup9OPnx4Ey4guSJ9WrktD4_Ot6/view?usp=drive_link | https://drive.google.com/thumbnail?id=1dMX3W21nvBkM9WPZUIo18OVNIoRxyreY&sz=w1000 | https://drive.google.com/file/d/1dMX3W21nvBkM9WPZUIo18OVNIoRxyreY/view?usp=drive_link
2024-08-30 | Al Shahama-School-P17 | P17 | SC-02 | 348 | 199 | 547 | • Annex Building - RCC Wall Concrete Upto FF Level – 100% Completed; 1FF Slab - Staging & Shutter fixing in progress • School Building - GF - RCC Wall Rebar fixing 99% Completed, FF - Rebar Fixing 70% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 23.77% | 25.14% | 1.37% | Notice to Commence | 2023-09-18 | 2023-09-26 |  | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – Wall Rebar, Shutter & Concrete pouring up to 1st FL level • Shelter Block - Substructure – Waterproofing & Backfilling works. • Shelter Block - Superstructure - RCC wall to progress GF & 1FL • Shelter Block - Surface Preparation & Application of CFRP • Shelter Block - Roof Slab Strengthening works to progress | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 10152055.77 | 180000 | https://drive.google.com/thumbnail?id=1j8yRlDYok5MJSeLQ4eUWBEa5wF2-pNRd&sz=w1000 | https://drive.google.com/file/d/1j8yRlDYok5MJSeLQ4eUWBEa5wF2-pNRd/view?usp=drive_link | https://drive.google.com/thumbnail?id=1Kj7pGsto2d8qxWBBNeFSXHt0ZCv3amEr&sz=w1000 | https://drive.google.com/file/d/1Kj7pGsto2d8qxWBBNeFSXHt0ZCv3amEr/view?usp=drive_link | https://drive.google.com/thumbnail?id=1rOTt3bC6ZLN5P-SA_JVctRcIj9J1mxVr&sz=w1000 | https://drive.google.com/file/d/1rOTt3bC6ZLN5P-SA_JVctRcIj9J1mxVr/view?usp=drive_link
2024-08-30 | Al Shahama-School-P17 | P17 | SC-02 | 348 | 199 | 547 | • Annex Building - RCC Wall Concrete Upto FF Level – 100% Completed; 1FF Slab - Staging & Shutter fixing in progress • School Building - GF - RCC Wall Rebar fixing 99% Completed, FF - Rebar Fixing 70% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 23.77% | 25.14% | 1.37% | Site Mobilization | 2023-10-21 | 2023-12-06 |  | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – Wall Rebar, Shutter & Concrete pouring up to 1st FL level • Shelter Block - Substructure – Waterproofing & Backfilling works. • Shelter Block - Superstructure - RCC wall to progress GF & 1FL • Shelter Block - Surface Preparation & Application of CFRP • Shelter Block - Roof Slab Strengthening works to progress | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 10152055.77 | 180000 | https://drive.google.com/thumbnail?id=1j8yRlDYok5MJSeLQ4eUWBEa5wF2-pNRd&sz=w1000 | https://drive.google.com/file/d/1j8yRlDYok5MJSeLQ4eUWBEa5wF2-pNRd/view?usp=drive_link | https://drive.google.com/thumbnail?id=1Kj7pGsto2d8qxWBBNeFSXHt0ZCv3amEr&sz=w1000 | https://drive.google.com/file/d/1Kj7pGsto2d8qxWBBNeFSXHt0ZCv3amEr/view?usp=drive_link | https://drive.google.com/thumbnail?id=1rOTt3bC6ZLN5P-SA_JVctRcIj9J1mxVr&sz=w1000 | https://drive.google.com/file/d/1rOTt3bC6ZLN5P-SA_JVctRcIj9J1mxVr/view?usp=drive_link
2024-08-30 | Al Shahama-School-P17 | P17 | SC-02 | 348 | 199 | 547 | • Annex Building - RCC Wall Concrete Upto FF Level – 100% Completed; 1FF Slab - Staging & Shutter fixing in progress • School Building - GF - RCC Wall Rebar fixing 99% Completed, FF - Rebar Fixing 70% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 23.77% | 25.14% | 1.37% | Building Permit | 2024-05-17 | 2024-05-23 |  | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – Wall Rebar, Shutter & Concrete pouring up to 1st FL level • Shelter Block - Substructure – Waterproofing & Backfilling works. • Shelter Block - Superstructure - RCC wall to progress GF & 1FL • Shelter Block - Surface Preparation & Application of CFRP • Shelter Block - Roof Slab Strengthening works to progress | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 10152055.77 | 180000 | https://drive.google.com/thumbnail?id=1j8yRlDYok5MJSeLQ4eUWBEa5wF2-pNRd&sz=w1000 | https://drive.google.com/file/d/1j8yRlDYok5MJSeLQ4eUWBEa5wF2-pNRd/view?usp=drive_link | https://drive.google.com/thumbnail?id=1Kj7pGsto2d8qxWBBNeFSXHt0ZCv3amEr&sz=w1000 | https://drive.google.com/file/d/1Kj7pGsto2d8qxWBBNeFSXHt0ZCv3amEr/view?usp=drive_link | https://drive.google.com/thumbnail?id=1rOTt3bC6ZLN5P-SA_JVctRcIj9J1mxVr&sz=w1000 | https://drive.google.com/file/d/1rOTt3bC6ZLN5P-SA_JVctRcIj9J1mxVr/view?usp=drive_link
2024-08-30 | Al Shahama-School-P17 | P17 | SC-02 | 348 | 199 | 547 | • Annex Building - RCC Wall Concrete Upto FF Level – 100% Completed; 1FF Slab - Staging & Shutter fixing in progress • School Building - GF - RCC Wall Rebar fixing 99% Completed, FF - Rebar Fixing 70% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 23.77% | 25.14% | 1.37% | School Substructure | 2024-08-06 |  | 2024-09-06 | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – Wall Rebar, Shutter & Concrete pouring up to 1st FL level • Shelter Block - Substructure – Waterproofing & Backfilling works. • Shelter Block - Superstructure - RCC wall to progress GF & 1FL • Shelter Block - Surface Preparation & Application of CFRP • Shelter Block - Roof Slab Strengthening works to progress | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 10152055.77 | 180000 | https://drive.google.com/thumbnail?id=1j8yRlDYok5MJSeLQ4eUWBEa5wF2-pNRd&sz=w1000 | https://drive.google.com/file/d/1j8yRlDYok5MJSeLQ4eUWBEa5wF2-pNRd/view?usp=drive_link | https://drive.google.com/thumbnail?id=1Kj7pGsto2d8qxWBBNeFSXHt0ZCv3amEr&sz=w1000 | https://drive.google.com/file/d/1Kj7pGsto2d8qxWBBNeFSXHt0ZCv3amEr/view?usp=drive_link | https://drive.google.com/thumbnail?id=1rOTt3bC6ZLN5P-SA_JVctRcIj9J1mxVr&sz=w1000 | https://drive.google.com/file/d/1rOTt3bC6ZLN5P-SA_JVctRcIj9J1mxVr/view?usp=drive_link
2024-08-30 | Al Shahama-School-P17 | P17 | SC-02 | 348 | 199 | 547 | • Annex Building - RCC Wall Concrete Upto FF Level – 100% Completed; 1FF Slab - Staging & Shutter fixing in progress • School Building - GF - RCC Wall Rebar fixing 99% Completed, FF - Rebar Fixing 70% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 23.77% | 25.14% | 1.37% | School Superstructure | 2024-11-07 |  | 2024-10-09 | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – Wall Rebar, Shutter & Concrete pouring up to 1st FL level • Shelter Block - Substructure – Waterproofing & Backfilling works. • Shelter Block - Superstructure - RCC wall to progress GF & 1FL • Shelter Block - Surface Preparation & Application of CFRP • Shelter Block - Roof Slab Strengthening works to progress | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 10152055.77 | 180000 | https://drive.google.com/thumbnail?id=1j8yRlDYok5MJSeLQ4eUWBEa5wF2-pNRd&sz=w1000 | https://drive.google.com/file/d/1j8yRlDYok5MJSeLQ4eUWBEa5wF2-pNRd/view?usp=drive_link | https://drive.google.com/thumbnail?id=1Kj7pGsto2d8qxWBBNeFSXHt0ZCv3amEr&sz=w1000 | https://drive.google.com/file/d/1Kj7pGsto2d8qxWBBNeFSXHt0ZCv3amEr/view?usp=drive_link | https://drive.google.com/thumbnail?id=1rOTt3bC6ZLN5P-SA_JVctRcIj9J1mxVr&sz=w1000 | https://drive.google.com/file/d/1rOTt3bC6ZLN5P-SA_JVctRcIj9J1mxVr/view?usp=drive_link
2024-08-30 | Al Shahama-School-P17 | P17 | SC-02 | 348 | 199 | 547 | • Annex Building - RCC Wall Concrete Upto FF Level – 100% Completed; 1FF Slab - Staging & Shutter fixing in progress • School Building - GF - RCC Wall Rebar fixing 99% Completed, FF - Rebar Fixing 70% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 23.77% | 25.14% | 1.37% | Annex Substructure | 2024-08-07 | 2024-07-04 |  | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – Wall Rebar, Shutter & Concrete pouring up to 1st FL level • Shelter Block - Substructure – Waterproofing & Backfilling works. • Shelter Block - Superstructure - RCC wall to progress GF & 1FL • Shelter Block - Surface Preparation & Application of CFRP • Shelter Block - Roof Slab Strengthening works to progress | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 10152055.77 | 180000 | https://drive.google.com/thumbnail?id=1j8yRlDYok5MJSeLQ4eUWBEa5wF2-pNRd&sz=w1000 | https://drive.google.com/file/d/1j8yRlDYok5MJSeLQ4eUWBEa5wF2-pNRd/view?usp=drive_link | https://drive.google.com/thumbnail?id=1Kj7pGsto2d8qxWBBNeFSXHt0ZCv3amEr&sz=w1000 | https://drive.google.com/file/d/1Kj7pGsto2d8qxWBBNeFSXHt0ZCv3amEr/view?usp=drive_link | https://drive.google.com/thumbnail?id=1rOTt3bC6ZLN5P-SA_JVctRcIj9J1mxVr&sz=w1000 | https://drive.google.com/file/d/1rOTt3bC6ZLN5P-SA_JVctRcIj9J1mxVr/view?usp=drive_link
2024-08-30 | Al Shahama-School-P17 | P17 | SC-02 | 348 | 199 | 547 | • Annex Building - RCC Wall Concrete Upto FF Level – 100% Completed; 1FF Slab - Staging & Shutter fixing in progress • School Building - GF - RCC Wall Rebar fixing 99% Completed, FF - Rebar Fixing 70% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 23.77% | 25.14% | 1.37% | Annex Superstructure | 2024-10-31 |  | 2024-10-25 | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – Wall Rebar, Shutter & Concrete pouring up to 1st FL level • Shelter Block - Substructure – Waterproofing & Backfilling works. • Shelter Block - Superstructure - RCC wall to progress GF & 1FL • Shelter Block - Surface Preparation & Application of CFRP • Shelter Block - Roof Slab Strengthening works to progress | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 10152055.77 | 180000 | https://drive.google.com/thumbnail?id=1j8yRlDYok5MJSeLQ4eUWBEa5wF2-pNRd&sz=w1000 | https://drive.google.com/file/d/1j8yRlDYok5MJSeLQ4eUWBEa5wF2-pNRd/view?usp=drive_link | https://drive.google.com/thumbnail?id=1Kj7pGsto2d8qxWBBNeFSXHt0ZCv3amEr&sz=w1000 | https://drive.google.com/file/d/1Kj7pGsto2d8qxWBBNeFSXHt0ZCv3amEr/view?usp=drive_link | https://drive.google.com/thumbnail?id=1rOTt3bC6ZLN5P-SA_JVctRcIj9J1mxVr&sz=w1000 | https://drive.google.com/file/d/1rOTt3bC6ZLN5P-SA_JVctRcIj9J1mxVr/view?usp=drive_link
2024-08-30 | Al Shahama-School-P17 | P17 | SC-02 | 348 | 199 | 547 | • Annex Building - RCC Wall Concrete Upto FF Level – 100% Completed; 1FF Slab - Staging & Shutter fixing in progress • School Building - GF - RCC Wall Rebar fixing 99% Completed, FF - Rebar Fixing 70% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 23.77% | 25.14% | 1.37% | MEP & Finishes | 2025-01-25 |  | 2025-05-10 | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – Wall Rebar, Shutter & Concrete pouring up to 1st FL level • Shelter Block - Substructure – Waterproofing & Backfilling works. • Shelter Block - Superstructure - RCC wall to progress GF & 1FL • Shelter Block - Surface Preparation & Application of CFRP • Shelter Block - Roof Slab Strengthening works to progress | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 10152055.77 | 180000 | https://drive.google.com/thumbnail?id=1j8yRlDYok5MJSeLQ4eUWBEa5wF2-pNRd&sz=w1000 | https://drive.google.com/file/d/1j8yRlDYok5MJSeLQ4eUWBEa5wF2-pNRd/view?usp=drive_link | https://drive.google.com/thumbnail?id=1Kj7pGsto2d8qxWBBNeFSXHt0ZCv3amEr&sz=w1000 | https://drive.google.com/file/d/1Kj7pGsto2d8qxWBBNeFSXHt0ZCv3amEr/view?usp=drive_link | https://drive.google.com/thumbnail?id=1rOTt3bC6ZLN5P-SA_JVctRcIj9J1mxVr&sz=w1000 | https://drive.google.com/file/d/1rOTt3bC6ZLN5P-SA_JVctRcIj9J1mxVr/view?usp=drive_link
2024-08-30 | Al Shahama-School-P17 | P17 | SC-02 | 348 | 199 | 547 | • Annex Building - RCC Wall Concrete Upto FF Level – 100% Completed; 1FF Slab - Staging & Shutter fixing in progress • School Building - GF - RCC Wall Rebar fixing 99% Completed, FF - Rebar Fixing 70% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 23.77% | 25.14% | 1.37% | BCC Inspection | 2025-02-13 |  | 2025-05-26 | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – Wall Rebar, Shutter & Concrete pouring up to 1st FL level • Shelter Block - Substructure – Waterproofing & Backfilling works. • Shelter Block - Superstructure - RCC wall to progress GF & 1FL • Shelter Block - Surface Preparation & Application of CFRP • Shelter Block - Roof Slab Strengthening works to progress | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 10152055.77 | 180000 | https://drive.google.com/thumbnail?id=1j8yRlDYok5MJSeLQ4eUWBEa5wF2-pNRd&sz=w1000 | https://drive.google.com/file/d/1j8yRlDYok5MJSeLQ4eUWBEa5wF2-pNRd/view?usp=drive_link | https://drive.google.com/thumbnail?id=1Kj7pGsto2d8qxWBBNeFSXHt0ZCv3amEr&sz=w1000 | https://drive.google.com/file/d/1Kj7pGsto2d8qxWBBNeFSXHt0ZCv3amEr/view?usp=drive_link | https://drive.google.com/thumbnail?id=1rOTt3bC6ZLN5P-SA_JVctRcIj9J1mxVr&sz=w1000 | https://drive.google.com/file/d/1rOTt3bC6ZLN5P-SA_JVctRcIj9J1mxVr/view?usp=drive_link
2024-08-30 | Al Shahama-School-P17 | P17 | SC-02 | 348 | 199 | 547 | • Annex Building - RCC Wall Concrete Upto FF Level – 100% Completed; 1FF Slab - Staging & Shutter fixing in progress • School Building - GF - RCC Wall Rebar fixing 99% Completed, FF - Rebar Fixing 70% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 23.77% | 25.14% | 1.37% | BCC Issuance | 2025-03-04 |  | 2025-06-16 | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – Wall Rebar, Shutter & Concrete pouring up to 1st FL level • Shelter Block - Substructure – Waterproofing & Backfilling works. • Shelter Block - Superstructure - RCC wall to progress GF & 1FL • Shelter Block - Surface Preparation & Application of CFRP • Shelter Block - Roof Slab Strengthening works to progress | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 10152055.77 | 180000 | https://drive.google.com/thumbnail?id=1j8yRlDYok5MJSeLQ4eUWBEa5wF2-pNRd&sz=w1000 | https://drive.google.com/file/d/1j8yRlDYok5MJSeLQ4eUWBEa5wF2-pNRd/view?usp=drive_link | https://drive.google.com/thumbnail?id=1Kj7pGsto2d8qxWBBNeFSXHt0ZCv3amEr&sz=w1000 | https://drive.google.com/file/d/1Kj7pGsto2d8qxWBBNeFSXHt0ZCv3amEr/view?usp=drive_link | https://drive.google.com/thumbnail?id=1rOTt3bC6ZLN5P-SA_JVctRcIj9J1mxVr&sz=w1000 | https://drive.google.com/file/d/1rOTt3bC6ZLN5P-SA_JVctRcIj9J1mxVr/view?usp=drive_link
2024-08-30 | Al Shahama-School-P17 | P17 | SC-02 | 348 | 199 | 547 | • Annex Building - RCC Wall Concrete Upto FF Level – 100% Completed; 1FF Slab - Staging & Shutter fixing in progress • School Building - GF - RCC Wall Rebar fixing 99% Completed, FF - Rebar Fixing 70% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 23.77% | 25.14% | 1.37% | Completion | 2025-03-17 |  | 2025-06-30 | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – Wall Rebar, Shutter & Concrete pouring up to 1st FL level • Shelter Block - Substructure – Waterproofing & Backfilling works. • Shelter Block - Superstructure - RCC wall to progress GF & 1FL • Shelter Block - Surface Preparation & Application of CFRP • Shelter Block - Roof Slab Strengthening works to progress | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 10152055.77 | 180000 | https://drive.google.com/thumbnail?id=1j8yRlDYok5MJSeLQ4eUWBEa5wF2-pNRd&sz=w1000 | https://drive.google.com/file/d/1j8yRlDYok5MJSeLQ4eUWBEa5wF2-pNRd/view?usp=drive_link | https://drive.google.com/thumbnail?id=1Kj7pGsto2d8qxWBBNeFSXHt0ZCv3amEr&sz=w1000 | https://drive.google.com/file/d/1Kj7pGsto2d8qxWBBNeFSXHt0ZCv3amEr/view?usp=drive_link | https://drive.google.com/thumbnail?id=1rOTt3bC6ZLN5P-SA_JVctRcIj9J1mxVr&sz=w1000 | https://drive.google.com/file/d/1rOTt3bC6ZLN5P-SA_JVctRcIj9J1mxVr/view?usp=drive_link
2024-08-30 | Al Sarouj-School-P2 | P2 | SC-03 | 275 | 272 | 547 | • Annex Building - Superstructure – Ground Floor Rebar work 95% Completed • School Building - RCC Wall Concrete Upto Plinth 98% completed, GF Rebar work 20% completed • School Building - GF Wall Rebar Fixing – 18% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 7.65% | 17.67% | 10.02% | Notice to Commence | 2023-11-30 | 2023-11-30 |  | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab & Beam Works to progress • Annex Building - Superstructure works – RCC wall up to FF level to progress • Shelter Block - Substructure –works to complete • Shelter Block - Superstructure – RCC Wall work to progress upto 1FL Level • Shelter Block - Surface Preparation for CRFP works to progress | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 9409120.25 | 180000 | https://drive.google.com/thumbnail?id=1ywKHanqfzSMK2cHlLA75K0HmRTEgQa4h&sz=w1000 | SC3https://drive.google.com/file/d/1ywKHanqfzSMK2cHlLA75K0HmRTEgQa4h/view?usp=drive_link | https://drive.google.com/thumbnail?id=12sTUZOMQU8Yb4ZMfjTWU89XE7G6Mx5fV&sz=w1000 | https://drive.google.com/file/d/12sTUZOMQU8Yb4ZMfjTWU89XE7G6Mx5fV/view?usp=drive_link | https://drive.google.com/thumbnail?id=1q1S8kM3uWaJrbD9mRZ_cWxaj0alzeKgN&sz=w1000 | https://drive.google.com/file/d/1q1S8kM3uWaJrbD9mRZ_cWxaj0alzeKgN/view?usp=drive_link
2024-08-30 | Al Sarouj-School-P2 | P2 | SC-03 | 275 | 272 | 547 | • Annex Building - Superstructure – Ground Floor Rebar work 95% Completed • School Building - RCC Wall Concrete Upto Plinth 98% completed, GF Rebar work 20% completed • School Building - GF Wall Rebar Fixing – 18% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 7.65% | 17.67% | 10.02% | Site Mobilization | 2024-01-05 | 2024-01-06 |  | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab & Beam Works to progress • Annex Building - Superstructure works – RCC wall up to FF level to progress • Shelter Block - Substructure –works to complete • Shelter Block - Superstructure – RCC Wall work to progress upto 1FL Level • Shelter Block - Surface Preparation for CRFP works to progress | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 9409120.25 | 180000 | https://drive.google.com/thumbnail?id=1ywKHanqfzSMK2cHlLA75K0HmRTEgQa4h&sz=w1000 | SC3https://drive.google.com/file/d/1ywKHanqfzSMK2cHlLA75K0HmRTEgQa4h/view?usp=drive_link | https://drive.google.com/thumbnail?id=12sTUZOMQU8Yb4ZMfjTWU89XE7G6Mx5fV&sz=w1000 | https://drive.google.com/file/d/12sTUZOMQU8Yb4ZMfjTWU89XE7G6Mx5fV/view?usp=drive_link | https://drive.google.com/thumbnail?id=1q1S8kM3uWaJrbD9mRZ_cWxaj0alzeKgN&sz=w1000 | https://drive.google.com/file/d/1q1S8kM3uWaJrbD9mRZ_cWxaj0alzeKgN/view?usp=drive_link
2024-08-30 | Al Sarouj-School-P2 | P2 | SC-03 | 275 | 272 | 547 | • Annex Building - Superstructure – Ground Floor Rebar work 95% Completed • School Building - RCC Wall Concrete Upto Plinth 98% completed, GF Rebar work 20% completed • School Building - GF Wall Rebar Fixing – 18% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 7.65% | 17.67% | 10.02% | Building Permit | 2024-07-29 | 2024-06-20 |  | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab & Beam Works to progress • Annex Building - Superstructure works – RCC wall up to FF level to progress • Shelter Block - Substructure –works to complete • Shelter Block - Superstructure – RCC Wall work to progress upto 1FL Level • Shelter Block - Surface Preparation for CRFP works to progress | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 9409120.25 | 180000 | https://drive.google.com/thumbnail?id=1ywKHanqfzSMK2cHlLA75K0HmRTEgQa4h&sz=w1000 | SC3https://drive.google.com/file/d/1ywKHanqfzSMK2cHlLA75K0HmRTEgQa4h/view?usp=drive_link | https://drive.google.com/thumbnail?id=12sTUZOMQU8Yb4ZMfjTWU89XE7G6Mx5fV&sz=w1000 | https://drive.google.com/file/d/12sTUZOMQU8Yb4ZMfjTWU89XE7G6Mx5fV/view?usp=drive_link | https://drive.google.com/thumbnail?id=1q1S8kM3uWaJrbD9mRZ_cWxaj0alzeKgN&sz=w1000 | https://drive.google.com/file/d/1q1S8kM3uWaJrbD9mRZ_cWxaj0alzeKgN/view?usp=drive_link
2024-08-30 | Al Sarouj-School-P2 | P2 | SC-03 | 275 | 272 | 547 | • Annex Building - Superstructure – Ground Floor Rebar work 95% Completed • School Building - RCC Wall Concrete Upto Plinth 98% completed, GF Rebar work 20% completed • School Building - GF Wall Rebar Fixing – 18% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 7.65% | 17.67% | 10.02% | School Substructure | 2024-10-14 |  | 2024-09-13 | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab & Beam Works to progress • Annex Building - Superstructure works – RCC wall up to FF level to progress • Shelter Block - Substructure –works to complete • Shelter Block - Superstructure – RCC Wall work to progress upto 1FL Level • Shelter Block - Surface Preparation for CRFP works to progress | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 9409120.25 | 180000 | https://drive.google.com/thumbnail?id=1ywKHanqfzSMK2cHlLA75K0HmRTEgQa4h&sz=w1000 | SC3https://drive.google.com/file/d/1ywKHanqfzSMK2cHlLA75K0HmRTEgQa4h/view?usp=drive_link | https://drive.google.com/thumbnail?id=12sTUZOMQU8Yb4ZMfjTWU89XE7G6Mx5fV&sz=w1000 | https://drive.google.com/file/d/12sTUZOMQU8Yb4ZMfjTWU89XE7G6Mx5fV/view?usp=drive_link | https://drive.google.com/thumbnail?id=1q1S8kM3uWaJrbD9mRZ_cWxaj0alzeKgN&sz=w1000 | https://drive.google.com/file/d/1q1S8kM3uWaJrbD9mRZ_cWxaj0alzeKgN/view?usp=drive_link
2024-08-30 | Al Sarouj-School-P2 | P2 | SC-03 | 275 | 272 | 547 | • Annex Building - Superstructure – Ground Floor Rebar work 95% Completed • School Building - RCC Wall Concrete Upto Plinth 98% completed, GF Rebar work 20% completed • School Building - GF Wall Rebar Fixing – 18% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 7.65% | 17.67% | 10.02% | School Superstructure | 2025-01-20 |  | 2024-11-18 | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab & Beam Works to progress • Annex Building - Superstructure works – RCC wall up to FF level to progress • Shelter Block - Substructure –works to complete • Shelter Block - Superstructure – RCC Wall work to progress upto 1FL Level • Shelter Block - Surface Preparation for CRFP works to progress | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 9409120.25 | 180000 | https://drive.google.com/thumbnail?id=1ywKHanqfzSMK2cHlLA75K0HmRTEgQa4h&sz=w1000 | SC3https://drive.google.com/file/d/1ywKHanqfzSMK2cHlLA75K0HmRTEgQa4h/view?usp=drive_link | https://drive.google.com/thumbnail?id=12sTUZOMQU8Yb4ZMfjTWU89XE7G6Mx5fV&sz=w1000 | https://drive.google.com/file/d/12sTUZOMQU8Yb4ZMfjTWU89XE7G6Mx5fV/view?usp=drive_link | https://drive.google.com/thumbnail?id=1q1S8kM3uWaJrbD9mRZ_cWxaj0alzeKgN&sz=w1000 | https://drive.google.com/file/d/1q1S8kM3uWaJrbD9mRZ_cWxaj0alzeKgN/view?usp=drive_link
2024-08-30 | Al Sarouj-School-P2 | P2 | SC-03 | 275 | 272 | 547 | • Annex Building - Superstructure – Ground Floor Rebar work 95% Completed • School Building - RCC Wall Concrete Upto Plinth 98% completed, GF Rebar work 20% completed • School Building - GF Wall Rebar Fixing – 18% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 7.65% | 17.67% | 10.02% | Annex Substructure | 2024-10-15 | 2024-06-29 |  | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab & Beam Works to progress • Annex Building - Superstructure works – RCC wall up to FF level to progress • Shelter Block - Substructure –works to complete • Shelter Block - Superstructure – RCC Wall work to progress upto 1FL Level • Shelter Block - Surface Preparation for CRFP works to progress | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 9409120.25 | 180000 | https://drive.google.com/thumbnail?id=1ywKHanqfzSMK2cHlLA75K0HmRTEgQa4h&sz=w1000 | SC3https://drive.google.com/file/d/1ywKHanqfzSMK2cHlLA75K0HmRTEgQa4h/view?usp=drive_link | https://drive.google.com/thumbnail?id=12sTUZOMQU8Yb4ZMfjTWU89XE7G6Mx5fV&sz=w1000 | https://drive.google.com/file/d/12sTUZOMQU8Yb4ZMfjTWU89XE7G6Mx5fV/view?usp=drive_link | https://drive.google.com/thumbnail?id=1q1S8kM3uWaJrbD9mRZ_cWxaj0alzeKgN&sz=w1000 | https://drive.google.com/file/d/1q1S8kM3uWaJrbD9mRZ_cWxaj0alzeKgN/view?usp=drive_link
2024-08-30 | Al Sarouj-School-P2 | P2 | SC-03 | 275 | 272 | 547 | • Annex Building - Superstructure – Ground Floor Rebar work 95% Completed • School Building - RCC Wall Concrete Upto Plinth 98% completed, GF Rebar work 20% completed • School Building - GF Wall Rebar Fixing – 18% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 7.65% | 17.67% | 10.02% | Annex Superstructure | 2025-01-14 |  | 2024-10-26 | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab & Beam Works to progress • Annex Building - Superstructure works – RCC wall up to FF level to progress • Shelter Block - Substructure –works to complete • Shelter Block - Superstructure – RCC Wall work to progress upto 1FL Level • Shelter Block - Surface Preparation for CRFP works to progress | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 9409120.25 | 180000 | https://drive.google.com/thumbnail?id=1ywKHanqfzSMK2cHlLA75K0HmRTEgQa4h&sz=w1000 | SC3https://drive.google.com/file/d/1ywKHanqfzSMK2cHlLA75K0HmRTEgQa4h/view?usp=drive_link | https://drive.google.com/thumbnail?id=12sTUZOMQU8Yb4ZMfjTWU89XE7G6Mx5fV&sz=w1000 | https://drive.google.com/file/d/12sTUZOMQU8Yb4ZMfjTWU89XE7G6Mx5fV/view?usp=drive_link | https://drive.google.com/thumbnail?id=1q1S8kM3uWaJrbD9mRZ_cWxaj0alzeKgN&sz=w1000 | https://drive.google.com/file/d/1q1S8kM3uWaJrbD9mRZ_cWxaj0alzeKgN/view?usp=drive_link
2024-08-30 | Al Sarouj-School-P2 | P2 | SC-03 | 275 | 272 | 547 | • Annex Building - Superstructure – Ground Floor Rebar work 95% Completed • School Building - RCC Wall Concrete Upto Plinth 98% completed, GF Rebar work 20% completed • School Building - GF Wall Rebar Fixing – 18% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 7.65% | 17.67% | 10.02% | MEP & Finishes | 2025-04-10 |  | 2025-05-15 | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab & Beam Works to progress • Annex Building - Superstructure works – RCC wall up to FF level to progress • Shelter Block - Substructure –works to complete • Shelter Block - Superstructure – RCC Wall work to progress upto 1FL Level • Shelter Block - Surface Preparation for CRFP works to progress | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 9409120.25 | 180000 | https://drive.google.com/thumbnail?id=1ywKHanqfzSMK2cHlLA75K0HmRTEgQa4h&sz=w1000 | SC3https://drive.google.com/file/d/1ywKHanqfzSMK2cHlLA75K0HmRTEgQa4h/view?usp=drive_link | https://drive.google.com/thumbnail?id=12sTUZOMQU8Yb4ZMfjTWU89XE7G6Mx5fV&sz=w1000 | https://drive.google.com/file/d/12sTUZOMQU8Yb4ZMfjTWU89XE7G6Mx5fV/view?usp=drive_link | https://drive.google.com/thumbnail?id=1q1S8kM3uWaJrbD9mRZ_cWxaj0alzeKgN&sz=w1000 | https://drive.google.com/file/d/1q1S8kM3uWaJrbD9mRZ_cWxaj0alzeKgN/view?usp=drive_link
2024-08-30 | Al Sarouj-School-P2 | P2 | SC-03 | 275 | 272 | 547 | • Annex Building - Superstructure – Ground Floor Rebar work 95% Completed • School Building - RCC Wall Concrete Upto Plinth 98% completed, GF Rebar work 20% completed • School Building - GF Wall Rebar Fixing – 18% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 7.65% | 17.67% | 10.02% | BCC Inspection | 2025-04-29 |  | 2025-05-26 | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab & Beam Works to progress • Annex Building - Superstructure works – RCC wall up to FF level to progress • Shelter Block - Substructure –works to complete • Shelter Block - Superstructure – RCC Wall work to progress upto 1FL Level • Shelter Block - Surface Preparation for CRFP works to progress | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 9409120.25 | 180000 | https://drive.google.com/thumbnail?id=1ywKHanqfzSMK2cHlLA75K0HmRTEgQa4h&sz=w1000 | SC3https://drive.google.com/file/d/1ywKHanqfzSMK2cHlLA75K0HmRTEgQa4h/view?usp=drive_link | https://drive.google.com/thumbnail?id=12sTUZOMQU8Yb4ZMfjTWU89XE7G6Mx5fV&sz=w1000 | https://drive.google.com/file/d/12sTUZOMQU8Yb4ZMfjTWU89XE7G6Mx5fV/view?usp=drive_link | https://drive.google.com/thumbnail?id=1q1S8kM3uWaJrbD9mRZ_cWxaj0alzeKgN&sz=w1000 | https://drive.google.com/file/d/1q1S8kM3uWaJrbD9mRZ_cWxaj0alzeKgN/view?usp=drive_link
2024-08-30 | Al Sarouj-School-P2 | P2 | SC-03 | 275 | 272 | 547 | • Annex Building - Superstructure – Ground Floor Rebar work 95% Completed • School Building - RCC Wall Concrete Upto Plinth 98% completed, GF Rebar work 20% completed • School Building - GF Wall Rebar Fixing – 18% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 7.65% | 17.67% | 10.02% | BCC Issuance | 2025-05-16 |  | 2025-06-16 | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab & Beam Works to progress • Annex Building - Superstructure works – RCC wall up to FF level to progress • Shelter Block - Substructure –works to complete • Shelter Block - Superstructure – RCC Wall work to progress upto 1FL Level • Shelter Block - Surface Preparation for CRFP works to progress | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 9409120.25 | 180000 | https://drive.google.com/thumbnail?id=1ywKHanqfzSMK2cHlLA75K0HmRTEgQa4h&sz=w1000 | SC3https://drive.google.com/file/d/1ywKHanqfzSMK2cHlLA75K0HmRTEgQa4h/view?usp=drive_link | https://drive.google.com/thumbnail?id=12sTUZOMQU8Yb4ZMfjTWU89XE7G6Mx5fV&sz=w1000 | https://drive.google.com/file/d/12sTUZOMQU8Yb4ZMfjTWU89XE7G6Mx5fV/view?usp=drive_link | https://drive.google.com/thumbnail?id=1q1S8kM3uWaJrbD9mRZ_cWxaj0alzeKgN&sz=w1000 | https://drive.google.com/file/d/1q1S8kM3uWaJrbD9mRZ_cWxaj0alzeKgN/view?usp=drive_link
2024-08-30 | Al Sarouj-School-P2 | P2 | SC-03 | 275 | 272 | 547 | • Annex Building - Superstructure – Ground Floor Rebar work 95% Completed • School Building - RCC Wall Concrete Upto Plinth 98% completed, GF Rebar work 20% completed • School Building - GF Wall Rebar Fixing – 18% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 7.65% | 17.67% | 10.02% | Completion | 2025-05-29 |  | 2025-06-30 | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab & Beam Works to progress • Annex Building - Superstructure works – RCC wall up to FF level to progress • Shelter Block - Substructure –works to complete • Shelter Block - Superstructure – RCC Wall work to progress upto 1FL Level • Shelter Block - Surface Preparation for CRFP works to progress | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 9409120.25 | 180000 | https://drive.google.com/thumbnail?id=1ywKHanqfzSMK2cHlLA75K0HmRTEgQa4h&sz=w1000 | SC3https://drive.google.com/file/d/1ywKHanqfzSMK2cHlLA75K0HmRTEgQa4h/view?usp=drive_link | https://drive.google.com/thumbnail?id=12sTUZOMQU8Yb4ZMfjTWU89XE7G6Mx5fV&sz=w1000 | https://drive.google.com/file/d/12sTUZOMQU8Yb4ZMfjTWU89XE7G6Mx5fV/view?usp=drive_link | https://drive.google.com/thumbnail?id=1q1S8kM3uWaJrbD9mRZ_cWxaj0alzeKgN&sz=w1000 | https://drive.google.com/file/d/1q1S8kM3uWaJrbD9mRZ_cWxaj0alzeKgN/view?usp=drive_link
2024-08-30 | Al Sarouj-School-P16 | P16 | SC-04 | 348 | 199 | 547 | • Annex Building - Backfilling 90% completed; GF RCC wall Rebar & Shutter fabrication ongoing • School Building - Plinth wall 95% completed; GF RCC Wall Rebar Fixing 20% done | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 23.77% | 15.33% | -8.44% | Notice to Commence | 2023-09-18 | 2023-09-26 |  | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure works to complete • Annex Building - Superstructure – RCC Wall works to progress • Shelter Block - Substructure – Plinth Wall construction to complete. • Shelter Block - GF – Rebar Fixing for Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 9055227.15 | 180000 | https://drive.google.com/thumbnail?id=1a0Y0yLRRfNYWEbl7hjxRwwCR8iQ52iEa&sz=w1000 | https://drive.google.com/file/d/1a0Y0yLRRfNYWEbl7hjxRwwCR8iQ52iEa/view?usp=drive_link | https://drive.google.com/thumbnail?id=1fVGTywNnBvbe_-XZ6i9qc-4BCJw5nmT1&sz=w1000 | https://drive.google.com/file/d/1fVGTywNnBvbe_-XZ6i9qc-4BCJw5nmT1/view?usp=drive_link | https://drive.google.com/thumbnail?id=14YXw1eE_uNUTiyyJLFE-3TZXAvUd7kRa&sz=w1000 | https://drive.google.com/file/d/14YXw1eE_uNUTiyyJLFE-3TZXAvUd7kRa/view?usp=drive_link
2024-08-30 | Al Sarouj-School-P16 | P16 | SC-04 | 348 | 199 | 547 | • Annex Building - Backfilling 90% completed; GF RCC wall Rebar & Shutter fabrication ongoing • School Building - Plinth wall 95% completed; GF RCC Wall Rebar Fixing 20% done | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 23.77% | 15.33% | -8.44% | Site Mobilization | 2023-10-21 | 2024-01-06 |  | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure works to complete • Annex Building - Superstructure – RCC Wall works to progress • Shelter Block - Substructure – Plinth Wall construction to complete. • Shelter Block - GF – Rebar Fixing for Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 9055227.15 | 180000 | https://drive.google.com/thumbnail?id=1a0Y0yLRRfNYWEbl7hjxRwwCR8iQ52iEa&sz=w1000 | https://drive.google.com/file/d/1a0Y0yLRRfNYWEbl7hjxRwwCR8iQ52iEa/view?usp=drive_link | https://drive.google.com/thumbnail?id=1fVGTywNnBvbe_-XZ6i9qc-4BCJw5nmT1&sz=w1000 | https://drive.google.com/file/d/1fVGTywNnBvbe_-XZ6i9qc-4BCJw5nmT1/view?usp=drive_link | https://drive.google.com/thumbnail?id=14YXw1eE_uNUTiyyJLFE-3TZXAvUd7kRa&sz=w1000 | https://drive.google.com/file/d/14YXw1eE_uNUTiyyJLFE-3TZXAvUd7kRa/view?usp=drive_link
2024-08-30 | Al Sarouj-School-P16 | P16 | SC-04 | 348 | 199 | 547 | • Annex Building - Backfilling 90% completed; GF RCC wall Rebar & Shutter fabrication ongoing • School Building - Plinth wall 95% completed; GF RCC Wall Rebar Fixing 20% done | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 23.77% | 15.33% | -8.44% | Building Permit | 2024-05-17 | 2024-06-20 |  | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure works to complete • Annex Building - Superstructure – RCC Wall works to progress • Shelter Block - Substructure – Plinth Wall construction to complete. • Shelter Block - GF – Rebar Fixing for Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 9055227.15 | 180000 | https://drive.google.com/thumbnail?id=1a0Y0yLRRfNYWEbl7hjxRwwCR8iQ52iEa&sz=w1000 | https://drive.google.com/file/d/1a0Y0yLRRfNYWEbl7hjxRwwCR8iQ52iEa/view?usp=drive_link | https://drive.google.com/thumbnail?id=1fVGTywNnBvbe_-XZ6i9qc-4BCJw5nmT1&sz=w1000 | https://drive.google.com/file/d/1fVGTywNnBvbe_-XZ6i9qc-4BCJw5nmT1/view?usp=drive_link | https://drive.google.com/thumbnail?id=14YXw1eE_uNUTiyyJLFE-3TZXAvUd7kRa&sz=w1000 | https://drive.google.com/file/d/14YXw1eE_uNUTiyyJLFE-3TZXAvUd7kRa/view?usp=drive_link
2024-08-30 | Al Sarouj-School-P16 | P16 | SC-04 | 348 | 199 | 547 | • Annex Building - Backfilling 90% completed; GF RCC wall Rebar & Shutter fabrication ongoing • School Building - Plinth wall 95% completed; GF RCC Wall Rebar Fixing 20% done | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 23.77% | 15.33% | -8.44% | School Substructure | 2024-08-06 |  | 2024-09-13 | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure works to complete • Annex Building - Superstructure – RCC Wall works to progress • Shelter Block - Substructure – Plinth Wall construction to complete. • Shelter Block - GF – Rebar Fixing for Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 9055227.15 | 180000 | https://drive.google.com/thumbnail?id=1a0Y0yLRRfNYWEbl7hjxRwwCR8iQ52iEa&sz=w1000 | https://drive.google.com/file/d/1a0Y0yLRRfNYWEbl7hjxRwwCR8iQ52iEa/view?usp=drive_link | https://drive.google.com/thumbnail?id=1fVGTywNnBvbe_-XZ6i9qc-4BCJw5nmT1&sz=w1000 | https://drive.google.com/file/d/1fVGTywNnBvbe_-XZ6i9qc-4BCJw5nmT1/view?usp=drive_link | https://drive.google.com/thumbnail?id=14YXw1eE_uNUTiyyJLFE-3TZXAvUd7kRa&sz=w1000 | https://drive.google.com/file/d/14YXw1eE_uNUTiyyJLFE-3TZXAvUd7kRa/view?usp=drive_link
2024-08-30 | Al Sarouj-School-P16 | P16 | SC-04 | 348 | 199 | 547 | • Annex Building - Backfilling 90% completed; GF RCC wall Rebar & Shutter fabrication ongoing • School Building - Plinth wall 95% completed; GF RCC Wall Rebar Fixing 20% done | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 23.77% | 15.33% | -8.44% | School Superstructure | 2024-11-07 |  | 2024-11-16 | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure works to complete • Annex Building - Superstructure – RCC Wall works to progress • Shelter Block - Substructure – Plinth Wall construction to complete. • Shelter Block - GF – Rebar Fixing for Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 9055227.15 | 180000 | https://drive.google.com/thumbnail?id=1a0Y0yLRRfNYWEbl7hjxRwwCR8iQ52iEa&sz=w1000 | https://drive.google.com/file/d/1a0Y0yLRRfNYWEbl7hjxRwwCR8iQ52iEa/view?usp=drive_link | https://drive.google.com/thumbnail?id=1fVGTywNnBvbe_-XZ6i9qc-4BCJw5nmT1&sz=w1000 | https://drive.google.com/file/d/1fVGTywNnBvbe_-XZ6i9qc-4BCJw5nmT1/view?usp=drive_link | https://drive.google.com/thumbnail?id=14YXw1eE_uNUTiyyJLFE-3TZXAvUd7kRa&sz=w1000 | https://drive.google.com/file/d/14YXw1eE_uNUTiyyJLFE-3TZXAvUd7kRa/view?usp=drive_link
2024-08-30 | Al Sarouj-School-P16 | P16 | SC-04 | 348 | 199 | 547 | • Annex Building - Backfilling 90% completed; GF RCC wall Rebar & Shutter fabrication ongoing • School Building - Plinth wall 95% completed; GF RCC Wall Rebar Fixing 20% done | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 23.77% | 15.33% | -8.44% | Annex Substructure | 2024-08-07 |  | 2024-08-31 | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure works to complete • Annex Building - Superstructure – RCC Wall works to progress • Shelter Block - Substructure – Plinth Wall construction to complete. • Shelter Block - GF – Rebar Fixing for Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 9055227.15 | 180000 | https://drive.google.com/thumbnail?id=1a0Y0yLRRfNYWEbl7hjxRwwCR8iQ52iEa&sz=w1000 | https://drive.google.com/file/d/1a0Y0yLRRfNYWEbl7hjxRwwCR8iQ52iEa/view?usp=drive_link | https://drive.google.com/thumbnail?id=1fVGTywNnBvbe_-XZ6i9qc-4BCJw5nmT1&sz=w1000 | https://drive.google.com/file/d/1fVGTywNnBvbe_-XZ6i9qc-4BCJw5nmT1/view?usp=drive_link | https://drive.google.com/thumbnail?id=14YXw1eE_uNUTiyyJLFE-3TZXAvUd7kRa&sz=w1000 | https://drive.google.com/file/d/14YXw1eE_uNUTiyyJLFE-3TZXAvUd7kRa/view?usp=drive_link
2024-08-30 | Al Sarouj-School-P16 | P16 | SC-04 | 348 | 199 | 547 | • Annex Building - Backfilling 90% completed; GF RCC wall Rebar & Shutter fabrication ongoing • School Building - Plinth wall 95% completed; GF RCC Wall Rebar Fixing 20% done | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 23.77% | 15.33% | -8.44% | Annex Superstructure | 2024-10-31 |  | 2024-11-14 | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure works to complete • Annex Building - Superstructure – RCC Wall works to progress • Shelter Block - Substructure – Plinth Wall construction to complete. • Shelter Block - GF – Rebar Fixing for Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 9055227.15 | 180000 | https://drive.google.com/thumbnail?id=1a0Y0yLRRfNYWEbl7hjxRwwCR8iQ52iEa&sz=w1000 | https://drive.google.com/file/d/1a0Y0yLRRfNYWEbl7hjxRwwCR8iQ52iEa/view?usp=drive_link | https://drive.google.com/thumbnail?id=1fVGTywNnBvbe_-XZ6i9qc-4BCJw5nmT1&sz=w1000 | https://drive.google.com/file/d/1fVGTywNnBvbe_-XZ6i9qc-4BCJw5nmT1/view?usp=drive_link | https://drive.google.com/thumbnail?id=14YXw1eE_uNUTiyyJLFE-3TZXAvUd7kRa&sz=w1000 | https://drive.google.com/file/d/14YXw1eE_uNUTiyyJLFE-3TZXAvUd7kRa/view?usp=drive_link
2024-08-30 | Al Sarouj-School-P16 | P16 | SC-04 | 348 | 199 | 547 | • Annex Building - Backfilling 90% completed; GF RCC wall Rebar & Shutter fabrication ongoing • School Building - Plinth wall 95% completed; GF RCC Wall Rebar Fixing 20% done | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 23.77% | 15.33% | -8.44% | MEP & Finishes | 2025-01-25 |  | 2025-05-15 | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure works to complete • Annex Building - Superstructure – RCC Wall works to progress • Shelter Block - Substructure – Plinth Wall construction to complete. • Shelter Block - GF – Rebar Fixing for Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 9055227.15 | 180000 | https://drive.google.com/thumbnail?id=1a0Y0yLRRfNYWEbl7hjxRwwCR8iQ52iEa&sz=w1000 | https://drive.google.com/file/d/1a0Y0yLRRfNYWEbl7hjxRwwCR8iQ52iEa/view?usp=drive_link | https://drive.google.com/thumbnail?id=1fVGTywNnBvbe_-XZ6i9qc-4BCJw5nmT1&sz=w1000 | https://drive.google.com/file/d/1fVGTywNnBvbe_-XZ6i9qc-4BCJw5nmT1/view?usp=drive_link | https://drive.google.com/thumbnail?id=14YXw1eE_uNUTiyyJLFE-3TZXAvUd7kRa&sz=w1000 | https://drive.google.com/file/d/14YXw1eE_uNUTiyyJLFE-3TZXAvUd7kRa/view?usp=drive_link
2024-08-30 | Al Sarouj-School-P16 | P16 | SC-04 | 348 | 199 | 547 | • Annex Building - Backfilling 90% completed; GF RCC wall Rebar & Shutter fabrication ongoing • School Building - Plinth wall 95% completed; GF RCC Wall Rebar Fixing 20% done | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 23.77% | 15.33% | -8.44% | BCC Inspection | 2025-02-13 |  | 2025-05-26 | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure works to complete • Annex Building - Superstructure – RCC Wall works to progress • Shelter Block - Substructure – Plinth Wall construction to complete. • Shelter Block - GF – Rebar Fixing for Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 9055227.15 | 180000 | https://drive.google.com/thumbnail?id=1a0Y0yLRRfNYWEbl7hjxRwwCR8iQ52iEa&sz=w1000 | https://drive.google.com/file/d/1a0Y0yLRRfNYWEbl7hjxRwwCR8iQ52iEa/view?usp=drive_link | https://drive.google.com/thumbnail?id=1fVGTywNnBvbe_-XZ6i9qc-4BCJw5nmT1&sz=w1000 | https://drive.google.com/file/d/1fVGTywNnBvbe_-XZ6i9qc-4BCJw5nmT1/view?usp=drive_link | https://drive.google.com/thumbnail?id=14YXw1eE_uNUTiyyJLFE-3TZXAvUd7kRa&sz=w1000 | https://drive.google.com/file/d/14YXw1eE_uNUTiyyJLFE-3TZXAvUd7kRa/view?usp=drive_link
2024-08-30 | Al Sarouj-School-P16 | P16 | SC-04 | 348 | 199 | 547 | • Annex Building - Backfilling 90% completed; GF RCC wall Rebar & Shutter fabrication ongoing • School Building - Plinth wall 95% completed; GF RCC Wall Rebar Fixing 20% done | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 23.77% | 15.33% | -8.44% | BCC Issuance | 2025-03-04 |  | 2025-06-16 | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure works to complete • Annex Building - Superstructure – RCC Wall works to progress • Shelter Block - Substructure – Plinth Wall construction to complete. • Shelter Block - GF – Rebar Fixing for Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 9055227.15 | 180000 | https://drive.google.com/thumbnail?id=1a0Y0yLRRfNYWEbl7hjxRwwCR8iQ52iEa&sz=w1000 | https://drive.google.com/file/d/1a0Y0yLRRfNYWEbl7hjxRwwCR8iQ52iEa/view?usp=drive_link | https://drive.google.com/thumbnail?id=1fVGTywNnBvbe_-XZ6i9qc-4BCJw5nmT1&sz=w1000 | https://drive.google.com/file/d/1fVGTywNnBvbe_-XZ6i9qc-4BCJw5nmT1/view?usp=drive_link | https://drive.google.com/thumbnail?id=14YXw1eE_uNUTiyyJLFE-3TZXAvUd7kRa&sz=w1000 | https://drive.google.com/file/d/14YXw1eE_uNUTiyyJLFE-3TZXAvUd7kRa/view?usp=drive_link
2024-08-30 | Al Sarouj-School-P16 | P16 | SC-04 | 348 | 199 | 547 | • Annex Building - Backfilling 90% completed; GF RCC wall Rebar & Shutter fabrication ongoing • School Building - Plinth wall 95% completed; GF RCC Wall Rebar Fixing 20% done | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 23.77% | 15.33% | -8.44% | Completion | 2025-03-17 |  | 2025-06-30 | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure works to complete • Annex Building - Superstructure – RCC Wall works to progress • Shelter Block - Substructure – Plinth Wall construction to complete. • Shelter Block - GF – Rebar Fixing for Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 9055227.15 | 180000 | https://drive.google.com/thumbnail?id=1a0Y0yLRRfNYWEbl7hjxRwwCR8iQ52iEa&sz=w1000 | https://drive.google.com/file/d/1a0Y0yLRRfNYWEbl7hjxRwwCR8iQ52iEa/view?usp=drive_link | https://drive.google.com/thumbnail?id=1fVGTywNnBvbe_-XZ6i9qc-4BCJw5nmT1&sz=w1000 | https://drive.google.com/file/d/1fVGTywNnBvbe_-XZ6i9qc-4BCJw5nmT1/view?usp=drive_link | https://drive.google.com/thumbnail?id=14YXw1eE_uNUTiyyJLFE-3TZXAvUd7kRa&sz=w1000 | https://drive.google.com/file/d/14YXw1eE_uNUTiyyJLFE-3TZXAvUd7kRa/view?usp=drive_link
2024-08-30 | Al Sila-School-P43 | P43 | SC-05 | 348 | 199 | 547 | • Annex Building - GF - RCC Wall Concrete 85% completed; Wall Concrete 65% Completed • School Building - RCC Plinth Wall - 98% Completed, GF Wall Rebar Fixing 20% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 23.77% | 17.97% | -5.8% | Notice to Commence | 2023-09-18 | 2023-09-26 |  | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works • Annex Building - Superstructure works – RCC Wall works upto 1FL Level • Shelter Block - Substructure –Foundation Cast & Existing Structure Strengthening works to progress • Shelter Block - RCC Plinth Wall & GF Wall Works to progress • Shelter Block - Surface Preparation for CFRP works | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 9105088.17 | 180000 | https://drive.google.com/thumbnail?id=1xtKK1s6-PHzFzBwpapa8NlHm2NARujAZ&sz=w1000 | https://drive.google.com/file/d/1xtKK1s6-PHzFzBwpapa8NlHm2NARujAZ/view?usp=drive_link | https://drive.google.com/thumbnail?id=1SVtLDrCgd-EGMvj8P0ZCjolJ1bcQnWdH&sz=w1000 | https://drive.google.com/file/d/1SVtLDrCgd-EGMvj8P0ZCjolJ1bcQnWdH/view?usp=drive_link | https://drive.google.com/thumbnail?id=1SQaSL7hmUFSKHN8i7pVPvx3STLMqAOAw&sz=w1000 | https://drive.google.com/file/d/1SQaSL7hmUFSKHN8i7pVPvx3STLMqAOAw/view?usp=drive_link
2024-08-30 | Al Sila-School-P43 | P43 | SC-05 | 348 | 199 | 547 | • Annex Building - GF - RCC Wall Concrete 85% completed; Wall Concrete 65% Completed • School Building - RCC Plinth Wall - 98% Completed, GF Wall Rebar Fixing 20% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 23.77% | 17.97% | -5.8% | Site Mobilization | 2023-10-21 | 2024-01-06 |  | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works • Annex Building - Superstructure works – RCC Wall works upto 1FL Level • Shelter Block - Substructure –Foundation Cast & Existing Structure Strengthening works to progress • Shelter Block - RCC Plinth Wall & GF Wall Works to progress • Shelter Block - Surface Preparation for CFRP works | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 9105088.17 | 180000 | https://drive.google.com/thumbnail?id=1xtKK1s6-PHzFzBwpapa8NlHm2NARujAZ&sz=w1000 | https://drive.google.com/file/d/1xtKK1s6-PHzFzBwpapa8NlHm2NARujAZ/view?usp=drive_link | https://drive.google.com/thumbnail?id=1SVtLDrCgd-EGMvj8P0ZCjolJ1bcQnWdH&sz=w1000 | https://drive.google.com/file/d/1SVtLDrCgd-EGMvj8P0ZCjolJ1bcQnWdH/view?usp=drive_link | https://drive.google.com/thumbnail?id=1SQaSL7hmUFSKHN8i7pVPvx3STLMqAOAw&sz=w1000 | https://drive.google.com/file/d/1SQaSL7hmUFSKHN8i7pVPvx3STLMqAOAw/view?usp=drive_link
2024-08-30 | Al Sila-School-P43 | P43 | SC-05 | 348 | 199 | 547 | • Annex Building - GF - RCC Wall Concrete 85% completed; Wall Concrete 65% Completed • School Building - RCC Plinth Wall - 98% Completed, GF Wall Rebar Fixing 20% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 23.77% | 17.97% | -5.8% | Building Permit | 2024-05-17 | 2024-06-04 |  | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works • Annex Building - Superstructure works – RCC Wall works upto 1FL Level • Shelter Block - Substructure –Foundation Cast & Existing Structure Strengthening works to progress • Shelter Block - RCC Plinth Wall & GF Wall Works to progress • Shelter Block - Surface Preparation for CFRP works | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 9105088.17 | 180000 | https://drive.google.com/thumbnail?id=1xtKK1s6-PHzFzBwpapa8NlHm2NARujAZ&sz=w1000 | https://drive.google.com/file/d/1xtKK1s6-PHzFzBwpapa8NlHm2NARujAZ/view?usp=drive_link | https://drive.google.com/thumbnail?id=1SVtLDrCgd-EGMvj8P0ZCjolJ1bcQnWdH&sz=w1000 | https://drive.google.com/file/d/1SVtLDrCgd-EGMvj8P0ZCjolJ1bcQnWdH/view?usp=drive_link | https://drive.google.com/thumbnail?id=1SQaSL7hmUFSKHN8i7pVPvx3STLMqAOAw&sz=w1000 | https://drive.google.com/file/d/1SQaSL7hmUFSKHN8i7pVPvx3STLMqAOAw/view?usp=drive_link
2024-08-30 | Al Sila-School-P43 | P43 | SC-05 | 348 | 199 | 547 | • Annex Building - GF - RCC Wall Concrete 85% completed; Wall Concrete 65% Completed • School Building - RCC Plinth Wall - 98% Completed, GF Wall Rebar Fixing 20% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 23.77% | 17.97% | -5.8% | School Substructure | 2024-08-06 |  | 2024-09-17 | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works • Annex Building - Superstructure works – RCC Wall works upto 1FL Level • Shelter Block - Substructure –Foundation Cast & Existing Structure Strengthening works to progress • Shelter Block - RCC Plinth Wall & GF Wall Works to progress • Shelter Block - Surface Preparation for CFRP works | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 9105088.17 | 180000 | https://drive.google.com/thumbnail?id=1xtKK1s6-PHzFzBwpapa8NlHm2NARujAZ&sz=w1000 | https://drive.google.com/file/d/1xtKK1s6-PHzFzBwpapa8NlHm2NARujAZ/view?usp=drive_link | https://drive.google.com/thumbnail?id=1SVtLDrCgd-EGMvj8P0ZCjolJ1bcQnWdH&sz=w1000 | https://drive.google.com/file/d/1SVtLDrCgd-EGMvj8P0ZCjolJ1bcQnWdH/view?usp=drive_link | https://drive.google.com/thumbnail?id=1SQaSL7hmUFSKHN8i7pVPvx3STLMqAOAw&sz=w1000 | https://drive.google.com/file/d/1SQaSL7hmUFSKHN8i7pVPvx3STLMqAOAw/view?usp=drive_link
2024-08-30 | Al Sila-School-P43 | P43 | SC-05 | 348 | 199 | 547 | • Annex Building - GF - RCC Wall Concrete 85% completed; Wall Concrete 65% Completed • School Building - RCC Plinth Wall - 98% Completed, GF Wall Rebar Fixing 20% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 23.77% | 17.97% | -5.8% | School Superstructure | 2024-11-07 |  | 2024-10-14 | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works • Annex Building - Superstructure works – RCC Wall works upto 1FL Level • Shelter Block - Substructure –Foundation Cast & Existing Structure Strengthening works to progress • Shelter Block - RCC Plinth Wall & GF Wall Works to progress • Shelter Block - Surface Preparation for CFRP works | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 9105088.17 | 180000 | https://drive.google.com/thumbnail?id=1xtKK1s6-PHzFzBwpapa8NlHm2NARujAZ&sz=w1000 | https://drive.google.com/file/d/1xtKK1s6-PHzFzBwpapa8NlHm2NARujAZ/view?usp=drive_link | https://drive.google.com/thumbnail?id=1SVtLDrCgd-EGMvj8P0ZCjolJ1bcQnWdH&sz=w1000 | https://drive.google.com/file/d/1SVtLDrCgd-EGMvj8P0ZCjolJ1bcQnWdH/view?usp=drive_link | https://drive.google.com/thumbnail?id=1SQaSL7hmUFSKHN8i7pVPvx3STLMqAOAw&sz=w1000 | https://drive.google.com/file/d/1SQaSL7hmUFSKHN8i7pVPvx3STLMqAOAw/view?usp=drive_link
2024-08-30 | Al Sila-School-P43 | P43 | SC-05 | 348 | 199 | 547 | • Annex Building - GF - RCC Wall Concrete 85% completed; Wall Concrete 65% Completed • School Building - RCC Plinth Wall - 98% Completed, GF Wall Rebar Fixing 20% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 23.77% | 17.97% | -5.8% | Annex Substructure | 2024-08-07 |  | 2024-08-31 | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works • Annex Building - Superstructure works – RCC Wall works upto 1FL Level • Shelter Block - Substructure –Foundation Cast & Existing Structure Strengthening works to progress • Shelter Block - RCC Plinth Wall & GF Wall Works to progress • Shelter Block - Surface Preparation for CFRP works | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 9105088.17 | 180000 | https://drive.google.com/thumbnail?id=1xtKK1s6-PHzFzBwpapa8NlHm2NARujAZ&sz=w1000 | https://drive.google.com/file/d/1xtKK1s6-PHzFzBwpapa8NlHm2NARujAZ/view?usp=drive_link | https://drive.google.com/thumbnail?id=1SVtLDrCgd-EGMvj8P0ZCjolJ1bcQnWdH&sz=w1000 | https://drive.google.com/file/d/1SVtLDrCgd-EGMvj8P0ZCjolJ1bcQnWdH/view?usp=drive_link | https://drive.google.com/thumbnail?id=1SQaSL7hmUFSKHN8i7pVPvx3STLMqAOAw&sz=w1000 | https://drive.google.com/file/d/1SQaSL7hmUFSKHN8i7pVPvx3STLMqAOAw/view?usp=drive_link
2024-08-30 | Al Sila-School-P43 | P43 | SC-05 | 348 | 199 | 547 | • Annex Building - GF - RCC Wall Concrete 85% completed; Wall Concrete 65% Completed • School Building - RCC Plinth Wall - 98% Completed, GF Wall Rebar Fixing 20% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 23.77% | 17.97% | -5.8% | Annex Superstructure | 2024-10-31 |  | 2024-11-02 | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works • Annex Building - Superstructure works – RCC Wall works upto 1FL Level • Shelter Block - Substructure –Foundation Cast & Existing Structure Strengthening works to progress • Shelter Block - RCC Plinth Wall & GF Wall Works to progress • Shelter Block - Surface Preparation for CFRP works | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 9105088.17 | 180000 | https://drive.google.com/thumbnail?id=1xtKK1s6-PHzFzBwpapa8NlHm2NARujAZ&sz=w1000 | https://drive.google.com/file/d/1xtKK1s6-PHzFzBwpapa8NlHm2NARujAZ/view?usp=drive_link | https://drive.google.com/thumbnail?id=1SVtLDrCgd-EGMvj8P0ZCjolJ1bcQnWdH&sz=w1000 | https://drive.google.com/file/d/1SVtLDrCgd-EGMvj8P0ZCjolJ1bcQnWdH/view?usp=drive_link | https://drive.google.com/thumbnail?id=1SQaSL7hmUFSKHN8i7pVPvx3STLMqAOAw&sz=w1000 | https://drive.google.com/file/d/1SQaSL7hmUFSKHN8i7pVPvx3STLMqAOAw/view?usp=drive_link
2024-08-30 | Al Sila-School-P43 | P43 | SC-05 | 348 | 199 | 547 | • Annex Building - GF - RCC Wall Concrete 85% completed; Wall Concrete 65% Completed • School Building - RCC Plinth Wall - 98% Completed, GF Wall Rebar Fixing 20% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 23.77% | 17.97% | -5.8% | MEP & Finishes | 2025-01-25 |  | 2025-05-15 | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works • Annex Building - Superstructure works – RCC Wall works upto 1FL Level • Shelter Block - Substructure –Foundation Cast & Existing Structure Strengthening works to progress • Shelter Block - RCC Plinth Wall & GF Wall Works to progress • Shelter Block - Surface Preparation for CFRP works | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 9105088.17 | 180000 | https://drive.google.com/thumbnail?id=1xtKK1s6-PHzFzBwpapa8NlHm2NARujAZ&sz=w1000 | https://drive.google.com/file/d/1xtKK1s6-PHzFzBwpapa8NlHm2NARujAZ/view?usp=drive_link | https://drive.google.com/thumbnail?id=1SVtLDrCgd-EGMvj8P0ZCjolJ1bcQnWdH&sz=w1000 | https://drive.google.com/file/d/1SVtLDrCgd-EGMvj8P0ZCjolJ1bcQnWdH/view?usp=drive_link | https://drive.google.com/thumbnail?id=1SQaSL7hmUFSKHN8i7pVPvx3STLMqAOAw&sz=w1000 | https://drive.google.com/file/d/1SQaSL7hmUFSKHN8i7pVPvx3STLMqAOAw/view?usp=drive_link
2024-08-30 | Al Sila-School-P43 | P43 | SC-05 | 348 | 199 | 547 | • Annex Building - GF - RCC Wall Concrete 85% completed; Wall Concrete 65% Completed • School Building - RCC Plinth Wall - 98% Completed, GF Wall Rebar Fixing 20% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 23.77% | 17.97% | -5.8% | BCC Inspection | 2025-02-13 |  | 2025-05-26 | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works • Annex Building - Superstructure works – RCC Wall works upto 1FL Level • Shelter Block - Substructure –Foundation Cast & Existing Structure Strengthening works to progress • Shelter Block - RCC Plinth Wall & GF Wall Works to progress • Shelter Block - Surface Preparation for CFRP works | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 9105088.17 | 180000 | https://drive.google.com/thumbnail?id=1xtKK1s6-PHzFzBwpapa8NlHm2NARujAZ&sz=w1000 | https://drive.google.com/file/d/1xtKK1s6-PHzFzBwpapa8NlHm2NARujAZ/view?usp=drive_link | https://drive.google.com/thumbnail?id=1SVtLDrCgd-EGMvj8P0ZCjolJ1bcQnWdH&sz=w1000 | https://drive.google.com/file/d/1SVtLDrCgd-EGMvj8P0ZCjolJ1bcQnWdH/view?usp=drive_link | https://drive.google.com/thumbnail?id=1SQaSL7hmUFSKHN8i7pVPvx3STLMqAOAw&sz=w1000 | https://drive.google.com/file/d/1SQaSL7hmUFSKHN8i7pVPvx3STLMqAOAw/view?usp=drive_link
2024-08-30 | Al Sila-School-P43 | P43 | SC-05 | 348 | 199 | 547 | • Annex Building - GF - RCC Wall Concrete 85% completed; Wall Concrete 65% Completed • School Building - RCC Plinth Wall - 98% Completed, GF Wall Rebar Fixing 20% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 23.77% | 17.97% | -5.8% | BCC Issuance | 2025-03-04 |  | 2025-06-16 | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works • Annex Building - Superstructure works – RCC Wall works upto 1FL Level • Shelter Block - Substructure –Foundation Cast & Existing Structure Strengthening works to progress • Shelter Block - RCC Plinth Wall & GF Wall Works to progress • Shelter Block - Surface Preparation for CFRP works | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 9105088.17 | 180000 | https://drive.google.com/thumbnail?id=1xtKK1s6-PHzFzBwpapa8NlHm2NARujAZ&sz=w1000 | https://drive.google.com/file/d/1xtKK1s6-PHzFzBwpapa8NlHm2NARujAZ/view?usp=drive_link | https://drive.google.com/thumbnail?id=1SVtLDrCgd-EGMvj8P0ZCjolJ1bcQnWdH&sz=w1000 | https://drive.google.com/file/d/1SVtLDrCgd-EGMvj8P0ZCjolJ1bcQnWdH/view?usp=drive_link | https://drive.google.com/thumbnail?id=1SQaSL7hmUFSKHN8i7pVPvx3STLMqAOAw&sz=w1000 | https://drive.google.com/file/d/1SQaSL7hmUFSKHN8i7pVPvx3STLMqAOAw/view?usp=drive_link
2024-08-30 | Al Sila-School-P43 | P43 | SC-05 | 348 | 199 | 547 | • Annex Building - GF - RCC Wall Concrete 85% completed; Wall Concrete 65% Completed • School Building - RCC Plinth Wall - 98% Completed, GF Wall Rebar Fixing 20% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 23.77% | 17.97% | -5.8% | Completion | 2025-03-17 |  | 2025-06-30 | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works • Annex Building - Superstructure works – RCC Wall works upto 1FL Level • Shelter Block - Substructure –Foundation Cast & Existing Structure Strengthening works to progress • Shelter Block - RCC Plinth Wall & GF Wall Works to progress • Shelter Block - Surface Preparation for CFRP works | 78077600 |  | 78077600 | 1576709 | 0 | 79654309 | 9105088.17 | 180000 | https://drive.google.com/thumbnail?id=1xtKK1s6-PHzFzBwpapa8NlHm2NARujAZ&sz=w1000 | https://drive.google.com/file/d/1xtKK1s6-PHzFzBwpapa8NlHm2NARujAZ/view?usp=drive_link | https://drive.google.com/thumbnail?id=1SVtLDrCgd-EGMvj8P0ZCjolJ1bcQnWdH&sz=w1000 | https://drive.google.com/file/d/1SVtLDrCgd-EGMvj8P0ZCjolJ1bcQnWdH/view?usp=drive_link | https://drive.google.com/thumbnail?id=1SQaSL7hmUFSKHN8i7pVPvx3STLMqAOAw&sz=w1000 | https://drive.google.com/file/d/1SQaSL7hmUFSKHN8i7pVPvx3STLMqAOAw/view?usp=drive_link
2024-08-30 | Madinat Zayed-School-P105 | P105 | SC-06 | 348 | 199 | 547 | • Annex Building - Superstructure – GF RCC Wall Concrete Cast 90 % Completed • School Building - Substructure –Plinth Wall Concrete 94% completed • School Building - GF RCC Wall Rebar Fixing – 35% completed. | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 23.88% | 20.24% | -3.64% | Notice to Commence | 2023-09-18 | 2023-09-26 |  | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works to progress • Annex Building - Superstructure works – RCC Wall works upto FF Level • Shelter Block - Substructure – Foundation Cast & Existing Structure Strengthening works to progress. • Shelter Block - Superstructure - GF & FF Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 |  | 78077600 | 1576709 | 0 | 79654309 | 9564148.07 | 180000 | https://drive.google.com/thumbnail?id=1ObN57YJNOg65CaDV-I6Uf3vEwf4ffCFW&sz=w1000 | https://drive.google.com/file/d/1ObN57YJNOg65CaDV-I6Uf3vEwf4ffCFW/view?usp=drive_link | https://drive.google.com/thumbnail?id=17_08NSWt7_gBt9GqJ59cc4phZ7kJIzsK&sz=w1000 | https://drive.google.com/file/d/17_08NSWt7_gBt9GqJ59cc4phZ7kJIzsK/view?usp=drive_link | https://drive.google.com/thumbnail?id=1eUqriZfZ8ZcnMu4n6LORw1pcnpQae1-d&sz=w1000 | https://drive.google.com/file/d/1eUqriZfZ8ZcnMu4n6LORw1pcnpQae1-d/view?usp=drive_link
2024-08-30 | Madinat Zayed-School-P105 | P105 | SC-06 | 348 | 199 | 547 | • Annex Building - Superstructure – GF RCC Wall Concrete Cast 90 % Completed • School Building - Substructure –Plinth Wall Concrete 94% completed • School Building - GF RCC Wall Rebar Fixing – 35% completed. | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 23.88% | 20.24% | -3.64% | Site Mobilization | 2023-10-21 | 2024-01-06 |  | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works to progress • Annex Building - Superstructure works – RCC Wall works upto FF Level • Shelter Block - Substructure – Foundation Cast & Existing Structure Strengthening works to progress. • Shelter Block - Superstructure - GF & FF Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 |  | 78077600 | 1576709 | 0 | 79654309 | 9564148.07 | 180000 | https://drive.google.com/thumbnail?id=1ObN57YJNOg65CaDV-I6Uf3vEwf4ffCFW&sz=w1000 | https://drive.google.com/file/d/1ObN57YJNOg65CaDV-I6Uf3vEwf4ffCFW/view?usp=drive_link | https://drive.google.com/thumbnail?id=17_08NSWt7_gBt9GqJ59cc4phZ7kJIzsK&sz=w1000 | https://drive.google.com/file/d/17_08NSWt7_gBt9GqJ59cc4phZ7kJIzsK/view?usp=drive_link | https://drive.google.com/thumbnail?id=1eUqriZfZ8ZcnMu4n6LORw1pcnpQae1-d&sz=w1000 | https://drive.google.com/file/d/1eUqriZfZ8ZcnMu4n6LORw1pcnpQae1-d/view?usp=drive_link
2024-08-30 | Madinat Zayed-School-P105 | P105 | SC-06 | 348 | 199 | 547 | • Annex Building - Superstructure – GF RCC Wall Concrete Cast 90 % Completed • School Building - Substructure –Plinth Wall Concrete 94% completed • School Building - GF RCC Wall Rebar Fixing – 35% completed. | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 23.88% | 20.24% | -3.64% | Building Permit | 2024-05-17 | 2024-05-23 |  | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works to progress • Annex Building - Superstructure works – RCC Wall works upto FF Level • Shelter Block - Substructure – Foundation Cast & Existing Structure Strengthening works to progress. • Shelter Block - Superstructure - GF & FF Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 |  | 78077600 | 1576709 | 0 | 79654309 | 9564148.07 | 180000 | https://drive.google.com/thumbnail?id=1ObN57YJNOg65CaDV-I6Uf3vEwf4ffCFW&sz=w1000 | https://drive.google.com/file/d/1ObN57YJNOg65CaDV-I6Uf3vEwf4ffCFW/view?usp=drive_link | https://drive.google.com/thumbnail?id=17_08NSWt7_gBt9GqJ59cc4phZ7kJIzsK&sz=w1000 | https://drive.google.com/file/d/17_08NSWt7_gBt9GqJ59cc4phZ7kJIzsK/view?usp=drive_link | https://drive.google.com/thumbnail?id=1eUqriZfZ8ZcnMu4n6LORw1pcnpQae1-d&sz=w1000 | https://drive.google.com/file/d/1eUqriZfZ8ZcnMu4n6LORw1pcnpQae1-d/view?usp=drive_link
2024-08-30 | Madinat Zayed-School-P105 | P105 | SC-06 | 348 | 199 | 547 | • Annex Building - Superstructure – GF RCC Wall Concrete Cast 90 % Completed • School Building - Substructure –Plinth Wall Concrete 94% completed • School Building - GF RCC Wall Rebar Fixing – 35% completed. | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 23.88% | 20.24% | -3.64% | School Substructure | 2024-08-06 |  | 2024-09-13 | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works to progress • Annex Building - Superstructure works – RCC Wall works upto FF Level • Shelter Block - Substructure – Foundation Cast & Existing Structure Strengthening works to progress. • Shelter Block - Superstructure - GF & FF Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 |  | 78077600 | 1576709 | 0 | 79654309 | 9564148.07 | 180000 | https://drive.google.com/thumbnail?id=1ObN57YJNOg65CaDV-I6Uf3vEwf4ffCFW&sz=w1000 | https://drive.google.com/file/d/1ObN57YJNOg65CaDV-I6Uf3vEwf4ffCFW/view?usp=drive_link | https://drive.google.com/thumbnail?id=17_08NSWt7_gBt9GqJ59cc4phZ7kJIzsK&sz=w1000 | https://drive.google.com/file/d/17_08NSWt7_gBt9GqJ59cc4phZ7kJIzsK/view?usp=drive_link | https://drive.google.com/thumbnail?id=1eUqriZfZ8ZcnMu4n6LORw1pcnpQae1-d&sz=w1000 | https://drive.google.com/file/d/1eUqriZfZ8ZcnMu4n6LORw1pcnpQae1-d/view?usp=drive_link
2024-08-30 | Madinat Zayed-School-P105 | P105 | SC-06 | 348 | 199 | 547 | • Annex Building - Superstructure – GF RCC Wall Concrete Cast 90 % Completed • School Building - Substructure –Plinth Wall Concrete 94% completed • School Building - GF RCC Wall Rebar Fixing – 35% completed. | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 23.88% | 20.24% | -3.64% | School Superstructure | 2024-11-07 |  | 2024-11-16 | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works to progress • Annex Building - Superstructure works – RCC Wall works upto FF Level • Shelter Block - Substructure – Foundation Cast & Existing Structure Strengthening works to progress. • Shelter Block - Superstructure - GF & FF Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 |  | 78077600 | 1576709 | 0 | 79654309 | 9564148.07 | 180000 | https://drive.google.com/thumbnail?id=1ObN57YJNOg65CaDV-I6Uf3vEwf4ffCFW&sz=w1000 | https://drive.google.com/file/d/1ObN57YJNOg65CaDV-I6Uf3vEwf4ffCFW/view?usp=drive_link | https://drive.google.com/thumbnail?id=17_08NSWt7_gBt9GqJ59cc4phZ7kJIzsK&sz=w1000 | https://drive.google.com/file/d/17_08NSWt7_gBt9GqJ59cc4phZ7kJIzsK/view?usp=drive_link | https://drive.google.com/thumbnail?id=1eUqriZfZ8ZcnMu4n6LORw1pcnpQae1-d&sz=w1000 | https://drive.google.com/file/d/1eUqriZfZ8ZcnMu4n6LORw1pcnpQae1-d/view?usp=drive_link
2024-08-30 | Madinat Zayed-School-P105 | P105 | SC-06 | 348 | 199 | 547 | • Annex Building - Superstructure – GF RCC Wall Concrete Cast 90 % Completed • School Building - Substructure –Plinth Wall Concrete 94% completed • School Building - GF RCC Wall Rebar Fixing – 35% completed. | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 23.88% | 20.24% | -3.64% | Annex Substructure | 2024-08-06 | 2024-07-13 |  | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works to progress • Annex Building - Superstructure works – RCC Wall works upto FF Level • Shelter Block - Substructure – Foundation Cast & Existing Structure Strengthening works to progress. • Shelter Block - Superstructure - GF & FF Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 |  | 78077600 | 1576709 | 0 | 79654309 | 9564148.07 | 180000 | https://drive.google.com/thumbnail?id=1ObN57YJNOg65CaDV-I6Uf3vEwf4ffCFW&sz=w1000 | https://drive.google.com/file/d/1ObN57YJNOg65CaDV-I6Uf3vEwf4ffCFW/view?usp=drive_link | https://drive.google.com/thumbnail?id=17_08NSWt7_gBt9GqJ59cc4phZ7kJIzsK&sz=w1000 | https://drive.google.com/file/d/17_08NSWt7_gBt9GqJ59cc4phZ7kJIzsK/view?usp=drive_link | https://drive.google.com/thumbnail?id=1eUqriZfZ8ZcnMu4n6LORw1pcnpQae1-d&sz=w1000 | https://drive.google.com/file/d/1eUqriZfZ8ZcnMu4n6LORw1pcnpQae1-d/view?usp=drive_link
2024-08-30 | Madinat Zayed-School-P105 | P105 | SC-06 | 348 | 199 | 547 | • Annex Building - Superstructure – GF RCC Wall Concrete Cast 90 % Completed • School Building - Substructure –Plinth Wall Concrete 94% completed • School Building - GF RCC Wall Rebar Fixing – 35% completed. | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 23.88% | 20.24% | -3.64% | Annex Superstructure | 2024-10-31 |  | 2024-10-21 | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works to progress • Annex Building - Superstructure works – RCC Wall works upto FF Level • Shelter Block - Substructure – Foundation Cast & Existing Structure Strengthening works to progress. • Shelter Block - Superstructure - GF & FF Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 |  | 78077600 | 1576709 | 0 | 79654309 | 9564148.07 | 180000 | https://drive.google.com/thumbnail?id=1ObN57YJNOg65CaDV-I6Uf3vEwf4ffCFW&sz=w1000 | https://drive.google.com/file/d/1ObN57YJNOg65CaDV-I6Uf3vEwf4ffCFW/view?usp=drive_link | https://drive.google.com/thumbnail?id=17_08NSWt7_gBt9GqJ59cc4phZ7kJIzsK&sz=w1000 | https://drive.google.com/file/d/17_08NSWt7_gBt9GqJ59cc4phZ7kJIzsK/view?usp=drive_link | https://drive.google.com/thumbnail?id=1eUqriZfZ8ZcnMu4n6LORw1pcnpQae1-d&sz=w1000 | https://drive.google.com/file/d/1eUqriZfZ8ZcnMu4n6LORw1pcnpQae1-d/view?usp=drive_link
2024-08-30 | Madinat Zayed-School-P105 | P105 | SC-06 | 348 | 199 | 547 | • Annex Building - Superstructure – GF RCC Wall Concrete Cast 90 % Completed • School Building - Substructure –Plinth Wall Concrete 94% completed • School Building - GF RCC Wall Rebar Fixing – 35% completed. | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 23.88% | 20.24% | -3.64% | MEP & Finishes | 2025-01-25 |  | 2025-05-15 | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works to progress • Annex Building - Superstructure works – RCC Wall works upto FF Level • Shelter Block - Substructure – Foundation Cast & Existing Structure Strengthening works to progress. • Shelter Block - Superstructure - GF & FF Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 |  | 78077600 | 1576709 | 0 | 79654309 | 9564148.07 | 180000 | https://drive.google.com/thumbnail?id=1ObN57YJNOg65CaDV-I6Uf3vEwf4ffCFW&sz=w1000 | https://drive.google.com/file/d/1ObN57YJNOg65CaDV-I6Uf3vEwf4ffCFW/view?usp=drive_link | https://drive.google.com/thumbnail?id=17_08NSWt7_gBt9GqJ59cc4phZ7kJIzsK&sz=w1000 | https://drive.google.com/file/d/17_08NSWt7_gBt9GqJ59cc4phZ7kJIzsK/view?usp=drive_link | https://drive.google.com/thumbnail?id=1eUqriZfZ8ZcnMu4n6LORw1pcnpQae1-d&sz=w1000 | https://drive.google.com/file/d/1eUqriZfZ8ZcnMu4n6LORw1pcnpQae1-d/view?usp=drive_link
2024-08-30 | Madinat Zayed-School-P105 | P105 | SC-06 | 348 | 199 | 547 | • Annex Building - Superstructure – GF RCC Wall Concrete Cast 90 % Completed • School Building - Substructure –Plinth Wall Concrete 94% completed • School Building - GF RCC Wall Rebar Fixing – 35% completed. | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 23.88% | 20.24% | -3.64% | BCC Inspection | 2025-02-13 |  | 2025-05-26 | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works to progress • Annex Building - Superstructure works – RCC Wall works upto FF Level • Shelter Block - Substructure – Foundation Cast & Existing Structure Strengthening works to progress. • Shelter Block - Superstructure - GF & FF Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 |  | 78077600 | 1576709 | 0 | 79654309 | 9564148.07 | 180000 | https://drive.google.com/thumbnail?id=1ObN57YJNOg65CaDV-I6Uf3vEwf4ffCFW&sz=w1000 | https://drive.google.com/file/d/1ObN57YJNOg65CaDV-I6Uf3vEwf4ffCFW/view?usp=drive_link | https://drive.google.com/thumbnail?id=17_08NSWt7_gBt9GqJ59cc4phZ7kJIzsK&sz=w1000 | https://drive.google.com/file/d/17_08NSWt7_gBt9GqJ59cc4phZ7kJIzsK/view?usp=drive_link | https://drive.google.com/thumbnail?id=1eUqriZfZ8ZcnMu4n6LORw1pcnpQae1-d&sz=w1000 | https://drive.google.com/file/d/1eUqriZfZ8ZcnMu4n6LORw1pcnpQae1-d/view?usp=drive_link
2024-08-30 | Madinat Zayed-School-P105 | P105 | SC-06 | 348 | 199 | 547 | • Annex Building - Superstructure – GF RCC Wall Concrete Cast 90 % Completed • School Building - Substructure –Plinth Wall Concrete 94% completed • School Building - GF RCC Wall Rebar Fixing – 35% completed. | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 23.88% | 20.24% | -3.64% | BCC Issuance | 2025-03-04 |  | 2025-06-16 | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works to progress • Annex Building - Superstructure works – RCC Wall works upto FF Level • Shelter Block - Substructure – Foundation Cast & Existing Structure Strengthening works to progress. • Shelter Block - Superstructure - GF & FF Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 |  | 78077600 | 1576709 | 0 | 79654309 | 9564148.07 | 180000 | https://drive.google.com/thumbnail?id=1ObN57YJNOg65CaDV-I6Uf3vEwf4ffCFW&sz=w1000 | https://drive.google.com/file/d/1ObN57YJNOg65CaDV-I6Uf3vEwf4ffCFW/view?usp=drive_link | https://drive.google.com/thumbnail?id=17_08NSWt7_gBt9GqJ59cc4phZ7kJIzsK&sz=w1000 | https://drive.google.com/file/d/17_08NSWt7_gBt9GqJ59cc4phZ7kJIzsK/view?usp=drive_link | https://drive.google.com/thumbnail?id=1eUqriZfZ8ZcnMu4n6LORw1pcnpQae1-d&sz=w1000 | https://drive.google.com/file/d/1eUqriZfZ8ZcnMu4n6LORw1pcnpQae1-d/view?usp=drive_link
2024-08-30 | Madinat Zayed-School-P105 | P105 | SC-06 | 348 | 199 | 547 | • Annex Building - Superstructure – GF RCC Wall Concrete Cast 90 % Completed • School Building - Substructure –Plinth Wall Concrete 94% completed • School Building - GF RCC Wall Rebar Fixing – 35% completed. | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 23.88% | 20.24% | -3.64% | Completion | 2025-03-17 |  | 2025-06-30 | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works to progress • Annex Building - Superstructure works – RCC Wall works upto FF Level • Shelter Block - Substructure – Foundation Cast & Existing Structure Strengthening works to progress. • Shelter Block - Superstructure - GF & FF Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 |  | 78077600 | 1576709 | 0 | 79654309 | 9564148.07 | 180000 | https://drive.google.com/thumbnail?id=1ObN57YJNOg65CaDV-I6Uf3vEwf4ffCFW&sz=w1000 | https://drive.google.com/file/d/1ObN57YJNOg65CaDV-I6Uf3vEwf4ffCFW/view?usp=drive_link | https://drive.google.com/thumbnail?id=17_08NSWt7_gBt9GqJ59cc4phZ7kJIzsK&sz=w1000 | https://drive.google.com/file/d/17_08NSWt7_gBt9GqJ59cc4phZ7kJIzsK/view?usp=drive_link | https://drive.google.com/thumbnail?id=1eUqriZfZ8ZcnMu4n6LORw1pcnpQae1-d&sz=w1000 | https://drive.google.com/file/d/1eUqriZfZ8ZcnMu4n6LORw1pcnpQae1-d/view?usp=drive_link
2024-08-30 | Madinat Zayed-School-P38 | P38 | SC-07 | 348 | 199 | 547 | • Annex Building - GF RCC Wall – Rebar fixing 92% Completed. • School Building - Superstructure – GF RCC Wall Rebar Fixing – 60% completed; FF Wall Rebar Fixing 12% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 23.88% | 23.84% | -0.04% | Notice to Commence | 2023-09-18 | 2023-09-26 |  | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – RCC Wall works upto FF Level • Shelter Block - Superstructure - GF – RCC Wall works upto 1FL Level to progress. • Shelter Block - Surface Preparation for CFRP Works. | 78077600 |  | 78077600 | 1576709 | 0 | 79654309 | 9741516.61 | 180000 | https://drive.google.com/thumbnail?id=1oaU6aDLcm-WgPEMXNtdBYkqXGGsSkflq&sz=w1000 | https://drive.google.com/file/d/1oaU6aDLcm-WgPEMXNtdBYkqXGGsSkflq/view?usp=drive_link | https://drive.google.com/thumbnail?id=1N9brwHmFW_PdvPj4vWj5-JYfwZ_j8qxo&sz=w1000 | https://drive.google.com/file/d/1N9brwHmFW_PdvPj4vWj5-JYfwZ_j8qxo/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hvQKcWIheA72v1UtBckv-ww6mLtFEX5e&sz=w1000 | https://drive.google.com/file/d/1hvQKcWIheA72v1UtBckv-ww6mLtFEX5e/view?usp=drive_link
2024-08-30 | Madinat Zayed-School-P38 | P38 | SC-07 | 348 | 199 | 547 | • Annex Building - GF RCC Wall – Rebar fixing 92% Completed. • School Building - Superstructure – GF RCC Wall Rebar Fixing – 60% completed; FF Wall Rebar Fixing 12% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 23.88% | 23.84% | -0.04% | Site Mobilization | 2023-10-21 | 2024-01-13 |  | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – RCC Wall works upto FF Level • Shelter Block - Superstructure - GF – RCC Wall works upto 1FL Level to progress. • Shelter Block - Surface Preparation for CFRP Works. | 78077600 |  | 78077600 | 1576709 | 0 | 79654309 | 9741516.61 | 180000 | https://drive.google.com/thumbnail?id=1oaU6aDLcm-WgPEMXNtdBYkqXGGsSkflq&sz=w1000 | https://drive.google.com/file/d/1oaU6aDLcm-WgPEMXNtdBYkqXGGsSkflq/view?usp=drive_link | https://drive.google.com/thumbnail?id=1N9brwHmFW_PdvPj4vWj5-JYfwZ_j8qxo&sz=w1000 | https://drive.google.com/file/d/1N9brwHmFW_PdvPj4vWj5-JYfwZ_j8qxo/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hvQKcWIheA72v1UtBckv-ww6mLtFEX5e&sz=w1000 | https://drive.google.com/file/d/1hvQKcWIheA72v1UtBckv-ww6mLtFEX5e/view?usp=drive_link
2024-08-30 | Madinat Zayed-School-P38 | P38 | SC-07 | 348 | 199 | 547 | • Annex Building - GF RCC Wall – Rebar fixing 92% Completed. • School Building - Superstructure – GF RCC Wall Rebar Fixing – 60% completed; FF Wall Rebar Fixing 12% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 23.88% | 23.84% | -0.04% | Building Permit | 2024-05-17 | 2024-05-27 |  | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – RCC Wall works upto FF Level • Shelter Block - Superstructure - GF – RCC Wall works upto 1FL Level to progress. • Shelter Block - Surface Preparation for CFRP Works. | 78077600 |  | 78077600 | 1576709 | 0 | 79654309 | 9741516.61 | 180000 | https://drive.google.com/thumbnail?id=1oaU6aDLcm-WgPEMXNtdBYkqXGGsSkflq&sz=w1000 | https://drive.google.com/file/d/1oaU6aDLcm-WgPEMXNtdBYkqXGGsSkflq/view?usp=drive_link | https://drive.google.com/thumbnail?id=1N9brwHmFW_PdvPj4vWj5-JYfwZ_j8qxo&sz=w1000 | https://drive.google.com/file/d/1N9brwHmFW_PdvPj4vWj5-JYfwZ_j8qxo/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hvQKcWIheA72v1UtBckv-ww6mLtFEX5e&sz=w1000 | https://drive.google.com/file/d/1hvQKcWIheA72v1UtBckv-ww6mLtFEX5e/view?usp=drive_link
2024-08-30 | Madinat Zayed-School-P38 | P38 | SC-07 | 348 | 199 | 547 | • Annex Building - GF RCC Wall – Rebar fixing 92% Completed. • School Building - Superstructure – GF RCC Wall Rebar Fixing – 60% completed; FF Wall Rebar Fixing 12% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 23.88% | 23.84% | -0.04% | School Substructure | 2024-08-06 | 2024-08-21 |  | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – RCC Wall works upto FF Level • Shelter Block - Superstructure - GF – RCC Wall works upto 1FL Level to progress. • Shelter Block - Surface Preparation for CFRP Works. | 78077600 |  | 78077600 | 1576709 | 0 | 79654309 | 9741516.61 | 180000 | https://drive.google.com/thumbnail?id=1oaU6aDLcm-WgPEMXNtdBYkqXGGsSkflq&sz=w1000 | https://drive.google.com/file/d/1oaU6aDLcm-WgPEMXNtdBYkqXGGsSkflq/view?usp=drive_link | https://drive.google.com/thumbnail?id=1N9brwHmFW_PdvPj4vWj5-JYfwZ_j8qxo&sz=w1000 | https://drive.google.com/file/d/1N9brwHmFW_PdvPj4vWj5-JYfwZ_j8qxo/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hvQKcWIheA72v1UtBckv-ww6mLtFEX5e&sz=w1000 | https://drive.google.com/file/d/1hvQKcWIheA72v1UtBckv-ww6mLtFEX5e/view?usp=drive_link
2024-08-30 | Madinat Zayed-School-P38 | P38 | SC-07 | 348 | 199 | 547 | • Annex Building - GF RCC Wall – Rebar fixing 92% Completed. • School Building - Superstructure – GF RCC Wall Rebar Fixing – 60% completed; FF Wall Rebar Fixing 12% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 23.88% | 23.84% | -0.04% | School Superstructure | 2024-11-07 |  | 2024-10-15 | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – RCC Wall works upto FF Level • Shelter Block - Superstructure - GF – RCC Wall works upto 1FL Level to progress. • Shelter Block - Surface Preparation for CFRP Works. | 78077600 |  | 78077600 | 1576709 | 0 | 79654309 | 9741516.61 | 180000 | https://drive.google.com/thumbnail?id=1oaU6aDLcm-WgPEMXNtdBYkqXGGsSkflq&sz=w1000 | https://drive.google.com/file/d/1oaU6aDLcm-WgPEMXNtdBYkqXGGsSkflq/view?usp=drive_link | https://drive.google.com/thumbnail?id=1N9brwHmFW_PdvPj4vWj5-JYfwZ_j8qxo&sz=w1000 | https://drive.google.com/file/d/1N9brwHmFW_PdvPj4vWj5-JYfwZ_j8qxo/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hvQKcWIheA72v1UtBckv-ww6mLtFEX5e&sz=w1000 | https://drive.google.com/file/d/1hvQKcWIheA72v1UtBckv-ww6mLtFEX5e/view?usp=drive_link
2024-08-30 | Madinat Zayed-School-P38 | P38 | SC-07 | 348 | 199 | 547 | • Annex Building - GF RCC Wall – Rebar fixing 92% Completed. • School Building - Superstructure – GF RCC Wall Rebar Fixing – 60% completed; FF Wall Rebar Fixing 12% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 23.88% | 23.84% | -0.04% | Annex Substructure | 2024-08-06 | 2024-07-31 |  | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – RCC Wall works upto FF Level • Shelter Block - Superstructure - GF – RCC Wall works upto 1FL Level to progress. • Shelter Block - Surface Preparation for CFRP Works. | 78077600 |  | 78077600 | 1576709 | 0 | 79654309 | 9741516.61 | 180000 | https://drive.google.com/thumbnail?id=1oaU6aDLcm-WgPEMXNtdBYkqXGGsSkflq&sz=w1000 | https://drive.google.com/file/d/1oaU6aDLcm-WgPEMXNtdBYkqXGGsSkflq/view?usp=drive_link | https://drive.google.com/thumbnail?id=1N9brwHmFW_PdvPj4vWj5-JYfwZ_j8qxo&sz=w1000 | https://drive.google.com/file/d/1N9brwHmFW_PdvPj4vWj5-JYfwZ_j8qxo/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hvQKcWIheA72v1UtBckv-ww6mLtFEX5e&sz=w1000 | https://drive.google.com/file/d/1hvQKcWIheA72v1UtBckv-ww6mLtFEX5e/view?usp=drive_link
2024-08-30 | Madinat Zayed-School-P38 | P38 | SC-07 | 348 | 199 | 547 | • Annex Building - GF RCC Wall – Rebar fixing 92% Completed. • School Building - Superstructure – GF RCC Wall Rebar Fixing – 60% completed; FF Wall Rebar Fixing 12% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 23.88% | 23.84% | -0.04% | Annex Superstructure | 2024-10-31 |  | 2024-11-02 | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – RCC Wall works upto FF Level • Shelter Block - Superstructure - GF – RCC Wall works upto 1FL Level to progress. • Shelter Block - Surface Preparation for CFRP Works. | 78077600 |  | 78077600 | 1576709 | 0 | 79654309 | 9741516.61 | 180000 | https://drive.google.com/thumbnail?id=1oaU6aDLcm-WgPEMXNtdBYkqXGGsSkflq&sz=w1000 | https://drive.google.com/file/d/1oaU6aDLcm-WgPEMXNtdBYkqXGGsSkflq/view?usp=drive_link | https://drive.google.com/thumbnail?id=1N9brwHmFW_PdvPj4vWj5-JYfwZ_j8qxo&sz=w1000 | https://drive.google.com/file/d/1N9brwHmFW_PdvPj4vWj5-JYfwZ_j8qxo/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hvQKcWIheA72v1UtBckv-ww6mLtFEX5e&sz=w1000 | https://drive.google.com/file/d/1hvQKcWIheA72v1UtBckv-ww6mLtFEX5e/view?usp=drive_link
2024-08-30 | Madinat Zayed-School-P38 | P38 | SC-07 | 348 | 199 | 547 | • Annex Building - GF RCC Wall – Rebar fixing 92% Completed. • School Building - Superstructure – GF RCC Wall Rebar Fixing – 60% completed; FF Wall Rebar Fixing 12% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 23.88% | 23.84% | -0.04% | MEP & Finishes | 2025-01-25 |  | 2025-05-15 | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – RCC Wall works upto FF Level • Shelter Block - Superstructure - GF – RCC Wall works upto 1FL Level to progress. • Shelter Block - Surface Preparation for CFRP Works. | 78077600 |  | 78077600 | 1576709 | 0 | 79654309 | 9741516.61 | 180000 | https://drive.google.com/thumbnail?id=1oaU6aDLcm-WgPEMXNtdBYkqXGGsSkflq&sz=w1000 | https://drive.google.com/file/d/1oaU6aDLcm-WgPEMXNtdBYkqXGGsSkflq/view?usp=drive_link | https://drive.google.com/thumbnail?id=1N9brwHmFW_PdvPj4vWj5-JYfwZ_j8qxo&sz=w1000 | https://drive.google.com/file/d/1N9brwHmFW_PdvPj4vWj5-JYfwZ_j8qxo/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hvQKcWIheA72v1UtBckv-ww6mLtFEX5e&sz=w1000 | https://drive.google.com/file/d/1hvQKcWIheA72v1UtBckv-ww6mLtFEX5e/view?usp=drive_link
2024-08-30 | Madinat Zayed-School-P38 | P38 | SC-07 | 348 | 199 | 547 | • Annex Building - GF RCC Wall – Rebar fixing 92% Completed. • School Building - Superstructure – GF RCC Wall Rebar Fixing – 60% completed; FF Wall Rebar Fixing 12% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 23.88% | 23.84% | -0.04% | BCC Inspection | 2025-02-13 |  | 2025-05-26 | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – RCC Wall works upto FF Level • Shelter Block - Superstructure - GF – RCC Wall works upto 1FL Level to progress. • Shelter Block - Surface Preparation for CFRP Works. | 78077600 |  | 78077600 | 1576709 | 0 | 79654309 | 9741516.61 | 180000 | https://drive.google.com/thumbnail?id=1oaU6aDLcm-WgPEMXNtdBYkqXGGsSkflq&sz=w1000 | https://drive.google.com/file/d/1oaU6aDLcm-WgPEMXNtdBYkqXGGsSkflq/view?usp=drive_link | https://drive.google.com/thumbnail?id=1N9brwHmFW_PdvPj4vWj5-JYfwZ_j8qxo&sz=w1000 | https://drive.google.com/file/d/1N9brwHmFW_PdvPj4vWj5-JYfwZ_j8qxo/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hvQKcWIheA72v1UtBckv-ww6mLtFEX5e&sz=w1000 | https://drive.google.com/file/d/1hvQKcWIheA72v1UtBckv-ww6mLtFEX5e/view?usp=drive_link
2024-08-30 | Madinat Zayed-School-P38 | P38 | SC-07 | 348 | 199 | 547 | • Annex Building - GF RCC Wall – Rebar fixing 92% Completed. • School Building - Superstructure – GF RCC Wall Rebar Fixing – 60% completed; FF Wall Rebar Fixing 12% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 23.88% | 23.84% | -0.04% | BCC Issuance | 2025-03-04 |  | 2025-06-16 | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – RCC Wall works upto FF Level • Shelter Block - Superstructure - GF – RCC Wall works upto 1FL Level to progress. • Shelter Block - Surface Preparation for CFRP Works. | 78077600 |  | 78077600 | 1576709 | 0 | 79654309 | 9741516.61 | 180000 | https://drive.google.com/thumbnail?id=1oaU6aDLcm-WgPEMXNtdBYkqXGGsSkflq&sz=w1000 | https://drive.google.com/file/d/1oaU6aDLcm-WgPEMXNtdBYkqXGGsSkflq/view?usp=drive_link | https://drive.google.com/thumbnail?id=1N9brwHmFW_PdvPj4vWj5-JYfwZ_j8qxo&sz=w1000 | https://drive.google.com/file/d/1N9brwHmFW_PdvPj4vWj5-JYfwZ_j8qxo/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hvQKcWIheA72v1UtBckv-ww6mLtFEX5e&sz=w1000 | https://drive.google.com/file/d/1hvQKcWIheA72v1UtBckv-ww6mLtFEX5e/view?usp=drive_link
2024-08-30 | Madinat Zayed-School-P38 | P38 | SC-07 | 348 | 199 | 547 | • Annex Building - GF RCC Wall – Rebar fixing 92% Completed. • School Building - Superstructure – GF RCC Wall Rebar Fixing – 60% completed; FF Wall Rebar Fixing 12% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 23.88% | 23.84% | -0.04% | Completion | 2025-03-17 |  | 2025-06-30 | 2024-08-30 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – RCC Wall works upto FF Level • Shelter Block - Superstructure - GF – RCC Wall works upto 1FL Level to progress. • Shelter Block - Surface Preparation for CFRP Works. | 78077600 |  | 78077600 | 1576709 | 0 | 79654309 | 9741516.61 | 180000 | https://drive.google.com/thumbnail?id=1oaU6aDLcm-WgPEMXNtdBYkqXGGsSkflq&sz=w1000 | https://drive.google.com/file/d/1oaU6aDLcm-WgPEMXNtdBYkqXGGsSkflq/view?usp=drive_link | https://drive.google.com/thumbnail?id=1N9brwHmFW_PdvPj4vWj5-JYfwZ_j8qxo&sz=w1000 | https://drive.google.com/file/d/1N9brwHmFW_PdvPj4vWj5-JYfwZ_j8qxo/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hvQKcWIheA72v1UtBckv-ww6mLtFEX5e&sz=w1000 | https://drive.google.com/file/d/1hvQKcWIheA72v1UtBckv-ww6mLtFEX5e/view?usp=drive_link
2024-09-06 | Mohamed Bin Zayed City-Majlis-P9 | P9 | MJ-07 | 117 | 493 | 610 | • Building Permits issued on 21/05/2024 • Completion of site fencing • Approval For Shoring Design 15/07/2024 | • Commencement Date 15/05/2024 | 6.43% | 2.92% | -3.51% | Notice to Commence | 2024-05-15 | 2024-05-15 |  | 2024-09-09 | • Relocation of existing services two (2) ADDC cables with feeder pillar. • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • Delay in submissions of and insurances and guarantees. • NOCs for fencing permit. (ADDC rejection) | • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities. Comply with Civil Defence requirements for inspection and approval. • Finalized the selection of shelter special equipment.(ongoing) • Procurement of MEP subcontractor. • Guide Beam and secant Piles for shoring works(ongoing) | 97238576.53 | 0 | 97238576.53 | 3344531.65 |  | 100583108.18 | 1208000 |  | https://drive.google.com/thumbnail?id=12AV6fpLdtW38tuWORsnwH2nidk3goR69&sz=w1000 | https://drive.google.com/file/d/12AV6fpLdtW38tuWORsnwH2nidk3goR69/view?usp=drive_link | https://drive.google.com/thumbnail?id=1qYcZEtoOCQloi5Md71V0KOa-RdfimHSV&sz=w1000 | https://drive.google.com/file/d/1qYcZEtoOCQloi5Md71V0KOa-RdfimHSV/view?usp=drive_link | https://drive.google.com/thumbnail?id=1LwFQ1l88f8Fb49UEDNaXpVHXZmj9cenr&sz=w1000 | https://drive.google.com/file/d/1LwFQ1l88f8Fb49UEDNaXpVHXZmj9cenr/view?usp=drive_link
2024-09-06 | Mohamed Bin Zayed City-Majlis-P9 | P9 | MJ-07 | 117 | 493 | 610 | • Building Permits issued on 21/05/2024 • Completion of site fencing • Approval For Shoring Design 15/07/2024 | • Commencement Date 15/05/2024 | 6.43% | 2.92% | -3.51% | Building Permit | 2024-05-21 | 2024-05-21 |  | 2024-09-09 | • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • Delay in submissions of and insurances and grantees. • NOCs for fencing permit. • Finalize the authorities approval for the Mosque | • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities. Comply with Civil Defence requirements for inspection and approval. • Finalized the selection of shelter special equipment.(ongoing) • Procurement of MEP subcontractor. • Guide Beam and secant Piles for shoring works(ongoing) | 97238576.53 | 0 | 97238576.53 | 3344531.65 |  | 100583108.18 | 1208000 |  | https://drive.google.com/thumbnail?id=12AV6fpLdtW38tuWORsnwH2nidk3goR69&sz=w1000 | https://drive.google.com/file/d/12AV6fpLdtW38tuWORsnwH2nidk3goR69/view?usp=drive_link | https://drive.google.com/thumbnail?id=1qYcZEtoOCQloi5Md71V0KOa-RdfimHSV&sz=w1000 | https://drive.google.com/file/d/1qYcZEtoOCQloi5Md71V0KOa-RdfimHSV/view?usp=drive_link | https://drive.google.com/thumbnail?id=1LwFQ1l88f8Fb49UEDNaXpVHXZmj9cenr&sz=w1000 | https://drive.google.com/file/d/1LwFQ1l88f8Fb49UEDNaXpVHXZmj9cenr/view?usp=drive_link
2024-09-06 | Mohamed Bin Zayed City-Majlis-P9 | P9 | MJ-07 | 117 | 493 | 610 | • Building Permits issued on 21/05/2024 • Completion of site fencing • Approval For Shoring Design 15/07/2024 | • Commencement Date 15/05/2024 | 6.43% | 2.92% | -3.51% | Site Mobilization | 2024-07-20 | 2024-08-31 |  | 2024-09-09 | • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • Delay in submissions of and insurances and grantees. • NOCs for fencing permit. • Finalize the authorities approval for the Mosque | • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities. Comply with Civil Defence requirements for inspection and approval. • Finalized the selection of shelter special equipment.(ongoing) • Procurement of MEP subcontractor. • Guide Beam and secant Piles for shoring works(ongoing) | 97238576.53 | 0 | 97238576.53 | 3344531.65 |  | 100583108.18 | 1208000 |  | https://drive.google.com/thumbnail?id=12AV6fpLdtW38tuWORsnwH2nidk3goR69&sz=w1000 | https://drive.google.com/file/d/12AV6fpLdtW38tuWORsnwH2nidk3goR69/view?usp=drive_link | https://drive.google.com/thumbnail?id=1qYcZEtoOCQloi5Md71V0KOa-RdfimHSV&sz=w1000 | https://drive.google.com/file/d/1qYcZEtoOCQloi5Md71V0KOa-RdfimHSV/view?usp=drive_link | https://drive.google.com/thumbnail?id=1LwFQ1l88f8Fb49UEDNaXpVHXZmj9cenr&sz=w1000 | https://drive.google.com/file/d/1LwFQ1l88f8Fb49UEDNaXpVHXZmj9cenr/view?usp=drive_link
2024-09-06 | Mohamed Bin Zayed City-Majlis-P9 | P9 | MJ-07 | 117 | 493 | 610 | • Building Permits issued on 21/05/2024 • Completion of site fencing • Approval For Shoring Design 15/07/2024 | • Commencement Date 15/05/2024 | 6.43% | 2.92% | -3.51% | Shoring & Piling Completion | 2024-11-07 |  | 2024-11-07 | 2024-09-09 | • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • Delay in submissions of and insurances and grantees. • NOCs for fencing permit. • Finalize the authorities approval for the Mosque | • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities. Comply with Civil Defence requirements for inspection and approval. • Finalized the selection of shelter special equipment.(ongoing) • Procurement of MEP subcontractor. • Guide Beam and secant Piles for shoring works(ongoing) | 97238576.53 | 0 | 97238576.53 | 3344531.65 |  | 100583108.18 | 1208000 |  | https://drive.google.com/thumbnail?id=12AV6fpLdtW38tuWORsnwH2nidk3goR69&sz=w1000 | https://drive.google.com/file/d/12AV6fpLdtW38tuWORsnwH2nidk3goR69/view?usp=drive_link | https://drive.google.com/thumbnail?id=1qYcZEtoOCQloi5Md71V0KOa-RdfimHSV&sz=w1000 | https://drive.google.com/file/d/1qYcZEtoOCQloi5Md71V0KOa-RdfimHSV/view?usp=drive_link | https://drive.google.com/thumbnail?id=1LwFQ1l88f8Fb49UEDNaXpVHXZmj9cenr&sz=w1000 | https://drive.google.com/file/d/1LwFQ1l88f8Fb49UEDNaXpVHXZmj9cenr/view?usp=drive_link
2024-09-06 | Mohamed Bin Zayed City-Majlis-P9 | P9 | MJ-07 | 117 | 493 | 610 | • Building Permits issued on 21/05/2024 • Completion of site fencing • Approval For Shoring Design 15/07/2024 | • Commencement Date 15/05/2024 | 6.43% | 2.92% | -3.51% | Substructure | 2024-12-18 |  | 2024-12-18 | 2024-09-09 | • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • Delay in submissions of and insurances and grantees. • NOCs for fencing permit. • Finalize the authorities approval for the Mosque | • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities. Comply with Civil Defence requirements for inspection and approval. • Finalized the selection of shelter special equipment.(ongoing) • Procurement of MEP subcontractor. • Guide Beam and secant Piles for shoring works(ongoing) | 97238576.53 | 0 | 97238576.53 | 3344531.65 |  | 100583108.18 | 1208000 |  | https://drive.google.com/thumbnail?id=12AV6fpLdtW38tuWORsnwH2nidk3goR69&sz=w1000 | https://drive.google.com/file/d/12AV6fpLdtW38tuWORsnwH2nidk3goR69/view?usp=drive_link | https://drive.google.com/thumbnail?id=1qYcZEtoOCQloi5Md71V0KOa-RdfimHSV&sz=w1000 | https://drive.google.com/file/d/1qYcZEtoOCQloi5Md71V0KOa-RdfimHSV/view?usp=drive_link | https://drive.google.com/thumbnail?id=1LwFQ1l88f8Fb49UEDNaXpVHXZmj9cenr&sz=w1000 | https://drive.google.com/file/d/1LwFQ1l88f8Fb49UEDNaXpVHXZmj9cenr/view?usp=drive_link
2024-09-06 | Mohamed Bin Zayed City-Majlis-P9 | P9 | MJ-07 | 117 | 493 | 610 | • Building Permits issued on 21/05/2024 • Completion of site fencing • Approval For Shoring Design 15/07/2024 | • Commencement Date 15/05/2024 | 6.43% | 2.92% | -3.51% | Superstructure | 2025-08-28 |  | 2024-08-28 | 2024-09-09 | • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • Delay in submissions of and insurances and grantees. • NOCs for fencing permit. • Finalize the authorities approval for the Mosque | • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities. Comply with Civil Defence requirements for inspection and approval. • Finalized the selection of shelter special equipment.(ongoing) • Procurement of MEP subcontractor. • Guide Beam and secant Piles for shoring works(ongoing) | 97238576.53 | 0 | 97238576.53 | 3344531.65 |  | 100583108.18 | 1208000 |  | https://drive.google.com/thumbnail?id=12AV6fpLdtW38tuWORsnwH2nidk3goR69&sz=w1000 | https://drive.google.com/file/d/12AV6fpLdtW38tuWORsnwH2nidk3goR69/view?usp=drive_link | https://drive.google.com/thumbnail?id=1qYcZEtoOCQloi5Md71V0KOa-RdfimHSV&sz=w1000 | https://drive.google.com/file/d/1qYcZEtoOCQloi5Md71V0KOa-RdfimHSV/view?usp=drive_link | https://drive.google.com/thumbnail?id=1LwFQ1l88f8Fb49UEDNaXpVHXZmj9cenr&sz=w1000 | https://drive.google.com/file/d/1LwFQ1l88f8Fb49UEDNaXpVHXZmj9cenr/view?usp=drive_link
2024-09-06 | Mohamed Bin Zayed City-Majlis-P9 | P9 | MJ-07 | 117 | 493 | 610 | • Building Permits issued on 21/05/2024 • Completion of site fencing • Approval For Shoring Design 15/07/2024 | • Commencement Date 15/05/2024 | 6.43% | 2.92% | -3.51% | MEP | 2025-11-04 |  | 2025-11-04 | 2024-09-09 | • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • Delay in submissions of and insurances and grantees. • NOCs for fencing permit. • Finalize the authorities approval for the Mosque | • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities. Comply with Civil Defence requirements for inspection and approval. • Finalized the selection of shelter special equipment.(ongoing) • Procurement of MEP subcontractor. • Guide Beam and secant Piles for shoring works(ongoing) | 97238576.53 | 0 | 97238576.53 | 3344531.65 |  | 100583108.18 | 1208000 |  | https://drive.google.com/thumbnail?id=12AV6fpLdtW38tuWORsnwH2nidk3goR69&sz=w1000 | https://drive.google.com/file/d/12AV6fpLdtW38tuWORsnwH2nidk3goR69/view?usp=drive_link | https://drive.google.com/thumbnail?id=1qYcZEtoOCQloi5Md71V0KOa-RdfimHSV&sz=w1000 | https://drive.google.com/file/d/1qYcZEtoOCQloi5Md71V0KOa-RdfimHSV/view?usp=drive_link | https://drive.google.com/thumbnail?id=1LwFQ1l88f8Fb49UEDNaXpVHXZmj9cenr&sz=w1000 | https://drive.google.com/file/d/1LwFQ1l88f8Fb49UEDNaXpVHXZmj9cenr/view?usp=drive_link
2024-09-06 | Mohamed Bin Zayed City-Majlis-P9 | P9 | MJ-07 | 117 | 493 | 610 | • Building Permits issued on 21/05/2024 • Completion of site fencing • Approval For Shoring Design 15/07/2024 | • Commencement Date 15/05/2024 | 6.43% | 2.92% | -3.51% | Power On | 2025-11-22 |  | 2025-11-22 | 2024-09-09 | • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • Delay in submissions of and insurances and grantees. • NOCs for fencing permit. • Finalize the authorities approval for the Mosque | • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities. Comply with Civil Defence requirements for inspection and approval. • Finalized the selection of shelter special equipment.(ongoing) • Procurement of MEP subcontractor. • Guide Beam and secant Piles for shoring works(ongoing) | 97238576.53 | 0 | 97238576.53 | 3344531.65 |  | 100583108.18 | 1208000 |  | https://drive.google.com/thumbnail?id=12AV6fpLdtW38tuWORsnwH2nidk3goR69&sz=w1000 | https://drive.google.com/file/d/12AV6fpLdtW38tuWORsnwH2nidk3goR69/view?usp=drive_link | https://drive.google.com/thumbnail?id=1qYcZEtoOCQloi5Md71V0KOa-RdfimHSV&sz=w1000 | https://drive.google.com/file/d/1qYcZEtoOCQloi5Md71V0KOa-RdfimHSV/view?usp=drive_link | https://drive.google.com/thumbnail?id=1LwFQ1l88f8Fb49UEDNaXpVHXZmj9cenr&sz=w1000 | https://drive.google.com/file/d/1LwFQ1l88f8Fb49UEDNaXpVHXZmj9cenr/view?usp=drive_link
2024-09-06 | Mohamed Bin Zayed City-Majlis-P9 | P9 | MJ-07 | 117 | 493 | 610 | • Building Permits issued on 21/05/2024 • Completion of site fencing • Approval For Shoring Design 15/07/2024 | • Commencement Date 15/05/2024 | 6.43% | 2.92% | -3.51% | Interior Finishes | 2025-11-22 |  | 2025-11-22 | 2024-09-09 | • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • Delay in submissions of and insurances and grantees. • NOCs for fencing permit. • Finalize the authorities approval for the Mosque | • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities. Comply with Civil Defence requirements for inspection and approval. • Finalized the selection of shelter special equipment.(ongoing) • Procurement of MEP subcontractor. • Guide Beam and secant Piles for shoring works(ongoing) | 97238576.53 | 0 | 97238576.53 | 3344531.65 |  | 100583108.18 | 1208000 |  | https://drive.google.com/thumbnail?id=12AV6fpLdtW38tuWORsnwH2nidk3goR69&sz=w1000 | https://drive.google.com/file/d/12AV6fpLdtW38tuWORsnwH2nidk3goR69/view?usp=drive_link | https://drive.google.com/thumbnail?id=1qYcZEtoOCQloi5Md71V0KOa-RdfimHSV&sz=w1000 | https://drive.google.com/file/d/1qYcZEtoOCQloi5Md71V0KOa-RdfimHSV/view?usp=drive_link | https://drive.google.com/thumbnail?id=1LwFQ1l88f8Fb49UEDNaXpVHXZmj9cenr&sz=w1000 | https://drive.google.com/file/d/1LwFQ1l88f8Fb49UEDNaXpVHXZmj9cenr/view?usp=drive_link
2024-09-06 | Mohamed Bin Zayed City-Majlis-P9 | P9 | MJ-07 | 117 | 493 | 610 | • Building Permits issued on 21/05/2024 • Completion of site fencing • Approval For Shoring Design 15/07/2024 | • Commencement Date 15/05/2024 | 6.43% | 2.92% | -3.51% | Substantial Completion | 2025-12-15 |  | 2025-12-15 | 2024-09-09 | • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • Delay in submissions of and insurances and grantees. • NOCs for fencing permit. • Finalize the authorities approval for the Mosque | • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities. Comply with Civil Defence requirements for inspection and approval. • Finalized the selection of shelter special equipment.(ongoing) • Procurement of MEP subcontractor. • Guide Beam and secant Piles for shoring works(ongoing) | 97238576.53 | 0 | 97238576.53 | 3344531.65 |  | 100583108.18 | 1208000 |  | https://drive.google.com/thumbnail?id=12AV6fpLdtW38tuWORsnwH2nidk3goR69&sz=w1000 | https://drive.google.com/file/d/12AV6fpLdtW38tuWORsnwH2nidk3goR69/view?usp=drive_link | https://drive.google.com/thumbnail?id=1qYcZEtoOCQloi5Md71V0KOa-RdfimHSV&sz=w1000 | https://drive.google.com/file/d/1qYcZEtoOCQloi5Md71V0KOa-RdfimHSV/view?usp=drive_link | https://drive.google.com/thumbnail?id=1LwFQ1l88f8Fb49UEDNaXpVHXZmj9cenr&sz=w1000 | https://drive.google.com/file/d/1LwFQ1l88f8Fb49UEDNaXpVHXZmj9cenr/view?usp=drive_link
2024-09-06 | Khalifa City-Majlis-P2 | P2 | MJ-06 | 117 | 493 | 610 | • Building Permits issued on 21/05/2024 • Approval For Shoring Design 15/07/2024 • Completion of site fencing and sign board | • Commencement Date 15/05/2024 | 4.19% | 2.17% | -2.02% | Notice to Commence | 4542700% | 2024-05-15 |  | 2024-09-09 | • Relocation of existing services two (2) ADDC cables with feeder pillar. • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • Delay in submissions of and insurances and guarantees. • NOCs for fencing permit. (ADDC rejection) | • Finalize the assignment of approved contractor to re-route the existing services-ongoing. • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities. Comply with Civil Defence requirements for inspection and approval. • Finalize the re-route the existing services procurement and commence the execution of re-routing.(PS) • Finalized the selection of shelter special equipment. Procurement of MEP subcontractor. | 94981423.15 |  | 94981423.15 | 3708466.35 |  | 98689889.5 | 1208000 |  | https://drive.google.com/thumbnail?id=1CeSC9RuPf2MOIArqvtve0RnhtNibXLIh&sz=w1000 | https://drive.google.com/file/d/1CeSC9RuPf2MOIArqvtve0RnhtNibXLIh/view?usp=drive_link | https://drive.google.com/thumbnail?id=1N3TOqypSQXwZ19iXs6aM8FH6uFb4dTeL&sz=w1000 | https://drive.google.com/file/d/1N3TOqypSQXwZ19iXs6aM8FH6uFb4dTeL/view?usp=drive_link | https://drive.google.com/thumbnail?id=1LOn864j5W04nT1NnABjKgwZUqForXK_4&sz=w1000 | https://drive.google.com/file/d/1LOn864j5W04nT1NnABjKgwZUqForXK_4/view?usp=drive_link
2024-09-06 | Khalifa City-Majlis-P2 | P2 | MJ-06 | 117 | 493 | 610 | • Building Permits issued on 21/05/2024 • Approval For Shoring Design 15/07/2024 • Completion of site fencing and sign board | • Commencement Date 15/05/2024 | 4.19% | 2.17% | -2.02% | Building Permit | 4543300% | 2024-05-21 |  | 2024-09-09 | • Relocation of existing services two (2) ADDC cables with feeder pillar. • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • Delay in submissions of and insurances and guarantees. • NOCs for fencing permit. (ADDC rejection) | • Finalize the assignment of approved contractor to re-route the existing services-ongoing. • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities. Comply with Civil Defence requirements for inspection and approval. • Finalize the re-route the existing services procurement and commence the execution of re-routing.(PS) • Finalized the selection of shelter special equipment. Procurement of MEP subcontractor. | 94981423.15 |  | 94981423.15 | 3708466.35 |  | 98689889.5 | 1208000 |  | https://drive.google.com/thumbnail?id=1CeSC9RuPf2MOIArqvtve0RnhtNibXLIh&sz=w1000 | https://drive.google.com/file/d/1CeSC9RuPf2MOIArqvtve0RnhtNibXLIh/view?usp=drive_link | https://drive.google.com/thumbnail?id=1N3TOqypSQXwZ19iXs6aM8FH6uFb4dTeL&sz=w1000 | https://drive.google.com/file/d/1N3TOqypSQXwZ19iXs6aM8FH6uFb4dTeL/view?usp=drive_link | https://drive.google.com/thumbnail?id=1LOn864j5W04nT1NnABjKgwZUqForXK_4&sz=w1000 | https://drive.google.com/file/d/1LOn864j5W04nT1NnABjKgwZUqForXK_4/view?usp=drive_link
2024-09-06 | Khalifa City-Majlis-P2 | P2 | MJ-06 | 117 | 493 | 610 | • Building Permits issued on 21/05/2024 • Approval For Shoring Design 15/07/2024 • Completion of site fencing and sign board | • Commencement Date 15/05/2024 | 4.19% | 2.17% | -2.02% | Site Mobilization | 4549500% | 2024-07-31 |  | 2024-09-09 | • Relocation of existing services two (2) ADDC cables with feeder pillar. • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • Delay in submissions of and insurances and guarantees. • NOCs for fencing permit. (ADDC rejection) | • Finalize the assignment of approved contractor to re-route the existing services-ongoing. • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities. Comply with Civil Defence requirements for inspection and approval. • Finalize the re-route the existing services procurement and commence the execution of re-routing.(PS) • Finalized the selection of shelter special equipment. Procurement of MEP subcontractor. | 94981423.15 |  | 94981423.15 | 3708466.35 |  | 98689889.5 | 1208000 |  | https://drive.google.com/thumbnail?id=1CeSC9RuPf2MOIArqvtve0RnhtNibXLIh&sz=w1000 | https://drive.google.com/file/d/1CeSC9RuPf2MOIArqvtve0RnhtNibXLIh/view?usp=drive_link | https://drive.google.com/thumbnail?id=1N3TOqypSQXwZ19iXs6aM8FH6uFb4dTeL&sz=w1000 | https://drive.google.com/file/d/1N3TOqypSQXwZ19iXs6aM8FH6uFb4dTeL/view?usp=drive_link | https://drive.google.com/thumbnail?id=1LOn864j5W04nT1NnABjKgwZUqForXK_4&sz=w1000 | https://drive.google.com/file/d/1LOn864j5W04nT1NnABjKgwZUqForXK_4/view?usp=drive_link
2024-09-06 | Khalifa City-Majlis-P2 | P2 | MJ-06 | 117 | 493 | 610 | • Building Permits issued on 21/05/2024 • Approval For Shoring Design 15/07/2024 • Completion of site fencing and sign board | • Commencement Date 15/05/2024 | 4.19% | 2.17% | -2.02% | Shoring Drilling & Casting Completion | 2024-11-06 |  | 2024-11-06 | 2024-09-09 | • Relocation of existing services two (2) ADDC cables with feeder pillar. • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • Delay in submissions of and insurances and guarantees. • NOCs for fencing permit. (ADDC rejection) | • Finalize the assignment of approved contractor to re-route the existing services-ongoing. • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities. Comply with Civil Defence requirements for inspection and approval. • Finalize the re-route the existing services procurement and commence the execution of re-routing.(PS) • Finalized the selection of shelter special equipment. Procurement of MEP subcontractor. | 94981423.15 |  | 94981423.15 | 3708466.35 |  | 98689889.5 | 1208000 |  | https://drive.google.com/thumbnail?id=1CeSC9RuPf2MOIArqvtve0RnhtNibXLIh&sz=w1000 | https://drive.google.com/file/d/1CeSC9RuPf2MOIArqvtve0RnhtNibXLIh/view?usp=drive_link | https://drive.google.com/thumbnail?id=1N3TOqypSQXwZ19iXs6aM8FH6uFb4dTeL&sz=w1000 | https://drive.google.com/file/d/1N3TOqypSQXwZ19iXs6aM8FH6uFb4dTeL/view?usp=drive_link | https://drive.google.com/thumbnail?id=1LOn864j5W04nT1NnABjKgwZUqForXK_4&sz=w1000 | https://drive.google.com/file/d/1LOn864j5W04nT1NnABjKgwZUqForXK_4/view?usp=drive_link
2024-09-06 | Khalifa City-Majlis-P2 | P2 | MJ-06 | 117 | 493 | 610 | • Building Permits issued on 21/05/2024 • Approval For Shoring Design 15/07/2024 • Completion of site fencing and sign board | • Commencement Date 15/05/2024 | 4.19% | 2.17% | -2.02% | Power On | 4598300% |  | 2025-11-22 | 2024-09-09 | • Relocation of existing services two (2) ADDC cables with feeder pillar. • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • Delay in submissions of and insurances and guarantees. • NOCs for fencing permit. (ADDC rejection) | • Finalize the assignment of approved contractor to re-route the existing services-ongoing. • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities. Comply with Civil Defence requirements for inspection and approval. • Finalize the re-route the existing services procurement and commence the execution of re-routing.(PS) • Finalized the selection of shelter special equipment. Procurement of MEP subcontractor. | 94981423.15 |  | 94981423.15 | 3708466.35 |  | 98689889.5 | 1208000 |  | https://drive.google.com/thumbnail?id=1CeSC9RuPf2MOIArqvtve0RnhtNibXLIh&sz=w1000 | https://drive.google.com/file/d/1CeSC9RuPf2MOIArqvtve0RnhtNibXLIh/view?usp=drive_link | https://drive.google.com/thumbnail?id=1N3TOqypSQXwZ19iXs6aM8FH6uFb4dTeL&sz=w1000 | https://drive.google.com/file/d/1N3TOqypSQXwZ19iXs6aM8FH6uFb4dTeL/view?usp=drive_link | https://drive.google.com/thumbnail?id=1LOn864j5W04nT1NnABjKgwZUqForXK_4&sz=w1000 | https://drive.google.com/file/d/1LOn864j5W04nT1NnABjKgwZUqForXK_4/view?usp=drive_link
2024-09-06 | Khalifa City-Majlis-P2 | P2 | MJ-06 | 117 | 493 | 610 | • Building Permits issued on 21/05/2024 • Approval For Shoring Design 15/07/2024 • Completion of site fencing and sign board | • Commencement Date 15/05/2024 | 4.19% | 2.17% | -2.02% | Interior Finishes | 4598300% |  | 2025-11-22 | 2024-09-09 | • Relocation of existing services two (2) ADDC cables with feeder pillar. • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • Delay in submissions of and insurances and guarantees. • NOCs for fencing permit. (ADDC rejection) | • Finalize the assignment of approved contractor to re-route the existing services-ongoing. • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities. Comply with Civil Defence requirements for inspection and approval. • Finalize the re-route the existing services procurement and commence the execution of re-routing.(PS) • Finalized the selection of shelter special equipment. Procurement of MEP subcontractor. | 94981423.15 |  | 94981423.15 | 3708466.35 |  | 98689889.5 | 1208000 |  | https://drive.google.com/thumbnail?id=1CeSC9RuPf2MOIArqvtve0RnhtNibXLIh&sz=w1000 | https://drive.google.com/file/d/1CeSC9RuPf2MOIArqvtve0RnhtNibXLIh/view?usp=drive_link | https://drive.google.com/thumbnail?id=1N3TOqypSQXwZ19iXs6aM8FH6uFb4dTeL&sz=w1000 | https://drive.google.com/file/d/1N3TOqypSQXwZ19iXs6aM8FH6uFb4dTeL/view?usp=drive_link | https://drive.google.com/thumbnail?id=1LOn864j5W04nT1NnABjKgwZUqForXK_4&sz=w1000 | https://drive.google.com/file/d/1LOn864j5W04nT1NnABjKgwZUqForXK_4/view?usp=drive_link
2024-09-06 | Khalifa City-Majlis-P2 | P2 | MJ-06 | 117 | 493 | 610 | • Building Permits issued on 21/05/2024 • Approval For Shoring Design 15/07/2024 • Completion of site fencing and sign board | • Commencement Date 15/05/2024 | 4.19% | 2.17% | -2.02% | Substantial Completion | 4600600% |  | 2025-12-15 | 2024-09-09 | • Relocation of existing services two (2) ADDC cables with feeder pillar. • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • Delay in submissions of and insurances and guarantees. • NOCs for fencing permit. (ADDC rejection) | • Finalize the assignment of approved contractor to re-route the existing services-ongoing. • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities. Comply with Civil Defence requirements for inspection and approval. • Finalize the re-route the existing services procurement and commence the execution of re-routing.(PS) • Finalized the selection of shelter special equipment. Procurement of MEP subcontractor. | 94981423.15 |  | 94981423.15 | 3708466.35 |  | 98689889.5 | 1208000 |  | https://drive.google.com/thumbnail?id=1CeSC9RuPf2MOIArqvtve0RnhtNibXLIh&sz=w1000 | https://drive.google.com/file/d/1CeSC9RuPf2MOIArqvtve0RnhtNibXLIh/view?usp=drive_link | https://drive.google.com/thumbnail?id=1N3TOqypSQXwZ19iXs6aM8FH6uFb4dTeL&sz=w1000 | https://drive.google.com/file/d/1N3TOqypSQXwZ19iXs6aM8FH6uFb4dTeL/view?usp=drive_link | https://drive.google.com/thumbnail?id=1LOn864j5W04nT1NnABjKgwZUqForXK_4&sz=w1000 | https://drive.google.com/file/d/1LOn864j5W04nT1NnABjKgwZUqForXK_4/view?usp=drive_link
2024-09-06 | Madinat Al Riyad-Majlis-P3 | P3 | MJ-08 | 50 | 743 | 793 | 1) Site Mobilization: Temporary power, water, sanitation, and parking have been completed. Labour prayer room construction is in progress. 2) Diesel Tank: Installed, with side wall construction ongoing. 3) Engineering Submissions: Prequalification, materials, and shop drawings are actively in progress. 4) Majlis Building: Levelling and grading work is ongoing. | *IFC drawings were issued on 12th September 2024 *The contractor has to submit baseline planning package in compliance with Engineer comments issued for R00 submission. Expected submission on 13 Sep, 2024. | 0% | 0% | 0% | Project Commencement | 2024-07-23 | 2024-07-23 |  | 2024-09-13 | 1) Issuance of Night Shift Permit 2)Possibility of High Water Table 3)Execution Plan Finalization for Piling & Shoring Works | 1) Action required 2) Proactive Measures shall be adopted 3) Specialized Contractors will Provide Execution Plan | • Concrete Lab Mobilization • Workers Rest Area Shed Fabrication • Access Road Construction • Shelter Area Shoring Excavation in Progress • Client & Consultant Office Porta Cabin Installation | 117010730 | 0 | 117010730 | 3645800 | 0 | 120656530 |  |  | https://drive.google.com/thumbnail?id=1XNlB-TCqjbu1MIFEoH3KzWJaFDA0h4Mr&sz=w1000 | https://drive.google.com/file/d/1XNlB-TCqjbu1MIFEoH3KzWJaFDA0h4Mr/view?usp=drive_link | https://drive.google.com/thumbnail?id=1XDJ17puSEKXRlcpoac80pcUkSirH5iqT&sz=w1000 | https://drive.google.com/file/d/1XDJ17puSEKXRlcpoac80pcUkSirH5iqT/view?usp=drive_link | https://drive.google.com/thumbnail?id=1_yjMQo6gzbHLiIya48Wdfww-Xb1eVGfK&sz=w1000 | https://drive.google.com/file/d/1_yjMQo6gzbHLiIya48Wdfww-Xb1eVGfK/view?usp=drive_link
2024-09-06 | Madinat Al Riyad-Majlis-P3 | P3 | MJ-08 | 50 | 743 | 793 | 1) Site Mobilization: Temporary power, water, sanitation, and parking have been completed. Labour prayer room construction is in progress. 2) Diesel Tank: Installed, with side wall construction ongoing. 3) Engineering Submissions: Prequalification, materials, and shop drawings are actively in progress. 4) Majlis Building: Levelling and grading work is ongoing. | *IFC drawings were issued on 12th September 2024 *The contractor has to submit baseline planning package in compliance with Engineer comments issued for R00 submission. Expected submission on 13 Sep, 2024. | 0% | 0% | 0% | Construction Permit & NOC | 2024-08-15 | 2024-08-15 |  | 2024-09-13 | 1) Issuance of Night Shift Permit 2)Possibility of High Water Table 3)Execution Plan Finalization for Piling & Shoring Works | 1) Issuance of Night Shift Permit 2)Possibility of High Water Table 3)Execution Plan Finalization for Piling & Shoring Works | • Concrete Lab Mobilization • Workers Rest Area Shed Fabrication • Access Road Construction • Shelter Area Shoring Excavation in Progress • Client & Consultant Office Porta Cabin Installation | 117010730 |  | 117010730 | 3645800 |  | 120656530 |  |  | https://drive.google.com/thumbnail?id=1XNlB-TCqjbu1MIFEoH3KzWJaFDA0h4Mr&sz=w1000 | https://drive.google.com/file/d/1XNlB-TCqjbu1MIFEoH3KzWJaFDA0h4Mr/view?usp=drive_link | https://drive.google.com/thumbnail?id=1XDJ17puSEKXRlcpoac80pcUkSirH5iqT&sz=w1000 | https://drive.google.com/file/d/1XDJ17puSEKXRlcpoac80pcUkSirH5iqT/view?usp=drive_link | https://drive.google.com/thumbnail?id=1_yjMQo6gzbHLiIya48Wdfww-Xb1eVGfK&sz=w1000 | https://drive.google.com/file/d/1_yjMQo6gzbHLiIya48Wdfww-Xb1eVGfK/view?usp=drive_link
2024-09-06 | Madinat Al Riyad-Majlis-P3 | P3 | MJ-08 | 50 | 743 | 793 | 1) Site Mobilization: Temporary power, water, sanitation, and parking have been completed. Labour prayer room construction is in progress. 2) Diesel Tank: Installed, with side wall construction ongoing. 3) Engineering Submissions: Prequalification, materials, and shop drawings are actively in progress. 4) Majlis Building: Levelling and grading work is ongoing. | *IFC drawings were issued on 12th September 2024 *The contractor has to submit baseline planning package in compliance with Engineer comments issued for R00 submission. Expected submission on 13 Sep, 2024. | 0% | 0% | 0% | Site Moblization | 2024-09-23 |  |  | 2024-09-13 | 1) Issuance of Night Shift Permit 2)Possibility of High Water Table 3)Execution Plan Finalization for Piling & Shoring Works | 1) Action required 2) Proactive Measures shall be adopted 3) Specialized Contractors will Provide Execution Plan | • Concrete Lab Mobilization • Workers Rest Area Shed Fabrication • Access Road Construction • Shelter Area Shoring Excavation in Progress • Client & Consultant Office Porta Cabin Installation | 117010730 |  | 117010730 | 3645800 |  | 120656530 |  |  | https://drive.google.com/thumbnail?id=1XNlB-TCqjbu1MIFEoH3KzWJaFDA0h4Mr&sz=w1000 | https://drive.google.com/file/d/1XNlB-TCqjbu1MIFEoH3KzWJaFDA0h4Mr/view?usp=drive_link | https://drive.google.com/thumbnail?id=1XDJ17puSEKXRlcpoac80pcUkSirH5iqT&sz=w1000 | https://drive.google.com/file/d/1XDJ17puSEKXRlcpoac80pcUkSirH5iqT/view?usp=drive_link | https://drive.google.com/thumbnail?id=1_yjMQo6gzbHLiIya48Wdfww-Xb1eVGfK&sz=w1000 | https://drive.google.com/file/d/1_yjMQo6gzbHLiIya48Wdfww-Xb1eVGfK/view?usp=drive_link
2024-09-06 | Madinat Al Riyad-Majlis-P3 | P3 | MJ-08 | 50 | 743 | 793 | 1) Site Mobilization: Temporary power, water, sanitation, and parking have been completed. Labour prayer room construction is in progress. 2) Diesel Tank: Installed, with side wall construction ongoing. 3) Engineering Submissions: Prequalification, materials, and shop drawings are actively in progress. 4) Majlis Building: Levelling and grading work is ongoing. | *IFC drawings were issued on 12th September 2024 *The contractor has to submit baseline planning package in compliance with Engineer comments issued for R00 submission. Expected submission on 13 Sep, 2024. | 0% | 0% | 0% | Engineering Works | 2026-01-31 |  |  | 2024-09-13 | 1) Issuance of Night Shift Permit 2)Possibility of High Water Table 3)Execution Plan Finalization for Piling & Shoring Works | 1) Issuance of Night Shift Permit 2)Possibility of High Water Table 3)Execution Plan Finalization for Piling & Shoring Works | • Concrete Lab Mobilization • Workers Rest Area Shed Fabrication • Access Road Construction • Shelter Area Shoring Excavation in Progress • Client & Consultant Office Porta Cabin Installation | 117010730 |  | 117010730 | 3645800 |  | 120656530 |  |  | https://drive.google.com/thumbnail?id=1XNlB-TCqjbu1MIFEoH3KzWJaFDA0h4Mr&sz=w1000 | https://drive.google.com/file/d/1XNlB-TCqjbu1MIFEoH3KzWJaFDA0h4Mr/view?usp=drive_link | https://drive.google.com/thumbnail?id=1XDJ17puSEKXRlcpoac80pcUkSirH5iqT&sz=w1000 | https://drive.google.com/file/d/1XDJ17puSEKXRlcpoac80pcUkSirH5iqT/view?usp=drive_link | https://drive.google.com/thumbnail?id=1_yjMQo6gzbHLiIya48Wdfww-Xb1eVGfK&sz=w1000 | https://drive.google.com/file/d/1_yjMQo6gzbHLiIya48Wdfww-Xb1eVGfK/view?usp=drive_link
2024-09-06 | Madinat Al Riyad-Majlis-P3 | P3 | MJ-08 | 50 | 743 | 793 | 1) Site Mobilization: Temporary power, water, sanitation, and parking have been completed. Labour prayer room construction is in progress. 2) Diesel Tank: Installed, with side wall construction ongoing. 3) Engineering Submissions: Prequalification, materials, and shop drawings are actively in progress. 4) Majlis Building: Levelling and grading work is ongoing. | *IFC drawings were issued on 12th September 2024 *The contractor has to submit baseline planning package in compliance with Engineer comments issued for R00 submission. Expected submission on 13 Sep, 2024. | 0% | 0% | 0% | Construction of Shelter | 2026-09-15 |  |  | 2024-09-13 | 1) Issuance of Night Shift Permit 2)Possibility of High Water Table 3)Execution Plan Finalization for Piling & Shoring Works | 1) Action required 2) Proactive Measures shall be adopted 3) Specialized Contractors will Provide Execution Plan | • Concrete Lab Mobilization • Workers Rest Area Shed Fabrication • Access Road Construction • Shelter Area Shoring Excavation in Progress • Client & Consultant Office Porta Cabin Installation | 117010730 |  | 117010730 | 3645800 |  | 120656530 |  |  | https://drive.google.com/thumbnail?id=1XNlB-TCqjbu1MIFEoH3KzWJaFDA0h4Mr&sz=w1000 | https://drive.google.com/file/d/1XNlB-TCqjbu1MIFEoH3KzWJaFDA0h4Mr/view?usp=drive_link | https://drive.google.com/thumbnail?id=1XDJ17puSEKXRlcpoac80pcUkSirH5iqT&sz=w1000 | https://drive.google.com/file/d/1XDJ17puSEKXRlcpoac80pcUkSirH5iqT/view?usp=drive_link | https://drive.google.com/thumbnail?id=1_yjMQo6gzbHLiIya48Wdfww-Xb1eVGfK&sz=w1000 | https://drive.google.com/file/d/1_yjMQo6gzbHLiIya48Wdfww-Xb1eVGfK/view?usp=drive_link
2024-09-06 | Madinat Al Riyad-Majlis-P3 | P3 | MJ-08 | 50 | 743 | 793 | 1) Site Mobilization: Temporary power, water, sanitation, and parking have been completed. Labour prayer room construction is in progress. 2) Diesel Tank: Installed, with side wall construction ongoing. 3) Engineering Submissions: Prequalification, materials, and shop drawings are actively in progress. 4) Majlis Building: Levelling and grading work is ongoing. | *IFC drawings were issued on 12th September 2024 *The contractor has to submit baseline planning package in compliance with Engineer comments issued for R00 submission. Expected submission on 13 Sep, 2024. | 0% | 0% | 0% | Construction of Majlis | 2024-07-27 |  |  | 2024-09-13 | 1) Issuance of Night Shift Permit 2)Possibility of High Water Table 3)Execution Plan Finalization for Piling & Shoring Works | 1) Issuance of Night Shift Permit 2)Possibility of High Water Table 3)Execution Plan Finalization for Piling & Shoring Works | • Concrete Lab Mobilization • Workers Rest Area Shed Fabrication • Access Road Construction • Shelter Area Shoring Excavation in Progress • Client & Consultant Office Porta Cabin Installation | 117010730 |  | 117010730 | 3645800 |  | 120656530 |  |  | https://drive.google.com/thumbnail?id=1XNlB-TCqjbu1MIFEoH3KzWJaFDA0h4Mr&sz=w1000 | https://drive.google.com/file/d/1XNlB-TCqjbu1MIFEoH3KzWJaFDA0h4Mr/view?usp=drive_link | https://drive.google.com/thumbnail?id=1XDJ17puSEKXRlcpoac80pcUkSirH5iqT&sz=w1000 | https://drive.google.com/file/d/1XDJ17puSEKXRlcpoac80pcUkSirH5iqT/view?usp=drive_link | https://drive.google.com/thumbnail?id=1_yjMQo6gzbHLiIya48Wdfww-Xb1eVGfK&sz=w1000 | https://drive.google.com/file/d/1_yjMQo6gzbHLiIya48Wdfww-Xb1eVGfK/view?usp=drive_link
2024-09-06 | Madinat Al Riyad-Majlis-P3 | P3 | MJ-08 | 50 | 743 | 793 | 1) Site Mobilization: Temporary power, water, sanitation, and parking have been completed. Labour prayer room construction is in progress. 2) Diesel Tank: Installed, with side wall construction ongoing. 3) Engineering Submissions: Prequalification, materials, and shop drawings are actively in progress. 4) Majlis Building: Levelling and grading work is ongoing. | *IFC drawings were issued on 12th September 2024 *The contractor has to submit baseline planning package in compliance with Engineer comments issued for R00 submission. Expected submission on 13 Sep, 2024. | 0% | 0% | 0% | Construction of Pump Room | 2026-11-02 |  |  | 2024-09-13 | 1) Issuance of Night Shift Permit 2)Possibility of High Water Table 3)Execution Plan Finalization for Piling & Shoring Works | 1) Action required 2) Proactive Measures shall be adopted 3) Specialized Contractors will Provide Execution Plan | • Concrete Lab Mobilization • Workers Rest Area Shed Fabrication • Access Road Construction • Shelter Area Shoring Excavation in Progress • Client & Consultant Office Porta Cabin Installation | 117010730 |  | 117010730 | 3645800 |  | 120656530 |  |  | https://drive.google.com/thumbnail?id=1XNlB-TCqjbu1MIFEoH3KzWJaFDA0h4Mr&sz=w1000 | https://drive.google.com/file/d/1XNlB-TCqjbu1MIFEoH3KzWJaFDA0h4Mr/view?usp=drive_link | https://drive.google.com/thumbnail?id=1XDJ17puSEKXRlcpoac80pcUkSirH5iqT&sz=w1000 | https://drive.google.com/file/d/1XDJ17puSEKXRlcpoac80pcUkSirH5iqT/view?usp=drive_link | https://drive.google.com/thumbnail?id=1_yjMQo6gzbHLiIya48Wdfww-Xb1eVGfK&sz=w1000 | https://drive.google.com/file/d/1_yjMQo6gzbHLiIya48Wdfww-Xb1eVGfK/view?usp=drive_link
2024-09-06 | Madinat Al Riyad-Majlis-P3 | P3 | MJ-08 | 50 | 743 | 793 | 1) Site Mobilization: Temporary power, water, sanitation, and parking have been completed. Labour prayer room construction is in progress. 2) Diesel Tank: Installed, with side wall construction ongoing. 3) Engineering Submissions: Prequalification, materials, and shop drawings are actively in progress. 4) Majlis Building: Levelling and grading work is ongoing. | *IFC drawings were issued on 12th September 2024 *The contractor has to submit baseline planning package in compliance with Engineer comments issued for R00 submission. Expected submission on 13 Sep, 2024. | 0% | 0% | 0% | Construction of Substation | 2025-05-12 |  |  | 2024-09-13 | 1) Issuance of Night Shift Permit 2)Possibility of High Water Table 3)Execution Plan Finalization for Piling & Shoring Works | 1) Issuance of Night Shift Permit 2)Possibility of High Water Table 3)Execution Plan Finalization for Piling & Shoring Works | • Concrete Lab Mobilization • Workers Rest Area Shed Fabrication • Access Road Construction • Shelter Area Shoring Excavation in Progress • Client & Consultant Office Porta Cabin Installation | 117010730 |  | 117010730 | 3645800 |  | 120656530 |  |  | https://drive.google.com/thumbnail?id=1XNlB-TCqjbu1MIFEoH3KzWJaFDA0h4Mr&sz=w1000 | https://drive.google.com/file/d/1XNlB-TCqjbu1MIFEoH3KzWJaFDA0h4Mr/view?usp=drive_link | https://drive.google.com/thumbnail?id=1XDJ17puSEKXRlcpoac80pcUkSirH5iqT&sz=w1000 | https://drive.google.com/file/d/1XDJ17puSEKXRlcpoac80pcUkSirH5iqT/view?usp=drive_link | https://drive.google.com/thumbnail?id=1_yjMQo6gzbHLiIya48Wdfww-Xb1eVGfK&sz=w1000 | https://drive.google.com/file/d/1_yjMQo6gzbHLiIya48Wdfww-Xb1eVGfK/view?usp=drive_link
2024-09-06 | Madinat Al Riyad-Majlis-P3 | P3 | MJ-08 | 50 | 743 | 793 | 1) Site Mobilization: Temporary power, water, sanitation, and parking have been completed. Labour prayer room construction is in progress. 2) Diesel Tank: Installed, with side wall construction ongoing. 3) Engineering Submissions: Prequalification, materials, and shop drawings are actively in progress. 4) Majlis Building: Levelling and grading work is ongoing. | *IFC drawings were issued on 12th September 2024 *The contractor has to submit baseline planning package in compliance with Engineer comments issued for R00 submission. Expected submission on 13 Sep, 2024. | 0% | 0% | 0% | External Works | 2026-04-14 |  |  | 2024-09-13 | 1) Issuance of Night Shift Permit 2)Possibility of High Water Table 3)Execution Plan Finalization for Piling & Shoring Works | 1) Action required 2) Proactive Measures shall be adopted 3) Specialized Contractors will Provide Execution Plan | • Concrete Lab Mobilization • Workers Rest Area Shed Fabrication • Access Road Construction • Shelter Area Shoring Excavation in Progress • Client & Consultant Office Porta Cabin Installation | 117010730 |  | 117010730 | 3645800 |  | 120656530 |  |  | https://drive.google.com/thumbnail?id=1XNlB-TCqjbu1MIFEoH3KzWJaFDA0h4Mr&sz=w1000 | https://drive.google.com/file/d/1XNlB-TCqjbu1MIFEoH3KzWJaFDA0h4Mr/view?usp=drive_link | https://drive.google.com/thumbnail?id=1XDJ17puSEKXRlcpoac80pcUkSirH5iqT&sz=w1000 | https://drive.google.com/file/d/1XDJ17puSEKXRlcpoac80pcUkSirH5iqT/view?usp=drive_link | https://drive.google.com/thumbnail?id=1_yjMQo6gzbHLiIya48Wdfww-Xb1eVGfK&sz=w1000 | https://drive.google.com/file/d/1_yjMQo6gzbHLiIya48Wdfww-Xb1eVGfK/view?usp=drive_link
2024-09-06 | Madinat Al Riyad-Majlis-P3 | P3 | MJ-08 | 50 | 743 | 793 | 1) Site Mobilization: Temporary power, water, sanitation, and parking have been completed. Labour prayer room construction is in progress. 2) Diesel Tank: Installed, with side wall construction ongoing. 3) Engineering Submissions: Prequalification, materials, and shop drawings are actively in progress. 4) Majlis Building: Levelling and grading work is ongoing. | *IFC drawings were issued on 12th September 2024 *The contractor has to submit baseline planning package in compliance with Engineer comments issued for R00 submission. Expected submission on 13 Sep, 2024. | 0% | 0% | 0% | Testing & Commissioning | 2026-09-21 |  |  | 2024-09-13 | 1) Issuance of Night Shift Permit 2)Possibility of High Water Table 3)Execution Plan Finalization for Piling & Shoring Works | 1) Issuance of Night Shift Permit 2)Possibility of High Water Table 3)Execution Plan Finalization for Piling & Shoring Works | • Concrete Lab Mobilization • Workers Rest Area Shed Fabrication • Access Road Construction • Shelter Area Shoring Excavation in Progress • Client & Consultant Office Porta Cabin Installation | 117010730 |  | 117010730 | 3645800 |  | 120656530 |  |  | https://drive.google.com/thumbnail?id=1XNlB-TCqjbu1MIFEoH3KzWJaFDA0h4Mr&sz=w1000 | https://drive.google.com/file/d/1XNlB-TCqjbu1MIFEoH3KzWJaFDA0h4Mr/view?usp=drive_link | https://drive.google.com/thumbnail?id=1XDJ17puSEKXRlcpoac80pcUkSirH5iqT&sz=w1000 | https://drive.google.com/file/d/1XDJ17puSEKXRlcpoac80pcUkSirH5iqT/view?usp=drive_link | https://drive.google.com/thumbnail?id=1_yjMQo6gzbHLiIya48Wdfww-Xb1eVGfK&sz=w1000 | https://drive.google.com/file/d/1_yjMQo6gzbHLiIya48Wdfww-Xb1eVGfK/view?usp=drive_link
2024-09-06 | Madinat Al Riyad-Majlis-P3 | P3 | MJ-08 | 50 | 743 | 793 | 1) Site Mobilization: Temporary power, water, sanitation, and parking have been completed. Labour prayer room construction is in progress. 2) Diesel Tank: Installed, with side wall construction ongoing. 3) Engineering Submissions: Prequalification, materials, and shop drawings are actively in progress. 4) Majlis Building: Levelling and grading work is ongoing. | *IFC drawings were issued on 12th September 2024 *The contractor has to submit baseline planning package in compliance with Engineer comments issued for R00 submission. Expected submission on 13 Sep, 2024. | 0% | 0% | 0% | Authorities Approvals | 2026-10-09 |  |  | 2024-09-13 | 1) Issuance of Night Shift Permit 2)Possibility of High Water Table 3)Execution Plan Finalization for Piling & Shoring Works | 1) Action required 2) Proactive Measures shall be adopted 3) Specialized Contractors will Provide Execution Plan | • Shamkha Cost Loaded Program Submission on 13-Sep-24 • Client & Consultant Office Porta Cabin Installation • Workers Rest Area Shed Fabrication • Access Road Construction • Excavation for Majlis • Shelter Area Shoring Excavation in Progress | 117010730 |  | 117010730 | 3645800 |  | 120656530 |  |  | https://drive.google.com/thumbnail?id=1XNlB-TCqjbu1MIFEoH3KzWJaFDA0h4Mr&sz=w1000 | https://drive.google.com/file/d/1XNlB-TCqjbu1MIFEoH3KzWJaFDA0h4Mr/view?usp=drive_link | https://drive.google.com/thumbnail?id=1XDJ17puSEKXRlcpoac80pcUkSirH5iqT&sz=w1000 | https://drive.google.com/file/d/1XDJ17puSEKXRlcpoac80pcUkSirH5iqT/view?usp=drive_link | https://drive.google.com/thumbnail?id=1_yjMQo6gzbHLiIya48Wdfww-Xb1eVGfK&sz=w1000 | https://drive.google.com/file/d/1_yjMQo6gzbHLiIya48Wdfww-Xb1eVGfK/view?usp=drive_link
2024-09-06 | Madinat Al Riyad-Majlis-P3 | P3 | MJ-08 | 50 | 743 | 793 | 1) Site Mobilization: Temporary power, water, sanitation, and parking have been completed. Labour prayer room construction is in progress. 2) Diesel Tank: Installed, with side wall construction ongoing. 3) Engineering Submissions: Prequalification, materials, and shop drawings are actively in progress. 4) Majlis Building: Levelling and grading work is ongoing. | *IFC drawings were issued on 12th September 2024 *The contractor has to submit baseline planning package in compliance with Engineer comments issued for R00 submission. Expected submission on 13 Sep, 2024. | 0% | 0% | 0% | Substantial Completion | 2026-09-23 |  |  | 2024-09-13 | 1) Issuance of Night Shift Permit 2)Possibility of High Water Table 3)Execution Plan Finalization for Piling & Shoring Works | 1) Issuance of Night Shift Permit 2)Possibility of High Water Table 3)Execution Plan Finalization for Piling & Shoring Works | • Shamkha Cost Loaded Program Submission on 13-Sep-24 • Client & Consultant Office Porta Cabin Installation • Workers Rest Area Shed Fabrication • Access Road Construction • Excavation for Majlis • Shelter Area Shoring Excavation in Progress | 117010730 |  | 117010730 | 3645800 |  | 120656530 |  |  | https://drive.google.com/thumbnail?id=1XNlB-TCqjbu1MIFEoH3KzWJaFDA0h4Mr&sz=w1000 | https://drive.google.com/file/d/1XNlB-TCqjbu1MIFEoH3KzWJaFDA0h4Mr/view?usp=drive_link | https://drive.google.com/thumbnail?id=1XDJ17puSEKXRlcpoac80pcUkSirH5iqT&sz=w1000 | https://drive.google.com/file/d/1XDJ17puSEKXRlcpoac80pcUkSirH5iqT/view?usp=drive_link | https://drive.google.com/thumbnail?id=1_yjMQo6gzbHLiIya48Wdfww-Xb1eVGfK&sz=w1000 | https://drive.google.com/file/d/1_yjMQo6gzbHLiIya48Wdfww-Xb1eVGfK/view?usp=drive_link
2024-09-06 | Al Shamkhah-Majlis-P6 | P6 | MJ-09 | 50 | 743 | 793 | 1) Excavation for Majlis Building: Commenced on 5th September 2024. Shuttering and scaffolding materials have been mobilized at the site. 2) Baseline Programme : Shamkha Cost Loaded program shall be submitted on 13-Sep-24. 3) Provision of Welfare Facilities: Ablution areas, drinking water cooler, and smoking zone are completed. Rest area and prayer room are in progress. 4) Site Offices for Client and Consultant: Foundation work is completed, portacabin fabrication in progress, with delivery expected by 13th September. 5) For Shoring and Piling Works: Equipment's Mobilized at site. Shoring Excavation In Progress for Guide Wall. 6) Mosque Construction: Grading Works in Progress. 7) Engineering Works Submissions: The submissions for prequalification's, material approvals, and shop drawings are actively in progress. | *IFC drawings were issued on 12th September 2024 *The contractor has to submit baseline planning package in compliance with Engineer comments issued for R00 submissio. * Dewatering Engineering Works to be initiated as a proactive approcah to mitigate the risk of GWT. * Finalization of Execution Plan for Shoring & Piling Works. AIC Schedule a meeting on Tuesday 17 Sep, 2024, in this regard and requsted contractor to submit program of works for execition of piling & shoring works in due consultation with Specialized subcontractor. | 0% | 0% | 0% | Project Commencement | 2024-07-23 | 2024-07-23 |  | 2024-09-13 | 1) Issuance of Night Shift Permit 2)Possibility of High Water Table 3)Execution Plan Finalization for Piling & Shoring Works | 1) Action required 2) Proactive Measures shall be adopted 3) Specialized Contractors will Provide Execution Plan | • Shamkha Cost Loaded Program Submission on 13-Sep-24 • Client & Consultant Office Porta Cabin Installation • Workers Rest Area Shed Fabrication • Access Road Construction • Excavation for Majlis • Shelter Area Shoring Excavation in Progress | 356759501 |  | 356759501 | 3645800 |  | 360405301 |  |  | https://drive.google.com/thumbnail?id=1N22qwC0vrqCOzXJ46mu1iA931nPdVUdV&sz=w1000 | https://drive.google.com/file/d/1N22qwC0vrqCOzXJ46mu1iA931nPdVUdV/view?usp=drive_link | https://drive.google.com/thumbnail?id=1AWxAuRE6Vg50Zv6iozolSxiyZ-AwV82_&sz=w1000 | https://drive.google.com/file/d/1AWxAuRE6Vg50Zv6iozolSxiyZ-AwV82_/view?usp=drive_link | https://drive.google.com/thumbnail?id=19aGB7slFQPfIgI387xmUjRUwIeJi_fXB&sz=w1000 | https://drive.google.com/file/d/19aGB7slFQPfIgI387xmUjRUwIeJi_fXB/view?usp=drive_link
2024-09-06 | Al Shamkhah-Majlis-P6 | P6 | MJ-09 | 50 | 743 | 793 | 1) Excavation for Majlis Building: Commenced on 5th September 2024. Shuttering and scaffolding materials have been mobilized at the site. 2) Baseline Programme : Shamkha Cost Loaded program shall be submitted on 13-Sep-24. 3) Provision of Welfare Facilities: Ablution areas, drinking water cooler, and smoking zone are completed. Rest area and prayer room are in progress. 4) Site Offices for Client and Consultant: Foundation work is completed, portacabin fabrication in progress, with delivery expected by 13th September. 5) For Shoring and Piling Works: Equipment's Mobilized at site. Shoring Excavation In Progress for Guide Wall. 6) Mosque Construction: Grading Works in Progress. 7) Engineering Works Submissions: The submissions for prequalification's, material approvals, and shop drawings are actively in progress. | *IFC drawings were issued on 12th September 2024 *The contractor has to submit baseline planning package in compliance with Engineer comments issued for R00 submissio. * Dewatering Engineering Works to be initiated as a proactive approcah to mitigate the risk of GWT. * Finalization of Execution Plan for Shoring & Piling Works. AIC Schedule a meeting on Tuesday 17 Sep, 2024, in this regard and requsted contractor to submit program of works for execition of piling & shoring works in due consultation with Specialized subcontractor. | 0% | 0% | 0% | Construction Permit & NOC | 2024-08-15 | 2024-06-08 |  | 2024-09-13 | 1) Issuance of Night Shift Permit 2)Possibility of High Water Table 3)Execution Plan Finalization for Piling & Shoring Works | 1) Issuance of Night Shift Permit 2)Possibility of High Water Table 3)Execution Plan Finalization for Piling & Shoring Works | • Shamkha Cost Loaded Program Submission on 13-Sep-24 • Client & Consultant Office Porta Cabin Installation • Workers Rest Area Shed Fabrication • Access Road Construction • Excavation for Majlis • Shelter Area Shoring Excavation in Progress | 356759501 |  | 356759501 | 3645800 |  | 360405301 |  |  | https://drive.google.com/thumbnail?id=1N22qwC0vrqCOzXJ46mu1iA931nPdVUdV&sz=w1000 | https://drive.google.com/file/d/1N22qwC0vrqCOzXJ46mu1iA931nPdVUdV/view?usp=drive_link | https://drive.google.com/thumbnail?id=1AWxAuRE6Vg50Zv6iozolSxiyZ-AwV82_&sz=w1000 | https://drive.google.com/file/d/1AWxAuRE6Vg50Zv6iozolSxiyZ-AwV82_/view?usp=drive_link | https://drive.google.com/thumbnail?id=19aGB7slFQPfIgI387xmUjRUwIeJi_fXB&sz=w1000 | https://drive.google.com/file/d/19aGB7slFQPfIgI387xmUjRUwIeJi_fXB/view?usp=drive_link
2024-09-06 | Al Shamkhah-Majlis-P6 | P6 | MJ-09 | 50 | 743 | 793 | 1) Excavation for Majlis Building: Commenced on 5th September 2024. Shuttering and scaffolding materials have been mobilized at the site. 2) Baseline Programme : Shamkha Cost Loaded program shall be submitted on 13-Sep-24. 3) Provision of Welfare Facilities: Ablution areas, drinking water cooler, and smoking zone are completed. Rest area and prayer room are in progress. 4) Site Offices for Client and Consultant: Foundation work is completed, portacabin fabrication in progress, with delivery expected by 13th September. 5) For Shoring and Piling Works: Equipment's Mobilized at site. Shoring Excavation In Progress for Guide Wall. 6) Mosque Construction: Grading Works in Progress. 7) Engineering Works Submissions: The submissions for prequalification's, material approvals, and shop drawings are actively in progress. | *IFC drawings were issued on 12th September 2024 *The contractor has to submit baseline planning package in compliance with Engineer comments issued for R00 submissio. * Dewatering Engineering Works to be initiated as a proactive approcah to mitigate the risk of GWT. * Finalization of Execution Plan for Shoring & Piling Works. AIC Schedule a meeting on Tuesday 17 Sep, 2024, in this regard and requsted contractor to submit program of works for execition of piling & shoring works in due consultation with Specialized subcontractor. | 0% | 0% | 0% | Site Moblization | 2026-09-23 |  |  | 2024-09-13 | 1) Issuance of Night Shift Permit 2)Possibility of High Water Table 3)Execution Plan Finalization for Piling & Shoring Works | 1) Action required 2) Proactive Measures shall be adopted 3) Specialized Contractors will Provide Execution Plan | • Shamkha Cost Loaded Program Submission on 13-Sep-24 • Client & Consultant Office Porta Cabin Installation • Workers Rest Area Shed Fabrication • Access Road Construction • Excavation for Majlis • Shelter Area Shoring Excavation in Progress | 356759501 |  | 356759501 | 3645800 |  | 360405301 |  |  | https://drive.google.com/thumbnail?id=1N22qwC0vrqCOzXJ46mu1iA931nPdVUdV&sz=w1000 | https://drive.google.com/file/d/1N22qwC0vrqCOzXJ46mu1iA931nPdVUdV/view?usp=drive_link | https://drive.google.com/thumbnail?id=1AWxAuRE6Vg50Zv6iozolSxiyZ-AwV82_&sz=w1000 | https://drive.google.com/file/d/1AWxAuRE6Vg50Zv6iozolSxiyZ-AwV82_/view?usp=drive_link | https://drive.google.com/thumbnail?id=19aGB7slFQPfIgI387xmUjRUwIeJi_fXB&sz=w1000 | https://drive.google.com/file/d/19aGB7slFQPfIgI387xmUjRUwIeJi_fXB/view?usp=drive_link
2024-09-06 | Al Shamkhah-Majlis-P6 | P6 | MJ-09 | 50 | 743 | 793 | 1) Excavation for Majlis Building: Commenced on 5th September 2024. Shuttering and scaffolding materials have been mobilized at the site. 2) Baseline Programme : Shamkha Cost Loaded program shall be submitted on 13-Sep-24. 3) Provision of Welfare Facilities: Ablution areas, drinking water cooler, and smoking zone are completed. Rest area and prayer room are in progress. 4) Site Offices for Client and Consultant: Foundation work is completed, portacabin fabrication in progress, with delivery expected by 13th September. 5) For Shoring and Piling Works: Equipment's Mobilized at site. Shoring Excavation In Progress for Guide Wall. 6) Mosque Construction: Grading Works in Progress. 7) Engineering Works Submissions: The submissions for prequalification's, material approvals, and shop drawings are actively in progress. | *IFC drawings were issued on 12th September 2024 *The contractor has to submit baseline planning package in compliance with Engineer comments issued for R00 submissio. * Dewatering Engineering Works to be initiated as a proactive approcah to mitigate the risk of GWT. * Finalization of Execution Plan for Shoring & Piling Works. AIC Schedule a meeting on Tuesday 17 Sep, 2024, in this regard and requsted contractor to submit program of works for execition of piling & shoring works in due consultation with Specialized subcontractor. | 0% | 0% | 0% | Engineering Works | 2026-01-31 |  |  | 2024-09-13 | 1) Issuance of Night Shift Permit 2)Possibility of High Water Table 3)Execution Plan Finalization for Piling & Shoring Works | 1) Issuance of Night Shift Permit 2)Possibility of High Water Table 3)Execution Plan Finalization for Piling & Shoring Works | • Shamkha Cost Loaded Program Submission on 13-Sep-24 • Client & Consultant Office Porta Cabin Installation • Workers Rest Area Shed Fabrication • Access Road Construction • Excavation for Majlis • Shelter Area Shoring Excavation in Progress | 356759501 |  | 356759501 | 3645800 |  | 360405301 |  |  | https://drive.google.com/thumbnail?id=1N22qwC0vrqCOzXJ46mu1iA931nPdVUdV&sz=w1000 | https://drive.google.com/file/d/1N22qwC0vrqCOzXJ46mu1iA931nPdVUdV/view?usp=drive_link | https://drive.google.com/thumbnail?id=1AWxAuRE6Vg50Zv6iozolSxiyZ-AwV82_&sz=w1000 | https://drive.google.com/file/d/1AWxAuRE6Vg50Zv6iozolSxiyZ-AwV82_/view?usp=drive_link | https://drive.google.com/thumbnail?id=19aGB7slFQPfIgI387xmUjRUwIeJi_fXB&sz=w1000 | https://drive.google.com/file/d/19aGB7slFQPfIgI387xmUjRUwIeJi_fXB/view?usp=drive_link
2024-09-06 | Al Shamkhah-Majlis-P6 | P6 | MJ-09 | 50 | 743 | 793 | 1) Excavation for Majlis Building: Commenced on 5th September 2024. Shuttering and scaffolding materials have been mobilized at the site. 2) Baseline Programme : Shamkha Cost Loaded program shall be submitted on 13-Sep-24. 3) Provision of Welfare Facilities: Ablution areas, drinking water cooler, and smoking zone are completed. Rest area and prayer room are in progress. 4) Site Offices for Client and Consultant: Foundation work is completed, portacabin fabrication in progress, with delivery expected by 13th September. 5) For Shoring and Piling Works: Equipment's Mobilized at site. Shoring Excavation In Progress for Guide Wall. 6) Mosque Construction: Grading Works in Progress. 7) Engineering Works Submissions: The submissions for prequalification's, material approvals, and shop drawings are actively in progress. | *IFC drawings were issued on 12th September 2024 *The contractor has to submit baseline planning package in compliance with Engineer comments issued for R00 submissio. * Dewatering Engineering Works to be initiated as a proactive approcah to mitigate the risk of GWT. * Finalization of Execution Plan for Shoring & Piling Works. AIC Schedule a meeting on Tuesday 17 Sep, 2024, in this regard and requsted contractor to submit program of works for execition of piling & shoring works in due consultation with Specialized subcontractor. | 0% | 0% | 0% | Shelter Construction | 2026-09-15 |  |  | 2024-09-13 | 1) Issuance of Night Shift Permit 2)Possibility of High Water Table 3)Execution Plan Finalization for Piling & Shoring Works | 1) Action required 2) Proactive Measures shall be adopted 3) Specialized Contractors will Provide Execution Plan | • Shamkha Cost Loaded Program Submission on 13-Sep-24 • Client & Consultant Office Porta Cabin Installation • Workers Rest Area Shed Fabrication • Access Road Construction • Excavation for Majlis • Shelter Area Shoring Excavation in Progress | 356759501 |  | 356759501 | 3645800 |  | 360405301 |  |  | https://drive.google.com/thumbnail?id=1N22qwC0vrqCOzXJ46mu1iA931nPdVUdV&sz=w1000 | https://drive.google.com/file/d/1N22qwC0vrqCOzXJ46mu1iA931nPdVUdV/view?usp=drive_link | https://drive.google.com/thumbnail?id=1AWxAuRE6Vg50Zv6iozolSxiyZ-AwV82_&sz=w1000 | https://drive.google.com/file/d/1AWxAuRE6Vg50Zv6iozolSxiyZ-AwV82_/view?usp=drive_link | https://drive.google.com/thumbnail?id=19aGB7slFQPfIgI387xmUjRUwIeJi_fXB&sz=w1000 | https://drive.google.com/file/d/19aGB7slFQPfIgI387xmUjRUwIeJi_fXB/view?usp=drive_link
2024-09-06 | Al Shamkhah-Majlis-P6 | P6 | MJ-09 | 50 | 743 | 793 | 1) Excavation for Majlis Building: Commenced on 5th September 2024. Shuttering and scaffolding materials have been mobilized at the site. 2) Baseline Programme : Shamkha Cost Loaded program shall be submitted on 13-Sep-24. 3) Provision of Welfare Facilities: Ablution areas, drinking water cooler, and smoking zone are completed. Rest area and prayer room are in progress. 4) Site Offices for Client and Consultant: Foundation work is completed, portacabin fabrication in progress, with delivery expected by 13th September. 5) For Shoring and Piling Works: Equipment's Mobilized at site. Shoring Excavation In Progress for Guide Wall. 6) Mosque Construction: Grading Works in Progress. 7) Engineering Works Submissions: The submissions for prequalification's, material approvals, and shop drawings are actively in progress. | *IFC drawings were issued on 12th September 2024 *The contractor has to submit baseline planning package in compliance with Engineer comments issued for R00 submissio. * Dewatering Engineering Works to be initiated as a proactive approcah to mitigate the risk of GWT. * Finalization of Execution Plan for Shoring & Piling Works. AIC Schedule a meeting on Tuesday 17 Sep, 2024, in this regard and requsted contractor to submit program of works for execition of piling & shoring works in due consultation with Specialized subcontractor. | 0% | 0% | 0% | Mosque Constuction | 2026-03-09 |  |  | 2024-09-13 | 1) Issuance of Night Shift Permit 2)Possibility of High Water Table 3)Execution Plan Finalization for Piling & Shoring Works | 1) Issuance of Night Shift Permit 2)Possibility of High Water Table 3)Execution Plan Finalization for Piling & Shoring Works | • Shamkha Cost Loaded Program Submission on 13-Sep-24 • Client & Consultant Office Porta Cabin Installation • Workers Rest Area Shed Fabrication • Access Road Construction • Excavation for Majlis • Shelter Area Shoring Excavation in Progress | 356759501 |  | 356759501 | 3645800 |  | 360405301 |  |  | https://drive.google.com/thumbnail?id=1N22qwC0vrqCOzXJ46mu1iA931nPdVUdV&sz=w1000 | https://drive.google.com/file/d/1N22qwC0vrqCOzXJ46mu1iA931nPdVUdV/view?usp=drive_link | https://drive.google.com/thumbnail?id=1AWxAuRE6Vg50Zv6iozolSxiyZ-AwV82_&sz=w1000 | https://drive.google.com/file/d/1AWxAuRE6Vg50Zv6iozolSxiyZ-AwV82_/view?usp=drive_link | https://drive.google.com/thumbnail?id=19aGB7slFQPfIgI387xmUjRUwIeJi_fXB&sz=w1000 | https://drive.google.com/file/d/19aGB7slFQPfIgI387xmUjRUwIeJi_fXB/view?usp=drive_link
2024-09-06 | Al Shamkhah-Majlis-P6 | P6 | MJ-09 | 50 | 743 | 793 | 1) Excavation for Majlis Building: Commenced on 5th September 2024. Shuttering and scaffolding materials have been mobilized at the site. 2) Baseline Programme : Shamkha Cost Loaded program shall be submitted on 13-Sep-24. 3) Provision of Welfare Facilities: Ablution areas, drinking water cooler, and smoking zone are completed. Rest area and prayer room are in progress. 4) Site Offices for Client and Consultant: Foundation work is completed, portacabin fabrication in progress, with delivery expected by 13th September. 5) For Shoring and Piling Works: Equipment's Mobilized at site. Shoring Excavation In Progress for Guide Wall. 6) Mosque Construction: Grading Works in Progress. 7) Engineering Works Submissions: The submissions for prequalification's, material approvals, and shop drawings are actively in progress. | *IFC drawings were issued on 12th September 2024 *The contractor has to submit baseline planning package in compliance with Engineer comments issued for R00 submissio. * Dewatering Engineering Works to be initiated as a proactive approcah to mitigate the risk of GWT. * Finalization of Execution Plan for Shoring & Piling Works. AIC Schedule a meeting on Tuesday 17 Sep, 2024, in this regard and requsted contractor to submit program of works for execition of piling & shoring works in due consultation with Specialized subcontractor. | 0% | 0% | 0% | Majlis Construction | 2026-07-09 |  |  | 2024-09-13 | 1) Issuance of Night Shift Permit 2)Possibility of High Water Table 3)Execution Plan Finalization for Piling & Shoring Works | 1) Action required 2) Proactive Measures shall be adopted 3) Specialized Contractors will Provide Execution Plan | • Shamkha Cost Loaded Program Submission on 13-Sep-24 • Client & Consultant Office Porta Cabin Installation • Workers Rest Area Shed Fabrication • Access Road Construction • Excavation for Majlis • Shelter Area Shoring Excavation in Progress | 356759501 |  | 356759501 | 3645800 |  | 360405301 |  |  | https://drive.google.com/thumbnail?id=1N22qwC0vrqCOzXJ46mu1iA931nPdVUdV&sz=w1000 | https://drive.google.com/file/d/1N22qwC0vrqCOzXJ46mu1iA931nPdVUdV/view?usp=drive_link | https://drive.google.com/thumbnail?id=1AWxAuRE6Vg50Zv6iozolSxiyZ-AwV82_&sz=w1000 | https://drive.google.com/file/d/1AWxAuRE6Vg50Zv6iozolSxiyZ-AwV82_/view?usp=drive_link | https://drive.google.com/thumbnail?id=19aGB7slFQPfIgI387xmUjRUwIeJi_fXB&sz=w1000 | https://drive.google.com/file/d/19aGB7slFQPfIgI387xmUjRUwIeJi_fXB/view?usp=drive_link
2024-09-06 | Al Shamkhah-Majlis-P6 | P6 | MJ-09 | 50 | 743 | 793 | 1) Excavation for Majlis Building: Commenced on 5th September 2024. Shuttering and scaffolding materials have been mobilized at the site. 2) Baseline Programme : Shamkha Cost Loaded program shall be submitted on 13-Sep-24. 3) Provision of Welfare Facilities: Ablution areas, drinking water cooler, and smoking zone are completed. Rest area and prayer room are in progress. 4) Site Offices for Client and Consultant: Foundation work is completed, portacabin fabrication in progress, with delivery expected by 13th September. 5) For Shoring and Piling Works: Equipment's Mobilized at site. Shoring Excavation In Progress for Guide Wall. 6) Mosque Construction: Grading Works in Progress. 7) Engineering Works Submissions: The submissions for prequalification's, material approvals, and shop drawings are actively in progress. | *IFC drawings were issued on 12th September 2024 *The contractor has to submit baseline planning package in compliance with Engineer comments issued for R00 submissio. * Dewatering Engineering Works to be initiated as a proactive approcah to mitigate the risk of GWT. * Finalization of Execution Plan for Shoring & Piling Works. AIC Schedule a meeting on Tuesday 17 Sep, 2024, in this regard and requsted contractor to submit program of works for execition of piling & shoring works in due consultation with Specialized subcontractor. | 0% | 0% | 0% | Ablution Construction | 2026-01-09 |  |  | 2024-09-13 | 1) Issuance of Night Shift Permit 2)Possibility of High Water Table 3)Execution Plan Finalization for Piling & Shoring Works | 1) Issuance of Night Shift Permit 2)Possibility of High Water Table 3)Execution Plan Finalization for Piling & Shoring Works | • Shamkha Cost Loaded Program Submission on 13-Sep-24 • Client & Consultant Office Porta Cabin Installation • Workers Rest Area Shed Fabrication • Access Road Construction • Excavation for Majlis • Shelter Area Shoring Excavation in Progress | 356759501 |  | 356759501 | 3645800 |  | 360405301 |  |  | https://drive.google.com/thumbnail?id=1N22qwC0vrqCOzXJ46mu1iA931nPdVUdV&sz=w1000 | https://drive.google.com/file/d/1N22qwC0vrqCOzXJ46mu1iA931nPdVUdV/view?usp=drive_link | https://drive.google.com/thumbnail?id=1AWxAuRE6Vg50Zv6iozolSxiyZ-AwV82_&sz=w1000 | https://drive.google.com/file/d/1AWxAuRE6Vg50Zv6iozolSxiyZ-AwV82_/view?usp=drive_link | https://drive.google.com/thumbnail?id=19aGB7slFQPfIgI387xmUjRUwIeJi_fXB&sz=w1000 | https://drive.google.com/file/d/19aGB7slFQPfIgI387xmUjRUwIeJi_fXB/view?usp=drive_link
2024-09-06 | Al Shamkhah-Majlis-P6 | P6 | MJ-09 | 50 | 743 | 793 | 1) Excavation for Majlis Building: Commenced on 5th September 2024. Shuttering and scaffolding materials have been mobilized at the site. 2) Baseline Programme : Shamkha Cost Loaded program shall be submitted on 13-Sep-24. 3) Provision of Welfare Facilities: Ablution areas, drinking water cooler, and smoking zone are completed. Rest area and prayer room are in progress. 4) Site Offices for Client and Consultant: Foundation work is completed, portacabin fabrication in progress, with delivery expected by 13th September. 5) For Shoring and Piling Works: Equipment's Mobilized at site. Shoring Excavation In Progress for Guide Wall. 6) Mosque Construction: Grading Works in Progress. 7) Engineering Works Submissions: The submissions for prequalification's, material approvals, and shop drawings are actively in progress. | *IFC drawings were issued on 12th September 2024 *The contractor has to submit baseline planning package in compliance with Engineer comments issued for R00 submissio. * Dewatering Engineering Works to be initiated as a proactive approcah to mitigate the risk of GWT. * Finalization of Execution Plan for Shoring & Piling Works. AIC Schedule a meeting on Tuesday 17 Sep, 2024, in this regard and requsted contractor to submit program of works for execition of piling & shoring works in due consultation with Specialized subcontractor. | 0% | 0% | 0% | Imam House Construction | 2026-07-22 |  |  | 2024-09-13 | 1) Issuance of Night Shift Permit 2)Possibility of High Water Table 3)Execution Plan Finalization for Piling & Shoring Works | 1) Action required 2) Proactive Measures shall be adopted 3) Specialized Contractors will Provide Execution Plan | • Shamkha Cost Loaded Program Submission on 13-Sep-24 • Client & Consultant Office Porta Cabin Installation • Workers Rest Area Shed Fabrication • Access Road Construction • Excavation for Majlis • Shelter Area Shoring Excavation in Progress | 356759501 |  | 356759501 | 3645800 |  | 360405301 |  |  | https://drive.google.com/thumbnail?id=1N22qwC0vrqCOzXJ46mu1iA931nPdVUdV&sz=w1000 | https://drive.google.com/file/d/1N22qwC0vrqCOzXJ46mu1iA931nPdVUdV/view?usp=drive_link | https://drive.google.com/thumbnail?id=1AWxAuRE6Vg50Zv6iozolSxiyZ-AwV82_&sz=w1000 | https://drive.google.com/file/d/1AWxAuRE6Vg50Zv6iozolSxiyZ-AwV82_/view?usp=drive_link | https://drive.google.com/thumbnail?id=19aGB7slFQPfIgI387xmUjRUwIeJi_fXB&sz=w1000 | https://drive.google.com/file/d/19aGB7slFQPfIgI387xmUjRUwIeJi_fXB/view?usp=drive_link
2024-09-06 | Al Shamkhah-Majlis-P6 | P6 | MJ-09 | 50 | 743 | 793 | 1) Excavation for Majlis Building: Commenced on 5th September 2024. Shuttering and scaffolding materials have been mobilized at the site. 2) Baseline Programme : Shamkha Cost Loaded program shall be submitted on 13-Sep-24. 3) Provision of Welfare Facilities: Ablution areas, drinking water cooler, and smoking zone are completed. Rest area and prayer room are in progress. 4) Site Offices for Client and Consultant: Foundation work is completed, portacabin fabrication in progress, with delivery expected by 13th September. 5) For Shoring and Piling Works: Equipment's Mobilized at site. Shoring Excavation In Progress for Guide Wall. 6) Mosque Construction: Grading Works in Progress. 7) Engineering Works Submissions: The submissions for prequalification's, material approvals, and shop drawings are actively in progress. | *IFC drawings were issued on 12th September 2024 *The contractor has to submit baseline planning package in compliance with Engineer comments issued for R00 submissio. * Dewatering Engineering Works to be initiated as a proactive approcah to mitigate the risk of GWT. * Finalization of Execution Plan for Shoring & Piling Works. AIC Schedule a meeting on Tuesday 17 Sep, 2024, in this regard and requsted contractor to submit program of works for execition of piling & shoring works in due consultation with Specialized subcontractor. | 0% | 0% | 0% | Pump Room Construction | 2026-07-31 |  |  | 2024-09-13 | 1) Issuance of Night Shift Permit 2)Possibility of High Water Table 3)Execution Plan Finalization for Piling & Shoring Works | 1) Issuance of Night Shift Permit 2)Possibility of High Water Table 3)Execution Plan Finalization for Piling & Shoring Works | • Shamkha Cost Loaded Program Submission on 13-Sep-24 • Client & Consultant Office Porta Cabin Installation • Workers Rest Area Shed Fabrication • Access Road Construction • Excavation for Majlis • Shelter Area Shoring Excavation in Progress | 356759501 |  | 356759501 | 3645800 |  | 360405301 |  |  | https://drive.google.com/thumbnail?id=1N22qwC0vrqCOzXJ46mu1iA931nPdVUdV&sz=w1000 | https://drive.google.com/file/d/1N22qwC0vrqCOzXJ46mu1iA931nPdVUdV/view?usp=drive_link | https://drive.google.com/thumbnail?id=1AWxAuRE6Vg50Zv6iozolSxiyZ-AwV82_&sz=w1000 | https://drive.google.com/file/d/1AWxAuRE6Vg50Zv6iozolSxiyZ-AwV82_/view?usp=drive_link | https://drive.google.com/thumbnail?id=19aGB7slFQPfIgI387xmUjRUwIeJi_fXB&sz=w1000 | https://drive.google.com/file/d/19aGB7slFQPfIgI387xmUjRUwIeJi_fXB/view?usp=drive_link
2024-09-06 | Al Shamkhah-Majlis-P6 | P6 | MJ-09 | 50 | 743 | 793 | 1) Excavation for Majlis Building: Commenced on 5th September 2024. Shuttering and scaffolding materials have been mobilized at the site. 2) Baseline Programme : Shamkha Cost Loaded program shall be submitted on 13-Sep-24. 3) Provision of Welfare Facilities: Ablution areas, drinking water cooler, and smoking zone are completed. Rest area and prayer room are in progress. 4) Site Offices for Client and Consultant: Foundation work is completed, portacabin fabrication in progress, with delivery expected by 13th September. 5) For Shoring and Piling Works: Equipment's Mobilized at site. Shoring Excavation In Progress for Guide Wall. 6) Mosque Construction: Grading Works in Progress. 7) Engineering Works Submissions: The submissions for prequalification's, material approvals, and shop drawings are actively in progress. | *IFC drawings were issued on 12th September 2024 *The contractor has to submit baseline planning package in compliance with Engineer comments issued for R00 submissio. * Dewatering Engineering Works to be initiated as a proactive approcah to mitigate the risk of GWT. * Finalization of Execution Plan for Shoring & Piling Works. AIC Schedule a meeting on Tuesday 17 Sep, 2024, in this regard and requsted contractor to submit program of works for execition of piling & shoring works in due consultation with Specialized subcontractor. | 0% | 0% | 0% | Sub Station Construction | 2025-05-12 |  |  | 2024-09-13 | 1) Issuance of Night Shift Permit 2)Possibility of High Water Table 3)Execution Plan Finalization for Piling & Shoring Works | 1) Action required 2) Proactive Measures shall be adopted 3) Specialized Contractors will Provide Execution Plan | • Shamkha Cost Loaded Program Submission on 13-Sep-24 • Client & Consultant Office Porta Cabin Installation • Workers Rest Area Shed Fabrication • Access Road Construction • Excavation for Majlis • Shelter Area Shoring Excavation in Progress | 356759501 |  | 356759501 | 3645800 |  | 360405301 |  |  | https://drive.google.com/thumbnail?id=1N22qwC0vrqCOzXJ46mu1iA931nPdVUdV&sz=w1000 | https://drive.google.com/file/d/1N22qwC0vrqCOzXJ46mu1iA931nPdVUdV/view?usp=drive_link | https://drive.google.com/thumbnail?id=1AWxAuRE6Vg50Zv6iozolSxiyZ-AwV82_&sz=w1000 | https://drive.google.com/file/d/1AWxAuRE6Vg50Zv6iozolSxiyZ-AwV82_/view?usp=drive_link | https://drive.google.com/thumbnail?id=19aGB7slFQPfIgI387xmUjRUwIeJi_fXB&sz=w1000 | https://drive.google.com/file/d/19aGB7slFQPfIgI387xmUjRUwIeJi_fXB/view?usp=drive_link
2024-09-06 | Al Shamkhah-Majlis-P6 | P6 | MJ-09 | 50 | 743 | 793 | 1) Excavation for Majlis Building: Commenced on 5th September 2024. Shuttering and scaffolding materials have been mobilized at the site. 2) Baseline Programme : Shamkha Cost Loaded program shall be submitted on 13-Sep-24. 3) Provision of Welfare Facilities: Ablution areas, drinking water cooler, and smoking zone are completed. Rest area and prayer room are in progress. 4) Site Offices for Client and Consultant: Foundation work is completed, portacabin fabrication in progress, with delivery expected by 13th September. 5) For Shoring and Piling Works: Equipment's Mobilized at site. Shoring Excavation In Progress for Guide Wall. 6) Mosque Construction: Grading Works in Progress. 7) Engineering Works Submissions: The submissions for prequalification's, material approvals, and shop drawings are actively in progress. | *IFC drawings were issued on 12th September 2024 *The contractor has to submit baseline planning package in compliance with Engineer comments issued for R00 submissio. * Dewatering Engineering Works to be initiated as a proactive approcah to mitigate the risk of GWT. * Finalization of Execution Plan for Shoring & Piling Works. AIC Schedule a meeting on Tuesday 17 Sep, 2024, in this regard and requsted contractor to submit program of works for execition of piling & shoring works in due consultation with Specialized subcontractor. | 0% | 0% | 0% | External Works | 2026-04-14 |  |  | 2024-09-13 | 1) Issuance of Night Shift Permit 2)Possibility of High Water Table 3)Execution Plan Finalization for Piling & Shoring Works | 1) Issuance of Night Shift Permit 2)Possibility of High Water Table 3)Execution Plan Finalization for Piling & Shoring Works | • Shamkha Cost Loaded Program Submission on 13-Sep-24 • Client & Consultant Office Porta Cabin Installation • Workers Rest Area Shed Fabrication • Access Road Construction • Excavation for Majlis • Shelter Area Shoring Excavation in Progress | 356759501 |  | 356759501 | 3645800 |  | 360405301 |  |  | https://drive.google.com/thumbnail?id=1N22qwC0vrqCOzXJ46mu1iA931nPdVUdV&sz=w1000 | https://drive.google.com/file/d/1N22qwC0vrqCOzXJ46mu1iA931nPdVUdV/view?usp=drive_link | https://drive.google.com/thumbnail?id=1AWxAuRE6Vg50Zv6iozolSxiyZ-AwV82_&sz=w1000 | https://drive.google.com/file/d/1AWxAuRE6Vg50Zv6iozolSxiyZ-AwV82_/view?usp=drive_link | https://drive.google.com/thumbnail?id=19aGB7slFQPfIgI387xmUjRUwIeJi_fXB&sz=w1000 | https://drive.google.com/file/d/19aGB7slFQPfIgI387xmUjRUwIeJi_fXB/view?usp=drive_link
2024-09-06 | Al Shamkhah-Majlis-P6 | P6 | MJ-09 | 50 | 743 | 793 | 1) Excavation for Majlis Building: Commenced on 5th September 2024. Shuttering and scaffolding materials have been mobilized at the site. 2) Baseline Programme : Shamkha Cost Loaded program shall be submitted on 13-Sep-24. 3) Provision of Welfare Facilities: Ablution areas, drinking water cooler, and smoking zone are completed. Rest area and prayer room are in progress. 4) Site Offices for Client and Consultant: Foundation work is completed, portacabin fabrication in progress, with delivery expected by 13th September. 5) For Shoring and Piling Works: Equipment's Mobilized at site. Shoring Excavation In Progress for Guide Wall. 6) Mosque Construction: Grading Works in Progress. 7) Engineering Works Submissions: The submissions for prequalification's, material approvals, and shop drawings are actively in progress. | *IFC drawings were issued on 12th September 2024 *The contractor has to submit baseline planning package in compliance with Engineer comments issued for R00 submissio. * Dewatering Engineering Works to be initiated as a proactive approcah to mitigate the risk of GWT. * Finalization of Execution Plan for Shoring & Piling Works. AIC Schedule a meeting on Tuesday 17 Sep, 2024, in this regard and requsted contractor to submit program of works for execition of piling & shoring works in due consultation with Specialized subcontractor. | 0% | 0% | 0% | Testing & Commissioning | 2026-09-21 |  |  | 2024-09-13 | 1) Issuance of Night Shift Permit 2)Possibility of High Water Table 3)Execution Plan Finalization for Piling & Shoring Works | 1) Action required 2) Proactive Measures shall be adopted 3) Specialized Contractors will Provide Execution Plan | • Shamkha Cost Loaded Program Submission on 13-Sep-24 • Client & Consultant Office Porta Cabin Installation • Workers Rest Area Shed Fabrication • Access Road Construction • Excavation for Majlis • Shelter Area Shoring Excavation in Progress | 356759501 |  | 356759501 | 3645800 |  | 360405301 |  |  | https://drive.google.com/thumbnail?id=1N22qwC0vrqCOzXJ46mu1iA931nPdVUdV&sz=w1000 | https://drive.google.com/file/d/1N22qwC0vrqCOzXJ46mu1iA931nPdVUdV/view?usp=drive_link | https://drive.google.com/thumbnail?id=1AWxAuRE6Vg50Zv6iozolSxiyZ-AwV82_&sz=w1000 | https://drive.google.com/file/d/1AWxAuRE6Vg50Zv6iozolSxiyZ-AwV82_/view?usp=drive_link | https://drive.google.com/thumbnail?id=19aGB7slFQPfIgI387xmUjRUwIeJi_fXB&sz=w1000 | https://drive.google.com/file/d/19aGB7slFQPfIgI387xmUjRUwIeJi_fXB/view?usp=drive_link
2024-09-06 | Al Shamkhah-Majlis-P6 | P6 | MJ-09 | 50 | 743 | 793 | 1) Excavation for Majlis Building: Commenced on 5th September 2024. Shuttering and scaffolding materials have been mobilized at the site. 2) Baseline Programme : Shamkha Cost Loaded program shall be submitted on 13-Sep-24. 3) Provision of Welfare Facilities: Ablution areas, drinking water cooler, and smoking zone are completed. Rest area and prayer room are in progress. 4) Site Offices for Client and Consultant: Foundation work is completed, portacabin fabrication in progress, with delivery expected by 13th September. 5) For Shoring and Piling Works: Equipment's Mobilized at site. Shoring Excavation In Progress for Guide Wall. 6) Mosque Construction: Grading Works in Progress. 7) Engineering Works Submissions: The submissions for prequalification's, material approvals, and shop drawings are actively in progress. | *IFC drawings were issued on 12th September 2024 *The contractor has to submit baseline planning package in compliance with Engineer comments issued for R00 submissio. * Dewatering Engineering Works to be initiated as a proactive approcah to mitigate the risk of GWT. * Finalization of Execution Plan for Shoring & Piling Works. AIC Schedule a meeting on Tuesday 17 Sep, 2024, in this regard and requsted contractor to submit program of works for execition of piling & shoring works in due consultation with Specialized subcontractor. | 0% | 0% | 0% | Authorities Approvals | 2026-10-09 |  |  | 2024-09-13 | 1) Issuance of Night Shift Permit 2)Possibility of High Water Table 3)Execution Plan Finalization for Piling & Shoring Works | 1) Issuance of Night Shift Permit 2)Possibility of High Water Table 3)Execution Plan Finalization for Piling & Shoring Works | • Shamkha Cost Loaded Program Submission on 13-Sep-24 • Client & Consultant Office Porta Cabin Installation • Workers Rest Area Shed Fabrication • Access Road Construction • Excavation for Majlis • Shelter Area Shoring Excavation in Progress | 356759501 |  | 356759501 | 3645800 |  | 360405301 |  |  | https://drive.google.com/thumbnail?id=1N22qwC0vrqCOzXJ46mu1iA931nPdVUdV&sz=w1000 | https://drive.google.com/file/d/1N22qwC0vrqCOzXJ46mu1iA931nPdVUdV/view?usp=drive_link | https://drive.google.com/thumbnail?id=1AWxAuRE6Vg50Zv6iozolSxiyZ-AwV82_&sz=w1000 | https://drive.google.com/file/d/1AWxAuRE6Vg50Zv6iozolSxiyZ-AwV82_/view?usp=drive_link | https://drive.google.com/thumbnail?id=19aGB7slFQPfIgI387xmUjRUwIeJi_fXB&sz=w1000 | https://drive.google.com/file/d/19aGB7slFQPfIgI387xmUjRUwIeJi_fXB/view?usp=drive_link
2024-09-06 | Al Shamkhah-Majlis-P6 | P6 | MJ-09 | 50 | 743 | 793 | 1) Excavation for Majlis Building: Commenced on 5th September 2024. Shuttering and scaffolding materials have been mobilized at the site. 2) Baseline Programme : Shamkha Cost Loaded program shall be submitted on 13-Sep-24. 3) Provision of Welfare Facilities: Ablution areas, drinking water cooler, and smoking zone are completed. Rest area and prayer room are in progress. 4) Site Offices for Client and Consultant: Foundation work is completed, portacabin fabrication in progress, with delivery expected by 13th September. 5) For Shoring and Piling Works: Equipment's Mobilized at site. Shoring Excavation In Progress for Guide Wall. 6) Mosque Construction: Grading Works in Progress. 7) Engineering Works Submissions: The submissions for prequalification's, material approvals, and shop drawings are actively in progress. | *IFC drawings were issued on 12th September 2024 *The contractor has to submit baseline planning package in compliance with Engineer comments issued for R00 submissio. * Dewatering Engineering Works to be initiated as a proactive approcah to mitigate the risk of GWT. * Finalization of Execution Plan for Shoring & Piling Works. AIC Schedule a meeting on Tuesday 17 Sep, 2024, in this regard and requsted contractor to submit program of works for execition of piling & shoring works in due consultation with Specialized subcontractor. | 0% | 0% | 0% | Substantial Completion | 2026-09-23 |  |  | 2024-09-13 | 1) Issuance of Night Shift Permit 2)Possibility of High Water Table 3)Execution Plan Finalization for Piling & Shoring Works | 1) Action required 2) Proactive Measures shall be adopted 3) Specialized Contractors will Provide Execution Plan | • Shamkha Cost Loaded Program Submission on 13-Sep-24 • Client & Consultant Office Porta Cabin Installation • Workers Rest Area Shed Fabrication • Access Road Construction • Excavation for Majlis • Shelter Area Shoring Excavation in Progress | 356759501 |  | 356759501 | 3645800 |  | 360405301 |  |  | https://drive.google.com/thumbnail?id=1N22qwC0vrqCOzXJ46mu1iA931nPdVUdV&sz=w1000 | https://drive.google.com/file/d/1N22qwC0vrqCOzXJ46mu1iA931nPdVUdV/view?usp=drive_link | https://drive.google.com/thumbnail?id=1AWxAuRE6Vg50Zv6iozolSxiyZ-AwV82_&sz=w1000 | https://drive.google.com/file/d/1AWxAuRE6Vg50Zv6iozolSxiyZ-AwV82_/view?usp=drive_link | https://drive.google.com/thumbnail?id=19aGB7slFQPfIgI387xmUjRUwIeJi_fXB&sz=w1000 | https://drive.google.com/file/d/19aGB7slFQPfIgI387xmUjRUwIeJi_fXB/view?usp=drive_link
2024-09-06 | Zayed City-Majlis-P17 | P17 | MJ-04 | 103 | 627 | 730 | • Shoring guide is Completed • Secant piles is Completed | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. | 8.68% | 8.99% | 0.31% | Commencement Date | 2024-06-03 | 2024-06-03 |  | 2024-09-13 | • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval (if any) for Contractor's Pile Design. • Design update (if any), in compliance with sevene comments | • Workshop meetings held with MAK & bidders to expedite bidders proposals re-submission. • Coordinate with sevene for ADM review schedule. • Design team submitted to sevene on 12 Sep.2024 | • Casting of Capping beam • Starting of Raft Piles. | 106953287.35 | 0 | 106953287.35 | 3824490.97 | 0 | 110777778.32 | 10680390 | 199302.08 | https://drive.google.com/thumbnail?id=1C77z3tm5EXrMVDwQXL6nGlcUbobUc3K6&sz=w1000 | https://drive.google.com/file/d/1C77z3tm5EXrMVDwQXL6nGlcUbobUc3K6/view | https://drive.google.com/thumbnail?id=1De6vO_A2TlUNz8pj1sCUy_mHHl1A_xUW&sz=w1000 | https://drive.google.com/file/d/1De6vO_A2TlUNz8pj1sCUy_mHHl1A_xUW/view | https://drive.google.com/thumbnail?id=1him6ZDHLJLy-eeKVRJfMXKdfGKVGBhI3&sz=w1000 | https://drive.google.com/file/d/1him6ZDHLJLy-eeKVRJfMXKdfGKVGBhI3/view
2024-09-06 | Zayed City-Majlis-P17 | P17 | MJ-04 | 103 | 627 | 730 | • Shoring guide is Completed • Secant piles is Completed | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. | 8.68% | 8.99% | 0.31% | Construction Permit | 2024-06-12 | 2024-05-27 |  | 2024-09-06 | • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval (if any) for Contractor's Pile Design. • Design update (if any), in compliance with sevene comments | • Workshop meetings held with MAK & bidders to expedite bidders proposals re-submission. • Coordinate with sevene for ADM review schedule. • Design team submitted to sevene on 12 Sep.2024 | • Casting of Capping beam • Starting of Raft Piles. | 106953287.35 | 0 | 106953287.35 | 3824490.97 | 0 | 110777778.32 | 10680390 | 199302.08 | https://drive.google.com/thumbnail?id=1C77z3tm5EXrMVDwQXL6nGlcUbobUc3K6&sz=w1000 | https://drive.google.com/file/d/1C77z3tm5EXrMVDwQXL6nGlcUbobUc3K6/view | https://drive.google.com/thumbnail?id=1De6vO_A2TlUNz8pj1sCUy_mHHl1A_xUW&sz=w1000 | https://drive.google.com/file/d/1De6vO_A2TlUNz8pj1sCUy_mHHl1A_xUW/view | https://drive.google.com/thumbnail?id=1him6ZDHLJLy-eeKVRJfMXKdfGKVGBhI3&sz=w1000 | https://drive.google.com/file/d/1him6ZDHLJLy-eeKVRJfMXKdfGKVGBhI3/view
2024-09-06 | Zayed City-Majlis-P17 | P17 | MJ-04 | 103 | 627 | 730 | • Shoring guide is Completed • Secant piles is Completed | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. | 8.68% | 8.99% | 0.31% | Site Mobilization | 2024-07-10 | 2024-08-15 | 2024-08-15 | 2024-09-06 | • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval (if any) for Contractor's Pile Design. • Design update (if any), in compliance with sevene comments | • Workshop meetings held with MAK & bidders to expedite bidders proposals re-submission. • Coordinate with sevene for ADM review schedule. • Design team submitted to sevene on 12 Sep.2024 | • Casting of Capping beam • Starting of Raft Piles. | 106953287.35 | 0 | 106953287.35 | 3824490.97 | 0 | 110777778.32 | 10680390 | 199302.08 | https://drive.google.com/thumbnail?id=1C77z3tm5EXrMVDwQXL6nGlcUbobUc3K6&sz=w1000 | https://drive.google.com/file/d/1C77z3tm5EXrMVDwQXL6nGlcUbobUc3K6/view | https://drive.google.com/thumbnail?id=1De6vO_A2TlUNz8pj1sCUy_mHHl1A_xUW&sz=w1000 | https://drive.google.com/file/d/1De6vO_A2TlUNz8pj1sCUy_mHHl1A_xUW/view | https://drive.google.com/thumbnail?id=1him6ZDHLJLy-eeKVRJfMXKdfGKVGBhI3&sz=w1000 | https://drive.google.com/file/d/1him6ZDHLJLy-eeKVRJfMXKdfGKVGBhI3/view
2024-09-06 | Zayed City-Majlis-P17 | P17 | MJ-04 | 103 | 627 | 730 | • Shoring guide is Completed • Secant piles is Completed | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. | 8.68% | 8.99% | 0.31% | Shoring Drilling & Casting | 2024-09-30 |  | 2024-09-30 | 2024-09-06 | • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval (if any) for Contractor's Pile Design. • Design update (if any), in compliance with sevene comments | • Workshop meetings held with MAK & bidders to expedite bidders proposals re-submission. • Coordinate with sevene for ADM review schedule. • Design team submitted to sevene on 12 Sep.2024 | • Casting of Capping beam • Starting of Raft Piles. | 106953287.35 | 0 | 106953287.35 | 3824490.97 | 0 | 110777778.32 | 10680390 | 199302.08 | https://drive.google.com/thumbnail?id=1C77z3tm5EXrMVDwQXL6nGlcUbobUc3K6&sz=w1000 | https://drive.google.com/file/d/1C77z3tm5EXrMVDwQXL6nGlcUbobUc3K6/view | https://drive.google.com/thumbnail?id=1De6vO_A2TlUNz8pj1sCUy_mHHl1A_xUW&sz=w1000 | https://drive.google.com/file/d/1De6vO_A2TlUNz8pj1sCUy_mHHl1A_xUW/view | https://drive.google.com/thumbnail?id=1him6ZDHLJLy-eeKVRJfMXKdfGKVGBhI3&sz=w1000 | https://drive.google.com/file/d/1him6ZDHLJLy-eeKVRJfMXKdfGKVGBhI3/view
2024-09-06 | Zayed City-Majlis-P17 | P17 | MJ-04 | 103 | 627 | 730 | • Shoring guide is Completed • Secant piles is Completed | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. | 8.68% | 8.99% | 0.31% | Piling Drilling & Casting | 2024-11-30 |  | 2024-11-30 | 2024-09-06 | • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval (if any) for Contractor's Pile Design. • Design update (if any), in compliance with sevene comments | • Workshop meetings held with MAK & bidders to expedite bidders proposals re-submission. • Coordinate with sevene for ADM review schedule. • Design team submitted to sevene on 12 Sep.2024 | • Casting of Capping beam • Starting of Raft Piles. | 106953287.35 | 0 | 106953287.35 | 3824490.97 | 0 | 110777778.32 | 10680390 | 199302.08 | https://drive.google.com/thumbnail?id=1C77z3tm5EXrMVDwQXL6nGlcUbobUc3K6&sz=w1000 | https://drive.google.com/file/d/1C77z3tm5EXrMVDwQXL6nGlcUbobUc3K6/view | https://drive.google.com/thumbnail?id=1De6vO_A2TlUNz8pj1sCUy_mHHl1A_xUW&sz=w1000 | https://drive.google.com/file/d/1De6vO_A2TlUNz8pj1sCUy_mHHl1A_xUW/view | https://drive.google.com/thumbnail?id=1him6ZDHLJLy-eeKVRJfMXKdfGKVGBhI3&sz=w1000 | https://drive.google.com/file/d/1him6ZDHLJLy-eeKVRJfMXKdfGKVGBhI3/view
2024-09-06 | Zayed City-Majlis-P17 | P17 | MJ-04 | 103 | 627 | 730 | • Shoring guide is Completed • Secant piles is Completed | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. | 8.68% | 8.99% | 0.31% | Excavation | 2025-02-13 |  | 2025-02-13 | 2024-09-06 | • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval (if any) for Contractor's Pile Design. • Design update (if any), in compliance with sevene comments | • Workshop meetings held with MAK & bidders to expedite bidders proposals re-submission. • Coordinate with sevene for ADM review schedule. • Design team submitted to sevene on 12 Sep.2024 | • Casting of Capping beam • Starting of Raft Piles. | 106953287.35 | 0 | 106953287.35 | 3824490.97 | 0 | 110777778.32 | 10680390 | 199302.08 | https://drive.google.com/thumbnail?id=1C77z3tm5EXrMVDwQXL6nGlcUbobUc3K6&sz=w1000 | https://drive.google.com/file/d/1C77z3tm5EXrMVDwQXL6nGlcUbobUc3K6/view | https://drive.google.com/thumbnail?id=1De6vO_A2TlUNz8pj1sCUy_mHHl1A_xUW&sz=w1000 | https://drive.google.com/file/d/1De6vO_A2TlUNz8pj1sCUy_mHHl1A_xUW/view | https://drive.google.com/thumbnail?id=1him6ZDHLJLy-eeKVRJfMXKdfGKVGBhI3&sz=w1000 | https://drive.google.com/file/d/1him6ZDHLJLy-eeKVRJfMXKdfGKVGBhI3/view
2024-09-06 | Zayed City-Majlis-P17 | P17 | MJ-04 | 103 | 627 | 730 | • Shoring guide is Completed • Secant piles is Completed | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. | 8.68% | 8.99% | 0.31% | Substructure | 2025-07-20 |  | 2025-07-20 | 2024-09-06 | • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval (if any) for Contractor's Pile Design. • Design update (if any), in compliance with sevene comments | • Workshop meetings held with MAK & bidders to expedite bidders proposals re-submission. • Coordinate with sevene for ADM review schedule. • Design team submitted to sevene on 12 Sep.2024 | • Casting of Capping beam • Starting of Raft Piles. | 106953287.35 | 0 | 106953287.35 | 3824490.97 | 0 | 110777778.32 | 10680390 | 199302.08 | https://drive.google.com/thumbnail?id=1C77z3tm5EXrMVDwQXL6nGlcUbobUc3K6&sz=w1000 | https://drive.google.com/file/d/1C77z3tm5EXrMVDwQXL6nGlcUbobUc3K6/view | https://drive.google.com/thumbnail?id=1De6vO_A2TlUNz8pj1sCUy_mHHl1A_xUW&sz=w1000 | https://drive.google.com/file/d/1De6vO_A2TlUNz8pj1sCUy_mHHl1A_xUW/view | https://drive.google.com/thumbnail?id=1him6ZDHLJLy-eeKVRJfMXKdfGKVGBhI3&sz=w1000 | https://drive.google.com/file/d/1him6ZDHLJLy-eeKVRJfMXKdfGKVGBhI3/view
2024-09-06 | Zayed City-Majlis-P17 | P17 | MJ-04 | 103 | 627 | 730 | • Shoring guide is Completed • Secant piles is Completed | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. | 8.68% | 8.99% | 0.31% | Superstructure | 2025-11-13 |  | 2025-11-13 | 2024-09-06 | • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval (if any) for Contractor's Pile Design. • Design update (if any), in compliance with sevene comments | • Workshop meetings held with MAK & bidders to expedite bidders proposals re-submission. • Coordinate with sevene for ADM review schedule. • Design team submitted to sevene on 12 Sep.2024 | • Casting of Capping beam • Starting of Raft Piles. | 106953287.35 | 0 | 106953287.35 | 3824490.97 | 0 | 110777778.32 | 10680390 | 199302.08 | https://drive.google.com/thumbnail?id=1C77z3tm5EXrMVDwQXL6nGlcUbobUc3K6&sz=w1000 | https://drive.google.com/file/d/1C77z3tm5EXrMVDwQXL6nGlcUbobUc3K6/view | https://drive.google.com/thumbnail?id=1De6vO_A2TlUNz8pj1sCUy_mHHl1A_xUW&sz=w1000 | https://drive.google.com/file/d/1De6vO_A2TlUNz8pj1sCUy_mHHl1A_xUW/view | https://drive.google.com/thumbnail?id=1him6ZDHLJLy-eeKVRJfMXKdfGKVGBhI3&sz=w1000 | https://drive.google.com/file/d/1him6ZDHLJLy-eeKVRJfMXKdfGKVGBhI3/view
2024-09-06 | Zayed City-Majlis-P17 | P17 | MJ-04 | 103 | 627 | 730 | • Shoring guide is Completed • Secant piles is Completed | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. | 8.68% | 8.99% | 0.31% | MEP & Finishes | 2026-05-08 |  | 2026-05-08 | 2024-09-06 | • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval (if any) for Contractor's Pile Design. • Design update (if any), in compliance with sevene comments | • Workshop meetings held with MAK & bidders to expedite bidders proposals re-submission. • Coordinate with sevene for ADM review schedule. • Design team submitted to sevene on 12 Sep.2024 | • Casting of Capping beam • Starting of Raft Piles. | 106953287.35 | 0 | 106953287.35 | 3824490.97 | 0 | 110777778.32 | 10680390 | 199302.08 | https://drive.google.com/thumbnail?id=1C77z3tm5EXrMVDwQXL6nGlcUbobUc3K6&sz=w1000 | https://drive.google.com/file/d/1C77z3tm5EXrMVDwQXL6nGlcUbobUc3K6/view | https://drive.google.com/thumbnail?id=1De6vO_A2TlUNz8pj1sCUy_mHHl1A_xUW&sz=w1000 | https://drive.google.com/file/d/1De6vO_A2TlUNz8pj1sCUy_mHHl1A_xUW/view | https://drive.google.com/thumbnail?id=1him6ZDHLJLy-eeKVRJfMXKdfGKVGBhI3&sz=w1000 | https://drive.google.com/file/d/1him6ZDHLJLy-eeKVRJfMXKdfGKVGBhI3/view
2024-09-06 | Zayed City-Majlis-P17 | P17 | MJ-04 | 103 | 627 | 730 | • Shoring guide is Completed • Secant piles is Completed | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. | 8.68% | 8.99% | 0.31% | Authorities NOCs/BCC | 2026-05-29 |  | 2026-05-29 | 2024-09-06 | • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval (if any) for Contractor's Pile Design. • Design update (if any), in compliance with sevene comments | • Workshop meetings held with MAK & bidders to expedite bidders proposals re-submission. • Coordinate with sevene for ADM review schedule. • Design team submitted to sevene on 12 Sep.2024 | • Casting of Capping beam • Starting of Raft Piles. | 106953287.35 | 0 | 106953287.35 | 3824490.97 | 0 | 110777778.32 | 10680390 | 199302.08 | https://drive.google.com/thumbnail?id=1C77z3tm5EXrMVDwQXL6nGlcUbobUc3K6&sz=w1000 | https://drive.google.com/file/d/1C77z3tm5EXrMVDwQXL6nGlcUbobUc3K6/view | https://drive.google.com/thumbnail?id=1De6vO_A2TlUNz8pj1sCUy_mHHl1A_xUW&sz=w1000 | https://drive.google.com/file/d/1De6vO_A2TlUNz8pj1sCUy_mHHl1A_xUW/view | https://drive.google.com/thumbnail?id=1him6ZDHLJLy-eeKVRJfMXKdfGKVGBhI3&sz=w1000 | https://drive.google.com/file/d/1him6ZDHLJLy-eeKVRJfMXKdfGKVGBhI3/view
2024-09-06 | Zayed City-Majlis-P17 | P17 | MJ-04 | 103 | 627 | 730 | • Shoring guide is Completed • Secant piles is Completed | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. | 8.68% | 8.99% | 0.31% | External Works | 2026-06-02 |  | 2026-06-02 | 2024-09-06 | • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval (if any) for Contractor's Pile Design. • Design update (if any), in compliance with sevene comments | • Workshop meetings held with MAK & bidders to expedite bidders proposals re-submission. • Coordinate with sevene for ADM review schedule. • Design team submitted to sevene on 12 Sep.2024 | • Casting of Capping beam • Starting of Raft Piles. | 106953287.35 | 0 | 106953287.35 | 3824490.97 | 0 | 110777778.32 | 10680390 | 199302.08 | https://drive.google.com/thumbnail?id=1C77z3tm5EXrMVDwQXL6nGlcUbobUc3K6&sz=w1000 | https://drive.google.com/file/d/1C77z3tm5EXrMVDwQXL6nGlcUbobUc3K6/view | https://drive.google.com/thumbnail?id=1De6vO_A2TlUNz8pj1sCUy_mHHl1A_xUW&sz=w1000 | https://drive.google.com/file/d/1De6vO_A2TlUNz8pj1sCUy_mHHl1A_xUW/view | https://drive.google.com/thumbnail?id=1him6ZDHLJLy-eeKVRJfMXKdfGKVGBhI3&sz=w1000 | https://drive.google.com/file/d/1him6ZDHLJLy-eeKVRJfMXKdfGKVGBhI3/view
2024-09-06 | Zayed City-Majlis-P17 | P17 | MJ-04 | 103 | 627 | 730 | • Shoring guide is Completed • Secant piles is Completed | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. | 8.68% | 8.99% | 0.31% | Testing & Commissioning | 2026-06-02 |  | 2026-06-02 | 2024-09-06 | • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval (if any) for Contractor's Pile Design. • Design update (if any), in compliance with sevene comments | • Workshop meetings held with MAK & bidders to expedite bidders proposals re-submission. • Coordinate with sevene for ADM review schedule. • Design team submitted to sevene on 12 Sep.2024 | • Casting of Capping beam • Starting of Raft Piles. | 106953287.35 | 0 | 106953287.35 | 3824490.97 | 0 | 110777778.32 | 10680390 | 199302.08 | https://drive.google.com/thumbnail?id=1C77z3tm5EXrMVDwQXL6nGlcUbobUc3K6&sz=w1000 | https://drive.google.com/file/d/1C77z3tm5EXrMVDwQXL6nGlcUbobUc3K6/view | https://drive.google.com/thumbnail?id=1De6vO_A2TlUNz8pj1sCUy_mHHl1A_xUW&sz=w1000 | https://drive.google.com/file/d/1De6vO_A2TlUNz8pj1sCUy_mHHl1A_xUW/view | https://drive.google.com/thumbnail?id=1him6ZDHLJLy-eeKVRJfMXKdfGKVGBhI3&sz=w1000 | https://drive.google.com/file/d/1him6ZDHLJLy-eeKVRJfMXKdfGKVGBhI3/view
2024-09-06 | Zayed City-Majlis-P17 | P17 | MJ-04 | 103 | 627 | 730 | • Shoring guide is Completed • Secant piles is Completed | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. | 8.68% | 8.99% | 0.31% | Substantial Completion | 2026-06-02 |  | 2026-06-02 | 2024-09-06 | • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval (if any) for Contractor's Pile Design. • Design update (if any), in compliance with sevene comments | • Workshop meetings held with MAK & bidders to expedite bidders proposals re-submission. • Coordinate with sevene for ADM review schedule. • Design team submitted to sevene on 12 Sep.2024 | • Casting of Capping beam • Starting of Raft Piles. | 106953287.35 | 0 | 106953287.35 | 3824490.97 | 0 | 110777778.32 | 10680390 | 199302.08 | https://drive.google.com/thumbnail?id=1C77z3tm5EXrMVDwQXL6nGlcUbobUc3K6&sz=w1000 | https://drive.google.com/file/d/1C77z3tm5EXrMVDwQXL6nGlcUbobUc3K6/view | https://drive.google.com/thumbnail?id=1De6vO_A2TlUNz8pj1sCUy_mHHl1A_xUW&sz=w1000 | https://drive.google.com/file/d/1De6vO_A2TlUNz8pj1sCUy_mHHl1A_xUW/view | https://drive.google.com/thumbnail?id=1him6ZDHLJLy-eeKVRJfMXKdfGKVGBhI3&sz=w1000 | https://drive.google.com/file/d/1him6ZDHLJLy-eeKVRJfMXKdfGKVGBhI3/view
2024-09-06 | Baniyas-Majlis-P13 | P13 | MJ-05 | 103 | 627 | 730 | • Shoring guide wall Completed. • Secant piles Completed. • AWQAF approved Mosque Design. • ADDC accepted protection of existing FH/ water pipeline. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. & PS diversion of existing utilities at Plot P1. • Mosque design assigned to APG. | 7.49% | 7.99% | 0.5% | Commencement Date | 2024-06-03 | 2024-06-03 |  | 2024-09-13 | • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • Appoint specialist for diversion of existing fire hydrant at Plot P1 (Mosque), to avoid delay in building permit issuance. • ADM approval (if any) for Contractor's Pile Design. • Design update (if any), in compliance with sevene comments | • Workshop meetings held with MAK & bidders to expedite bidders proposals re-submission. • sevene review & endorsement. • Coordinate with sevene for ADM review schedule. • Design team submitted to sevene on 12 Sep.2024 | • Casting of Capping Beam • Starting of Raft piles | 130388712.65 | 0 | 130388712.65 | 4662507.03 | 0 | 135051219.68 | 13053810 | 243591.44 | https://drive.google.com/thumbnail?id=1Ea4IsWWBHCZ29uRy7Zxp0SvMnOmdjCvn&sz=w1000 | https://drive.google.com/file/d/1Ea4IsWWBHCZ29uRy7Zxp0SvMnOmdjCvn/view | https://drive.google.com/thumbnail?id=1gB5Fi3nL6FCTnmd91Ei3_QQJ9QXEVQuG&sz=w1000 | https://drive.google.com/file/d/1gB5Fi3nL6FCTnmd91Ei3_QQJ9QXEVQuG/view | https://drive.google.com/thumbnail?id=1xvK7oL2060tGjomnxIMM_vkytJCIFbUM&sz=w1000 | https://drive.google.com/file/d/1xvK7oL2060tGjomnxIMM_vkytJCIFbUM/view
2024-09-06 | Baniyas-Majlis-P13 | P13 | MJ-05 | 103 | 627 | 730 | • Shoring guide wall Completed. • Secant piles Completed. • AWQAF approved Mosque Design. • ADDC accepted protection of existing FH/ water pipeline. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. & PS diversion of existing utilities at Plot P1. • Mosque design assigned to APG. | 7.49% | 7.99% | 0.5% | Construction Permit | 2024-06-12 | 2024-05-22 |  | 2024-09-13 | • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • Appoint specialist for diversion of existing fire hydrant at Plot P1 (Mosque), to avoid delay in building permit issuance. • ADM approval (if any) for Contractor's Pile Design. • Design update (if any), in compliance with sevene comments | • Workshop meetings held with MAK & bidders to expedite bidders proposals re-submission. • sevene review & endorsement. • Coordinate with sevene for ADM review schedule. • Design team submitted to sevene on 12 Sep.2024 | • Casting of Capping Beam • Starting of Raft piles | 130388712.65 | 0 | 130388712.65 | 4662507.03 | 0 | 135051219.68 | 13053810 | 243591.44 | https://drive.google.com/thumbnail?id=1Ea4IsWWBHCZ29uRy7Zxp0SvMnOmdjCvn&sz=w1000 | https://drive.google.com/file/d/1Ea4IsWWBHCZ29uRy7Zxp0SvMnOmdjCvn/view | https://drive.google.com/thumbnail?id=1gB5Fi3nL6FCTnmd91Ei3_QQJ9QXEVQuG&sz=w1000 | https://drive.google.com/file/d/1gB5Fi3nL6FCTnmd91Ei3_QQJ9QXEVQuG/view | https://drive.google.com/thumbnail?id=1xvK7oL2060tGjomnxIMM_vkytJCIFbUM&sz=w1000 | https://drive.google.com/file/d/1xvK7oL2060tGjomnxIMM_vkytJCIFbUM/view
2024-09-06 | Baniyas-Majlis-P13 | P13 | MJ-05 | 103 | 627 | 730 | • Shoring guide wall Completed. • Secant piles Completed. • AWQAF approved Mosque Design. • ADDC accepted protection of existing FH/ water pipeline. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. & PS diversion of existing utilities at Plot P1. • Mosque design assigned to APG. | 7.49% | 7.99% | 0.5% | Site Mobilization | 2024-07-10 | 2024-08-08 | 2024-08-08 | 2024-09-13 | • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • Appoint specialist for diversion of existing fire hydrant at Plot P1 (Mosque), to avoid delay in building permit issuance. • ADM approval (if any) for Contractor's Pile Design. • Design update (if any), in compliance with sevene comments | • Workshop meetings held with MAK & bidders to expedite bidders proposals re-submission. • sevene review & endorsement. • Coordinate with sevene for ADM review schedule. • Design team submitted to sevene on 12 Sep.2024 | • Casting of Capping Beam • Starting of Raft piles | 130388712.65 | 0 | 130388712.65 | 4662507.03 | 0 | 135051219.68 | 13053810 | 243591.44 | https://drive.google.com/thumbnail?id=1Ea4IsWWBHCZ29uRy7Zxp0SvMnOmdjCvn&sz=w1000 | https://drive.google.com/file/d/1Ea4IsWWBHCZ29uRy7Zxp0SvMnOmdjCvn/view | https://drive.google.com/thumbnail?id=1gB5Fi3nL6FCTnmd91Ei3_QQJ9QXEVQuG&sz=w1000 | https://drive.google.com/file/d/1gB5Fi3nL6FCTnmd91Ei3_QQJ9QXEVQuG/view | https://drive.google.com/thumbnail?id=1xvK7oL2060tGjomnxIMM_vkytJCIFbUM&sz=w1000 | https://drive.google.com/file/d/1xvK7oL2060tGjomnxIMM_vkytJCIFbUM/view
2024-09-06 | Baniyas-Majlis-P13 | P13 | MJ-05 | 103 | 627 | 730 | • Shoring guide wall Completed. • Secant piles Completed. • AWQAF approved Mosque Design. • ADDC accepted protection of existing FH/ water pipeline. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. & PS diversion of existing utilities at Plot P1. • Mosque design assigned to APG. | 7.49% | 7.99% | 0.5% | Shoring Drilling & Casting | 2024-09-28 |  | 2024-09-28 | 2024-09-13 | • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • Appoint specialist for diversion of existing fire hydrant at Plot P1 (Mosque), to avoid delay in building permit issuance. • ADM approval (if any) for Contractor's Pile Design. • Design update (if any), in compliance with sevene comments | • Workshop meetings held with MAK & bidders to expedite bidders proposals re-submission. • sevene review & endorsement. • Coordinate with sevene for ADM review schedule. • Design team submitted to sevene on 12 Sep.2024 | • Casting of Capping Beam • Starting of Raft piles | 130388712.65 | 0 | 130388712.65 | 4662507.03 | 0 | 135051219.68 | 13053810 | 243591.44 | https://drive.google.com/thumbnail?id=1Ea4IsWWBHCZ29uRy7Zxp0SvMnOmdjCvn&sz=w1000 | https://drive.google.com/file/d/1Ea4IsWWBHCZ29uRy7Zxp0SvMnOmdjCvn/view | https://drive.google.com/thumbnail?id=1gB5Fi3nL6FCTnmd91Ei3_QQJ9QXEVQuG&sz=w1000 | https://drive.google.com/file/d/1gB5Fi3nL6FCTnmd91Ei3_QQJ9QXEVQuG/view | https://drive.google.com/thumbnail?id=1xvK7oL2060tGjomnxIMM_vkytJCIFbUM&sz=w1000 | https://drive.google.com/file/d/1xvK7oL2060tGjomnxIMM_vkytJCIFbUM/view
2024-09-06 | Baniyas-Majlis-P13 | P13 | MJ-05 | 103 | 627 | 730 | • Shoring guide wall Completed. • Secant piles Completed. • AWQAF approved Mosque Design. • ADDC accepted protection of existing FH/ water pipeline. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. & PS diversion of existing utilities at Plot P1. • Mosque design assigned to APG. | 7.49% | 7.99% | 0.5% | Piling Drilling & Casting | 2024-11-29 |  | 2024-11-29 | 2024-09-13 | • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • Appoint specialist for diversion of existing fire hydrant at Plot P1 (Mosque), to avoid delay in building permit issuance. • ADM approval (if any) for Contractor's Pile Design. • Design update (if any), in compliance with sevene comments | • Workshop meetings held with MAK & bidders to expedite bidders proposals re-submission. • sevene review & endorsement. • Coordinate with sevene for ADM review schedule. • Design team submitted to sevene on 12 Sep.2024 | • Casting of Capping Beam • Starting of Raft piles | 130388712.65 | 0 | 130388712.65 | 4662507.03 | 0 | 135051219.68 | 13053810 | 243591.44 | https://drive.google.com/thumbnail?id=1Ea4IsWWBHCZ29uRy7Zxp0SvMnOmdjCvn&sz=w1000 | https://drive.google.com/file/d/1Ea4IsWWBHCZ29uRy7Zxp0SvMnOmdjCvn/view | https://drive.google.com/thumbnail?id=1gB5Fi3nL6FCTnmd91Ei3_QQJ9QXEVQuG&sz=w1000 | https://drive.google.com/file/d/1gB5Fi3nL6FCTnmd91Ei3_QQJ9QXEVQuG/view | https://drive.google.com/thumbnail?id=1xvK7oL2060tGjomnxIMM_vkytJCIFbUM&sz=w1000 | https://drive.google.com/file/d/1xvK7oL2060tGjomnxIMM_vkytJCIFbUM/view
2024-09-06 | Baniyas-Majlis-P13 | P13 | MJ-05 | 103 | 627 | 730 | • Shoring guide wall Completed. • Secant piles Completed. • AWQAF approved Mosque Design. • ADDC accepted protection of existing FH/ water pipeline. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. & PS diversion of existing utilities at Plot P1. • Mosque design assigned to APG. | 7.49% | 7.99% | 0.5% | Excavation | 2025-02-12 |  | 2025-02-12 | 2024-09-13 | • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • Appoint specialist for diversion of existing fire hydrant at Plot P1 (Mosque), to avoid delay in building permit issuance. • ADM approval (if any) for Contractor's Pile Design. • Design update (if any), in compliance with sevene comments | • Workshop meetings held with MAK & bidders to expedite bidders proposals re-submission. • sevene review & endorsement. • Coordinate with sevene for ADM review schedule. • Design team submitted to sevene on 12 Sep.2024 | • Casting of Capping Beam • Starting of Raft piles | 130388712.65 | 0 | 130388712.65 | 4662507.03 | 0 | 135051219.68 | 13053810 | 243591.44 | https://drive.google.com/thumbnail?id=1Ea4IsWWBHCZ29uRy7Zxp0SvMnOmdjCvn&sz=w1000 | https://drive.google.com/file/d/1Ea4IsWWBHCZ29uRy7Zxp0SvMnOmdjCvn/view | https://drive.google.com/thumbnail?id=1gB5Fi3nL6FCTnmd91Ei3_QQJ9QXEVQuG&sz=w1000 | https://drive.google.com/file/d/1gB5Fi3nL6FCTnmd91Ei3_QQJ9QXEVQuG/view | https://drive.google.com/thumbnail?id=1xvK7oL2060tGjomnxIMM_vkytJCIFbUM&sz=w1000 | https://drive.google.com/file/d/1xvK7oL2060tGjomnxIMM_vkytJCIFbUM/view
2024-09-06 | Baniyas-Majlis-P13 | P13 | MJ-05 | 103 | 627 | 730 | • Shoring guide wall Completed. • Secant piles Completed. • AWQAF approved Mosque Design. • ADDC accepted protection of existing FH/ water pipeline. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. & PS diversion of existing utilities at Plot P1. • Mosque design assigned to APG. | 7.49% | 7.99% | 0.5% | Substructure | 2025-07-20 |  | 2025-07-20 | 2024-09-13 | • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • Appoint specialist for diversion of existing fire hydrant at Plot P1 (Mosque), to avoid delay in building permit issuance. • ADM approval (if any) for Contractor's Pile Design. • Design update (if any), in compliance with sevene comments | • Workshop meetings held with MAK & bidders to expedite bidders proposals re-submission. • sevene review & endorsement. • Coordinate with sevene for ADM review schedule. • Design team submitted to sevene on 12 Sep.2024 | • Casting of Capping Beam • Starting of Raft piles | 130388712.65 | 0 | 130388712.65 | 4662507.03 | 0 | 135051219.68 | 13053810 | 243591.44 | https://drive.google.com/thumbnail?id=1Ea4IsWWBHCZ29uRy7Zxp0SvMnOmdjCvn&sz=w1000 | https://drive.google.com/file/d/1Ea4IsWWBHCZ29uRy7Zxp0SvMnOmdjCvn/view | https://drive.google.com/thumbnail?id=1gB5Fi3nL6FCTnmd91Ei3_QQJ9QXEVQuG&sz=w1000 | https://drive.google.com/file/d/1gB5Fi3nL6FCTnmd91Ei3_QQJ9QXEVQuG/view | https://drive.google.com/thumbnail?id=1xvK7oL2060tGjomnxIMM_vkytJCIFbUM&sz=w1000 | https://drive.google.com/file/d/1xvK7oL2060tGjomnxIMM_vkytJCIFbUM/view
2024-09-06 | Baniyas-Majlis-P13 | P13 | MJ-05 | 103 | 627 | 730 | • Shoring guide wall Completed. • Secant piles Completed. • AWQAF approved Mosque Design. • ADDC accepted protection of existing FH/ water pipeline. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. & PS diversion of existing utilities at Plot P1. • Mosque design assigned to APG. | 7.49% | 7.99% | 0.5% | Superstructure | 2025-11-06 |  | 2025-11-06 | 2024-09-13 | • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • Appoint specialist for diversion of existing fire hydrant at Plot P1 (Mosque), to avoid delay in building permit issuance. • ADM approval (if any) for Contractor's Pile Design. • Design update (if any), in compliance with sevene comments | • Workshop meetings held with MAK & bidders to expedite bidders proposals re-submission. • sevene review & endorsement. • Coordinate with sevene for ADM review schedule. • Design team submitted to sevene on 12 Sep.2024 | • Casting of Capping Beam • Starting of Raft piles | 130388712.65 | 0 | 130388712.65 | 4662507.03 | 0 | 135051219.68 | 13053810 | 243591.44 | https://drive.google.com/thumbnail?id=1Ea4IsWWBHCZ29uRy7Zxp0SvMnOmdjCvn&sz=w1000 | https://drive.google.com/file/d/1Ea4IsWWBHCZ29uRy7Zxp0SvMnOmdjCvn/view | https://drive.google.com/thumbnail?id=1gB5Fi3nL6FCTnmd91Ei3_QQJ9QXEVQuG&sz=w1000 | https://drive.google.com/file/d/1gB5Fi3nL6FCTnmd91Ei3_QQJ9QXEVQuG/view | https://drive.google.com/thumbnail?id=1xvK7oL2060tGjomnxIMM_vkytJCIFbUM&sz=w1000 | https://drive.google.com/file/d/1xvK7oL2060tGjomnxIMM_vkytJCIFbUM/view
2024-09-06 | Baniyas-Majlis-P13 | P13 | MJ-05 | 103 | 627 | 730 | • Shoring guide wall Completed. • Secant piles Completed. • AWQAF approved Mosque Design. • ADDC accepted protection of existing FH/ water pipeline. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. & PS diversion of existing utilities at Plot P1. • Mosque design assigned to APG. | 7.49% | 7.99% | 0.5% | MEP & Finishes | 2026-05-08 |  | 2026-05-08 | 2024-09-13 | • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • Appoint specialist for diversion of existing fire hydrant at Plot P1 (Mosque), to avoid delay in building permit issuance. • ADM approval (if any) for Contractor's Pile Design. • Design update (if any), in compliance with sevene comments | • Workshop meetings held with MAK & bidders to expedite bidders proposals re-submission. • sevene review & endorsement. • Coordinate with sevene for ADM review schedule. • Design team submitted to sevene on 12 Sep.2024 | • Casting of Capping Beam • Starting of Raft piles | 130388712.65 | 0 | 130388712.65 | 4662507.03 | 0 | 135051219.68 | 13053810 | 243591.44 | https://drive.google.com/thumbnail?id=1Ea4IsWWBHCZ29uRy7Zxp0SvMnOmdjCvn&sz=w1000 | https://drive.google.com/file/d/1Ea4IsWWBHCZ29uRy7Zxp0SvMnOmdjCvn/view | https://drive.google.com/thumbnail?id=1gB5Fi3nL6FCTnmd91Ei3_QQJ9QXEVQuG&sz=w1000 | https://drive.google.com/file/d/1gB5Fi3nL6FCTnmd91Ei3_QQJ9QXEVQuG/view | https://drive.google.com/thumbnail?id=1xvK7oL2060tGjomnxIMM_vkytJCIFbUM&sz=w1000 | https://drive.google.com/file/d/1xvK7oL2060tGjomnxIMM_vkytJCIFbUM/view
2024-09-06 | Baniyas-Majlis-P13 | P13 | MJ-05 | 103 | 627 | 730 | • Shoring guide wall Completed. • Secant piles Completed. • AWQAF approved Mosque Design. • ADDC accepted protection of existing FH/ water pipeline. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. & PS diversion of existing utilities at Plot P1. • Mosque design assigned to APG. | 7.49% | 7.99% | 0.5% | Authorities NOCs/BCC | 2026-05-22 |  | 2026-05-22 | 2024-09-13 | • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • Appoint specialist for diversion of existing fire hydrant at Plot P1 (Mosque), to avoid delay in building permit issuance. • ADM approval (if any) for Contractor's Pile Design. • Design update (if any), in compliance with sevene comments | • Workshop meetings held with MAK & bidders to expedite bidders proposals re-submission. • sevene review & endorsement. • Coordinate with sevene for ADM review schedule. • Design team submitted to sevene on 12 Sep.2024 | • Casting of Capping Beam • Starting of Raft piles | 130388712.65 | 0 | 130388712.65 | 4662507.03 | 0 | 135051219.68 | 13053810 | 243591.44 | https://drive.google.com/thumbnail?id=1Ea4IsWWBHCZ29uRy7Zxp0SvMnOmdjCvn&sz=w1000 | https://drive.google.com/file/d/1Ea4IsWWBHCZ29uRy7Zxp0SvMnOmdjCvn/view | https://drive.google.com/thumbnail?id=1gB5Fi3nL6FCTnmd91Ei3_QQJ9QXEVQuG&sz=w1000 | https://drive.google.com/file/d/1gB5Fi3nL6FCTnmd91Ei3_QQJ9QXEVQuG/view | https://drive.google.com/thumbnail?id=1xvK7oL2060tGjomnxIMM_vkytJCIFbUM&sz=w1000 | https://drive.google.com/file/d/1xvK7oL2060tGjomnxIMM_vkytJCIFbUM/view
2024-09-06 | Baniyas-Majlis-P13 | P13 | MJ-05 | 103 | 627 | 730 | • Shoring guide wall Completed. • Secant piles Completed. • AWQAF approved Mosque Design. • ADDC accepted protection of existing FH/ water pipeline. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. & PS diversion of existing utilities at Plot P1. • Mosque design assigned to APG. | 7.49% | 7.99% | 0.5% | External Works | 2026-06-01 |  | 2026-06-01 | 2024-09-13 | • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • Appoint specialist for diversion of existing fire hydrant at Plot P1 (Mosque), to avoid delay in building permit issuance. • ADM approval (if any) for Contractor's Pile Design. • Design update (if any), in compliance with sevene comments | • Workshop meetings held with MAK & bidders to expedite bidders proposals re-submission. • sevene review & endorsement. • Coordinate with sevene for ADM review schedule. • Design team submitted to sevene on 12 Sep.2024 | • Casting of Capping Beam • Starting of Raft piles | 130388712.65 | 0 | 130388712.65 | 4662507.03 | 0 | 135051219.68 | 13053810 | 243591.44 | https://drive.google.com/thumbnail?id=1Ea4IsWWBHCZ29uRy7Zxp0SvMnOmdjCvn&sz=w1000 | https://drive.google.com/file/d/1Ea4IsWWBHCZ29uRy7Zxp0SvMnOmdjCvn/view | https://drive.google.com/thumbnail?id=1gB5Fi3nL6FCTnmd91Ei3_QQJ9QXEVQuG&sz=w1000 | https://drive.google.com/file/d/1gB5Fi3nL6FCTnmd91Ei3_QQJ9QXEVQuG/view | https://drive.google.com/thumbnail?id=1xvK7oL2060tGjomnxIMM_vkytJCIFbUM&sz=w1000 | https://drive.google.com/file/d/1xvK7oL2060tGjomnxIMM_vkytJCIFbUM/view
2024-09-06 | Baniyas-Majlis-P13 | P13 | MJ-05 | 103 | 627 | 730 | • Shoring guide wall Completed. • Secant piles Completed. • AWQAF approved Mosque Design. • ADDC accepted protection of existing FH/ water pipeline. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. & PS diversion of existing utilities at Plot P1. • Mosque design assigned to APG. | 7.49% | 7.99% | 0.5% | Testing & Commissioning | 2026-06-02 |  | 2026-06-02 | 2024-09-13 | • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • Appoint specialist for diversion of existing fire hydrant at Plot P1 (Mosque), to avoid delay in building permit issuance. • ADM approval (if any) for Contractor's Pile Design. • Design update (if any), in compliance with sevene comments | • Workshop meetings held with MAK & bidders to expedite bidders proposals re-submission. • sevene review & endorsement. • Coordinate with sevene for ADM review schedule. • Design team submitted to sevene on 12 Sep.2024 | • Casting of Capping Beam • Starting of Raft piles | 130388712.65 | 0 | 130388712.65 | 4662507.03 | 0 | 135051219.68 | 13053810 | 243591.44 | https://drive.google.com/thumbnail?id=1Ea4IsWWBHCZ29uRy7Zxp0SvMnOmdjCvn&sz=w1000 | https://drive.google.com/file/d/1Ea4IsWWBHCZ29uRy7Zxp0SvMnOmdjCvn/view | https://drive.google.com/thumbnail?id=1gB5Fi3nL6FCTnmd91Ei3_QQJ9QXEVQuG&sz=w1000 | https://drive.google.com/file/d/1gB5Fi3nL6FCTnmd91Ei3_QQJ9QXEVQuG/view | https://drive.google.com/thumbnail?id=1xvK7oL2060tGjomnxIMM_vkytJCIFbUM&sz=w1000 | https://drive.google.com/file/d/1xvK7oL2060tGjomnxIMM_vkytJCIFbUM/view
2024-09-06 | Baniyas-Majlis-P13 | P13 | MJ-05 | 103 | 627 | 730 | • Shoring guide wall Completed. • Secant piles Completed. • AWQAF approved Mosque Design. • ADDC accepted protection of existing FH/ water pipeline. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. & PS diversion of existing utilities at Plot P1. • Mosque design assigned to APG. | 7.49% | 7.99% | 0.5% | Substantial Completion | 2026-06-02 |  | 2026-06-02 | 2024-09-13 | • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • Appoint specialist for diversion of existing fire hydrant at Plot P1 (Mosque), to avoid delay in building permit issuance. • ADM approval (if any) for Contractor's Pile Design. • Design update (if any), in compliance with sevene comments | • Workshop meetings held with MAK & bidders to expedite bidders proposals re-submission. • sevene review & endorsement. • Coordinate with sevene for ADM review schedule. • Design team submitted to sevene on 12 Sep.2024 | • Casting of Capping Beam • Starting of Raft piles | 130388712.65 | 0 | 130388712.65 | 4662507.03 | 0 | 135051219.68 | 13053810 | 243591.44 | https://drive.google.com/thumbnail?id=1Ea4IsWWBHCZ29uRy7Zxp0SvMnOmdjCvn&sz=w1000 | https://drive.google.com/file/d/1Ea4IsWWBHCZ29uRy7Zxp0SvMnOmdjCvn/view | https://drive.google.com/thumbnail?id=1gB5Fi3nL6FCTnmd91Ei3_QQJ9QXEVQuG&sz=w1000 | https://drive.google.com/file/d/1gB5Fi3nL6FCTnmd91Ei3_QQJ9QXEVQuG/view | https://drive.google.com/thumbnail?id=1xvK7oL2060tGjomnxIMM_vkytJCIFbUM&sz=w1000 | https://drive.google.com/file/d/1xvK7oL2060tGjomnxIMM_vkytJCIFbUM/view
2024-09-06 | Khalifa City-Majlis-P2 | P2 | MJ-06 | 124 | 486 | 610 | • Building Permits issued on 21/05/2024 • Approval For Shoring Design 15/07/2024 • Completion of site fencing and sign board • Project Staff moved in to Site Office on 09/09/2024 • Relocation of Utilities started on 09/09/2024 • Relocation of three (3) existing ADDC cables completed on 13/09/2024 | • Commencement Date 15/05/2024 | 4.78% | 2.2% | -2.58% | Notice to Commence | 2024-05-15 | 2024-05-15 |  | 2024-09-13 | • Relocation of existing ADDC feeder pillar. • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • Delay in submissions of and insurances and guarantees. • NOCs for fencing permit. (ADDC rejection) • Change of Piling Layout. | • Follow-up NOC from ADDC for shutdown to relocate feeder pillar. • Finalize the assignment of approved contractor to re-route the existing services-ongoing. • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities. Comply with Civil Defence requirements for inspection and approval. • Finalize the re-route the existing services procurement and commence the execution of re-routing.(PS) • Finalized the selection of shelter special equipment. Procurement of MEP subcontractor. • Prepare for the start of Shoring Works (after Issuance of NOC from ADDC). | 94981423.15 | 0 | 94981423.15 | 3708466.35 | 0 | 98689889.5 | 1208000 |  | https://drive.google.com/thumbnail?id=1ns9WVi4LIlCy9kRsqLx6fuozbqpfzmaZ&sz=w1000 | https://drive.google.com/file/d/1ns9WVi4LIlCy9kRsqLx6fuozbqpfzmaZ/view?usp=drive_link | https://drive.google.com/thumbnail?id=1l1qtJWULZ9Ls8rKQ1VUw4meyuzKWs1jT&sz=w1000 | https://drive.google.com/file/d/1l1qtJWULZ9Ls8rKQ1VUw4meyuzKWs1jT/view?usp=drive_link | https://drive.google.com/thumbnail?id=1p6hIUtd-nvQqhm5QfcZ7_NmYe6thw_QN&sz=w1000 | https://drive.google.com/file/d/1p6hIUtd-nvQqhm5QfcZ7_NmYe6thw_QN/view?usp=drive_link
2024-09-06 | Khalifa City-Majlis-P2 | P2 | MJ-06 | 124 | 486 | 610 | • Building Permits issued on 21/05/2024 • Approval For Shoring Design 15/07/2024 • Completion of site fencing and sign board • Project Staff moved in to Site Office on 09/09/2024 • Relocation of Utilities started on 09/09/2024 • Relocation of three (3) existing ADDC cables completed on 13/09/2024 | • Commencement Date 15/05/2024 | 4.78% | 2.2% | -2.58% | Building Permit | 2024-05-21 | 2024-05-21 |  | 2024-09-13 | • Relocation of existing ADDC feeder pillar. • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • Delay in submissions of and insurances and guarantees. • NOCs for fencing permit. (ADDC rejection) • Change of Piling Layout. | • Follow-up NOC from ADDC for shutdown to relocate feeder pillar. • Finalize the assignment of approved contractor to re-route the existing services-ongoing. • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities. Comply with Civil Defence requirements for inspection and approval. • Finalize the re-route the existing services procurement and commence the execution of re-routing.(PS) • Finalized the selection of shelter special equipment. Procurement of MEP subcontractor. • Prepare for the start of Shoring Works (after Issuance of NOC from ADDC). | 94981423.15 | 0 | 94981423.15 | 3708466.35 | 0 | 98689889.5 | 1208000 |  | https://drive.google.com/thumbnail?id=1ns9WVi4LIlCy9kRsqLx6fuozbqpfzmaZ&sz=w1000 | https://drive.google.com/file/d/1ns9WVi4LIlCy9kRsqLx6fuozbqpfzmaZ/view?usp=drive_link | https://drive.google.com/thumbnail?id=1l1qtJWULZ9Ls8rKQ1VUw4meyuzKWs1jT&sz=w1000 | https://drive.google.com/file/d/1l1qtJWULZ9Ls8rKQ1VUw4meyuzKWs1jT/view?usp=drive_link | https://drive.google.com/thumbnail?id=1p6hIUtd-nvQqhm5QfcZ7_NmYe6thw_QN&sz=w1000 | https://drive.google.com/file/d/1p6hIUtd-nvQqhm5QfcZ7_NmYe6thw_QN/view?usp=drive_link
2024-09-06 | Khalifa City-Majlis-P2 | P2 | MJ-06 | 124 | 486 | 610 | • Building Permits issued on 21/05/2024 • Approval For Shoring Design 15/07/2024 • Completion of site fencing and sign board • Project Staff moved in to Site Office on 09/09/2024 • Relocation of Utilities started on 09/09/2024 • Relocation of three (3) existing ADDC cables completed on 13/09/2024 | • Commencement Date 15/05/2024 | 4.78% | 2.2% | -2.58% | Site Mobilization | 2024-07-22 |  | 2024-09-16 | 2024-09-13 | • Relocation of existing ADDC feeder pillar. • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • Delay in submissions of and insurances and guarantees. • NOCs for fencing permit. (ADDC rejection) • Change of Piling Layout. | • Follow-up NOC from ADDC for shutdown to relocate feeder pillar. • Finalize the assignment of approved contractor to re-route the existing services-ongoing. • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities. Comply with Civil Defence requirements for inspection and approval. • Finalize the re-route the existing services procurement and commence the execution of re-routing.(PS) • Finalized the selection of shelter special equipment. Procurement of MEP subcontractor. • Prepare for the start of Shoring Works (after Issuance of NOC from ADDC). | 94981423.15 | 0 | 94981423.15 | 3708466.35 | 0 | 98689889.5 | 1208000 |  | https://drive.google.com/thumbnail?id=1ns9WVi4LIlCy9kRsqLx6fuozbqpfzmaZ&sz=w1000 | https://drive.google.com/file/d/1ns9WVi4LIlCy9kRsqLx6fuozbqpfzmaZ/view?usp=drive_link | https://drive.google.com/thumbnail?id=1l1qtJWULZ9Ls8rKQ1VUw4meyuzKWs1jT&sz=w1000 | https://drive.google.com/file/d/1l1qtJWULZ9Ls8rKQ1VUw4meyuzKWs1jT/view?usp=drive_link | https://drive.google.com/thumbnail?id=1p6hIUtd-nvQqhm5QfcZ7_NmYe6thw_QN&sz=w1000 | https://drive.google.com/file/d/1p6hIUtd-nvQqhm5QfcZ7_NmYe6thw_QN/view?usp=drive_link
2024-09-06 | Khalifa City-Majlis-P2 | P2 | MJ-06 | 124 | 486 | 610 | • Building Permits issued on 21/05/2024 • Approval For Shoring Design 15/07/2024 • Completion of site fencing and sign board • Project Staff moved in to Site Office on 09/09/2024 • Relocation of Utilities started on 09/09/2024 • Relocation of three (3) existing ADDC cables completed on 13/09/2024 | • Commencement Date 15/05/2024 | 4.78% | 2.2% | -2.58% | Guide Beam Completion | 2024-09-14 |  | 2024-10-24 | 2024-09-13 | • Relocation of existing ADDC feeder pillar. • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • Delay in submissions of and insurances and guarantees. • NOCs for fencing permit. (ADDC rejection) • Change of Piling Layout. | • Follow-up NOC from ADDC for shutdown to relocate feeder pillar. • Finalize the assignment of approved contractor to re-route the existing services-ongoing. • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities. Comply with Civil Defence requirements for inspection and approval. • Finalize the re-route the existing services procurement and commence the execution of re-routing.(PS) • Finalized the selection of shelter special equipment. Procurement of MEP subcontractor. • Prepare for the start of Shoring Works (after Issuance of NOC from ADDC). | 94981423.15 | 0 | 94981423.15 | 3708466.35 | 0 | 98689889.5 | 1208000 |  | https://drive.google.com/thumbnail?id=1ns9WVi4LIlCy9kRsqLx6fuozbqpfzmaZ&sz=w1000 | https://drive.google.com/file/d/1ns9WVi4LIlCy9kRsqLx6fuozbqpfzmaZ/view?usp=drive_link | https://drive.google.com/thumbnail?id=1l1qtJWULZ9Ls8rKQ1VUw4meyuzKWs1jT&sz=w1000 | https://drive.google.com/file/d/1l1qtJWULZ9Ls8rKQ1VUw4meyuzKWs1jT/view?usp=drive_link | https://drive.google.com/thumbnail?id=1p6hIUtd-nvQqhm5QfcZ7_NmYe6thw_QN&sz=w1000 | https://drive.google.com/file/d/1p6hIUtd-nvQqhm5QfcZ7_NmYe6thw_QN/view?usp=drive_link
2024-09-06 | Khalifa City-Majlis-P2 | P2 | MJ-06 | 124 | 486 | 610 | • Building Permits issued on 21/05/2024 • Approval For Shoring Design 15/07/2024 • Completion of site fencing and sign board • Project Staff moved in to Site Office on 09/09/2024 • Relocation of Utilities started on 09/09/2024 • Relocation of three (3) existing ADDC cables completed on 13/09/2024 | • Commencement Date 15/05/2024 | 4.78% | 2.2% | -2.58% | Shoring Drilling & Casting Completion | 2024-09-14 |  | 2024-10-24 | 2024-09-13 | • Relocation of existing ADDC feeder pillar. • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • Delay in submissions of and insurances and guarantees. • NOCs for fencing permit. (ADDC rejection) • Change of Piling Layout. | • Follow-up NOC from ADDC for shutdown to relocate feeder pillar. • Finalize the assignment of approved contractor to re-route the existing services-ongoing. • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities. Comply with Civil Defence requirements for inspection and approval. • Finalize the re-route the existing services procurement and commence the execution of re-routing.(PS) • Finalized the selection of shelter special equipment. Procurement of MEP subcontractor. • Prepare for the start of Shoring Works (after Issuance of NOC from ADDC). | 94981423.15 | 0 | 94981423.15 | 3708466.35 | 0 | 98689889.5 | 1208000 |  | https://drive.google.com/thumbnail?id=1ns9WVi4LIlCy9kRsqLx6fuozbqpfzmaZ&sz=w1000 | https://drive.google.com/file/d/1ns9WVi4LIlCy9kRsqLx6fuozbqpfzmaZ/view?usp=drive_link | https://drive.google.com/thumbnail?id=1l1qtJWULZ9Ls8rKQ1VUw4meyuzKWs1jT&sz=w1000 | https://drive.google.com/file/d/1l1qtJWULZ9Ls8rKQ1VUw4meyuzKWs1jT/view?usp=drive_link | https://drive.google.com/thumbnail?id=1p6hIUtd-nvQqhm5QfcZ7_NmYe6thw_QN&sz=w1000 | https://drive.google.com/file/d/1p6hIUtd-nvQqhm5QfcZ7_NmYe6thw_QN/view?usp=drive_link
2024-09-06 | Khalifa City-Majlis-P2 | P2 | MJ-06 | 124 | 486 | 610 | • Building Permits issued on 21/05/2024 • Approval For Shoring Design 15/07/2024 • Completion of site fencing and sign board • Project Staff moved in to Site Office on 09/09/2024 • Relocation of Utilities started on 09/09/2024 • Relocation of three (3) existing ADDC cables completed on 13/09/2024 | • Commencement Date 15/05/2024 | 4.78% | 2.2% | -2.58% | Shoring Capping Beam Completion | 2024-09-21 |  | 2024-10-31 | 2024-09-13 | • Relocation of existing ADDC feeder pillar. • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • Delay in submissions of and insurances and guarantees. • NOCs for fencing permit. (ADDC rejection) • Change of Piling Layout. | • Follow-up NOC from ADDC for shutdown to relocate feeder pillar. • Finalize the assignment of approved contractor to re-route the existing services-ongoing. • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities. Comply with Civil Defence requirements for inspection and approval. • Finalize the re-route the existing services procurement and commence the execution of re-routing.(PS) • Finalized the selection of shelter special equipment. Procurement of MEP subcontractor. • Prepare for the start of Shoring Works (after Issuance of NOC from ADDC). | 94981423.15 | 0 | 94981423.15 | 3708466.35 | 0 | 98689889.5 | 1208000 |  | https://drive.google.com/thumbnail?id=1ns9WVi4LIlCy9kRsqLx6fuozbqpfzmaZ&sz=w1000 | https://drive.google.com/file/d/1ns9WVi4LIlCy9kRsqLx6fuozbqpfzmaZ/view?usp=drive_link | https://drive.google.com/thumbnail?id=1l1qtJWULZ9Ls8rKQ1VUw4meyuzKWs1jT&sz=w1000 | https://drive.google.com/file/d/1l1qtJWULZ9Ls8rKQ1VUw4meyuzKWs1jT/view?usp=drive_link | https://drive.google.com/thumbnail?id=1p6hIUtd-nvQqhm5QfcZ7_NmYe6thw_QN&sz=w1000 | https://drive.google.com/file/d/1p6hIUtd-nvQqhm5QfcZ7_NmYe6thw_QN/view?usp=drive_link
2024-09-06 | Khalifa City-Majlis-P2 | P2 | MJ-06 | 124 | 486 | 610 | • Building Permits issued on 21/05/2024 • Approval For Shoring Design 15/07/2024 • Completion of site fencing and sign board • Project Staff moved in to Site Office on 09/09/2024 • Relocation of Utilities started on 09/09/2024 • Relocation of three (3) existing ADDC cables completed on 13/09/2024 | • Commencement Date 15/05/2024 | 4.78% | 2.2% | -2.58% | Stage 1 Excavation Completion | 2024-09-21 |  | 2024-10-31 | 2024-09-13 | • Relocation of existing ADDC feeder pillar. • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • Delay in submissions of and insurances and guarantees. • NOCs for fencing permit. (ADDC rejection) • Change of Piling Layout. | • Follow-up NOC from ADDC for shutdown to relocate feeder pillar. • Finalize the assignment of approved contractor to re-route the existing services-ongoing. • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities. Comply with Civil Defence requirements for inspection and approval. • Finalize the re-route the existing services procurement and commence the execution of re-routing.(PS) • Finalized the selection of shelter special equipment. Procurement of MEP subcontractor. • Prepare for the start of Shoring Works (after Issuance of NOC from ADDC). | 94981423.15 | 0 | 94981423.15 | 3708466.35 | 0 | 98689889.5 | 1208000 |  | https://drive.google.com/thumbnail?id=1ns9WVi4LIlCy9kRsqLx6fuozbqpfzmaZ&sz=w1000 | https://drive.google.com/file/d/1ns9WVi4LIlCy9kRsqLx6fuozbqpfzmaZ/view?usp=drive_link | https://drive.google.com/thumbnail?id=1l1qtJWULZ9Ls8rKQ1VUw4meyuzKWs1jT&sz=w1000 | https://drive.google.com/file/d/1l1qtJWULZ9Ls8rKQ1VUw4meyuzKWs1jT/view?usp=drive_link | https://drive.google.com/thumbnail?id=1p6hIUtd-nvQqhm5QfcZ7_NmYe6thw_QN&sz=w1000 | https://drive.google.com/file/d/1p6hIUtd-nvQqhm5QfcZ7_NmYe6thw_QN/view?usp=drive_link
2024-09-06 | Mohamed Bin Zayed City-Majlis-P9 | P9 | MJ-07 | 124 | 486 | 610 | • Building Permits issued on 21/05/2024 • Completion of site fencing • Approval for Shoring Design 15/07/2024 • Guide Beam completed on 06/09/2024 | • Commencement Date 15/05/2024 | 6.96% | 2.99% | -3.97% | Notice to Commence | 2024-05-15 | 2024-05-15 |  | 2024-09-13 | • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • Delay in submissions of and insurances and grantees. • NOCs for fencing permit. • Finalize the authorities approval for the Mosque | • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) • Expedite the submission of revised Piling Layout. | • Complete site mobilization and establishment of site facilities. Comply with Civil Defence requirements for inspection and approval. • Finalized the selection of shelter special equipment.(ongoing) • Procurement of MEP subcontractor. • Secant Piles for shoring works(ongoing) • Piling works. | 97238576.53 | 0 | 97238576.53 | 3344531.65 | 0 | 100583108.18 | 1208000 |  | https://drive.google.com/thumbnail?id=1dRnOElIobWmdZEkO8BRVE7TU1yvuxQXW&sz=w1000 | https://drive.google.com/file/d/1dRnOElIobWmdZEkO8BRVE7TU1yvuxQXW/view?usp=drive_link | https://drive.google.com/thumbnail?id=19xTvun6qzsNy4xAj6wKum7MQ98om515z&sz=w1000 | https://drive.google.com/file/d/19xTvun6qzsNy4xAj6wKum7MQ98om515z/view?usp=drive_link | https://drive.google.com/thumbnail?id=1zGDlAkBICsrR-ZMduYzZLDdRYy5sHjtH&sz=w1000 | https://drive.google.com/file/d/1zGDlAkBICsrR-ZMduYzZLDdRYy5sHjtH/view?usp=drive_link
2024-09-06 | Mohamed Bin Zayed City-Majlis-P9 | P9 | MJ-07 | 124 | 486 | 610 | • Building Permits issued on 21/05/2024 • Completion of site fencing • Approval for Shoring Design 15/07/2024 • Guide Beam completed on 06/09/2024 | • Commencement Date 15/05/2024 | 6.96% | 2.99% | -3.97% | Building Permit | 2024-05-21 | 2024-05-21 |  | 2024-09-13 | • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • Delay in submissions of and insurances and grantees. • NOCs for fencing permit. • Finalize the authorities approval for the Mosque | • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities. Comply with Civil Defence requirements for inspection and approval. • Finalized the selection of shelter special equipment.(ongoing) • Procurement of MEP subcontractor. • Guide Beam and secant Piles for shoring works(ongoing) | 97238576.53 | 0 | 97238576.53 | 3344531.65 | 0 | 100583108.18 | 1208000 |  | https://drive.google.com/thumbnail?id=1dRnOElIobWmdZEkO8BRVE7TU1yvuxQXW&sz=w1000 | https://drive.google.com/file/d/1dRnOElIobWmdZEkO8BRVE7TU1yvuxQXW/view?usp=drive_link | https://drive.google.com/thumbnail?id=19xTvun6qzsNy4xAj6wKum7MQ98om515z&sz=w1000 | https://drive.google.com/file/d/19xTvun6qzsNy4xAj6wKum7MQ98om515z/view?usp=drive_link | https://drive.google.com/thumbnail?id=1zGDlAkBICsrR-ZMduYzZLDdRYy5sHjtH&sz=w1000 | https://drive.google.com/file/d/1zGDlAkBICsrR-ZMduYzZLDdRYy5sHjtH/view?usp=drive_link
2024-09-06 | Mohamed Bin Zayed City-Majlis-P9 | P9 | MJ-07 | 124 | 486 | 610 | • Building Permits issued on 21/05/2024 • Completion of site fencing • Approval for Shoring Design 15/07/2024 • Guide Beam completed on 06/09/2024 | • Commencement Date 15/05/2024 | 6.96% | 2.99% | -3.97% | Site Mobilization | 2024-07-20 |  | 2024-09-19 | 2024-09-13 | • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • Delay in submissions of and insurances and grantees. • NOCs for fencing permit. • Finalize the authorities approval for the Mosque | • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities. Comply with Civil Defence requirements for inspection and approval. • Finalized the selection of shelter special equipment.(ongoing) • Procurement of MEP subcontractor. • Guide Beam and secant Piles for shoring works(ongoing) | 97238576.53 | 0 | 97238576.53 | 3344531.65 | 0 | 100583108.18 | 1208000 |  | https://drive.google.com/thumbnail?id=1dRnOElIobWmdZEkO8BRVE7TU1yvuxQXW&sz=w1000 | https://drive.google.com/file/d/1dRnOElIobWmdZEkO8BRVE7TU1yvuxQXW/view?usp=drive_link | https://drive.google.com/thumbnail?id=19xTvun6qzsNy4xAj6wKum7MQ98om515z&sz=w1000 | https://drive.google.com/file/d/19xTvun6qzsNy4xAj6wKum7MQ98om515z/view?usp=drive_link | https://drive.google.com/thumbnail?id=1zGDlAkBICsrR-ZMduYzZLDdRYy5sHjtH&sz=w1000 | https://drive.google.com/file/d/1zGDlAkBICsrR-ZMduYzZLDdRYy5sHjtH/view?usp=drive_link
2024-09-06 | Mohamed Bin Zayed City-Majlis-P9 | P9 | MJ-07 | 124 | 486 | 610 | • Building Permits issued on 21/05/2024 • Completion of site fencing • Approval for Shoring Design 15/07/2024 • Guide Beam completed on 06/09/2024 | • Commencement Date 15/05/2024 | 6.96% | 2.99% | -3.97% | Shoring & Piling Completion | 2024-11-07 |  | 2024-11-07 | 2024-09-13 | • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • Delay in submissions of and insurances and grantees. • NOCs for fencing permit. • Finalize the authorities approval for the Mosque | • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities. Comply with Civil Defence requirements for inspection and approval. • Finalized the selection of shelter special equipment.(ongoing) • Procurement of MEP subcontractor. • Guide Beam and secant Piles for shoring works(ongoing) | 97238576.53 | 0 | 97238576.53 | 3344531.65 | 0 | 100583108.18 | 1208000 |  | https://drive.google.com/thumbnail?id=1dRnOElIobWmdZEkO8BRVE7TU1yvuxQXW&sz=w1000 | https://drive.google.com/file/d/1dRnOElIobWmdZEkO8BRVE7TU1yvuxQXW/view?usp=drive_link | https://drive.google.com/thumbnail?id=19xTvun6qzsNy4xAj6wKum7MQ98om515z&sz=w1000 | https://drive.google.com/file/d/19xTvun6qzsNy4xAj6wKum7MQ98om515z/view?usp=drive_link | https://drive.google.com/thumbnail?id=1zGDlAkBICsrR-ZMduYzZLDdRYy5sHjtH&sz=w1000 | https://drive.google.com/file/d/1zGDlAkBICsrR-ZMduYzZLDdRYy5sHjtH/view?usp=drive_link
2024-09-06 | Mohamed Bin Zayed City-Majlis-P9 | P9 | MJ-07 | 124 | 486 | 610 | • Building Permits issued on 21/05/2024 • Completion of site fencing • Approval for Shoring Design 15/07/2024 • Guide Beam completed on 06/09/2024 | • Commencement Date 15/05/2024 | 6.96% | 2.99% | -3.97% | Substructure | 2024-12-18 |  | 2024-12-18 | 2024-09-13 | • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • Delay in submissions of and insurances and grantees. • NOCs for fencing permit. • Finalize the authorities approval for the Mosque | • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities. Comply with Civil Defence requirements for inspection and approval. • Finalized the selection of shelter special equipment.(ongoing) • Procurement of MEP subcontractor. • Guide Beam and secant Piles for shoring works(ongoing) | 97238576.53 | 0 | 97238576.53 | 3344531.65 | 0 | 100583108.18 | 1208000 |  | https://drive.google.com/thumbnail?id=1dRnOElIobWmdZEkO8BRVE7TU1yvuxQXW&sz=w1000 | https://drive.google.com/file/d/1dRnOElIobWmdZEkO8BRVE7TU1yvuxQXW/view?usp=drive_link | https://drive.google.com/thumbnail?id=19xTvun6qzsNy4xAj6wKum7MQ98om515z&sz=w1000 | https://drive.google.com/file/d/19xTvun6qzsNy4xAj6wKum7MQ98om515z/view?usp=drive_link | https://drive.google.com/thumbnail?id=1zGDlAkBICsrR-ZMduYzZLDdRYy5sHjtH&sz=w1000 | https://drive.google.com/file/d/1zGDlAkBICsrR-ZMduYzZLDdRYy5sHjtH/view?usp=drive_link
2024-09-06 | Mohamed Bin Zayed City-Majlis-P9 | P9 | MJ-07 | 124 | 486 | 610 | • Building Permits issued on 21/05/2024 • Completion of site fencing • Approval for Shoring Design 15/07/2024 • Guide Beam completed on 06/09/2024 | • Commencement Date 15/05/2024 | 6.96% | 2.99% | -3.97% | Superstructure | 2025-08-28 |  |  | 2024-09-13 | • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • Delay in submissions of and insurances and grantees. • NOCs for fencing permit. • Finalize the authorities approval for the Mosque | • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities. Comply with Civil Defence requirements for inspection and approval. • Finalized the selection of shelter special equipment.(ongoing) • Procurement of MEP subcontractor. • Guide Beam and secant Piles for shoring works(ongoing) | 97238576.53 | 0 | 97238576.53 | 3344531.65 | 0 | 100583108.18 | 1208000 |  | https://drive.google.com/thumbnail?id=1dRnOElIobWmdZEkO8BRVE7TU1yvuxQXW&sz=w1000 | https://drive.google.com/file/d/1dRnOElIobWmdZEkO8BRVE7TU1yvuxQXW/view?usp=drive_link | https://drive.google.com/thumbnail?id=19xTvun6qzsNy4xAj6wKum7MQ98om515z&sz=w1000 | https://drive.google.com/file/d/19xTvun6qzsNy4xAj6wKum7MQ98om515z/view?usp=drive_link | https://drive.google.com/thumbnail?id=1zGDlAkBICsrR-ZMduYzZLDdRYy5sHjtH&sz=w1000 | https://drive.google.com/file/d/1zGDlAkBICsrR-ZMduYzZLDdRYy5sHjtH/view?usp=drive_link
2024-09-06 | Mohamed Bin Zayed City-Majlis-P9 | P9 | MJ-07 | 124 | 486 | 610 | • Building Permits issued on 21/05/2024 • Completion of site fencing • Approval for Shoring Design 15/07/2024 • Guide Beam completed on 06/09/2024 | • Commencement Date 15/05/2024 | 6.96% | 2.99% | -3.97% | MEP | 2025-11-04 |  | 2025-11-04 | 2024-09-13 | • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • Delay in submissions of and insurances and grantees. • NOCs for fencing permit. • Finalize the authorities approval for the Mosque | • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities. Comply with Civil Defence requirements for inspection and approval. • Finalized the selection of shelter special equipment.(ongoing) • Procurement of MEP subcontractor. • Guide Beam and secant Piles for shoring works(ongoing) | 97238576.53 | 0 | 97238576.53 | 3344531.65 | 0 | 100583108.18 | 1208000 |  | https://drive.google.com/thumbnail?id=1dRnOElIobWmdZEkO8BRVE7TU1yvuxQXW&sz=w1000 | https://drive.google.com/file/d/1dRnOElIobWmdZEkO8BRVE7TU1yvuxQXW/view?usp=drive_link | https://drive.google.com/thumbnail?id=19xTvun6qzsNy4xAj6wKum7MQ98om515z&sz=w1000 | https://drive.google.com/file/d/19xTvun6qzsNy4xAj6wKum7MQ98om515z/view?usp=drive_link | https://drive.google.com/thumbnail?id=1zGDlAkBICsrR-ZMduYzZLDdRYy5sHjtH&sz=w1000 | https://drive.google.com/file/d/1zGDlAkBICsrR-ZMduYzZLDdRYy5sHjtH/view?usp=drive_link
2024-09-06 | Mohamed Bin Zayed City-Majlis-P9 | P9 | MJ-07 | 124 | 486 | 610 | • Building Permits issued on 21/05/2024 • Completion of site fencing • Approval for Shoring Design 15/07/2024 • Guide Beam completed on 06/09/2024 | • Commencement Date 15/05/2024 | 6.96% | 2.99% | -3.97% | Power On | 2025-11-22 |  | 2025-11-22 | 2024-09-13 | • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • Delay in submissions of and insurances and grantees. • NOCs for fencing permit. • Finalize the authorities approval for the Mosque | • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities. Comply with Civil Defence requirements for inspection and approval. • Finalized the selection of shelter special equipment.(ongoing) • Procurement of MEP subcontractor. • Guide Beam and secant Piles for shoring works(ongoing) | 97238576.53 | 0 | 97238576.53 | 3344531.65 | 0 | 100583108.18 | 1208000 |  | https://drive.google.com/thumbnail?id=1dRnOElIobWmdZEkO8BRVE7TU1yvuxQXW&sz=w1000 | https://drive.google.com/file/d/1dRnOElIobWmdZEkO8BRVE7TU1yvuxQXW/view?usp=drive_link | https://drive.google.com/thumbnail?id=19xTvun6qzsNy4xAj6wKum7MQ98om515z&sz=w1000 | https://drive.google.com/file/d/19xTvun6qzsNy4xAj6wKum7MQ98om515z/view?usp=drive_link | https://drive.google.com/thumbnail?id=1zGDlAkBICsrR-ZMduYzZLDdRYy5sHjtH&sz=w1000 | https://drive.google.com/file/d/1zGDlAkBICsrR-ZMduYzZLDdRYy5sHjtH/view?usp=drive_link
2024-09-06 | Mohamed Bin Zayed City-Majlis-P9 | P9 | MJ-07 | 124 | 486 | 610 | • Building Permits issued on 21/05/2024 • Completion of site fencing • Approval for Shoring Design 15/07/2024 • Guide Beam completed on 06/09/2024 | • Commencement Date 15/05/2024 | 6.96% | 2.99% | -3.97% | Interior Finishes | 2025-11-22 |  | 2025-11-22 | 2024-09-13 | • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • Delay in submissions of and insurances and grantees. • NOCs for fencing permit. • Finalize the authorities approval for the Mosque | • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities. Comply with Civil Defence requirements for inspection and approval. • Finalized the selection of shelter special equipment.(ongoing) • Procurement of MEP subcontractor. • Guide Beam and secant Piles for shoring works(ongoing) | 97238576.53 | 0 | 97238576.53 | 3344531.65 | 0 | 100583108.18 | 1208000 |  | https://drive.google.com/thumbnail?id=1dRnOElIobWmdZEkO8BRVE7TU1yvuxQXW&sz=w1000 | https://drive.google.com/file/d/1dRnOElIobWmdZEkO8BRVE7TU1yvuxQXW/view?usp=drive_link | https://drive.google.com/thumbnail?id=19xTvun6qzsNy4xAj6wKum7MQ98om515z&sz=w1000 | https://drive.google.com/file/d/19xTvun6qzsNy4xAj6wKum7MQ98om515z/view?usp=drive_link | https://drive.google.com/thumbnail?id=1zGDlAkBICsrR-ZMduYzZLDdRYy5sHjtH&sz=w1000 | https://drive.google.com/file/d/1zGDlAkBICsrR-ZMduYzZLDdRYy5sHjtH/view?usp=drive_link
2024-09-06 | Mohamed Bin Zayed City-Majlis-P9 | P9 | MJ-07 | 124 | 486 | 610 | • Building Permits issued on 21/05/2024 • Completion of site fencing • Approval for Shoring Design 15/07/2024 • Guide Beam completed on 06/09/2024 | • Commencement Date 15/05/2024 | 6.96% | 2.99% | -3.97% | Substantial Completion | 2025-12-15 |  | 2025-12-15 | 2024-09-13 | • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • Delay in submissions of and insurances and grantees. • NOCs for fencing permit. • Finalize the authorities approval for the Mosque | • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities. Comply with Civil Defence requirements for inspection and approval. • Finalized the selection of shelter special equipment.(ongoing) • Procurement of MEP subcontractor. • Guide Beam and secant Piles for shoring works(ongoing) | 97238576.53 | 0 | 97238576.53 | 3344531.65 | 0 | 100583108.18 | 1208000 |  | https://drive.google.com/thumbnail?id=1dRnOElIobWmdZEkO8BRVE7TU1yvuxQXW&sz=w1000 | https://drive.google.com/file/d/1dRnOElIobWmdZEkO8BRVE7TU1yvuxQXW/view?usp=drive_link | https://drive.google.com/thumbnail?id=19xTvun6qzsNy4xAj6wKum7MQ98om515z&sz=w1000 | https://drive.google.com/file/d/19xTvun6qzsNy4xAj6wKum7MQ98om515z/view?usp=drive_link | https://drive.google.com/thumbnail?id=1zGDlAkBICsrR-ZMduYzZLDdRYy5sHjtH&sz=w1000 | https://drive.google.com/file/d/1zGDlAkBICsrR-ZMduYzZLDdRYy5sHjtH/view?usp=drive_link
2024-09-06 | Mohamed Bin Zayed City-Majlis-P2 | P2 | MJ-12 | 60 | 548 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.56% | 1.38% | -0.18% | Commencement Date | 2024-07-16 |  |  | 2024-09-13 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 116841278.4538 | 0 | 116841278.4538 | 3229333.33 |  | 120070611.7838 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1hU_NG6jWFnAFsctWfxIixSLdfdg-2vbM&sz=w1000 | https://drive.google.com/file/d/1hU_NG6jWFnAFsctWfxIixSLdfdg-2vbM/view | https://drive.google.com/thumbnail?id=1AjudEJfSeA5pObV4i_-2eZywBMH4FjUH&sz=w1000 | https://drive.google.com/file/d/1AjudEJfSeA5pObV4i_-2eZywBMH4FjUH/view | https://drive.google.com/thumbnail?id=1PBCEYtD7A6r3bmKeU8hWJH7w8BXVVzH1&sz=w1000 | https://drive.google.com/file/d/1PBCEYtD7A6r3bmKeU8hWJH7w8BXVVzH1/view
2024-09-06 | Mohamed Bin Zayed City-Majlis-P2 | P2 | MJ-12 | 60 | 548 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.56% | 1.38% | -0.18% | Construction Permit |  |  |  | 2024-09-13 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 116841278.4538 | 0 | 116841278.4538 | 3229333.33 |  | 120070611.7838 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1hU_NG6jWFnAFsctWfxIixSLdfdg-2vbM&sz=w1000 | https://drive.google.com/file/d/1hU_NG6jWFnAFsctWfxIixSLdfdg-2vbM/view | https://drive.google.com/thumbnail?id=1AjudEJfSeA5pObV4i_-2eZywBMH4FjUH&sz=w1000 | https://drive.google.com/file/d/1AjudEJfSeA5pObV4i_-2eZywBMH4FjUH/view | https://drive.google.com/thumbnail?id=1PBCEYtD7A6r3bmKeU8hWJH7w8BXVVzH1&sz=w1000 | https://drive.google.com/file/d/1PBCEYtD7A6r3bmKeU8hWJH7w8BXVVzH1/view
2024-09-06 | Mohamed Bin Zayed City-Majlis-P2 | P2 | MJ-12 | 60 | 548 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.56% | 1.38% | -0.18% | Site Mobilization |  |  |  | 2024-09-13 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 116841278.4538 | 0 | 116841278.4538 | 3229333.33 |  | 120070611.7838 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1hU_NG6jWFnAFsctWfxIixSLdfdg-2vbM&sz=w1000 | https://drive.google.com/file/d/1hU_NG6jWFnAFsctWfxIixSLdfdg-2vbM/view | https://drive.google.com/thumbnail?id=1AjudEJfSeA5pObV4i_-2eZywBMH4FjUH&sz=w1000 | https://drive.google.com/file/d/1AjudEJfSeA5pObV4i_-2eZywBMH4FjUH/view | https://drive.google.com/thumbnail?id=1PBCEYtD7A6r3bmKeU8hWJH7w8BXVVzH1&sz=w1000 | https://drive.google.com/file/d/1PBCEYtD7A6r3bmKeU8hWJH7w8BXVVzH1/view
2024-09-06 | Mohamed Bin Zayed City-Majlis-P2 | P2 | MJ-12 | 60 | 548 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.56% | 1.38% | -0.18% | Shoring Drilling & Casting |  |  |  | 2024-09-13 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 116841278.4538 | 0 | 116841278.4538 | 3229333.33 |  | 120070611.7838 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1hU_NG6jWFnAFsctWfxIixSLdfdg-2vbM&sz=w1000 | https://drive.google.com/file/d/1hU_NG6jWFnAFsctWfxIixSLdfdg-2vbM/view | https://drive.google.com/thumbnail?id=1AjudEJfSeA5pObV4i_-2eZywBMH4FjUH&sz=w1000 | https://drive.google.com/file/d/1AjudEJfSeA5pObV4i_-2eZywBMH4FjUH/view | https://drive.google.com/thumbnail?id=1PBCEYtD7A6r3bmKeU8hWJH7w8BXVVzH1&sz=w1000 | https://drive.google.com/file/d/1PBCEYtD7A6r3bmKeU8hWJH7w8BXVVzH1/view
2024-09-06 | Mohamed Bin Zayed City-Majlis-P2 | P2 | MJ-12 | 60 | 548 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.56% | 1.38% | -0.18% | Piling Drilling & Casting |  |  |  | 2024-09-13 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 116841278.4538 | 0 | 116841278.4538 | 3229333.33 |  | 120070611.7838 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1hU_NG6jWFnAFsctWfxIixSLdfdg-2vbM&sz=w1000 | https://drive.google.com/file/d/1hU_NG6jWFnAFsctWfxIixSLdfdg-2vbM/view | https://drive.google.com/thumbnail?id=1AjudEJfSeA5pObV4i_-2eZywBMH4FjUH&sz=w1000 | https://drive.google.com/file/d/1AjudEJfSeA5pObV4i_-2eZywBMH4FjUH/view | https://drive.google.com/thumbnail?id=1PBCEYtD7A6r3bmKeU8hWJH7w8BXVVzH1&sz=w1000 | https://drive.google.com/file/d/1PBCEYtD7A6r3bmKeU8hWJH7w8BXVVzH1/view
2024-09-06 | Mohamed Bin Zayed City-Majlis-P2 | P2 | MJ-12 | 60 | 548 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.56% | 1.38% | -0.18% | Excavation |  |  |  | 2024-09-13 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 116841278.4538 | 0 | 116841278.4538 | 3229333.33 |  | 120070611.7838 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1hU_NG6jWFnAFsctWfxIixSLdfdg-2vbM&sz=w1000 | https://drive.google.com/file/d/1hU_NG6jWFnAFsctWfxIixSLdfdg-2vbM/view | https://drive.google.com/thumbnail?id=1AjudEJfSeA5pObV4i_-2eZywBMH4FjUH&sz=w1000 | https://drive.google.com/file/d/1AjudEJfSeA5pObV4i_-2eZywBMH4FjUH/view | https://drive.google.com/thumbnail?id=1PBCEYtD7A6r3bmKeU8hWJH7w8BXVVzH1&sz=w1000 | https://drive.google.com/file/d/1PBCEYtD7A6r3bmKeU8hWJH7w8BXVVzH1/view
2024-09-06 | Mohamed Bin Zayed City-Majlis-P2 | P2 | MJ-12 | 60 | 548 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.56% | 1.38% | -0.18% | Substructure |  |  |  | 2024-09-13 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 116841278.4538 | 0 | 116841278.4538 | 3229333.33 |  | 120070611.7838 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1hU_NG6jWFnAFsctWfxIixSLdfdg-2vbM&sz=w1000 | https://drive.google.com/file/d/1hU_NG6jWFnAFsctWfxIixSLdfdg-2vbM/view | https://drive.google.com/thumbnail?id=1AjudEJfSeA5pObV4i_-2eZywBMH4FjUH&sz=w1000 | https://drive.google.com/file/d/1AjudEJfSeA5pObV4i_-2eZywBMH4FjUH/view | https://drive.google.com/thumbnail?id=1PBCEYtD7A6r3bmKeU8hWJH7w8BXVVzH1&sz=w1000 | https://drive.google.com/file/d/1PBCEYtD7A6r3bmKeU8hWJH7w8BXVVzH1/view
2024-09-06 | Mohamed Bin Zayed City-Majlis-P2 | P2 | MJ-12 | 60 | 548 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.56% | 1.38% | -0.18% | Superstructure |  |  |  | 2024-09-13 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 116841278.4538 | 0 | 116841278.4538 | 3229333.33 |  | 120070611.7838 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1hU_NG6jWFnAFsctWfxIixSLdfdg-2vbM&sz=w1000 | https://drive.google.com/file/d/1hU_NG6jWFnAFsctWfxIixSLdfdg-2vbM/view | https://drive.google.com/thumbnail?id=1AjudEJfSeA5pObV4i_-2eZywBMH4FjUH&sz=w1000 | https://drive.google.com/file/d/1AjudEJfSeA5pObV4i_-2eZywBMH4FjUH/view | https://drive.google.com/thumbnail?id=1PBCEYtD7A6r3bmKeU8hWJH7w8BXVVzH1&sz=w1000 | https://drive.google.com/file/d/1PBCEYtD7A6r3bmKeU8hWJH7w8BXVVzH1/view
2024-09-06 | Mohamed Bin Zayed City-Majlis-P2 | P2 | MJ-12 | 60 | 548 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.56% | 1.38% | -0.18% | MEP & Finishes |  |  |  | 2024-09-13 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 116841278.4538 | 0 | 116841278.4538 | 3229333.33 |  | 120070611.7838 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1hU_NG6jWFnAFsctWfxIixSLdfdg-2vbM&sz=w1000 | https://drive.google.com/file/d/1hU_NG6jWFnAFsctWfxIixSLdfdg-2vbM/view | https://drive.google.com/thumbnail?id=1AjudEJfSeA5pObV4i_-2eZywBMH4FjUH&sz=w1000 | https://drive.google.com/file/d/1AjudEJfSeA5pObV4i_-2eZywBMH4FjUH/view | https://drive.google.com/thumbnail?id=1PBCEYtD7A6r3bmKeU8hWJH7w8BXVVzH1&sz=w1000 | https://drive.google.com/file/d/1PBCEYtD7A6r3bmKeU8hWJH7w8BXVVzH1/view
2024-09-06 | Mohamed Bin Zayed City-Majlis-P2 | P2 | MJ-12 | 60 | 548 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.56% | 1.38% | -0.18% | Authorities NOCs/BCC |  |  |  | 2024-09-13 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 116841278.4538 | 0 | 116841278.4538 | 3229333.33 |  | 120070611.7838 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1hU_NG6jWFnAFsctWfxIixSLdfdg-2vbM&sz=w1000 | https://drive.google.com/file/d/1hU_NG6jWFnAFsctWfxIixSLdfdg-2vbM/view | https://drive.google.com/thumbnail?id=1AjudEJfSeA5pObV4i_-2eZywBMH4FjUH&sz=w1000 | https://drive.google.com/file/d/1AjudEJfSeA5pObV4i_-2eZywBMH4FjUH/view | https://drive.google.com/thumbnail?id=1PBCEYtD7A6r3bmKeU8hWJH7w8BXVVzH1&sz=w1000 | https://drive.google.com/file/d/1PBCEYtD7A6r3bmKeU8hWJH7w8BXVVzH1/view
2024-09-06 | Mohamed Bin Zayed City-Majlis-P2 | P2 | MJ-12 | 60 | 548 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.56% | 1.38% | -0.18% | External Works |  |  |  | 2024-09-13 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 116841278.4538 | 0 | 116841278.4538 | 3229333.33 |  | 120070611.7838 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1hU_NG6jWFnAFsctWfxIixSLdfdg-2vbM&sz=w1000 | https://drive.google.com/file/d/1hU_NG6jWFnAFsctWfxIixSLdfdg-2vbM/view | https://drive.google.com/thumbnail?id=1AjudEJfSeA5pObV4i_-2eZywBMH4FjUH&sz=w1000 | https://drive.google.com/file/d/1AjudEJfSeA5pObV4i_-2eZywBMH4FjUH/view | https://drive.google.com/thumbnail?id=1PBCEYtD7A6r3bmKeU8hWJH7w8BXVVzH1&sz=w1000 | https://drive.google.com/file/d/1PBCEYtD7A6r3bmKeU8hWJH7w8BXVVzH1/view
2024-09-06 | Mohamed Bin Zayed City-Majlis-P2 | P2 | MJ-12 | 60 | 548 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.56% | 1.38% | -0.18% | Testing & Commissioning |  |  |  | 2024-09-13 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 116841278.4538 | 0 | 116841278.4538 | 3229333.33 |  | 120070611.7838 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1hU_NG6jWFnAFsctWfxIixSLdfdg-2vbM&sz=w1000 | https://drive.google.com/file/d/1hU_NG6jWFnAFsctWfxIixSLdfdg-2vbM/view | https://drive.google.com/thumbnail?id=1AjudEJfSeA5pObV4i_-2eZywBMH4FjUH&sz=w1000 | https://drive.google.com/file/d/1AjudEJfSeA5pObV4i_-2eZywBMH4FjUH/view | https://drive.google.com/thumbnail?id=1PBCEYtD7A6r3bmKeU8hWJH7w8BXVVzH1&sz=w1000 | https://drive.google.com/file/d/1PBCEYtD7A6r3bmKeU8hWJH7w8BXVVzH1/view
2024-09-06 | Mohamed Bin Zayed City-Majlis-P2 | P2 | MJ-12 | 60 | 548 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.56% | 1.38% | -0.18% | Substantial Completion |  |  |  | 2024-09-13 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 116841278.4538 | 0 | 116841278.4538 | 3229333.33 |  | 120070611.7838 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1hU_NG6jWFnAFsctWfxIixSLdfdg-2vbM&sz=w1000 | https://drive.google.com/file/d/1hU_NG6jWFnAFsctWfxIixSLdfdg-2vbM/view | https://drive.google.com/thumbnail?id=1AjudEJfSeA5pObV4i_-2eZywBMH4FjUH&sz=w1000 | https://drive.google.com/file/d/1AjudEJfSeA5pObV4i_-2eZywBMH4FjUH/view | https://drive.google.com/thumbnail?id=1PBCEYtD7A6r3bmKeU8hWJH7w8BXVVzH1&sz=w1000 | https://drive.google.com/file/d/1PBCEYtD7A6r3bmKeU8hWJH7w8BXVVzH1/view
2024-09-06 | Madinat Al Riyad-Majlis-P162 | P162 | MJ-13 | 60 | 548 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.56% | 1.41% | -0.15% | Commencement Date | 2024-07-16 |  |  | 2024-09-13 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 98073241.5243 | 0 | 98073241.5243 | 3229333.33 |  | 101302574.8543 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN&sz=w1000 | https://drive.google.com/file/d/1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN/view | https://drive.google.com/thumbnail?id=10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce&sz=w1000 | https://drive.google.com/file/d/10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce/view | https://drive.google.com/thumbnail?id=1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU&sz=w1000 | https://drive.google.com/file/d/1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU/view
2024-09-06 | Madinat Al Riyad-Majlis-P162 | P162 | MJ-13 | 60 | 548 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.56% | 1.41% | -0.15% | Construction Permit |  |  |  | 2024-09-13 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 98073241.5243 | 0 | 98073241.5243 | 3229333.33 |  | 101302574.8543 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN&sz=w1000 | https://drive.google.com/file/d/1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN/view | https://drive.google.com/thumbnail?id=10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce&sz=w1000 | https://drive.google.com/file/d/10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce/view | https://drive.google.com/thumbnail?id=1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU&sz=w1000 | https://drive.google.com/file/d/1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU/view
2024-09-06 | Madinat Al Riyad-Majlis-P162 | P162 | MJ-13 | 60 | 548 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.56% | 1.41% | -0.15% | Site Mobilization |  |  |  | 2024-09-13 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 98073241.5243 | 0 | 98073241.5243 | 3229333.33 |  | 101302574.8543 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN&sz=w1000 | https://drive.google.com/file/d/1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN/view | https://drive.google.com/thumbnail?id=10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce&sz=w1000 | https://drive.google.com/file/d/10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce/view | https://drive.google.com/thumbnail?id=1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU&sz=w1000 | https://drive.google.com/file/d/1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU/view
2024-09-06 | Madinat Al Riyad-Majlis-P162 | P162 | MJ-13 | 60 | 548 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.56% | 1.41% | -0.15% | Shoring Drilling & Casting |  |  |  | 2024-09-13 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 98073241.5243 | 0 | 98073241.5243 | 3229333.33 |  | 101302574.8543 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN&sz=w1000 | https://drive.google.com/file/d/1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN/view | https://drive.google.com/thumbnail?id=10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce&sz=w1000 | https://drive.google.com/file/d/10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce/view | https://drive.google.com/thumbnail?id=1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU&sz=w1000 | https://drive.google.com/file/d/1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU/view
2024-09-06 | Madinat Al Riyad-Majlis-P162 | P162 | MJ-13 | 60 | 548 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.56% | 1.41% | -0.15% | Piling Drilling & Casting |  |  |  | 2024-09-13 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 98073241.5243 | 0 | 98073241.5243 | 3229333.33 |  | 101302574.8543 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN&sz=w1000 | https://drive.google.com/file/d/1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN/view | https://drive.google.com/thumbnail?id=10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce&sz=w1000 | https://drive.google.com/file/d/10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce/view | https://drive.google.com/thumbnail?id=1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU&sz=w1000 | https://drive.google.com/file/d/1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU/view
2024-09-06 | Madinat Al Riyad-Majlis-P162 | P162 | MJ-13 | 60 | 548 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.56% | 1.41% | -0.15% | Excavation |  |  |  | 2024-09-13 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 98073241.5243 | 0 | 98073241.5243 | 3229333.33 |  | 101302574.8543 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN&sz=w1000 | https://drive.google.com/file/d/1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN/view | https://drive.google.com/thumbnail?id=10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce&sz=w1000 | https://drive.google.com/file/d/10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce/view | https://drive.google.com/thumbnail?id=1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU&sz=w1000 | https://drive.google.com/file/d/1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU/view
2024-09-06 | Madinat Al Riyad-Majlis-P162 | P162 | MJ-13 | 60 | 548 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.56% | 1.41% | -0.15% | Substructure |  |  |  | 2024-09-13 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 98073241.5243 | 0 | 98073241.5243 | 3229333.33 |  | 101302574.8543 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN&sz=w1000 | https://drive.google.com/file/d/1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN/view | https://drive.google.com/thumbnail?id=10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce&sz=w1000 | https://drive.google.com/file/d/10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce/view | https://drive.google.com/thumbnail?id=1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU&sz=w1000 | https://drive.google.com/file/d/1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU/view
2024-09-06 | Madinat Al Riyad-Majlis-P162 | P162 | MJ-13 | 60 | 548 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.56% | 1.41% | -0.15% | Superstructure |  |  |  | 2024-09-13 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 98073241.5243 | 0 | 98073241.5243 | 3229333.33 |  | 101302574.8543 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN&sz=w1000 | https://drive.google.com/file/d/1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN/view | https://drive.google.com/thumbnail?id=10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce&sz=w1000 | https://drive.google.com/file/d/10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce/view | https://drive.google.com/thumbnail?id=1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU&sz=w1000 | https://drive.google.com/file/d/1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU/view
2024-09-06 | Madinat Al Riyad-Majlis-P162 | P162 | MJ-13 | 60 | 548 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.56% | 1.41% | -0.15% | MEP & Finishes |  |  |  | 2024-09-13 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 98073241.5243 | 0 | 98073241.5243 | 3229333.33 |  | 101302574.8543 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN&sz=w1000 | https://drive.google.com/file/d/1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN/view | https://drive.google.com/thumbnail?id=10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce&sz=w1000 | https://drive.google.com/file/d/10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce/view | https://drive.google.com/thumbnail?id=1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU&sz=w1000 | https://drive.google.com/file/d/1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU/view
2024-09-06 | Madinat Al Riyad-Majlis-P162 | P162 | MJ-13 | 60 | 548 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.56% | 1.41% | -0.15% | Authorities NOCs/BCC |  |  |  | 2024-09-13 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 98073241.5243 | 0 | 98073241.5243 | 3229333.33 |  | 101302574.8543 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN&sz=w1000 | https://drive.google.com/file/d/1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN/view | https://drive.google.com/thumbnail?id=10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce&sz=w1000 | https://drive.google.com/file/d/10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce/view | https://drive.google.com/thumbnail?id=1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU&sz=w1000 | https://drive.google.com/file/d/1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU/view
2024-09-06 | Madinat Al Riyad-Majlis-P162 | P162 | MJ-13 | 60 | 548 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.56% | 1.41% | -0.15% | External Works |  |  |  | 2024-09-13 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 98073241.5243 | 0 | 98073241.5243 | 3229333.33 |  | 101302574.8543 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN&sz=w1000 | https://drive.google.com/file/d/1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN/view | https://drive.google.com/thumbnail?id=10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce&sz=w1000 | https://drive.google.com/file/d/10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce/view | https://drive.google.com/thumbnail?id=1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU&sz=w1000 | https://drive.google.com/file/d/1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU/view
2024-09-06 | Madinat Al Riyad-Majlis-P162 | P162 | MJ-13 | 60 | 548 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.56% | 1.41% | -0.15% | Testing & Commissioning |  |  |  | 2024-09-13 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 98073241.5243 | 0 | 98073241.5243 | 3229333.33 |  | 101302574.8543 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN&sz=w1000 | https://drive.google.com/file/d/1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN/view | https://drive.google.com/thumbnail?id=10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce&sz=w1000 | https://drive.google.com/file/d/10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce/view | https://drive.google.com/thumbnail?id=1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU&sz=w1000 | https://drive.google.com/file/d/1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU/view
2024-09-06 | Madinat Al Riyad-Majlis-P162 | P162 | MJ-13 | 60 | 548 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.56% | 1.41% | -0.15% | Substantial Completion |  |  |  | 2024-09-13 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 98073241.5243 | 0 | 98073241.5243 | 3229333.33 |  | 101302574.8543 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN&sz=w1000 | https://drive.google.com/file/d/1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN/view | https://drive.google.com/thumbnail?id=10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce&sz=w1000 | https://drive.google.com/file/d/10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce/view | https://drive.google.com/thumbnail?id=1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU&sz=w1000 | https://drive.google.com/file/d/1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU/view
2024-09-06 | Al Samhah-Majlis-P206 | P206 | MJ-14 | 60 | 548 | 608 | • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.56% | 1.38% | -0.18% | Commencement Date | 2024-07-16 |  |  | 2024-09-13 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S • Building Permit | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan • Following up with authroties | • Mobilizing the team for shoring works • Starting of Shoring works | 110585480.0219 | 0 | 110585480.0219 | 3229333.33 |  | 113814813.3519 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1P8dv2yDVWK28813AIv4m4F9tgxPrdqDO&sz=w1000 | https://drive.google.com/file/d/1P8dv2yDVWK28813AIv4m4F9tgxPrdqDO/view | https://drive.google.com/thumbnail?id=11gAT3uSf6EhqY1gp7ESxBQx3ZJOIXz2O&sz=w1000 | https://drive.google.com/file/d/11gAT3uSf6EhqY1gp7ESxBQx3ZJOIXz2O/view | https://drive.google.com/thumbnail?id=10HQlUfuCM9rvKh755NA9pHKofaluje0o&sz=w1000 | https://drive.google.com/file/d/10HQlUfuCM9rvKh755NA9pHKofaluje0o/view
2024-09-06 | Al Samhah-Majlis-P206 | P206 | MJ-14 | 60 | 555 | 615 | • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.56% | 1.38% | -0.18% | Construction Permit |  |  |  | 2024-09-13 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S • Building Permit | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan • Following up with authroties | • Mobilizing the team for shoring works • Starting of Shoring works | 110585480.0219 | 0 | 110585480.0219 | 3229333.33 |  | 113814813.3519 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1P8dv2yDVWK28813AIv4m4F9tgxPrdqDO&sz=w1000 | https://drive.google.com/file/d/1P8dv2yDVWK28813AIv4m4F9tgxPrdqDO/view | https://drive.google.com/thumbnail?id=11gAT3uSf6EhqY1gp7ESxBQx3ZJOIXz2O&sz=w1000 | https://drive.google.com/file/d/11gAT3uSf6EhqY1gp7ESxBQx3ZJOIXz2O/view | https://drive.google.com/thumbnail?id=10HQlUfuCM9rvKh755NA9pHKofaluje0o&sz=w1000 | https://drive.google.com/file/d/10HQlUfuCM9rvKh755NA9pHKofaluje0o/view
2024-09-06 | Al Samhah-Majlis-P206 | P206 | MJ-14 | 60 | 555 | 615 | • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.56% | 1.38% | -0.18% | Site Mobilization |  |  |  | 2024-09-13 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S • Building Permit | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan • Following up with authroties | • Mobilizing the team for shoring works • Starting of Shoring works | 110585480.0219 | 0 | 110585480.0219 | 3229333.33 |  | 113814813.3519 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1P8dv2yDVWK28813AIv4m4F9tgxPrdqDO&sz=w1000 | https://drive.google.com/file/d/1P8dv2yDVWK28813AIv4m4F9tgxPrdqDO/view | https://drive.google.com/thumbnail?id=11gAT3uSf6EhqY1gp7ESxBQx3ZJOIXz2O&sz=w1000 | https://drive.google.com/file/d/11gAT3uSf6EhqY1gp7ESxBQx3ZJOIXz2O/view | https://drive.google.com/thumbnail?id=10HQlUfuCM9rvKh755NA9pHKofaluje0o&sz=w1000 | https://drive.google.com/file/d/10HQlUfuCM9rvKh755NA9pHKofaluje0o/view
2024-09-06 | Al Samhah-Majlis-P206 | P206 | MJ-14 | 60 | 555 | 615 | • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.56% | 1.38% | -0.18% | Shoring Drilling & Casting |  |  |  | 2024-09-13 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S • Building Permit | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan • Following up with authroties | • Mobilizing the team for shoring works • Starting of Shoring works | 110585480.0219 | 0 | 110585480.0219 | 3229333.33 |  | 113814813.3519 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1P8dv2yDVWK28813AIv4m4F9tgxPrdqDO&sz=w1000 | https://drive.google.com/file/d/1P8dv2yDVWK28813AIv4m4F9tgxPrdqDO/view | https://drive.google.com/thumbnail?id=11gAT3uSf6EhqY1gp7ESxBQx3ZJOIXz2O&sz=w1000 | https://drive.google.com/file/d/11gAT3uSf6EhqY1gp7ESxBQx3ZJOIXz2O/view | https://drive.google.com/thumbnail?id=10HQlUfuCM9rvKh755NA9pHKofaluje0o&sz=w1000 | https://drive.google.com/file/d/10HQlUfuCM9rvKh755NA9pHKofaluje0o/view
2024-09-06 | Al Samhah-Majlis-P206 | P206 | MJ-14 | 60 | 555 | 615 | • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.56% | 1.38% | -0.18% | Piling Drilling & Casting |  |  |  | 2024-09-13 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S • Building Permit | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan • Following up with authroties | • Mobilizing the team for shoring works • Starting of Shoring works | 110585480.0219 | 0 | 110585480.0219 | 3229333.33 |  | 113814813.3519 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1P8dv2yDVWK28813AIv4m4F9tgxPrdqDO&sz=w1000 | https://drive.google.com/file/d/1P8dv2yDVWK28813AIv4m4F9tgxPrdqDO/view | https://drive.google.com/thumbnail?id=11gAT3uSf6EhqY1gp7ESxBQx3ZJOIXz2O&sz=w1000 | https://drive.google.com/file/d/11gAT3uSf6EhqY1gp7ESxBQx3ZJOIXz2O/view | https://drive.google.com/thumbnail?id=10HQlUfuCM9rvKh755NA9pHKofaluje0o&sz=w1000 | https://drive.google.com/file/d/10HQlUfuCM9rvKh755NA9pHKofaluje0o/view
2024-09-06 | Al Samhah-Majlis-P206 | P206 | MJ-14 | 60 | 555 | 615 | • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.56% | 1.38% | -0.18% | Excavation |  |  |  | 2024-09-13 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S • Building Permit | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan • Following up with authroties | • Mobilizing the team for shoring works • Starting of Shoring works | 110585480.0219 | 0 | 110585480.0219 | 3229333.33 |  | 113814813.3519 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1P8dv2yDVWK28813AIv4m4F9tgxPrdqDO&sz=w1000 | https://drive.google.com/file/d/1P8dv2yDVWK28813AIv4m4F9tgxPrdqDO/view | https://drive.google.com/thumbnail?id=11gAT3uSf6EhqY1gp7ESxBQx3ZJOIXz2O&sz=w1000 | https://drive.google.com/file/d/11gAT3uSf6EhqY1gp7ESxBQx3ZJOIXz2O/view | https://drive.google.com/thumbnail?id=10HQlUfuCM9rvKh755NA9pHKofaluje0o&sz=w1000 | https://drive.google.com/file/d/10HQlUfuCM9rvKh755NA9pHKofaluje0o/view
2024-09-06 | Al Samhah-Majlis-P206 | P206 | MJ-14 | 60 | 555 | 615 | • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.56% | 1.38% | -0.18% | Substructure |  |  |  | 2024-09-13 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S • Building Permit | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan • Following up with authroties | • Mobilizing the team for shoring works • Starting of Shoring works | 110585480.0219 | 0 | 110585480.0219 | 3229333.33 |  | 113814813.3519 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1P8dv2yDVWK28813AIv4m4F9tgxPrdqDO&sz=w1000 | https://drive.google.com/file/d/1P8dv2yDVWK28813AIv4m4F9tgxPrdqDO/view | https://drive.google.com/thumbnail?id=11gAT3uSf6EhqY1gp7ESxBQx3ZJOIXz2O&sz=w1000 | https://drive.google.com/file/d/11gAT3uSf6EhqY1gp7ESxBQx3ZJOIXz2O/view | https://drive.google.com/thumbnail?id=10HQlUfuCM9rvKh755NA9pHKofaluje0o&sz=w1000 | https://drive.google.com/file/d/10HQlUfuCM9rvKh755NA9pHKofaluje0o/view
2024-09-06 | Al Samhah-Majlis-P206 | P206 | MJ-14 | 60 | 555 | 615 | • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.56% | 1.38% | -0.18% | Superstructure |  |  |  | 2024-09-13 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S • Building Permit | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan • Following up with authroties | • Mobilizing the team for shoring works • Starting of Shoring works | 110585480.0219 | 0 | 110585480.0219 | 3229333.33 |  | 113814813.3519 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1P8dv2yDVWK28813AIv4m4F9tgxPrdqDO&sz=w1000 | https://drive.google.com/file/d/1P8dv2yDVWK28813AIv4m4F9tgxPrdqDO/view | https://drive.google.com/thumbnail?id=11gAT3uSf6EhqY1gp7ESxBQx3ZJOIXz2O&sz=w1000 | https://drive.google.com/file/d/11gAT3uSf6EhqY1gp7ESxBQx3ZJOIXz2O/view | https://drive.google.com/thumbnail?id=10HQlUfuCM9rvKh755NA9pHKofaluje0o&sz=w1000 | https://drive.google.com/file/d/10HQlUfuCM9rvKh755NA9pHKofaluje0o/view
2024-09-06 | Al Samhah-Majlis-P206 | P206 | MJ-14 | 60 | 555 | 615 | • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.56% | 1.38% | -0.18% | MEP & Finishes |  |  |  | 2024-09-13 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S • Building Permit | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan • Following up with authroties | • Mobilizing the team for shoring works • Starting of Shoring works | 110585480.0219 | 0 | 110585480.0219 | 3229333.33 |  | 113814813.3519 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1P8dv2yDVWK28813AIv4m4F9tgxPrdqDO&sz=w1000 | https://drive.google.com/file/d/1P8dv2yDVWK28813AIv4m4F9tgxPrdqDO/view | https://drive.google.com/thumbnail?id=11gAT3uSf6EhqY1gp7ESxBQx3ZJOIXz2O&sz=w1000 | https://drive.google.com/file/d/11gAT3uSf6EhqY1gp7ESxBQx3ZJOIXz2O/view | https://drive.google.com/thumbnail?id=10HQlUfuCM9rvKh755NA9pHKofaluje0o&sz=w1000 | https://drive.google.com/file/d/10HQlUfuCM9rvKh755NA9pHKofaluje0o/view
2024-09-06 | Al Samhah-Majlis-P206 | P206 | MJ-14 | 60 | 555 | 615 | • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.56% | 1.38% | -0.18% | Authorities NOCs/BCC |  |  |  | 2024-09-13 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S • Building Permit | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan • Following up with authroties | • Mobilizing the team for shoring works • Starting of Shoring works | 110585480.0219 | 0 | 110585480.0219 | 3229333.33 |  | 113814813.3519 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1P8dv2yDVWK28813AIv4m4F9tgxPrdqDO&sz=w1000 | https://drive.google.com/file/d/1P8dv2yDVWK28813AIv4m4F9tgxPrdqDO/view | https://drive.google.com/thumbnail?id=11gAT3uSf6EhqY1gp7ESxBQx3ZJOIXz2O&sz=w1000 | https://drive.google.com/file/d/11gAT3uSf6EhqY1gp7ESxBQx3ZJOIXz2O/view | https://drive.google.com/thumbnail?id=10HQlUfuCM9rvKh755NA9pHKofaluje0o&sz=w1000 | https://drive.google.com/file/d/10HQlUfuCM9rvKh755NA9pHKofaluje0o/view
2024-09-06 | Al Samhah-Majlis-P206 | P206 | MJ-14 | 60 | 555 | 615 | • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.56% | 1.38% | -0.18% | External Works |  |  |  | 2024-09-13 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S • Building Permit | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan • Following up with authroties | • Mobilizing the team for shoring works • Starting of Shoring works | 110585480.0219 | 0 | 110585480.0219 | 3229333.33 |  | 113814813.3519 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1P8dv2yDVWK28813AIv4m4F9tgxPrdqDO&sz=w1000 | https://drive.google.com/file/d/1P8dv2yDVWK28813AIv4m4F9tgxPrdqDO/view | https://drive.google.com/thumbnail?id=11gAT3uSf6EhqY1gp7ESxBQx3ZJOIXz2O&sz=w1000 | https://drive.google.com/file/d/11gAT3uSf6EhqY1gp7ESxBQx3ZJOIXz2O/view | https://drive.google.com/thumbnail?id=10HQlUfuCM9rvKh755NA9pHKofaluje0o&sz=w1000 | https://drive.google.com/file/d/10HQlUfuCM9rvKh755NA9pHKofaluje0o/view
2024-09-06 | Al Samhah-Majlis-P206 | P206 | MJ-14 | 60 | 555 | 615 | • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.56% | 1.38% | -0.18% | Testing & Commissioning |  |  |  | 2024-09-13 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S • Building Permit | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan • Following up with authroties | • Mobilizing the team for shoring works • Starting of Shoring works | 110585480.0219 | 0 | 110585480.0219 | 3229333.33 |  | 113814813.3519 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1P8dv2yDVWK28813AIv4m4F9tgxPrdqDO&sz=w1000 | https://drive.google.com/file/d/1P8dv2yDVWK28813AIv4m4F9tgxPrdqDO/view | https://drive.google.com/thumbnail?id=11gAT3uSf6EhqY1gp7ESxBQx3ZJOIXz2O&sz=w1000 | https://drive.google.com/file/d/11gAT3uSf6EhqY1gp7ESxBQx3ZJOIXz2O/view | https://drive.google.com/thumbnail?id=10HQlUfuCM9rvKh755NA9pHKofaluje0o&sz=w1000 | https://drive.google.com/file/d/10HQlUfuCM9rvKh755NA9pHKofaluje0o/view
2024-09-06 | Al Samhah-Majlis-P206 | P206 | MJ-14 | 60 | 555 | 615 | • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 |  | 1.56% | 1.38% | -0.18% | Substantial Completion |  |  |  | 2024-09-13 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S • Building Permit | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan • Following up with authroties | • Mobilizing the team for shoring works • Starting of Shoring works | 110585480.0219 | 0 | 110585480.0219 | 3229333.33 |  | 113814813.3519 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1P8dv2yDVWK28813AIv4m4F9tgxPrdqDO&sz=w1000 | https://drive.google.com/file/d/1P8dv2yDVWK28813AIv4m4F9tgxPrdqDO/view | https://drive.google.com/thumbnail?id=11gAT3uSf6EhqY1gp7ESxBQx3ZJOIXz2O&sz=w1000 | https://drive.google.com/file/d/11gAT3uSf6EhqY1gp7ESxBQx3ZJOIXz2O/view | https://drive.google.com/thumbnail?id=10HQlUfuCM9rvKh755NA9pHKofaluje0o&sz=w1000 | https://drive.google.com/file/d/10HQlUfuCM9rvKh755NA9pHKofaluje0o/view
2024-09-06 | Baniyas-School-P77 | P77 | SC-01 | 186 | 363 | 549 | • Annex Building - GF Rebar fixing – 35% Completed; Concrete 8% Completed • School Building - RCC Plinth Wall Concrete pouring 95% Completed; GF Rebar Fixing 51% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 0.0375 | 0.1536 | 11.61% | Notice to Commence | 2024-03-05 | 2024-03-05 |  | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Grade slab works to progress • Annex Building - GF RCC wall works to progress • Shelter Block - Substructure –RCC Wall upto Plinth to progress. • Shelter Block - RCC Wall Rebar Fixing to progress at GF & FF Level • Shelter Block - Surface Preparation for CRFP works | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 8897764.4965 | 180000 | https://drive.google.com/thumbnail?id=1dtmjjVifpdyX31hTWKtbOj-VXJHs1FLR&sz=w1000 | https://drive.google.com/file/d/1dtmjjVifpdyX31hTWKtbOj-VXJHs1FLR/view?usp=drive_link | https://drive.google.com/thumbnail?id=1JSFImQsE-aSNBi1_XGaeHY1TM31sTpH0&sz=w1000 | https://drive.google.com/file/d/1JSFImQsE-aSNBi1_XGaeHY1TM31sTpH0/view?usp=drive_link | https://drive.google.com/thumbnail?id=1OXVVqgSOAs7Kf0OYXBLzBzLajLz35A4_&sz=w1000 | https://drive.google.com/file/d/1OXVVqgSOAs7Kf0OYXBLzBzLajLz35A4_/view?usp=drive_link
2024-09-06 | Baniyas-School-P77 | P77 | SC-01 | 186 | 363 | 549 | • Annex Building - GF Rebar fixing – 35% Completed; Concrete 8% Completed • School Building - RCC Plinth Wall Concrete pouring 95% Completed; GF Rebar Fixing 51% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 0.0375 | 0.1536 | 11.61% | Site Mobilization | 2024-04-09 | 2024-05-18 |  | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Grade slab works to progress • Annex Building - GF RCC wall works to progress • Shelter Block - Substructure –RCC Wall upto Plinth to progress. • Shelter Block - RCC Wall Rebar Fixing to progress at GF & FF Level • Shelter Block - Surface Preparation for CRFP works | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 8897764.4965 | 180000 | https://drive.google.com/thumbnail?id=1dtmjjVifpdyX31hTWKtbOj-VXJHs1FLR&sz=w1000 | https://drive.google.com/file/d/1dtmjjVifpdyX31hTWKtbOj-VXJHs1FLR/view?usp=drive_link | https://drive.google.com/thumbnail?id=1JSFImQsE-aSNBi1_XGaeHY1TM31sTpH0&sz=w1000 | https://drive.google.com/file/d/1JSFImQsE-aSNBi1_XGaeHY1TM31sTpH0/view?usp=drive_link | https://drive.google.com/thumbnail?id=1OXVVqgSOAs7Kf0OYXBLzBzLajLz35A4_&sz=w1000 | https://drive.google.com/file/d/1OXVVqgSOAs7Kf0OYXBLzBzLajLz35A4_/view?usp=drive_link
2024-09-06 | Baniyas-School-P77 | P77 | SC-01 | 186 | 363 | 549 | • Annex Building - GF Rebar fixing – 35% Completed; Concrete 8% Completed • School Building - RCC Plinth Wall Concrete pouring 95% Completed; GF Rebar Fixing 51% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 0.0375 | 0.1536 | 11.61% | Building Permit | 2024-11-01 | 2024-08-06 |  | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Grade slab works to progress • Annex Building - GF RCC wall works to progress • Shelter Block - Substructure –RCC Wall upto Plinth to progress. • Shelter Block - RCC Wall Rebar Fixing to progress at GF & FF Level • Shelter Block - Surface Preparation for CRFP works | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 8897764.4965 | 180000 | https://drive.google.com/thumbnail?id=1dtmjjVifpdyX31hTWKtbOj-VXJHs1FLR&sz=w1000 | https://drive.google.com/file/d/1dtmjjVifpdyX31hTWKtbOj-VXJHs1FLR/view?usp=drive_link | https://drive.google.com/thumbnail?id=1JSFImQsE-aSNBi1_XGaeHY1TM31sTpH0&sz=w1000 | https://drive.google.com/file/d/1JSFImQsE-aSNBi1_XGaeHY1TM31sTpH0/view?usp=drive_link | https://drive.google.com/thumbnail?id=1OXVVqgSOAs7Kf0OYXBLzBzLajLz35A4_&sz=w1000 | https://drive.google.com/file/d/1OXVVqgSOAs7Kf0OYXBLzBzLajLz35A4_/view?usp=drive_link
2024-09-06 | Baniyas-School-P77 | P77 | SC-01 | 186 | 363 | 549 | • Annex Building - GF Rebar fixing – 35% Completed; Concrete 8% Completed • School Building - RCC Plinth Wall Concrete pouring 95% Completed; GF Rebar Fixing 51% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 0.0375 | 0.1536 | 11.61% | School Substructure | 2025-01-21 |  | 2024-09-20 | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Grade slab works to progress • Annex Building - GF RCC wall works to progress • Shelter Block - Substructure –RCC Wall upto Plinth to progress. • Shelter Block - RCC Wall Rebar Fixing to progress at GF & FF Level • Shelter Block - Surface Preparation for CRFP works | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 8897764.4965 | 180000 | https://drive.google.com/thumbnail?id=1dtmjjVifpdyX31hTWKtbOj-VXJHs1FLR&sz=w1000 | https://drive.google.com/file/d/1dtmjjVifpdyX31hTWKtbOj-VXJHs1FLR/view?usp=drive_link | https://drive.google.com/thumbnail?id=1JSFImQsE-aSNBi1_XGaeHY1TM31sTpH0&sz=w1000 | https://drive.google.com/file/d/1JSFImQsE-aSNBi1_XGaeHY1TM31sTpH0/view?usp=drive_link | https://drive.google.com/thumbnail?id=1OXVVqgSOAs7Kf0OYXBLzBzLajLz35A4_&sz=w1000 | https://drive.google.com/file/d/1OXVVqgSOAs7Kf0OYXBLzBzLajLz35A4_/view?usp=drive_link
2024-09-06 | Baniyas-School-P77 | P77 | SC-01 | 186 | 377 | 563 | • Annex Building - GF Rebar fixing – 35% Completed; Concrete 8% Completed • School Building - RCC Plinth Wall Concrete pouring 95% Completed; GF Rebar Fixing 51% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 0.0375 | 0.1536 | 11.61% | School Superstructure | 2025-04-28 |  | 2024-10-21 | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Grade slab works to progress • Annex Building - GF RCC wall works to progress • Shelter Block - Substructure –RCC Wall upto Plinth to progress. • Shelter Block - RCC Wall Rebar Fixing to progress at GF & FF Level • Shelter Block - Surface Preparation for CRFP works | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 8897764.4965 | 180000 | https://drive.google.com/thumbnail?id=1dtmjjVifpdyX31hTWKtbOj-VXJHs1FLR&sz=w1000 | https://drive.google.com/file/d/1dtmjjVifpdyX31hTWKtbOj-VXJHs1FLR/view?usp=drive_link | https://drive.google.com/thumbnail?id=1JSFImQsE-aSNBi1_XGaeHY1TM31sTpH0&sz=w1000 | https://drive.google.com/file/d/1JSFImQsE-aSNBi1_XGaeHY1TM31sTpH0/view?usp=drive_link | https://drive.google.com/thumbnail?id=1OXVVqgSOAs7Kf0OYXBLzBzLajLz35A4_&sz=w1000 | https://drive.google.com/file/d/1OXVVqgSOAs7Kf0OYXBLzBzLajLz35A4_/view?usp=drive_link
2024-09-06 | Baniyas-School-P77 | P77 | SC-01 | 186 | 377 | 563 | • Annex Building - GF Rebar fixing – 35% Completed; Concrete 8% Completed • School Building - RCC Plinth Wall Concrete pouring 95% Completed; GF Rebar Fixing 51% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 0.0375 | 0.1536 | 11.61% | Annex Substructure | 2025-01-22 | 2024-08-17 |  | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Grade slab works to progress • Annex Building - GF RCC wall works to progress • Shelter Block - Substructure –RCC Wall upto Plinth to progress. • Shelter Block - RCC Wall Rebar Fixing to progress at GF & FF Level • Shelter Block - Surface Preparation for CRFP works | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 8897764.4965 | 180000 | https://drive.google.com/thumbnail?id=1dtmjjVifpdyX31hTWKtbOj-VXJHs1FLR&sz=w1000 | https://drive.google.com/file/d/1dtmjjVifpdyX31hTWKtbOj-VXJHs1FLR/view?usp=drive_link | https://drive.google.com/thumbnail?id=1JSFImQsE-aSNBi1_XGaeHY1TM31sTpH0&sz=w1000 | https://drive.google.com/file/d/1JSFImQsE-aSNBi1_XGaeHY1TM31sTpH0/view?usp=drive_link | https://drive.google.com/thumbnail?id=1OXVVqgSOAs7Kf0OYXBLzBzLajLz35A4_&sz=w1000 | https://drive.google.com/file/d/1OXVVqgSOAs7Kf0OYXBLzBzLajLz35A4_/view?usp=drive_link
2024-09-06 | Baniyas-School-P77 | P77 | SC-01 | 186 | 377 | 563 | • Annex Building - GF Rebar fixing – 35% Completed; Concrete 8% Completed • School Building - RCC Plinth Wall Concrete pouring 95% Completed; GF Rebar Fixing 51% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 0.0375 | 0.1536 | 11.61% | Annex Superstructure | 2025-04-21 |  | 2025-01-16 | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Grade slab works to progress • Annex Building - GF RCC wall works to progress • Shelter Block - Substructure –RCC Wall upto Plinth to progress. • Shelter Block - RCC Wall Rebar Fixing to progress at GF & FF Level • Shelter Block - Surface Preparation for CRFP works | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 8897764.4965 | 180000 | https://drive.google.com/thumbnail?id=1dtmjjVifpdyX31hTWKtbOj-VXJHs1FLR&sz=w1000 | https://drive.google.com/file/d/1dtmjjVifpdyX31hTWKtbOj-VXJHs1FLR/view?usp=drive_link | https://drive.google.com/thumbnail?id=1JSFImQsE-aSNBi1_XGaeHY1TM31sTpH0&sz=w1000 | https://drive.google.com/file/d/1JSFImQsE-aSNBi1_XGaeHY1TM31sTpH0/view?usp=drive_link | https://drive.google.com/thumbnail?id=1OXVVqgSOAs7Kf0OYXBLzBzLajLz35A4_&sz=w1000 | https://drive.google.com/file/d/1OXVVqgSOAs7Kf0OYXBLzBzLajLz35A4_/view?usp=drive_link
2024-09-06 | Baniyas-School-P77 | P77 | SC-01 | 186 | 377 | 563 | • Annex Building - GF Rebar fixing – 35% Completed; Concrete 8% Completed • School Building - RCC Plinth Wall Concrete pouring 95% Completed; GF Rebar Fixing 51% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 0.0375 | 0.1536 | 11.61% | MEP & Finishes | 2025-07-19 |  | 2025-06-11 | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Grade slab works to progress • Annex Building - GF RCC wall works to progress • Shelter Block - Substructure –RCC Wall upto Plinth to progress. • Shelter Block - RCC Wall Rebar Fixing to progress at GF & FF Level • Shelter Block - Surface Preparation for CRFP works | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 8897764.4965 | 180000 | https://drive.google.com/thumbnail?id=1dtmjjVifpdyX31hTWKtbOj-VXJHs1FLR&sz=w1000 | https://drive.google.com/file/d/1dtmjjVifpdyX31hTWKtbOj-VXJHs1FLR/view?usp=drive_link | https://drive.google.com/thumbnail?id=1JSFImQsE-aSNBi1_XGaeHY1TM31sTpH0&sz=w1000 | https://drive.google.com/file/d/1JSFImQsE-aSNBi1_XGaeHY1TM31sTpH0/view?usp=drive_link | https://drive.google.com/thumbnail?id=1OXVVqgSOAs7Kf0OYXBLzBzLajLz35A4_&sz=w1000 | https://drive.google.com/file/d/1OXVVqgSOAs7Kf0OYXBLzBzLajLz35A4_/view?usp=drive_link
2024-09-06 | Baniyas-School-P77 | P77 | SC-01 | 186 | 377 | 563 | • Annex Building - GF Rebar fixing – 35% Completed; Concrete 8% Completed • School Building - RCC Plinth Wall Concrete pouring 95% Completed; GF Rebar Fixing 51% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 0.0375 | 0.1536 | 11.61% | BCC Inspection | 2025-08-05 |  | 2025-06-21 | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Grade slab works to progress • Annex Building - GF RCC wall works to progress • Shelter Block - Substructure –RCC Wall upto Plinth to progress. • Shelter Block - RCC Wall Rebar Fixing to progress at GF & FF Level • Shelter Block - Surface Preparation for CRFP works | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 8897764.4965 | 180000 | https://drive.google.com/thumbnail?id=1dtmjjVifpdyX31hTWKtbOj-VXJHs1FLR&sz=w1000 | https://drive.google.com/file/d/1dtmjjVifpdyX31hTWKtbOj-VXJHs1FLR/view?usp=drive_link | https://drive.google.com/thumbnail?id=1JSFImQsE-aSNBi1_XGaeHY1TM31sTpH0&sz=w1000 | https://drive.google.com/file/d/1JSFImQsE-aSNBi1_XGaeHY1TM31sTpH0/view?usp=drive_link | https://drive.google.com/thumbnail?id=1OXVVqgSOAs7Kf0OYXBLzBzLajLz35A4_&sz=w1000 | https://drive.google.com/file/d/1OXVVqgSOAs7Kf0OYXBLzBzLajLz35A4_/view?usp=drive_link
2024-09-06 | Baniyas-School-P77 | P77 | SC-01 | 186 | 377 | 563 | • Annex Building - GF Rebar fixing – 35% Completed; Concrete 8% Completed • School Building - RCC Plinth Wall Concrete pouring 95% Completed; GF Rebar Fixing 51% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 0.0375 | 0.1536 | 11.61% | BCC Issuance | 2025-08-22 |  | 2025-07-09 | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Grade slab works to progress • Annex Building - GF RCC wall works to progress • Shelter Block - Substructure –RCC Wall upto Plinth to progress. • Shelter Block - RCC Wall Rebar Fixing to progress at GF & FF Level • Shelter Block - Surface Preparation for CRFP works | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 8897764.4965 | 180000 | https://drive.google.com/thumbnail?id=1dtmjjVifpdyX31hTWKtbOj-VXJHs1FLR&sz=w1000 | https://drive.google.com/file/d/1dtmjjVifpdyX31hTWKtbOj-VXJHs1FLR/view?usp=drive_link | https://drive.google.com/thumbnail?id=1JSFImQsE-aSNBi1_XGaeHY1TM31sTpH0&sz=w1000 | https://drive.google.com/file/d/1JSFImQsE-aSNBi1_XGaeHY1TM31sTpH0/view?usp=drive_link | https://drive.google.com/thumbnail?id=1OXVVqgSOAs7Kf0OYXBLzBzLajLz35A4_&sz=w1000 | https://drive.google.com/file/d/1OXVVqgSOAs7Kf0OYXBLzBzLajLz35A4_/view?usp=drive_link
2024-09-06 | Baniyas-School-P77 | P77 | SC-01 | 186 | 377 | 563 | • Annex Building - GF Rebar fixing – 35% Completed; Concrete 8% Completed • School Building - RCC Plinth Wall Concrete pouring 95% Completed; GF Rebar Fixing 51% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 0.0375 | 0.1536 | 11.61% | Completion | 2025-09-04 |  | 2025-08-04 | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Grade slab works to progress • Annex Building - GF RCC wall works to progress • Shelter Block - Substructure –RCC Wall upto Plinth to progress. • Shelter Block - RCC Wall Rebar Fixing to progress at GF & FF Level • Shelter Block - Surface Preparation for CRFP works | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 8897764.4965 | 180000 | https://drive.google.com/thumbnail?id=1dtmjjVifpdyX31hTWKtbOj-VXJHs1FLR&sz=w1000 | https://drive.google.com/file/d/1dtmjjVifpdyX31hTWKtbOj-VXJHs1FLR/view?usp=drive_link | https://drive.google.com/thumbnail?id=1JSFImQsE-aSNBi1_XGaeHY1TM31sTpH0&sz=w1000 | https://drive.google.com/file/d/1JSFImQsE-aSNBi1_XGaeHY1TM31sTpH0/view?usp=drive_link | https://drive.google.com/thumbnail?id=1OXVVqgSOAs7Kf0OYXBLzBzLajLz35A4_&sz=w1000 | https://drive.google.com/file/d/1OXVVqgSOAs7Kf0OYXBLzBzLajLz35A4_/view?usp=drive_link
2024-09-06 | Al Shahama-School-P17 | P17 | SC-02 | 355 | 192 | 547 | • Annex Building - 1FF Slab - Staging & Shutter fixing 95% Completed • School Building - GF - RCC Wall Rebar fixing100% Completed, FF - Rebar Fixing 85% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 26.9% | 27.44% | 0.54% | Notice to Commence | 2023-09-18 | 2023-09-26 |  | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – FF Slab work & FF Wall Rebar, Shutter & Concrete pouring up to RF FL level • Shelter Block - Substructure – Waterproofing & Backfilling works. • Shelter Block - Superstructure - RCC wall to progress GF & 1FL • Shelter Block - Surface Preparation & Application of CFRP • Shelter Block - Roof Slab Strengthening works to progress | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 12271635.5944 | 180000 | https://drive.google.com/thumbnail?id=1rB6fHuIxGh5D4VZSJD6ZhvSpEbCfXrnN&sz=w1000 | https://drive.google.com/file/d/1rB6fHuIxGh5D4VZSJD6ZhvSpEbCfXrnN/view?usp=drive_link | https://drive.google.com/thumbnail?id=1qRnd6QBDXGDZrXClC7fkscnVjqbMHsCo&sz=w1000 | https://drive.google.com/file/d/1qRnd6QBDXGDZrXClC7fkscnVjqbMHsCo/view?usp=drive_link | https://drive.google.com/thumbnail?id=16iCRVZ9FIxsqJnxI634PDZC4GeoM1QjJ&sz=w1000 | https://drive.google.com/file/d/16iCRVZ9FIxsqJnxI634PDZC4GeoM1QjJ/view?usp=drive_link
2024-09-06 | Al Shahama-School-P17 | P17 | SC-02 | 355 | 192 | 547 | • Annex Building - 1FF Slab - Staging & Shutter fixing 95% Completed • School Building - GF - RCC Wall Rebar fixing100% Completed, FF - Rebar Fixing 85% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 26.9% | 27.44% | 0.54% | Site Mobilization | 2023-10-21 | 2023-12-06 |  | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – FF Slab work & FF Wall Rebar, Shutter & Concrete pouring up to RF FL level • Shelter Block - Substructure – Waterproofing & Backfilling works. • Shelter Block - Superstructure - RCC wall to progress GF & 1FL • Shelter Block - Surface Preparation & Application of CFRP • Shelter Block - Roof Slab Strengthening works to progress | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 12271635.5944 | 180000 | https://drive.google.com/thumbnail?id=1rB6fHuIxGh5D4VZSJD6ZhvSpEbCfXrnN&sz=w1000 | https://drive.google.com/file/d/1rB6fHuIxGh5D4VZSJD6ZhvSpEbCfXrnN/view?usp=drive_link | https://drive.google.com/thumbnail?id=1qRnd6QBDXGDZrXClC7fkscnVjqbMHsCo&sz=w1000 | https://drive.google.com/file/d/1qRnd6QBDXGDZrXClC7fkscnVjqbMHsCo/view?usp=drive_link | https://drive.google.com/thumbnail?id=16iCRVZ9FIxsqJnxI634PDZC4GeoM1QjJ&sz=w1000 | https://drive.google.com/file/d/16iCRVZ9FIxsqJnxI634PDZC4GeoM1QjJ/view?usp=drive_link
2024-09-06 | Al Shahama-School-P17 | P17 | SC-02 | 355 | 192 | 547 | • Annex Building - 1FF Slab - Staging & Shutter fixing 95% Completed • School Building - GF - RCC Wall Rebar fixing100% Completed, FF - Rebar Fixing 85% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 26.9% | 27.44% | 0.54% | Building Permit | 2024-05-17 | 2024-05-23 |  | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – FF Slab work & FF Wall Rebar, Shutter & Concrete pouring up to RF FL level • Shelter Block - Substructure – Waterproofing & Backfilling works. • Shelter Block - Superstructure - RCC wall to progress GF & 1FL • Shelter Block - Surface Preparation & Application of CFRP • Shelter Block - Roof Slab Strengthening works to progress | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 12271635.5944 | 180000 | https://drive.google.com/thumbnail?id=1rB6fHuIxGh5D4VZSJD6ZhvSpEbCfXrnN&sz=w1000 | https://drive.google.com/file/d/1rB6fHuIxGh5D4VZSJD6ZhvSpEbCfXrnN/view?usp=drive_link | https://drive.google.com/thumbnail?id=1qRnd6QBDXGDZrXClC7fkscnVjqbMHsCo&sz=w1000 | https://drive.google.com/file/d/1qRnd6QBDXGDZrXClC7fkscnVjqbMHsCo/view?usp=drive_link | https://drive.google.com/thumbnail?id=16iCRVZ9FIxsqJnxI634PDZC4GeoM1QjJ&sz=w1000 | https://drive.google.com/file/d/16iCRVZ9FIxsqJnxI634PDZC4GeoM1QjJ/view?usp=drive_link
2024-09-06 | Al Shahama-School-P17 | P17 | SC-02 | 355 | 192 | 547 | • Annex Building - 1FF Slab - Staging & Shutter fixing 95% Completed • School Building - GF - RCC Wall Rebar fixing100% Completed, FF - Rebar Fixing 85% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 26.9% | 27.44% | 0.54% | School Substructure | 2024-08-06 |  | 2024-09-13 | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – FF Slab work & FF Wall Rebar, Shutter & Concrete pouring up to RF FL level • Shelter Block - Substructure – Waterproofing & Backfilling works. • Shelter Block - Superstructure - RCC wall to progress GF & 1FL • Shelter Block - Surface Preparation & Application of CFRP • Shelter Block - Roof Slab Strengthening works to progress | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 12271635.5944 | 180000 | https://drive.google.com/thumbnail?id=1rB6fHuIxGh5D4VZSJD6ZhvSpEbCfXrnN&sz=w1000 | https://drive.google.com/file/d/1rB6fHuIxGh5D4VZSJD6ZhvSpEbCfXrnN/view?usp=drive_link | https://drive.google.com/thumbnail?id=1qRnd6QBDXGDZrXClC7fkscnVjqbMHsCo&sz=w1000 | https://drive.google.com/file/d/1qRnd6QBDXGDZrXClC7fkscnVjqbMHsCo/view?usp=drive_link | https://drive.google.com/thumbnail?id=16iCRVZ9FIxsqJnxI634PDZC4GeoM1QjJ&sz=w1000 | https://drive.google.com/file/d/16iCRVZ9FIxsqJnxI634PDZC4GeoM1QjJ/view?usp=drive_link
2024-09-06 | Al Shahama-School-P17 | P17 | SC-02 | 355 | 192 | 547 | • Annex Building - 1FF Slab - Staging & Shutter fixing 95% Completed • School Building - GF - RCC Wall Rebar fixing100% Completed, FF - Rebar Fixing 85% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 26.9% | 27.44% | 0.54% | School Superstructure | 2024-11-07 |  | 2024-10-02 | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – FF Slab work & FF Wall Rebar, Shutter & Concrete pouring up to RF FL level • Shelter Block - Substructure – Waterproofing & Backfilling works. • Shelter Block - Superstructure - RCC wall to progress GF & 1FL • Shelter Block - Surface Preparation & Application of CFRP • Shelter Block - Roof Slab Strengthening works to progress | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 12271635.5944 | 180000 | https://drive.google.com/thumbnail?id=1rB6fHuIxGh5D4VZSJD6ZhvSpEbCfXrnN&sz=w1000 | https://drive.google.com/file/d/1rB6fHuIxGh5D4VZSJD6ZhvSpEbCfXrnN/view?usp=drive_link | https://drive.google.com/thumbnail?id=1qRnd6QBDXGDZrXClC7fkscnVjqbMHsCo&sz=w1000 | https://drive.google.com/file/d/1qRnd6QBDXGDZrXClC7fkscnVjqbMHsCo/view?usp=drive_link | https://drive.google.com/thumbnail?id=16iCRVZ9FIxsqJnxI634PDZC4GeoM1QjJ&sz=w1000 | https://drive.google.com/file/d/16iCRVZ9FIxsqJnxI634PDZC4GeoM1QjJ/view?usp=drive_link
2024-09-06 | Al Shahama-School-P17 | P17 | SC-02 | 355 | 192 | 547 | • Annex Building - 1FF Slab - Staging & Shutter fixing 95% Completed • School Building - GF - RCC Wall Rebar fixing100% Completed, FF - Rebar Fixing 85% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 26.9% | 27.44% | 0.54% | Annex Substructure | 2024-08-07 | 2024-07-04 |  | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – FF Slab work & FF Wall Rebar, Shutter & Concrete pouring up to RF FL level • Shelter Block - Substructure – Waterproofing & Backfilling works. • Shelter Block - Superstructure - RCC wall to progress GF & 1FL • Shelter Block - Surface Preparation & Application of CFRP • Shelter Block - Roof Slab Strengthening works to progress | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 12271635.5944 | 180000 | https://drive.google.com/thumbnail?id=1rB6fHuIxGh5D4VZSJD6ZhvSpEbCfXrnN&sz=w1000 | https://drive.google.com/file/d/1rB6fHuIxGh5D4VZSJD6ZhvSpEbCfXrnN/view?usp=drive_link | https://drive.google.com/thumbnail?id=1qRnd6QBDXGDZrXClC7fkscnVjqbMHsCo&sz=w1000 | https://drive.google.com/file/d/1qRnd6QBDXGDZrXClC7fkscnVjqbMHsCo/view?usp=drive_link | https://drive.google.com/thumbnail?id=16iCRVZ9FIxsqJnxI634PDZC4GeoM1QjJ&sz=w1000 | https://drive.google.com/file/d/16iCRVZ9FIxsqJnxI634PDZC4GeoM1QjJ/view?usp=drive_link
2024-09-06 | Al Shahama-School-P17 | P17 | SC-02 | 355 | 192 | 547 | • Annex Building - 1FF Slab - Staging & Shutter fixing 95% Completed • School Building - GF - RCC Wall Rebar fixing100% Completed, FF - Rebar Fixing 85% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 26.9% | 27.44% | 0.54% | Annex Superstructure | 2024-10-31 |  | 2024-10-29 | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – FF Slab work & FF Wall Rebar, Shutter & Concrete pouring up to RF FL level • Shelter Block - Substructure – Waterproofing & Backfilling works. • Shelter Block - Superstructure - RCC wall to progress GF & 1FL • Shelter Block - Surface Preparation & Application of CFRP • Shelter Block - Roof Slab Strengthening works to progress | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 12271635.5944 | 180000 | https://drive.google.com/thumbnail?id=1rB6fHuIxGh5D4VZSJD6ZhvSpEbCfXrnN&sz=w1000 | https://drive.google.com/file/d/1rB6fHuIxGh5D4VZSJD6ZhvSpEbCfXrnN/view?usp=drive_link | https://drive.google.com/thumbnail?id=1qRnd6QBDXGDZrXClC7fkscnVjqbMHsCo&sz=w1000 | https://drive.google.com/file/d/1qRnd6QBDXGDZrXClC7fkscnVjqbMHsCo/view?usp=drive_link | https://drive.google.com/thumbnail?id=16iCRVZ9FIxsqJnxI634PDZC4GeoM1QjJ&sz=w1000 | https://drive.google.com/file/d/16iCRVZ9FIxsqJnxI634PDZC4GeoM1QjJ/view?usp=drive_link
2024-09-06 | Al Shahama-School-P17 | P17 | SC-02 | 355 | 192 | 547 | • Annex Building - 1FF Slab - Staging & Shutter fixing 95% Completed • School Building - GF - RCC Wall Rebar fixing100% Completed, FF - Rebar Fixing 85% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 26.9% | 27.44% | 0.54% | MEP & Finishes | 2025-01-25 |  | 2025-05-06 | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – FF Slab work & FF Wall Rebar, Shutter & Concrete pouring up to RF FL level • Shelter Block - Substructure – Waterproofing & Backfilling works. • Shelter Block - Superstructure - RCC wall to progress GF & 1FL • Shelter Block - Surface Preparation & Application of CFRP • Shelter Block - Roof Slab Strengthening works to progress | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 12271635.5944 | 180000 | https://drive.google.com/thumbnail?id=1rB6fHuIxGh5D4VZSJD6ZhvSpEbCfXrnN&sz=w1000 | https://drive.google.com/file/d/1rB6fHuIxGh5D4VZSJD6ZhvSpEbCfXrnN/view?usp=drive_link | https://drive.google.com/thumbnail?id=1qRnd6QBDXGDZrXClC7fkscnVjqbMHsCo&sz=w1000 | https://drive.google.com/file/d/1qRnd6QBDXGDZrXClC7fkscnVjqbMHsCo/view?usp=drive_link | https://drive.google.com/thumbnail?id=16iCRVZ9FIxsqJnxI634PDZC4GeoM1QjJ&sz=w1000 | https://drive.google.com/file/d/16iCRVZ9FIxsqJnxI634PDZC4GeoM1QjJ/view?usp=drive_link
2024-09-06 | Al Shahama-School-P17 | P17 | SC-02 | 355 | 192 | 547 | • Annex Building - 1FF Slab - Staging & Shutter fixing 95% Completed • School Building - GF - RCC Wall Rebar fixing100% Completed, FF - Rebar Fixing 85% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 26.9% | 27.44% | 0.54% | BCC Inspection | 2025-02-13 |  | 2025-05-26 | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – FF Slab work & FF Wall Rebar, Shutter & Concrete pouring up to RF FL level • Shelter Block - Substructure – Waterproofing & Backfilling works. • Shelter Block - Superstructure - RCC wall to progress GF & 1FL • Shelter Block - Surface Preparation & Application of CFRP • Shelter Block - Roof Slab Strengthening works to progress | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 12271635.5944 | 180000 | https://drive.google.com/thumbnail?id=1rB6fHuIxGh5D4VZSJD6ZhvSpEbCfXrnN&sz=w1000 | https://drive.google.com/file/d/1rB6fHuIxGh5D4VZSJD6ZhvSpEbCfXrnN/view?usp=drive_link | https://drive.google.com/thumbnail?id=1qRnd6QBDXGDZrXClC7fkscnVjqbMHsCo&sz=w1000 | https://drive.google.com/file/d/1qRnd6QBDXGDZrXClC7fkscnVjqbMHsCo/view?usp=drive_link | https://drive.google.com/thumbnail?id=16iCRVZ9FIxsqJnxI634PDZC4GeoM1QjJ&sz=w1000 | https://drive.google.com/file/d/16iCRVZ9FIxsqJnxI634PDZC4GeoM1QjJ/view?usp=drive_link
2024-09-06 | Al Shahama-School-P17 | P17 | SC-02 | 355 | 192 | 547 | • Annex Building - 1FF Slab - Staging & Shutter fixing 95% Completed • School Building - GF - RCC Wall Rebar fixing100% Completed, FF - Rebar Fixing 85% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 26.9% | 27.44% | 0.54% | BCC Issuance | 2025-03-04 |  | 2025-06-16 | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – FF Slab work & FF Wall Rebar, Shutter & Concrete pouring up to RF FL level • Shelter Block - Substructure – Waterproofing & Backfilling works. • Shelter Block - Superstructure - RCC wall to progress GF & 1FL • Shelter Block - Surface Preparation & Application of CFRP • Shelter Block - Roof Slab Strengthening works to progress | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 12271635.5944 | 180000 | https://drive.google.com/thumbnail?id=1rB6fHuIxGh5D4VZSJD6ZhvSpEbCfXrnN&sz=w1000 | https://drive.google.com/file/d/1rB6fHuIxGh5D4VZSJD6ZhvSpEbCfXrnN/view?usp=drive_link | https://drive.google.com/thumbnail?id=1qRnd6QBDXGDZrXClC7fkscnVjqbMHsCo&sz=w1000 | https://drive.google.com/file/d/1qRnd6QBDXGDZrXClC7fkscnVjqbMHsCo/view?usp=drive_link | https://drive.google.com/thumbnail?id=16iCRVZ9FIxsqJnxI634PDZC4GeoM1QjJ&sz=w1000 | https://drive.google.com/file/d/16iCRVZ9FIxsqJnxI634PDZC4GeoM1QjJ/view?usp=drive_link
2024-09-06 | Al Shahama-School-P17 | P17 | SC-02 | 355 | 192 | 547 | • Annex Building - 1FF Slab - Staging & Shutter fixing 95% Completed • School Building - GF - RCC Wall Rebar fixing100% Completed, FF - Rebar Fixing 85% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 26.9% | 27.44% | 0.54% | Completion | 2025-03-17 |  | 2025-06-30 | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – FF Slab work & FF Wall Rebar, Shutter & Concrete pouring up to RF FL level • Shelter Block - Substructure – Waterproofing & Backfilling works. • Shelter Block - Superstructure - RCC wall to progress GF & 1FL • Shelter Block - Surface Preparation & Application of CFRP • Shelter Block - Roof Slab Strengthening works to progress | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 12271635.5944 | 180000 | https://drive.google.com/thumbnail?id=1rB6fHuIxGh5D4VZSJD6ZhvSpEbCfXrnN&sz=w1000 | https://drive.google.com/file/d/1rB6fHuIxGh5D4VZSJD6ZhvSpEbCfXrnN/view?usp=drive_link | https://drive.google.com/thumbnail?id=1qRnd6QBDXGDZrXClC7fkscnVjqbMHsCo&sz=w1000 | https://drive.google.com/file/d/1qRnd6QBDXGDZrXClC7fkscnVjqbMHsCo/view?usp=drive_link | https://drive.google.com/thumbnail?id=16iCRVZ9FIxsqJnxI634PDZC4GeoM1QjJ&sz=w1000 | https://drive.google.com/file/d/16iCRVZ9FIxsqJnxI634PDZC4GeoM1QjJ/view?usp=drive_link
2024-09-06 | Al Sarouj-School-P2 | P2 | SC-03 | 282 | 265 | 547 | • Annex Building - Superstructure – Ground Floor RCC Wall 80% Completed • School Building - RCC Wall Concrete Upto Plinth 98% completed • School Building - GF Wall Rebar Fixing – 30% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 9.66% | 18.84% | 9.18% | Notice to Commence | 2023-11-30 | 2023-11-30 |  | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab & Beam Works to progress • Annex Building - Superstructure works – RCC wall up to FF level to progress; FF Slab Works • Shelter Block - Substructure –works to complete • Shelter Block - Superstructure – RCC Wall work GF & FF Level • Shelter Block - Surface Preparation for CRFP works to progress | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 10955306.883 | 180000 | https://drive.google.com/thumbnail?id=1EShm-JCEBeUL9t9jvi_3B6OF8gY5AK0w&sz=w1000 | https://drive.google.com/file/d/1EShm-JCEBeUL9t9jvi_3B6OF8gY5AK0w/view?usp=drive_link | https://drive.google.com/thumbnail?id=1wFL1KQ-QVw5hSLZv1AF-r-UdMul7WJMk&sz=w1000 | https://drive.google.com/file/d/1wFL1KQ-QVw5hSLZv1AF-r-UdMul7WJMk/view?usp=drive_link | https://drive.google.com/thumbnail?id=1TDk98vxQ3RO5Vex4gTvzQ8srdHf8VMYQ&sz=w1000 | https://drive.google.com/file/d/1TDk98vxQ3RO5Vex4gTvzQ8srdHf8VMYQ/view?usp=drive_link
2024-09-06 | Al Sarouj-School-P2 | P2 | SC-03 | 282 | 265 | 547 | • Annex Building - Superstructure – Ground Floor RCC Wall 80% Completed • School Building - RCC Wall Concrete Upto Plinth 98% completed • School Building - GF Wall Rebar Fixing – 30% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 9.66% | 18.84% | 9.18% | Site Mobilization | 2024-01-05 | 2024-01-06 |  | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab & Beam Works to progress • Annex Building - Superstructure works – RCC wall up to FF level to progress; FF Slab Works • Shelter Block - Substructure –works to complete • Shelter Block - Superstructure – RCC Wall work GF & FF Level • Shelter Block - Surface Preparation for CRFP works to progress | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 10955306.883 | 180000 | https://drive.google.com/thumbnail?id=1EShm-JCEBeUL9t9jvi_3B6OF8gY5AK0w&sz=w1000 | https://drive.google.com/file/d/1EShm-JCEBeUL9t9jvi_3B6OF8gY5AK0w/view?usp=drive_link | https://drive.google.com/thumbnail?id=1wFL1KQ-QVw5hSLZv1AF-r-UdMul7WJMk&sz=w1000 | https://drive.google.com/file/d/1wFL1KQ-QVw5hSLZv1AF-r-UdMul7WJMk/view?usp=drive_link | https://drive.google.com/thumbnail?id=1TDk98vxQ3RO5Vex4gTvzQ8srdHf8VMYQ&sz=w1000 | https://drive.google.com/file/d/1TDk98vxQ3RO5Vex4gTvzQ8srdHf8VMYQ/view?usp=drive_link
2024-09-06 | Al Sarouj-School-P2 | P2 | SC-03 | 282 | 265 | 547 | • Annex Building - Superstructure – Ground Floor RCC Wall 80% Completed • School Building - RCC Wall Concrete Upto Plinth 98% completed • School Building - GF Wall Rebar Fixing – 30% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 9.66% | 18.84% | 9.18% | Building Permit | 2024-07-29 | 2024-06-20 |  | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab & Beam Works to progress • Annex Building - Superstructure works – RCC wall up to FF level to progress; FF Slab Works • Shelter Block - Substructure –works to complete • Shelter Block - Superstructure – RCC Wall work GF & FF Level • Shelter Block - Surface Preparation for CRFP works to progress | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 10955306.883 | 180000 | https://drive.google.com/thumbnail?id=1EShm-JCEBeUL9t9jvi_3B6OF8gY5AK0w&sz=w1000 | https://drive.google.com/file/d/1EShm-JCEBeUL9t9jvi_3B6OF8gY5AK0w/view?usp=drive_link | https://drive.google.com/thumbnail?id=1wFL1KQ-QVw5hSLZv1AF-r-UdMul7WJMk&sz=w1000 | https://drive.google.com/file/d/1wFL1KQ-QVw5hSLZv1AF-r-UdMul7WJMk/view?usp=drive_link | https://drive.google.com/thumbnail?id=1TDk98vxQ3RO5Vex4gTvzQ8srdHf8VMYQ&sz=w1000 | https://drive.google.com/file/d/1TDk98vxQ3RO5Vex4gTvzQ8srdHf8VMYQ/view?usp=drive_link
2024-09-06 | Al Sarouj-School-P2 | P2 | SC-03 | 282 | 265 | 547 | • Annex Building - Superstructure – Ground Floor RCC Wall 80% Completed • School Building - RCC Wall Concrete Upto Plinth 98% completed • School Building - GF Wall Rebar Fixing – 30% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 9.66% | 18.84% | 9.18% | School Substructure | 2024-10-14 |  | 2024-09-20 | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab & Beam Works to progress • Annex Building - Superstructure works – RCC wall up to FF level to progress; FF Slab Works • Shelter Block - Substructure –works to complete • Shelter Block - Superstructure – RCC Wall work GF & FF Level • Shelter Block - Surface Preparation for CRFP works to progress | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 10955306.883 | 180000 | https://drive.google.com/thumbnail?id=1EShm-JCEBeUL9t9jvi_3B6OF8gY5AK0w&sz=w1000 | https://drive.google.com/file/d/1EShm-JCEBeUL9t9jvi_3B6OF8gY5AK0w/view?usp=drive_link | https://drive.google.com/thumbnail?id=1wFL1KQ-QVw5hSLZv1AF-r-UdMul7WJMk&sz=w1000 | https://drive.google.com/file/d/1wFL1KQ-QVw5hSLZv1AF-r-UdMul7WJMk/view?usp=drive_link | https://drive.google.com/thumbnail?id=1TDk98vxQ3RO5Vex4gTvzQ8srdHf8VMYQ&sz=w1000 | https://drive.google.com/file/d/1TDk98vxQ3RO5Vex4gTvzQ8srdHf8VMYQ/view?usp=drive_link
2024-09-06 | Al Sarouj-School-P2 | P2 | SC-03 | 282 | 265 | 547 | • Annex Building - Superstructure – Ground Floor RCC Wall 80% Completed • School Building - RCC Wall Concrete Upto Plinth 98% completed • School Building - GF Wall Rebar Fixing – 30% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 9.66% | 18.84% | 9.18% | School Superstructure | 2025-01-20 |  | 2024-10-23 | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab & Beam Works to progress • Annex Building - Superstructure works – RCC wall up to FF level to progress; FF Slab Works • Shelter Block - Substructure –works to complete • Shelter Block - Superstructure – RCC Wall work GF & FF Level • Shelter Block - Surface Preparation for CRFP works to progress | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 10955306.883 | 180000 | https://drive.google.com/thumbnail?id=1EShm-JCEBeUL9t9jvi_3B6OF8gY5AK0w&sz=w1000 | https://drive.google.com/file/d/1EShm-JCEBeUL9t9jvi_3B6OF8gY5AK0w/view?usp=drive_link | https://drive.google.com/thumbnail?id=1wFL1KQ-QVw5hSLZv1AF-r-UdMul7WJMk&sz=w1000 | https://drive.google.com/file/d/1wFL1KQ-QVw5hSLZv1AF-r-UdMul7WJMk/view?usp=drive_link | https://drive.google.com/thumbnail?id=1TDk98vxQ3RO5Vex4gTvzQ8srdHf8VMYQ&sz=w1000 | https://drive.google.com/file/d/1TDk98vxQ3RO5Vex4gTvzQ8srdHf8VMYQ/view?usp=drive_link
2024-09-06 | Al Sarouj-School-P2 | P2 | SC-03 | 282 | 265 | 547 | • Annex Building - Superstructure – Ground Floor RCC Wall 80% Completed • School Building - RCC Wall Concrete Upto Plinth 98% completed • School Building - GF Wall Rebar Fixing – 30% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 9.66% | 18.84% | 9.18% | Annex Substructure | 2024-10-15 | 2024-06-29 |  | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab & Beam Works to progress • Annex Building - Superstructure works – RCC wall up to FF level to progress; FF Slab Works • Shelter Block - Substructure –works to complete • Shelter Block - Superstructure – RCC Wall work GF & FF Level • Shelter Block - Surface Preparation for CRFP works to progress | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 10955306.883 | 180000 | https://drive.google.com/thumbnail?id=1EShm-JCEBeUL9t9jvi_3B6OF8gY5AK0w&sz=w1000 | https://drive.google.com/file/d/1EShm-JCEBeUL9t9jvi_3B6OF8gY5AK0w/view?usp=drive_link | https://drive.google.com/thumbnail?id=1wFL1KQ-QVw5hSLZv1AF-r-UdMul7WJMk&sz=w1000 | https://drive.google.com/file/d/1wFL1KQ-QVw5hSLZv1AF-r-UdMul7WJMk/view?usp=drive_link | https://drive.google.com/thumbnail?id=1TDk98vxQ3RO5Vex4gTvzQ8srdHf8VMYQ&sz=w1000 | https://drive.google.com/file/d/1TDk98vxQ3RO5Vex4gTvzQ8srdHf8VMYQ/view?usp=drive_link
2024-09-06 | Al Sarouj-School-P2 | P2 | SC-03 | 282 | 265 | 547 | • Annex Building - Superstructure – Ground Floor RCC Wall 80% Completed • School Building - RCC Wall Concrete Upto Plinth 98% completed • School Building - GF Wall Rebar Fixing – 30% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 9.66% | 18.84% | 9.18% | Annex Superstructure | 2025-01-14 |  | 2024-11-02 | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab & Beam Works to progress • Annex Building - Superstructure works – RCC wall up to FF level to progress; FF Slab Works • Shelter Block - Substructure –works to complete • Shelter Block - Superstructure – RCC Wall work GF & FF Level • Shelter Block - Surface Preparation for CRFP works to progress | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 10955306.883 | 180000 | https://drive.google.com/thumbnail?id=1EShm-JCEBeUL9t9jvi_3B6OF8gY5AK0w&sz=w1000 | https://drive.google.com/file/d/1EShm-JCEBeUL9t9jvi_3B6OF8gY5AK0w/view?usp=drive_link | https://drive.google.com/thumbnail?id=1wFL1KQ-QVw5hSLZv1AF-r-UdMul7WJMk&sz=w1000 | https://drive.google.com/file/d/1wFL1KQ-QVw5hSLZv1AF-r-UdMul7WJMk/view?usp=drive_link | https://drive.google.com/thumbnail?id=1TDk98vxQ3RO5Vex4gTvzQ8srdHf8VMYQ&sz=w1000 | https://drive.google.com/file/d/1TDk98vxQ3RO5Vex4gTvzQ8srdHf8VMYQ/view?usp=drive_link
2024-09-06 | Al Sarouj-School-P2 | P2 | SC-03 | 282 | 265 | 547 | • Annex Building - Superstructure – Ground Floor RCC Wall 80% Completed • School Building - RCC Wall Concrete Upto Plinth 98% completed • School Building - GF Wall Rebar Fixing – 30% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 9.66% | 18.84% | 9.18% | MEP & Finishes | 2025-04-10 |  | 2025-05-15 | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab & Beam Works to progress • Annex Building - Superstructure works – RCC wall up to FF level to progress; FF Slab Works • Shelter Block - Substructure –works to complete • Shelter Block - Superstructure – RCC Wall work GF & FF Level • Shelter Block - Surface Preparation for CRFP works to progress | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 10955306.883 | 180000 | https://drive.google.com/thumbnail?id=1EShm-JCEBeUL9t9jvi_3B6OF8gY5AK0w&sz=w1000 | https://drive.google.com/file/d/1EShm-JCEBeUL9t9jvi_3B6OF8gY5AK0w/view?usp=drive_link | https://drive.google.com/thumbnail?id=1wFL1KQ-QVw5hSLZv1AF-r-UdMul7WJMk&sz=w1000 | https://drive.google.com/file/d/1wFL1KQ-QVw5hSLZv1AF-r-UdMul7WJMk/view?usp=drive_link | https://drive.google.com/thumbnail?id=1TDk98vxQ3RO5Vex4gTvzQ8srdHf8VMYQ&sz=w1000 | https://drive.google.com/file/d/1TDk98vxQ3RO5Vex4gTvzQ8srdHf8VMYQ/view?usp=drive_link
2024-09-06 | Al Sarouj-School-P2 | P2 | SC-03 | 282 | 265 | 547 | • Annex Building - Superstructure – Ground Floor RCC Wall 80% Completed • School Building - RCC Wall Concrete Upto Plinth 98% completed • School Building - GF Wall Rebar Fixing – 30% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 9.66% | 18.84% | 9.18% | BCC Inspection | 2025-04-29 |  | 2025-05-26 | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab & Beam Works to progress • Annex Building - Superstructure works – RCC wall up to FF level to progress; FF Slab Works • Shelter Block - Substructure –works to complete • Shelter Block - Superstructure – RCC Wall work GF & FF Level • Shelter Block - Surface Preparation for CRFP works to progress | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 10955306.883 | 180000 | https://drive.google.com/thumbnail?id=1EShm-JCEBeUL9t9jvi_3B6OF8gY5AK0w&sz=w1000 | https://drive.google.com/file/d/1EShm-JCEBeUL9t9jvi_3B6OF8gY5AK0w/view?usp=drive_link | https://drive.google.com/thumbnail?id=1wFL1KQ-QVw5hSLZv1AF-r-UdMul7WJMk&sz=w1000 | https://drive.google.com/file/d/1wFL1KQ-QVw5hSLZv1AF-r-UdMul7WJMk/view?usp=drive_link | https://drive.google.com/thumbnail?id=1TDk98vxQ3RO5Vex4gTvzQ8srdHf8VMYQ&sz=w1000 | https://drive.google.com/file/d/1TDk98vxQ3RO5Vex4gTvzQ8srdHf8VMYQ/view?usp=drive_link
2024-09-06 | Al Sarouj-School-P2 | P2 | SC-03 | 282 | 265 | 547 | • Annex Building - Superstructure – Ground Floor RCC Wall 80% Completed • School Building - RCC Wall Concrete Upto Plinth 98% completed • School Building - GF Wall Rebar Fixing – 30% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 9.66% | 18.84% | 9.18% | BCC Issuance | 2025-05-16 |  | 2025-06-16 | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab & Beam Works to progress • Annex Building - Superstructure works – RCC wall up to FF level to progress; FF Slab Works • Shelter Block - Substructure –works to complete • Shelter Block - Superstructure – RCC Wall work GF & FF Level • Shelter Block - Surface Preparation for CRFP works to progress | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 10955306.883 | 180000 | https://drive.google.com/thumbnail?id=1EShm-JCEBeUL9t9jvi_3B6OF8gY5AK0w&sz=w1000 | https://drive.google.com/file/d/1EShm-JCEBeUL9t9jvi_3B6OF8gY5AK0w/view?usp=drive_link | https://drive.google.com/thumbnail?id=1wFL1KQ-QVw5hSLZv1AF-r-UdMul7WJMk&sz=w1000 | https://drive.google.com/file/d/1wFL1KQ-QVw5hSLZv1AF-r-UdMul7WJMk/view?usp=drive_link | https://drive.google.com/thumbnail?id=1TDk98vxQ3RO5Vex4gTvzQ8srdHf8VMYQ&sz=w1000 | https://drive.google.com/file/d/1TDk98vxQ3RO5Vex4gTvzQ8srdHf8VMYQ/view?usp=drive_link
2024-09-06 | Al Sarouj-School-P2 | P2 | SC-03 | 282 | 265 | 547 | • Annex Building - Superstructure – Ground Floor RCC Wall 80% Completed • School Building - RCC Wall Concrete Upto Plinth 98% completed • School Building - GF Wall Rebar Fixing – 30% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 9.66% | 18.84% | 9.18% | Completion | 2025-05-29 |  | 2025-06-30 | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab & Beam Works to progress • Annex Building - Superstructure works – RCC wall up to FF level to progress; FF Slab Works • Shelter Block - Substructure –works to complete • Shelter Block - Superstructure – RCC Wall work GF & FF Level • Shelter Block - Surface Preparation for CRFP works to progress | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 10955306.883 | 180000 | https://drive.google.com/thumbnail?id=1EShm-JCEBeUL9t9jvi_3B6OF8gY5AK0w&sz=w1000 | https://drive.google.com/file/d/1EShm-JCEBeUL9t9jvi_3B6OF8gY5AK0w/view?usp=drive_link | https://drive.google.com/thumbnail?id=1wFL1KQ-QVw5hSLZv1AF-r-UdMul7WJMk&sz=w1000 | https://drive.google.com/file/d/1wFL1KQ-QVw5hSLZv1AF-r-UdMul7WJMk/view?usp=drive_link | https://drive.google.com/thumbnail?id=1TDk98vxQ3RO5Vex4gTvzQ8srdHf8VMYQ&sz=w1000 | https://drive.google.com/file/d/1TDk98vxQ3RO5Vex4gTvzQ8srdHf8VMYQ/view?usp=drive_link
2024-09-06 | Al Sarouj-School-P16 | P16 | SC-04 | 355 | 192 | 547 | • Annex Building - Backfilling 100% completed; Grade Slab work PCC in progress • GF RCC wall Rebar & Shutter fabrication ongoing • School Building - Plinth wall 97% completed; GF RCC Wall Rebar Fixing 23% done | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 26.9% | 15.76% | -11.14% | Notice to Commence | 2023-09-18 | 2023-09-26 |  | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure works to complete • Annex Building - Superstructure – GF RCC Wall works to progress • Shelter Block - Substructure – Plinth Wall construction to complete. • Shelter Block - GF – Rebar Fixing for Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 10206907.2387 | 180000 | https://drive.google.com/thumbnail?id=17TfQKd0Cd9yG2mhJV3bja_JAtLRy5Hq5&sz=w1000 | https://drive.google.com/file/d/17TfQKd0Cd9yG2mhJV3bja_JAtLRy5Hq5/view?usp=drive_link | https://drive.google.com/thumbnail?id=1g0qE64GhrUOttT19f46pAEKIpTihMBf3&sz=w1000 | https://drive.google.com/file/d/1g0qE64GhrUOttT19f46pAEKIpTihMBf3/view?usp=drive_link | https://drive.google.com/thumbnail?id=1IobvhS63KW7w3xiQvQNpxHjV7ZiZaVbc&sz=w1000 | https://drive.google.com/file/d/1IobvhS63KW7w3xiQvQNpxHjV7ZiZaVbc/view?usp=drive_link
2024-09-06 | Al Sarouj-School-P16 | P16 | SC-04 | 355 | 192 | 547 | • Annex Building - Backfilling 100% completed; Grade Slab work PCC in progress • GF RCC wall Rebar & Shutter fabrication ongoing • School Building - Plinth wall 97% completed; GF RCC Wall Rebar Fixing 23% done | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 26.9% | 15.76% | -11.14% | Site Mobilization | 2023-10-21 | 2024-01-06 |  | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure works to complete • Annex Building - Superstructure – GF RCC Wall works to progress • Shelter Block - Substructure – Plinth Wall construction to complete. • Shelter Block - GF – Rebar Fixing for Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 10206907.2387 | 180000 | https://drive.google.com/thumbnail?id=17TfQKd0Cd9yG2mhJV3bja_JAtLRy5Hq5&sz=w1000 | https://drive.google.com/file/d/17TfQKd0Cd9yG2mhJV3bja_JAtLRy5Hq5/view?usp=drive_link | https://drive.google.com/thumbnail?id=1g0qE64GhrUOttT19f46pAEKIpTihMBf3&sz=w1000 | https://drive.google.com/file/d/1g0qE64GhrUOttT19f46pAEKIpTihMBf3/view?usp=drive_link | https://drive.google.com/thumbnail?id=1IobvhS63KW7w3xiQvQNpxHjV7ZiZaVbc&sz=w1000 | https://drive.google.com/file/d/1IobvhS63KW7w3xiQvQNpxHjV7ZiZaVbc/view?usp=drive_link
2024-09-06 | Al Sarouj-School-P16 | P16 | SC-04 | 355 | 192 | 547 | • Annex Building - Backfilling 100% completed; Grade Slab work PCC in progress • GF RCC wall Rebar & Shutter fabrication ongoing • School Building - Plinth wall 97% completed; GF RCC Wall Rebar Fixing 23% done | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 26.9% | 15.76% | -11.14% | Building Permit | 2024-05-17 | 2024-06-20 |  | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure works to complete • Annex Building - Superstructure – GF RCC Wall works to progress • Shelter Block - Substructure – Plinth Wall construction to complete. • Shelter Block - GF – Rebar Fixing for Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 10206907.2387 | 180000 | https://drive.google.com/thumbnail?id=17TfQKd0Cd9yG2mhJV3bja_JAtLRy5Hq5&sz=w1000 | https://drive.google.com/file/d/17TfQKd0Cd9yG2mhJV3bja_JAtLRy5Hq5/view?usp=drive_link | https://drive.google.com/thumbnail?id=1g0qE64GhrUOttT19f46pAEKIpTihMBf3&sz=w1000 | https://drive.google.com/file/d/1g0qE64GhrUOttT19f46pAEKIpTihMBf3/view?usp=drive_link | https://drive.google.com/thumbnail?id=1IobvhS63KW7w3xiQvQNpxHjV7ZiZaVbc&sz=w1000 | https://drive.google.com/file/d/1IobvhS63KW7w3xiQvQNpxHjV7ZiZaVbc/view?usp=drive_link
2024-09-06 | Al Sarouj-School-P16 | P16 | SC-04 | 355 | 192 | 547 | • Annex Building - Backfilling 100% completed; Grade Slab work PCC in progress • GF RCC wall Rebar & Shutter fabrication ongoing • School Building - Plinth wall 97% completed; GF RCC Wall Rebar Fixing 23% done | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 26.9% | 15.76% | -11.14% | School Substructure | 2024-08-06 |  | 2024-09-20 | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure works to complete • Annex Building - Superstructure – GF RCC Wall works to progress • Shelter Block - Substructure – Plinth Wall construction to complete. • Shelter Block - GF – Rebar Fixing for Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 10206907.2387 | 180000 | https://drive.google.com/thumbnail?id=17TfQKd0Cd9yG2mhJV3bja_JAtLRy5Hq5&sz=w1000 | https://drive.google.com/file/d/17TfQKd0Cd9yG2mhJV3bja_JAtLRy5Hq5/view?usp=drive_link | https://drive.google.com/thumbnail?id=1g0qE64GhrUOttT19f46pAEKIpTihMBf3&sz=w1000 | https://drive.google.com/file/d/1g0qE64GhrUOttT19f46pAEKIpTihMBf3/view?usp=drive_link | https://drive.google.com/thumbnail?id=1IobvhS63KW7w3xiQvQNpxHjV7ZiZaVbc&sz=w1000 | https://drive.google.com/file/d/1IobvhS63KW7w3xiQvQNpxHjV7ZiZaVbc/view?usp=drive_link
2024-09-06 | Al Sarouj-School-P16 | P16 | SC-04 | 355 | 192 | 547 | • Annex Building - Backfilling 100% completed; Grade Slab work PCC in progress • GF RCC wall Rebar & Shutter fabrication ongoing • School Building - Plinth wall 97% completed; GF RCC Wall Rebar Fixing 23% done | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 26.9% | 15.76% | -11.14% | School Superstructure | 2024-11-07 |  | 2024-10-23 | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure works to complete • Annex Building - Superstructure – GF RCC Wall works to progress • Shelter Block - Substructure – Plinth Wall construction to complete. • Shelter Block - GF – Rebar Fixing for Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 10206907.2387 | 180000 | https://drive.google.com/thumbnail?id=17TfQKd0Cd9yG2mhJV3bja_JAtLRy5Hq5&sz=w1000 | https://drive.google.com/file/d/17TfQKd0Cd9yG2mhJV3bja_JAtLRy5Hq5/view?usp=drive_link | https://drive.google.com/thumbnail?id=1g0qE64GhrUOttT19f46pAEKIpTihMBf3&sz=w1000 | https://drive.google.com/file/d/1g0qE64GhrUOttT19f46pAEKIpTihMBf3/view?usp=drive_link | https://drive.google.com/thumbnail?id=1IobvhS63KW7w3xiQvQNpxHjV7ZiZaVbc&sz=w1000 | https://drive.google.com/file/d/1IobvhS63KW7w3xiQvQNpxHjV7ZiZaVbc/view?usp=drive_link
2024-09-06 | Al Sarouj-School-P16 | P16 | SC-04 | 355 | 192 | 547 | • Annex Building - Backfilling 100% completed; Grade Slab work PCC in progress • GF RCC wall Rebar & Shutter fabrication ongoing • School Building - Plinth wall 97% completed; GF RCC Wall Rebar Fixing 23% done | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 26.9% | 15.76% | -11.14% | Annex Substructure | 2024-08-07 |  |  | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure works to complete • Annex Building - Superstructure – GF RCC Wall works to progress • Shelter Block - Substructure – Plinth Wall construction to complete. • Shelter Block - GF – Rebar Fixing for Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 10206907.2387 | 180000 | https://drive.google.com/thumbnail?id=17TfQKd0Cd9yG2mhJV3bja_JAtLRy5Hq5&sz=w1000 | https://drive.google.com/file/d/17TfQKd0Cd9yG2mhJV3bja_JAtLRy5Hq5/view?usp=drive_link | https://drive.google.com/thumbnail?id=1g0qE64GhrUOttT19f46pAEKIpTihMBf3&sz=w1000 | https://drive.google.com/file/d/1g0qE64GhrUOttT19f46pAEKIpTihMBf3/view?usp=drive_link | https://drive.google.com/thumbnail?id=1IobvhS63KW7w3xiQvQNpxHjV7ZiZaVbc&sz=w1000 | https://drive.google.com/file/d/1IobvhS63KW7w3xiQvQNpxHjV7ZiZaVbc/view?usp=drive_link
2024-09-06 | Al Sarouj-School-P16 | P16 | SC-04 | 355 | 192 | 547 | • Annex Building - Backfilling 100% completed; Grade Slab work PCC in progress • GF RCC wall Rebar & Shutter fabrication ongoing • School Building - Plinth wall 97% completed; GF RCC Wall Rebar Fixing 23% done | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 26.9% | 15.76% | -11.14% | Annex Superstructure | 2024-10-31 |  | 2024-11-21 | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure works to complete • Annex Building - Superstructure – GF RCC Wall works to progress • Shelter Block - Substructure – Plinth Wall construction to complete. • Shelter Block - GF – Rebar Fixing for Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 10206907.2387 | 180000 | https://drive.google.com/thumbnail?id=17TfQKd0Cd9yG2mhJV3bja_JAtLRy5Hq5&sz=w1000 | https://drive.google.com/file/d/17TfQKd0Cd9yG2mhJV3bja_JAtLRy5Hq5/view?usp=drive_link | https://drive.google.com/thumbnail?id=1g0qE64GhrUOttT19f46pAEKIpTihMBf3&sz=w1000 | https://drive.google.com/file/d/1g0qE64GhrUOttT19f46pAEKIpTihMBf3/view?usp=drive_link | https://drive.google.com/thumbnail?id=1IobvhS63KW7w3xiQvQNpxHjV7ZiZaVbc&sz=w1000 | https://drive.google.com/file/d/1IobvhS63KW7w3xiQvQNpxHjV7ZiZaVbc/view?usp=drive_link
2024-09-06 | Al Sarouj-School-P16 | P16 | SC-04 | 355 | 192 | 547 | • Annex Building - Backfilling 100% completed; Grade Slab work PCC in progress • GF RCC wall Rebar & Shutter fabrication ongoing • School Building - Plinth wall 97% completed; GF RCC Wall Rebar Fixing 23% done | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 26.9% | 15.76% | -11.14% | MEP & Finishes | 2025-01-25 |  | 2025-05-15 | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure works to complete • Annex Building - Superstructure – GF RCC Wall works to progress • Shelter Block - Substructure – Plinth Wall construction to complete. • Shelter Block - GF – Rebar Fixing for Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 10206907.2387 | 180000 | https://drive.google.com/thumbnail?id=17TfQKd0Cd9yG2mhJV3bja_JAtLRy5Hq5&sz=w1000 | https://drive.google.com/file/d/17TfQKd0Cd9yG2mhJV3bja_JAtLRy5Hq5/view?usp=drive_link | https://drive.google.com/thumbnail?id=1g0qE64GhrUOttT19f46pAEKIpTihMBf3&sz=w1000 | https://drive.google.com/file/d/1g0qE64GhrUOttT19f46pAEKIpTihMBf3/view?usp=drive_link | https://drive.google.com/thumbnail?id=1IobvhS63KW7w3xiQvQNpxHjV7ZiZaVbc&sz=w1000 | https://drive.google.com/file/d/1IobvhS63KW7w3xiQvQNpxHjV7ZiZaVbc/view?usp=drive_link
2024-09-06 | Al Sarouj-School-P16 | P16 | SC-04 | 355 | 192 | 547 | • Annex Building - Backfilling 100% completed; Grade Slab work PCC in progress • GF RCC wall Rebar & Shutter fabrication ongoing • School Building - Plinth wall 97% completed; GF RCC Wall Rebar Fixing 23% done | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 26.9% | 15.76% | -11.14% | BCC Inspection | 2025-02-13 |  | 2025-05-26 | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure works to complete • Annex Building - Superstructure – GF RCC Wall works to progress • Shelter Block - Substructure – Plinth Wall construction to complete. • Shelter Block - GF – Rebar Fixing for Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 10206907.2387 | 180000 | https://drive.google.com/thumbnail?id=17TfQKd0Cd9yG2mhJV3bja_JAtLRy5Hq5&sz=w1000 | https://drive.google.com/file/d/17TfQKd0Cd9yG2mhJV3bja_JAtLRy5Hq5/view?usp=drive_link | https://drive.google.com/thumbnail?id=1g0qE64GhrUOttT19f46pAEKIpTihMBf3&sz=w1000 | https://drive.google.com/file/d/1g0qE64GhrUOttT19f46pAEKIpTihMBf3/view?usp=drive_link | https://drive.google.com/thumbnail?id=1IobvhS63KW7w3xiQvQNpxHjV7ZiZaVbc&sz=w1000 | https://drive.google.com/file/d/1IobvhS63KW7w3xiQvQNpxHjV7ZiZaVbc/view?usp=drive_link
2024-09-06 | Al Sarouj-School-P16 | P16 | SC-04 | 355 | 192 | 547 | • Annex Building - Backfilling 100% completed; Grade Slab work PCC in progress • GF RCC wall Rebar & Shutter fabrication ongoing • School Building - Plinth wall 97% completed; GF RCC Wall Rebar Fixing 23% done | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 26.9% | 15.76% | -11.14% | BCC Issuance | 2025-03-04 |  | 2025-06-16 | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure works to complete • Annex Building - Superstructure – GF RCC Wall works to progress • Shelter Block - Substructure – Plinth Wall construction to complete. • Shelter Block - GF – Rebar Fixing for Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 10206907.2387 | 180000 | https://drive.google.com/thumbnail?id=17TfQKd0Cd9yG2mhJV3bja_JAtLRy5Hq5&sz=w1000 | https://drive.google.com/file/d/17TfQKd0Cd9yG2mhJV3bja_JAtLRy5Hq5/view?usp=drive_link | https://drive.google.com/thumbnail?id=1g0qE64GhrUOttT19f46pAEKIpTihMBf3&sz=w1000 | https://drive.google.com/file/d/1g0qE64GhrUOttT19f46pAEKIpTihMBf3/view?usp=drive_link | https://drive.google.com/thumbnail?id=1IobvhS63KW7w3xiQvQNpxHjV7ZiZaVbc&sz=w1000 | https://drive.google.com/file/d/1IobvhS63KW7w3xiQvQNpxHjV7ZiZaVbc/view?usp=drive_link
2024-09-06 | Al Sarouj-School-P16 | P16 | SC-04 | 355 | 192 | 547 | • Annex Building - Backfilling 100% completed; Grade Slab work PCC in progress • GF RCC wall Rebar & Shutter fabrication ongoing • School Building - Plinth wall 97% completed; GF RCC Wall Rebar Fixing 23% done | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 26.9% | 15.76% | -11.14% | Completion | 2025-03-17 |  | 2025-06-30 | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure works to complete • Annex Building - Superstructure – GF RCC Wall works to progress • Shelter Block - Substructure – Plinth Wall construction to complete. • Shelter Block - GF – Rebar Fixing for Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 10206907.2387 | 180000 | https://drive.google.com/thumbnail?id=17TfQKd0Cd9yG2mhJV3bja_JAtLRy5Hq5&sz=w1000 | https://drive.google.com/file/d/17TfQKd0Cd9yG2mhJV3bja_JAtLRy5Hq5/view?usp=drive_link | https://drive.google.com/thumbnail?id=1g0qE64GhrUOttT19f46pAEKIpTihMBf3&sz=w1000 | https://drive.google.com/file/d/1g0qE64GhrUOttT19f46pAEKIpTihMBf3/view?usp=drive_link | https://drive.google.com/thumbnail?id=1IobvhS63KW7w3xiQvQNpxHjV7ZiZaVbc&sz=w1000 | https://drive.google.com/file/d/1IobvhS63KW7w3xiQvQNpxHjV7ZiZaVbc/view?usp=drive_link
2024-09-06 | Al Sila-School-P43 | P43 | SC-05 | 355 | 192 | 547 | • Annex Building - GF - RCC Wall Rebar Fixing 90% completed • School Building - RCC Plinth Wall - 98% Completed, GF Wall Rebar Fixing 26% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 26.9% | 18.84% | -8.06% | Notice to Commence | 2023-09-18 | 2023-09-26 |  | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works to Complete • Annex Building - Superstructure works – GF RCC Wall works & FF Slab Works • Shelter Block - RCC Plinth Wall & GF Wall Works to progress • Shelter Block - Roof Slab Strenthening Works to progress • Shelter Block - Surface Preparation for CFRP works | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 10232670.5172 | 180000 | https://drive.google.com/thumbnail?id=1lHsS9HToAAkVgzUpu0SvP6Q74MdwpNaD&sz=w1000 | https://drive.google.com/file/d/1lHsS9HToAAkVgzUpu0SvP6Q74MdwpNaD/view?usp=drive_link | https://drive.google.com/thumbnail?id=1QSpwAu5G5jYzzAO2U4PsRnfbTsKxHd6s&sz=w1000 | https://drive.google.com/file/d/1QSpwAu5G5jYzzAO2U4PsRnfbTsKxHd6s/view?usp=drive_link | https://drive.google.com/thumbnail?id=1FFvziYQynsq9IGYLQaJ37iQbYGYyI7tt&sz=w1000 | https://drive.google.com/file/d/1FFvziYQynsq9IGYLQaJ37iQbYGYyI7tt/view?usp=drive_link
2024-09-06 | Al Sila-School-P43 | P43 | SC-05 | 355 | 192 | 547 | • Annex Building - GF - RCC Wall Rebar Fixing 90% completed • School Building - RCC Plinth Wall - 98% Completed, GF Wall Rebar Fixing 26% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 26.9% | 18.84% | -8.06% | Site Mobilization | 2023-10-21 | 2024-01-06 |  | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works to Complete • Annex Building - Superstructure works – GF RCC Wall works & FF Slab Works • Shelter Block - RCC Plinth Wall & GF Wall Works to progress • Shelter Block - Roof Slab Strenthening Works to progress • Shelter Block - Surface Preparation for CFRP works | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 10232670.5172 | 180000 | https://drive.google.com/thumbnail?id=1lHsS9HToAAkVgzUpu0SvP6Q74MdwpNaD&sz=w1000 | https://drive.google.com/file/d/1lHsS9HToAAkVgzUpu0SvP6Q74MdwpNaD/view?usp=drive_link | https://drive.google.com/thumbnail?id=1QSpwAu5G5jYzzAO2U4PsRnfbTsKxHd6s&sz=w1000 | https://drive.google.com/file/d/1QSpwAu5G5jYzzAO2U4PsRnfbTsKxHd6s/view?usp=drive_link | https://drive.google.com/thumbnail?id=1FFvziYQynsq9IGYLQaJ37iQbYGYyI7tt&sz=w1000 | https://drive.google.com/file/d/1FFvziYQynsq9IGYLQaJ37iQbYGYyI7tt/view?usp=drive_link
2024-09-06 | Al Sila-School-P43 | P43 | SC-05 | 355 | 192 | 547 | • Annex Building - GF - RCC Wall Rebar Fixing 90% completed • School Building - RCC Plinth Wall - 98% Completed, GF Wall Rebar Fixing 26% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 26.9% | 18.84% | -8.06% | Building Permit | 2024-05-17 | 2024-06-04 |  | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works to Complete • Annex Building - Superstructure works – GF RCC Wall works & FF Slab Works • Shelter Block - RCC Plinth Wall & GF Wall Works to progress • Shelter Block - Roof Slab Strenthening Works to progress • Shelter Block - Surface Preparation for CFRP works | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 10232670.5172 | 180000 | https://drive.google.com/thumbnail?id=1lHsS9HToAAkVgzUpu0SvP6Q74MdwpNaD&sz=w1000 | https://drive.google.com/file/d/1lHsS9HToAAkVgzUpu0SvP6Q74MdwpNaD/view?usp=drive_link | https://drive.google.com/thumbnail?id=1QSpwAu5G5jYzzAO2U4PsRnfbTsKxHd6s&sz=w1000 | https://drive.google.com/file/d/1QSpwAu5G5jYzzAO2U4PsRnfbTsKxHd6s/view?usp=drive_link | https://drive.google.com/thumbnail?id=1FFvziYQynsq9IGYLQaJ37iQbYGYyI7tt&sz=w1000 | https://drive.google.com/file/d/1FFvziYQynsq9IGYLQaJ37iQbYGYyI7tt/view?usp=drive_link
2024-09-06 | Al Sila-School-P43 | P43 | SC-05 | 355 | 192 | 547 | • Annex Building - GF - RCC Wall Rebar Fixing 90% completed • School Building - RCC Plinth Wall - 98% Completed, GF Wall Rebar Fixing 26% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 26.9% | 18.84% | -8.06% | School Substructure | 2024-08-06 |  | 2024-09-21 | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works to Complete • Annex Building - Superstructure works – GF RCC Wall works & FF Slab Works • Shelter Block - RCC Plinth Wall & GF Wall Works to progress • Shelter Block - Roof Slab Strenthening Works to progress • Shelter Block - Surface Preparation for CFRP works | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 10232670.5172 | 180000 | https://drive.google.com/thumbnail?id=1lHsS9HToAAkVgzUpu0SvP6Q74MdwpNaD&sz=w1000 | https://drive.google.com/file/d/1lHsS9HToAAkVgzUpu0SvP6Q74MdwpNaD/view?usp=drive_link | https://drive.google.com/thumbnail?id=1QSpwAu5G5jYzzAO2U4PsRnfbTsKxHd6s&sz=w1000 | https://drive.google.com/file/d/1QSpwAu5G5jYzzAO2U4PsRnfbTsKxHd6s/view?usp=drive_link | https://drive.google.com/thumbnail?id=1FFvziYQynsq9IGYLQaJ37iQbYGYyI7tt&sz=w1000 | https://drive.google.com/file/d/1FFvziYQynsq9IGYLQaJ37iQbYGYyI7tt/view?usp=drive_link
2024-09-06 | Al Sila-School-P43 | P43 | SC-05 | 355 | 192 | 547 | • Annex Building - GF - RCC Wall Rebar Fixing 90% completed • School Building - RCC Plinth Wall - 98% Completed, GF Wall Rebar Fixing 26% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 26.9% | 18.84% | -8.06% | School Superstructure | 2024-11-07 |  | 2024-10-21 | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works to Complete • Annex Building - Superstructure works – GF RCC Wall works & FF Slab Works • Shelter Block - RCC Plinth Wall & GF Wall Works to progress • Shelter Block - Roof Slab Strenthening Works to progress • Shelter Block - Surface Preparation for CFRP works | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 10232670.5172 | 180000 | https://drive.google.com/thumbnail?id=1lHsS9HToAAkVgzUpu0SvP6Q74MdwpNaD&sz=w1000 | https://drive.google.com/file/d/1lHsS9HToAAkVgzUpu0SvP6Q74MdwpNaD/view?usp=drive_link | https://drive.google.com/thumbnail?id=1QSpwAu5G5jYzzAO2U4PsRnfbTsKxHd6s&sz=w1000 | https://drive.google.com/file/d/1QSpwAu5G5jYzzAO2U4PsRnfbTsKxHd6s/view?usp=drive_link | https://drive.google.com/thumbnail?id=1FFvziYQynsq9IGYLQaJ37iQbYGYyI7tt&sz=w1000 | https://drive.google.com/file/d/1FFvziYQynsq9IGYLQaJ37iQbYGYyI7tt/view?usp=drive_link
2024-09-06 | Al Sila-School-P43 | P43 | SC-05 | 355 | 192 | 547 | • Annex Building - GF - RCC Wall Rebar Fixing 90% completed • School Building - RCC Plinth Wall - 98% Completed, GF Wall Rebar Fixing 26% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 26.9% | 18.84% | -8.06% | Annex Substructure | 2024-08-07 | 2024-08-31 |  | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works to Complete • Annex Building - Superstructure works – GF RCC Wall works & FF Slab Works • Shelter Block - RCC Plinth Wall & GF Wall Works to progress • Shelter Block - Roof Slab Strenthening Works to progress • Shelter Block - Surface Preparation for CFRP works | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 10232670.5172 | 180000 | https://drive.google.com/thumbnail?id=1lHsS9HToAAkVgzUpu0SvP6Q74MdwpNaD&sz=w1000 | https://drive.google.com/file/d/1lHsS9HToAAkVgzUpu0SvP6Q74MdwpNaD/view?usp=drive_link | https://drive.google.com/thumbnail?id=1QSpwAu5G5jYzzAO2U4PsRnfbTsKxHd6s&sz=w1000 | https://drive.google.com/file/d/1QSpwAu5G5jYzzAO2U4PsRnfbTsKxHd6s/view?usp=drive_link | https://drive.google.com/thumbnail?id=1FFvziYQynsq9IGYLQaJ37iQbYGYyI7tt&sz=w1000 | https://drive.google.com/file/d/1FFvziYQynsq9IGYLQaJ37iQbYGYyI7tt/view?usp=drive_link
2024-09-06 | Al Sila-School-P43 | P43 | SC-05 | 355 | 192 | 547 | • Annex Building - GF - RCC Wall Rebar Fixing 90% completed • School Building - RCC Plinth Wall - 98% Completed, GF Wall Rebar Fixing 26% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 26.9% | 18.84% | -8.06% | Annex Superstructure | 2024-10-31 |  | 2024-11-09 | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works to Complete • Annex Building - Superstructure works – GF RCC Wall works & FF Slab Works • Shelter Block - RCC Plinth Wall & GF Wall Works to progress • Shelter Block - Roof Slab Strenthening Works to progress • Shelter Block - Surface Preparation for CFRP works | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 10232670.5172 | 180000 | https://drive.google.com/thumbnail?id=1lHsS9HToAAkVgzUpu0SvP6Q74MdwpNaD&sz=w1000 | https://drive.google.com/file/d/1lHsS9HToAAkVgzUpu0SvP6Q74MdwpNaD/view?usp=drive_link | https://drive.google.com/thumbnail?id=1QSpwAu5G5jYzzAO2U4PsRnfbTsKxHd6s&sz=w1000 | https://drive.google.com/file/d/1QSpwAu5G5jYzzAO2U4PsRnfbTsKxHd6s/view?usp=drive_link | https://drive.google.com/thumbnail?id=1FFvziYQynsq9IGYLQaJ37iQbYGYyI7tt&sz=w1000 | https://drive.google.com/file/d/1FFvziYQynsq9IGYLQaJ37iQbYGYyI7tt/view?usp=drive_link
2024-09-06 | Al Sila-School-P43 | P43 | SC-05 | 355 | 192 | 547 | • Annex Building - GF - RCC Wall Rebar Fixing 90% completed • School Building - RCC Plinth Wall - 98% Completed, GF Wall Rebar Fixing 26% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 26.9% | 18.84% | -8.06% | MEP & Finishes | 2025-01-25 |  | 2025-05-15 | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works to Complete • Annex Building - Superstructure works – GF RCC Wall works & FF Slab Works • Shelter Block - RCC Plinth Wall & GF Wall Works to progress • Shelter Block - Roof Slab Strenthening Works to progress • Shelter Block - Surface Preparation for CFRP works | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 10232670.5172 | 180000 | https://drive.google.com/thumbnail?id=1lHsS9HToAAkVgzUpu0SvP6Q74MdwpNaD&sz=w1000 | https://drive.google.com/file/d/1lHsS9HToAAkVgzUpu0SvP6Q74MdwpNaD/view?usp=drive_link | https://drive.google.com/thumbnail?id=1QSpwAu5G5jYzzAO2U4PsRnfbTsKxHd6s&sz=w1000 | https://drive.google.com/file/d/1QSpwAu5G5jYzzAO2U4PsRnfbTsKxHd6s/view?usp=drive_link | https://drive.google.com/thumbnail?id=1FFvziYQynsq9IGYLQaJ37iQbYGYyI7tt&sz=w1000 | https://drive.google.com/file/d/1FFvziYQynsq9IGYLQaJ37iQbYGYyI7tt/view?usp=drive_link
2024-09-06 | Al Sila-School-P43 | P43 | SC-05 | 355 | 192 | 547 | • Annex Building - GF - RCC Wall Rebar Fixing 90% completed • School Building - RCC Plinth Wall - 98% Completed, GF Wall Rebar Fixing 26% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 26.9% | 18.84% | -8.06% | BCC Inspection | 2025-02-13 |  | 2025-05-26 | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works to Complete • Annex Building - Superstructure works – GF RCC Wall works & FF Slab Works • Shelter Block - RCC Plinth Wall & GF Wall Works to progress • Shelter Block - Roof Slab Strenthening Works to progress • Shelter Block - Surface Preparation for CFRP works | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 10232670.5172 | 180000 | https://drive.google.com/thumbnail?id=1lHsS9HToAAkVgzUpu0SvP6Q74MdwpNaD&sz=w1000 | https://drive.google.com/file/d/1lHsS9HToAAkVgzUpu0SvP6Q74MdwpNaD/view?usp=drive_link | https://drive.google.com/thumbnail?id=1QSpwAu5G5jYzzAO2U4PsRnfbTsKxHd6s&sz=w1000 | https://drive.google.com/file/d/1QSpwAu5G5jYzzAO2U4PsRnfbTsKxHd6s/view?usp=drive_link | https://drive.google.com/thumbnail?id=1FFvziYQynsq9IGYLQaJ37iQbYGYyI7tt&sz=w1000 | https://drive.google.com/file/d/1FFvziYQynsq9IGYLQaJ37iQbYGYyI7tt/view?usp=drive_link
2024-09-06 | Al Sila-School-P43 | P43 | SC-05 | 355 | 192 | 547 | • Annex Building - GF - RCC Wall Rebar Fixing 90% completed • School Building - RCC Plinth Wall - 98% Completed, GF Wall Rebar Fixing 26% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 26.9% | 18.84% | -8.06% | BCC Issuance | 2025-03-04 |  | 2025-06-16 | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works to Complete • Annex Building - Superstructure works – GF RCC Wall works & FF Slab Works • Shelter Block - RCC Plinth Wall & GF Wall Works to progress • Shelter Block - Roof Slab Strenthening Works to progress • Shelter Block - Surface Preparation for CFRP works | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 10232670.5172 | 180000 | https://drive.google.com/thumbnail?id=1lHsS9HToAAkVgzUpu0SvP6Q74MdwpNaD&sz=w1000 | https://drive.google.com/file/d/1lHsS9HToAAkVgzUpu0SvP6Q74MdwpNaD/view?usp=drive_link | https://drive.google.com/thumbnail?id=1QSpwAu5G5jYzzAO2U4PsRnfbTsKxHd6s&sz=w1000 | https://drive.google.com/file/d/1QSpwAu5G5jYzzAO2U4PsRnfbTsKxHd6s/view?usp=drive_link | https://drive.google.com/thumbnail?id=1FFvziYQynsq9IGYLQaJ37iQbYGYyI7tt&sz=w1000 | https://drive.google.com/file/d/1FFvziYQynsq9IGYLQaJ37iQbYGYyI7tt/view?usp=drive_link
2024-09-06 | Al Sila-School-P43 | P43 | SC-05 | 355 | 192 | 547 | • Annex Building - GF - RCC Wall Rebar Fixing 90% completed • School Building - RCC Plinth Wall - 98% Completed, GF Wall Rebar Fixing 26% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 26.9% | 18.84% | -8.06% | Completion | 2025-03-17 |  | 2025-06-30 | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works to Complete • Annex Building - Superstructure works – GF RCC Wall works & FF Slab Works • Shelter Block - RCC Plinth Wall & GF Wall Works to progress • Shelter Block - Roof Slab Strenthening Works to progress • Shelter Block - Surface Preparation for CFRP works | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 10232670.5172 | 180000 | https://drive.google.com/thumbnail?id=1lHsS9HToAAkVgzUpu0SvP6Q74MdwpNaD&sz=w1000 | https://drive.google.com/file/d/1lHsS9HToAAkVgzUpu0SvP6Q74MdwpNaD/view?usp=drive_link | https://drive.google.com/thumbnail?id=1QSpwAu5G5jYzzAO2U4PsRnfbTsKxHd6s&sz=w1000 | https://drive.google.com/file/d/1QSpwAu5G5jYzzAO2U4PsRnfbTsKxHd6s/view?usp=drive_link | https://drive.google.com/thumbnail?id=1FFvziYQynsq9IGYLQaJ37iQbYGYyI7tt&sz=w1000 | https://drive.google.com/file/d/1FFvziYQynsq9IGYLQaJ37iQbYGYyI7tt/view?usp=drive_link
2024-09-06 | Madinat Zayed-School-P105 | P105 | SC-06 | 355 | 192 | 547 | • Annex Building - Superstructure – GF RCC Wall Concrete Cast 100 % completed • Annex Building - FF Slab Staging & Formwork fixing 85% completed • School Building - Substructure –Plinth Wall Concrete 95% completed • School Building - GF RCC Wall Rebar Fixing – 35% completed. | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 27.01% | 20.78% | -6.23% | Notice to Commence | 2023-09-18 | 2023-09-26 |  | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works to progress • Annex Building - Superstructure works – GF RCC Wall works & FF Slab Works • Shelter Block - Substructure – Plinth Wall Works to complete; Existing Structure Strengthening works to progress. • Shelter Block - Superstructure - GF & FF Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 10862786.8946 | 180000 | https://drive.google.com/thumbnail?id=1LGG-xHMY2FIvsrUQHdBsimZyc6oVwUHI&sz=w1000 | https://drive.google.com/file/d/1LGG-xHMY2FIvsrUQHdBsimZyc6oVwUHI/view?usp=drive_link | https://drive.google.com/thumbnail?id=1Fr7FnU1zhPXLqSCHSNAy1t-LB8P_O5uZ&sz=w1000 | https://drive.google.com/file/d/1Fr7FnU1zhPXLqSCHSNAy1t-LB8P_O5uZ/view?usp=drive_link | https://drive.google.com/thumbnail?id=1bB7YXERU6N6l2CgGXhfHlbgLBpqYC7xS&sz=w1000 | https://drive.google.com/file/d/1bB7YXERU6N6l2CgGXhfHlbgLBpqYC7xS/view?usp=drive_link
2024-09-06 | Madinat Zayed-School-P105 | P105 | SC-06 | 355 | 192 | 547 | • Annex Building - Superstructure – GF RCC Wall Concrete Cast 100 % completed • Annex Building - FF Slab Staging & Formwork fixing 85% completed • School Building - Substructure –Plinth Wall Concrete 95% completed • School Building - GF RCC Wall Rebar Fixing – 35% completed. | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 27.01% | 20.78% | -6.23% | Site Mobilization | 2023-10-21 | 2024-01-06 |  | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works to progress • Annex Building - Superstructure works – GF RCC Wall works & FF Slab Works • Shelter Block - Substructure – Plinth Wall Works to complete; Existing Structure Strengthening works to progress. • Shelter Block - Superstructure - GF & FF Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 10862786.8946 | 180000 | https://drive.google.com/thumbnail?id=1LGG-xHMY2FIvsrUQHdBsimZyc6oVwUHI&sz=w1000 | https://drive.google.com/file/d/1LGG-xHMY2FIvsrUQHdBsimZyc6oVwUHI/view?usp=drive_link | https://drive.google.com/thumbnail?id=1Fr7FnU1zhPXLqSCHSNAy1t-LB8P_O5uZ&sz=w1000 | https://drive.google.com/file/d/1Fr7FnU1zhPXLqSCHSNAy1t-LB8P_O5uZ/view?usp=drive_link | https://drive.google.com/thumbnail?id=1bB7YXERU6N6l2CgGXhfHlbgLBpqYC7xS&sz=w1000 | https://drive.google.com/file/d/1bB7YXERU6N6l2CgGXhfHlbgLBpqYC7xS/view?usp=drive_link
2024-09-06 | Madinat Zayed-School-P105 | P105 | SC-06 | 355 | 192 | 547 | • Annex Building - Superstructure – GF RCC Wall Concrete Cast 100 % completed • Annex Building - FF Slab Staging & Formwork fixing 85% completed • School Building - Substructure –Plinth Wall Concrete 95% completed • School Building - GF RCC Wall Rebar Fixing – 35% completed. | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 27.01% | 20.78% | -6.23% | Building Permit | 2024-05-17 | 2024-05-23 |  | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works to progress • Annex Building - Superstructure works – GF RCC Wall works & FF Slab Works • Shelter Block - Substructure – Plinth Wall Works to complete; Existing Structure Strengthening works to progress. • Shelter Block - Superstructure - GF & FF Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 10862786.8946 | 180000 | https://drive.google.com/thumbnail?id=1LGG-xHMY2FIvsrUQHdBsimZyc6oVwUHI&sz=w1000 | https://drive.google.com/file/d/1LGG-xHMY2FIvsrUQHdBsimZyc6oVwUHI/view?usp=drive_link | https://drive.google.com/thumbnail?id=1Fr7FnU1zhPXLqSCHSNAy1t-LB8P_O5uZ&sz=w1000 | https://drive.google.com/file/d/1Fr7FnU1zhPXLqSCHSNAy1t-LB8P_O5uZ/view?usp=drive_link | https://drive.google.com/thumbnail?id=1bB7YXERU6N6l2CgGXhfHlbgLBpqYC7xS&sz=w1000 | https://drive.google.com/file/d/1bB7YXERU6N6l2CgGXhfHlbgLBpqYC7xS/view?usp=drive_link
2024-09-06 | Madinat Zayed-School-P105 | P105 | SC-06 | 355 | 192 | 547 | • Annex Building - Superstructure – GF RCC Wall Concrete Cast 100 % completed • Annex Building - FF Slab Staging & Formwork fixing 85% completed • School Building - Substructure –Plinth Wall Concrete 95% completed • School Building - GF RCC Wall Rebar Fixing – 35% completed. | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 27.01% | 20.78% | -6.23% | School Substructure | 2024-08-06 |  | 2024-09-20 | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works to progress • Annex Building - Superstructure works – GF RCC Wall works & FF Slab Works • Shelter Block - Substructure – Plinth Wall Works to complete; Existing Structure Strengthening works to progress. • Shelter Block - Superstructure - GF & FF Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 10862786.8946 | 180000 | https://drive.google.com/thumbnail?id=1LGG-xHMY2FIvsrUQHdBsimZyc6oVwUHI&sz=w1000 | https://drive.google.com/file/d/1LGG-xHMY2FIvsrUQHdBsimZyc6oVwUHI/view?usp=drive_link | https://drive.google.com/thumbnail?id=1Fr7FnU1zhPXLqSCHSNAy1t-LB8P_O5uZ&sz=w1000 | https://drive.google.com/file/d/1Fr7FnU1zhPXLqSCHSNAy1t-LB8P_O5uZ/view?usp=drive_link | https://drive.google.com/thumbnail?id=1bB7YXERU6N6l2CgGXhfHlbgLBpqYC7xS&sz=w1000 | https://drive.google.com/file/d/1bB7YXERU6N6l2CgGXhfHlbgLBpqYC7xS/view?usp=drive_link
2024-09-06 | Madinat Zayed-School-P105 | P105 | SC-06 | 355 | 192 | 547 | • Annex Building - Superstructure – GF RCC Wall Concrete Cast 100 % completed • Annex Building - FF Slab Staging & Formwork fixing 85% completed • School Building - Substructure –Plinth Wall Concrete 95% completed • School Building - GF RCC Wall Rebar Fixing – 35% completed. | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 27.01% | 20.78% | -6.23% | School Superstructure | 2024-11-07 |  | 2024-10-23 | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works to progress • Annex Building - Superstructure works – GF RCC Wall works & FF Slab Works • Shelter Block - Substructure – Plinth Wall Works to complete; Existing Structure Strengthening works to progress. • Shelter Block - Superstructure - GF & FF Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 10862786.8946 | 180000 | https://drive.google.com/thumbnail?id=1LGG-xHMY2FIvsrUQHdBsimZyc6oVwUHI&sz=w1000 | https://drive.google.com/file/d/1LGG-xHMY2FIvsrUQHdBsimZyc6oVwUHI/view?usp=drive_link | https://drive.google.com/thumbnail?id=1Fr7FnU1zhPXLqSCHSNAy1t-LB8P_O5uZ&sz=w1000 | https://drive.google.com/file/d/1Fr7FnU1zhPXLqSCHSNAy1t-LB8P_O5uZ/view?usp=drive_link | https://drive.google.com/thumbnail?id=1bB7YXERU6N6l2CgGXhfHlbgLBpqYC7xS&sz=w1000 | https://drive.google.com/file/d/1bB7YXERU6N6l2CgGXhfHlbgLBpqYC7xS/view?usp=drive_link
2024-09-06 | Madinat Zayed-School-P105 | P105 | SC-06 | 355 | 192 | 547 | • Annex Building - Superstructure – GF RCC Wall Concrete Cast 100 % completed • Annex Building - FF Slab Staging & Formwork fixing 85% completed • School Building - Substructure –Plinth Wall Concrete 95% completed • School Building - GF RCC Wall Rebar Fixing – 35% completed. | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 27.01% | 20.78% | -6.23% | Annex Substructure | 2024-08-06 | 2024-07-13 |  | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works to progress • Annex Building - Superstructure works – GF RCC Wall works & FF Slab Works • Shelter Block - Substructure – Plinth Wall Works to complete; Existing Structure Strengthening works to progress. • Shelter Block - Superstructure - GF & FF Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 10862786.8946 | 180000 | https://drive.google.com/thumbnail?id=1LGG-xHMY2FIvsrUQHdBsimZyc6oVwUHI&sz=w1000 | https://drive.google.com/file/d/1LGG-xHMY2FIvsrUQHdBsimZyc6oVwUHI/view?usp=drive_link | https://drive.google.com/thumbnail?id=1Fr7FnU1zhPXLqSCHSNAy1t-LB8P_O5uZ&sz=w1000 | https://drive.google.com/file/d/1Fr7FnU1zhPXLqSCHSNAy1t-LB8P_O5uZ/view?usp=drive_link | https://drive.google.com/thumbnail?id=1bB7YXERU6N6l2CgGXhfHlbgLBpqYC7xS&sz=w1000 | https://drive.google.com/file/d/1bB7YXERU6N6l2CgGXhfHlbgLBpqYC7xS/view?usp=drive_link
2024-09-06 | Madinat Zayed-School-P105 | P105 | SC-06 | 355 | 192 | 547 | • Annex Building - Superstructure – GF RCC Wall Concrete Cast 100 % completed • Annex Building - FF Slab Staging & Formwork fixing 85% completed • School Building - Substructure –Plinth Wall Concrete 95% completed • School Building - GF RCC Wall Rebar Fixing – 35% completed. | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 27.01% | 20.78% | -6.23% | Annex Superstructure | 2024-10-31 |  | 2024-10-26 | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works to progress • Annex Building - Superstructure works – GF RCC Wall works & FF Slab Works • Shelter Block - Substructure – Plinth Wall Works to complete; Existing Structure Strengthening works to progress. • Shelter Block - Superstructure - GF & FF Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 10862786.8946 | 180000 | https://drive.google.com/thumbnail?id=1LGG-xHMY2FIvsrUQHdBsimZyc6oVwUHI&sz=w1000 | https://drive.google.com/file/d/1LGG-xHMY2FIvsrUQHdBsimZyc6oVwUHI/view?usp=drive_link | https://drive.google.com/thumbnail?id=1Fr7FnU1zhPXLqSCHSNAy1t-LB8P_O5uZ&sz=w1000 | https://drive.google.com/file/d/1Fr7FnU1zhPXLqSCHSNAy1t-LB8P_O5uZ/view?usp=drive_link | https://drive.google.com/thumbnail?id=1bB7YXERU6N6l2CgGXhfHlbgLBpqYC7xS&sz=w1000 | https://drive.google.com/file/d/1bB7YXERU6N6l2CgGXhfHlbgLBpqYC7xS/view?usp=drive_link
2024-09-06 | Madinat Zayed-School-P105 | P105 | SC-06 | 355 | 192 | 547 | • Annex Building - Superstructure – GF RCC Wall Concrete Cast 100 % completed • Annex Building - FF Slab Staging & Formwork fixing 85% completed • School Building - Substructure –Plinth Wall Concrete 95% completed • School Building - GF RCC Wall Rebar Fixing – 35% completed. | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 27.01% | 20.78% | -6.23% | MEP & Finishes | 2025-01-25 |  | 2025-05-15 | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works to progress • Annex Building - Superstructure works – GF RCC Wall works & FF Slab Works • Shelter Block - Substructure – Plinth Wall Works to complete; Existing Structure Strengthening works to progress. • Shelter Block - Superstructure - GF & FF Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 10862786.8946 | 180000 | https://drive.google.com/thumbnail?id=1LGG-xHMY2FIvsrUQHdBsimZyc6oVwUHI&sz=w1000 | https://drive.google.com/file/d/1LGG-xHMY2FIvsrUQHdBsimZyc6oVwUHI/view?usp=drive_link | https://drive.google.com/thumbnail?id=1Fr7FnU1zhPXLqSCHSNAy1t-LB8P_O5uZ&sz=w1000 | https://drive.google.com/file/d/1Fr7FnU1zhPXLqSCHSNAy1t-LB8P_O5uZ/view?usp=drive_link | https://drive.google.com/thumbnail?id=1bB7YXERU6N6l2CgGXhfHlbgLBpqYC7xS&sz=w1000 | https://drive.google.com/file/d/1bB7YXERU6N6l2CgGXhfHlbgLBpqYC7xS/view?usp=drive_link
2024-09-06 | Madinat Zayed-School-P105 | P105 | SC-06 | 355 | 192 | 547 | • Annex Building - Superstructure – GF RCC Wall Concrete Cast 100 % completed • Annex Building - FF Slab Staging & Formwork fixing 85% completed • School Building - Substructure –Plinth Wall Concrete 95% completed • School Building - GF RCC Wall Rebar Fixing – 35% completed. | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 27.01% | 20.78% | -6.23% | BCC Inspection | 2025-02-13 |  | 2025-05-26 | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works to progress • Annex Building - Superstructure works – GF RCC Wall works & FF Slab Works • Shelter Block - Substructure – Plinth Wall Works to complete; Existing Structure Strengthening works to progress. • Shelter Block - Superstructure - GF & FF Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 10862786.8946 | 180000 | https://drive.google.com/thumbnail?id=1LGG-xHMY2FIvsrUQHdBsimZyc6oVwUHI&sz=w1000 | https://drive.google.com/file/d/1LGG-xHMY2FIvsrUQHdBsimZyc6oVwUHI/view?usp=drive_link | https://drive.google.com/thumbnail?id=1Fr7FnU1zhPXLqSCHSNAy1t-LB8P_O5uZ&sz=w1000 | https://drive.google.com/file/d/1Fr7FnU1zhPXLqSCHSNAy1t-LB8P_O5uZ/view?usp=drive_link | https://drive.google.com/thumbnail?id=1bB7YXERU6N6l2CgGXhfHlbgLBpqYC7xS&sz=w1000 | https://drive.google.com/file/d/1bB7YXERU6N6l2CgGXhfHlbgLBpqYC7xS/view?usp=drive_link
2024-09-06 | Madinat Zayed-School-P105 | P105 | SC-06 | 355 | 192 | 547 | • Annex Building - Superstructure – GF RCC Wall Concrete Cast 100 % completed • Annex Building - FF Slab Staging & Formwork fixing 85% completed • School Building - Substructure –Plinth Wall Concrete 95% completed • School Building - GF RCC Wall Rebar Fixing – 35% completed. | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 27.01% | 20.78% | -6.23% | BCC Issuance | 2025-03-04 |  | 2025-06-16 | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works to progress • Annex Building - Superstructure works – GF RCC Wall works & FF Slab Works • Shelter Block - Substructure – Plinth Wall Works to complete; Existing Structure Strengthening works to progress. • Shelter Block - Superstructure - GF & FF Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 10862786.8946 | 180000 | https://drive.google.com/thumbnail?id=1LGG-xHMY2FIvsrUQHdBsimZyc6oVwUHI&sz=w1000 | https://drive.google.com/file/d/1LGG-xHMY2FIvsrUQHdBsimZyc6oVwUHI/view?usp=drive_link | https://drive.google.com/thumbnail?id=1Fr7FnU1zhPXLqSCHSNAy1t-LB8P_O5uZ&sz=w1000 | https://drive.google.com/file/d/1Fr7FnU1zhPXLqSCHSNAy1t-LB8P_O5uZ/view?usp=drive_link | https://drive.google.com/thumbnail?id=1bB7YXERU6N6l2CgGXhfHlbgLBpqYC7xS&sz=w1000 | https://drive.google.com/file/d/1bB7YXERU6N6l2CgGXhfHlbgLBpqYC7xS/view?usp=drive_link
2024-09-06 | Madinat Zayed-School-P105 | P105 | SC-06 | 355 | 192 | 547 | • Annex Building - Superstructure – GF RCC Wall Concrete Cast 100 % completed • Annex Building - FF Slab Staging & Formwork fixing 85% completed • School Building - Substructure –Plinth Wall Concrete 95% completed • School Building - GF RCC Wall Rebar Fixing – 35% completed. | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 27.01% | 20.78% | -6.23% | Completion | 2025-03-17 |  | 2025-06-30 | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works to progress • Annex Building - Superstructure works – GF RCC Wall works & FF Slab Works • Shelter Block - Substructure – Plinth Wall Works to complete; Existing Structure Strengthening works to progress. • Shelter Block - Superstructure - GF & FF Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 10862786.8946 | 180000 | https://drive.google.com/thumbnail?id=1LGG-xHMY2FIvsrUQHdBsimZyc6oVwUHI&sz=w1000 | https://drive.google.com/file/d/1LGG-xHMY2FIvsrUQHdBsimZyc6oVwUHI/view?usp=drive_link | https://drive.google.com/thumbnail?id=1Fr7FnU1zhPXLqSCHSNAy1t-LB8P_O5uZ&sz=w1000 | https://drive.google.com/file/d/1Fr7FnU1zhPXLqSCHSNAy1t-LB8P_O5uZ/view?usp=drive_link | https://drive.google.com/thumbnail?id=1bB7YXERU6N6l2CgGXhfHlbgLBpqYC7xS&sz=w1000 | https://drive.google.com/file/d/1bB7YXERU6N6l2CgGXhfHlbgLBpqYC7xS/view?usp=drive_link
2024-09-06 | Madinat Zayed-School-P38 | P38 | SC-07 | 355 | 192 | 547 | • Annex Building - GF RCC Wall – Rebar fixing 96% Completed. • Annex Building - GF RCC Wall – Concrete pouring 60% Completed; FF Slab Staging works started • School Building - Superstructure – GF RCC Wall Rebar Fixing – 70% completed; GF Wall Concrete 30% completed • School Building - FF RCC Wall Rebar Fixing – 15% completed; | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 27.01% | 25% | -2.01% | Notice to Commence | 2023-09-18 | 2023-09-26 |  | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – GF RCC Wall works to complete; FF Slab works to progress • Shelter Block - Superstructure - GF & FF Structure Strentheing & RCC Wall works to progress. • Shelter Block - Surface Preparation for CFRP Works. | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 11500494.3905 | 180000 | https://drive.google.com/thumbnail?id=1bSZghuFPNMDy724R2VmzwB1Jr2rl9y3T&sz=w1000 | https://drive.google.com/file/d/1bSZghuFPNMDy724R2VmzwB1Jr2rl9y3T/view?usp=drive_link | https://drive.google.com/thumbnail?id=18HTGOY9i7bxWMrMLMgWvctC0TQbGDm_d&sz=w1000 | https://drive.google.com/file/d/18HTGOY9i7bxWMrMLMgWvctC0TQbGDm_d/view?usp=drive_link | https://drive.google.com/thumbnail?id=1nxqhANLSmBJ-olV0_wGYRyXJpm4XiNGD&sz=w1000 | https://drive.google.com/file/d/1nxqhANLSmBJ-olV0_wGYRyXJpm4XiNGD/view?usp=drive_link
2024-09-06 | Madinat Zayed-School-P38 | P38 | SC-07 | 355 | 192 | 547 | • Annex Building - GF RCC Wall – Rebar fixing 96% Completed. • Annex Building - GF RCC Wall – Concrete pouring 60% Completed; FF Slab Staging works started • School Building - Superstructure – GF RCC Wall Rebar Fixing – 70% completed; GF Wall Concrete 30% completed • School Building - FF RCC Wall Rebar Fixing – 15% completed; | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 27.01% | 25% | -2.01% | Site Mobilization | 2023-10-21 | 2024-01-13 |  | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – GF RCC Wall works to complete; FF Slab works to progress • Shelter Block - Superstructure - GF & FF Structure Strentheing & RCC Wall works to progress. • Shelter Block - Surface Preparation for CFRP Works. | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 11500494.3905 | 180000 | https://drive.google.com/thumbnail?id=1bSZghuFPNMDy724R2VmzwB1Jr2rl9y3T&sz=w1000 | https://drive.google.com/file/d/1bSZghuFPNMDy724R2VmzwB1Jr2rl9y3T/view?usp=drive_link | https://drive.google.com/thumbnail?id=18HTGOY9i7bxWMrMLMgWvctC0TQbGDm_d&sz=w1000 | https://drive.google.com/file/d/18HTGOY9i7bxWMrMLMgWvctC0TQbGDm_d/view?usp=drive_link | https://drive.google.com/thumbnail?id=1nxqhANLSmBJ-olV0_wGYRyXJpm4XiNGD&sz=w1000 | https://drive.google.com/file/d/1nxqhANLSmBJ-olV0_wGYRyXJpm4XiNGD/view?usp=drive_link
2024-09-06 | Madinat Zayed-School-P38 | P38 | SC-07 | 355 | 192 | 547 | • Annex Building - GF RCC Wall – Rebar fixing 96% Completed. • Annex Building - GF RCC Wall – Concrete pouring 60% Completed; FF Slab Staging works started • School Building - Superstructure – GF RCC Wall Rebar Fixing – 70% completed; GF Wall Concrete 30% completed • School Building - FF RCC Wall Rebar Fixing – 15% completed; | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 27.01% | 25% | -2.01% | Building Permit | 2024-05-17 | 2024-05-27 |  | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – GF RCC Wall works to complete; FF Slab works to progress • Shelter Block - Superstructure - GF & FF Structure Strentheing & RCC Wall works to progress. • Shelter Block - Surface Preparation for CFRP Works. | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 11500494.3905 | 180000 | https://drive.google.com/thumbnail?id=1bSZghuFPNMDy724R2VmzwB1Jr2rl9y3T&sz=w1000 | https://drive.google.com/file/d/1bSZghuFPNMDy724R2VmzwB1Jr2rl9y3T/view?usp=drive_link | https://drive.google.com/thumbnail?id=18HTGOY9i7bxWMrMLMgWvctC0TQbGDm_d&sz=w1000 | https://drive.google.com/file/d/18HTGOY9i7bxWMrMLMgWvctC0TQbGDm_d/view?usp=drive_link | https://drive.google.com/thumbnail?id=1nxqhANLSmBJ-olV0_wGYRyXJpm4XiNGD&sz=w1000 | https://drive.google.com/file/d/1nxqhANLSmBJ-olV0_wGYRyXJpm4XiNGD/view?usp=drive_link
2024-09-06 | Madinat Zayed-School-P38 | P38 | SC-07 | 355 | 192 | 547 | • Annex Building - GF RCC Wall – Rebar fixing 96% Completed. • Annex Building - GF RCC Wall – Concrete pouring 60% Completed; FF Slab Staging works started • School Building - Superstructure – GF RCC Wall Rebar Fixing – 70% completed; GF Wall Concrete 30% completed • School Building - FF RCC Wall Rebar Fixing – 15% completed; | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 27.01% | 25% | -2.01% | School Substructure | 2024-08-06 | 2024-08-21 |  | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – GF RCC Wall works to complete; FF Slab works to progress • Shelter Block - Superstructure - GF & FF Structure Strentheing & RCC Wall works to progress. • Shelter Block - Surface Preparation for CFRP Works. | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 11500494.3905 | 180000 | https://drive.google.com/thumbnail?id=1bSZghuFPNMDy724R2VmzwB1Jr2rl9y3T&sz=w1000 | https://drive.google.com/file/d/1bSZghuFPNMDy724R2VmzwB1Jr2rl9y3T/view?usp=drive_link | https://drive.google.com/thumbnail?id=18HTGOY9i7bxWMrMLMgWvctC0TQbGDm_d&sz=w1000 | https://drive.google.com/file/d/18HTGOY9i7bxWMrMLMgWvctC0TQbGDm_d/view?usp=drive_link | https://drive.google.com/thumbnail?id=1nxqhANLSmBJ-olV0_wGYRyXJpm4XiNGD&sz=w1000 | https://drive.google.com/file/d/1nxqhANLSmBJ-olV0_wGYRyXJpm4XiNGD/view?usp=drive_link
2024-09-06 | Madinat Zayed-School-P38 | P38 | SC-07 | 355 | 192 | 547 | • Annex Building - GF RCC Wall – Rebar fixing 96% Completed. • Annex Building - GF RCC Wall – Concrete pouring 60% Completed; FF Slab Staging works started • School Building - Superstructure – GF RCC Wall Rebar Fixing – 70% completed; GF Wall Concrete 30% completed • School Building - FF RCC Wall Rebar Fixing – 15% completed; | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 27.01% | 25% | -2.01% | School Superstructure | 2024-11-07 |  | 2024-10-21 | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – GF RCC Wall works to complete; FF Slab works to progress • Shelter Block - Superstructure - GF & FF Structure Strentheing & RCC Wall works to progress. • Shelter Block - Surface Preparation for CFRP Works. | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 11500494.3905 | 180000 | https://drive.google.com/thumbnail?id=1bSZghuFPNMDy724R2VmzwB1Jr2rl9y3T&sz=w1000 | https://drive.google.com/file/d/1bSZghuFPNMDy724R2VmzwB1Jr2rl9y3T/view?usp=drive_link | https://drive.google.com/thumbnail?id=18HTGOY9i7bxWMrMLMgWvctC0TQbGDm_d&sz=w1000 | https://drive.google.com/file/d/18HTGOY9i7bxWMrMLMgWvctC0TQbGDm_d/view?usp=drive_link | https://drive.google.com/thumbnail?id=1nxqhANLSmBJ-olV0_wGYRyXJpm4XiNGD&sz=w1000 | https://drive.google.com/file/d/1nxqhANLSmBJ-olV0_wGYRyXJpm4XiNGD/view?usp=drive_link
2024-09-06 | Madinat Zayed-School-P38 | P38 | SC-07 | 355 | 192 | 547 | • Annex Building - GF RCC Wall – Rebar fixing 96% Completed. • Annex Building - GF RCC Wall – Concrete pouring 60% Completed; FF Slab Staging works started • School Building - Superstructure – GF RCC Wall Rebar Fixing – 70% completed; GF Wall Concrete 30% completed • School Building - FF RCC Wall Rebar Fixing – 15% completed; | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 27.01% | 25% | -2.01% | Annex Substructure | 2024-08-06 | 2024-07-31 |  | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – GF RCC Wall works to complete; FF Slab works to progress • Shelter Block - Superstructure - GF & FF Structure Strentheing & RCC Wall works to progress. • Shelter Block - Surface Preparation for CFRP Works. | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 11500494.3905 | 180000 | https://drive.google.com/thumbnail?id=1bSZghuFPNMDy724R2VmzwB1Jr2rl9y3T&sz=w1000 | https://drive.google.com/file/d/1bSZghuFPNMDy724R2VmzwB1Jr2rl9y3T/view?usp=drive_link | https://drive.google.com/thumbnail?id=18HTGOY9i7bxWMrMLMgWvctC0TQbGDm_d&sz=w1000 | https://drive.google.com/file/d/18HTGOY9i7bxWMrMLMgWvctC0TQbGDm_d/view?usp=drive_link | https://drive.google.com/thumbnail?id=1nxqhANLSmBJ-olV0_wGYRyXJpm4XiNGD&sz=w1000 | https://drive.google.com/file/d/1nxqhANLSmBJ-olV0_wGYRyXJpm4XiNGD/view?usp=drive_link
2024-09-06 | Madinat Zayed-School-P38 | P38 | SC-07 | 355 | 192 | 547 | • Annex Building - GF RCC Wall – Rebar fixing 96% Completed. • Annex Building - GF RCC Wall – Concrete pouring 60% Completed; FF Slab Staging works started • School Building - Superstructure – GF RCC Wall Rebar Fixing – 70% completed; GF Wall Concrete 30% completed • School Building - FF RCC Wall Rebar Fixing – 15% completed; | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 27.01% | 25% | -2.01% | Annex Superstructure | 2024-10-31 |  | 2024-11-02 | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – GF RCC Wall works to complete; FF Slab works to progress • Shelter Block - Superstructure - GF & FF Structure Strentheing & RCC Wall works to progress. • Shelter Block - Surface Preparation for CFRP Works. | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 11500494.3905 | 180000 | https://drive.google.com/thumbnail?id=1bSZghuFPNMDy724R2VmzwB1Jr2rl9y3T&sz=w1000 | https://drive.google.com/file/d/1bSZghuFPNMDy724R2VmzwB1Jr2rl9y3T/view?usp=drive_link | https://drive.google.com/thumbnail?id=18HTGOY9i7bxWMrMLMgWvctC0TQbGDm_d&sz=w1000 | https://drive.google.com/file/d/18HTGOY9i7bxWMrMLMgWvctC0TQbGDm_d/view?usp=drive_link | https://drive.google.com/thumbnail?id=1nxqhANLSmBJ-olV0_wGYRyXJpm4XiNGD&sz=w1000 | https://drive.google.com/file/d/1nxqhANLSmBJ-olV0_wGYRyXJpm4XiNGD/view?usp=drive_link
2024-09-06 | Madinat Zayed-School-P38 | P38 | SC-07 | 355 | 192 | 547 | • Annex Building - GF RCC Wall – Rebar fixing 96% Completed. • Annex Building - GF RCC Wall – Concrete pouring 60% Completed; FF Slab Staging works started • School Building - Superstructure – GF RCC Wall Rebar Fixing – 70% completed; GF Wall Concrete 30% completed • School Building - FF RCC Wall Rebar Fixing – 15% completed; | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 27.01% | 25% | -2.01% | MEP & Finishes | 2025-01-25 |  | 2025-05-15 | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – GF RCC Wall works to complete; FF Slab works to progress • Shelter Block - Superstructure - GF & FF Structure Strentheing & RCC Wall works to progress. • Shelter Block - Surface Preparation for CFRP Works. | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 11500494.3905 | 180000 | https://drive.google.com/thumbnail?id=1bSZghuFPNMDy724R2VmzwB1Jr2rl9y3T&sz=w1000 | https://drive.google.com/file/d/1bSZghuFPNMDy724R2VmzwB1Jr2rl9y3T/view?usp=drive_link | https://drive.google.com/thumbnail?id=18HTGOY9i7bxWMrMLMgWvctC0TQbGDm_d&sz=w1000 | https://drive.google.com/file/d/18HTGOY9i7bxWMrMLMgWvctC0TQbGDm_d/view?usp=drive_link | https://drive.google.com/thumbnail?id=1nxqhANLSmBJ-olV0_wGYRyXJpm4XiNGD&sz=w1000 | https://drive.google.com/file/d/1nxqhANLSmBJ-olV0_wGYRyXJpm4XiNGD/view?usp=drive_link
2024-09-06 | Madinat Zayed-School-P38 | P38 | SC-07 | 355 | 192 | 547 | • Annex Building - GF RCC Wall – Rebar fixing 96% Completed. • Annex Building - GF RCC Wall – Concrete pouring 60% Completed; FF Slab Staging works started • School Building - Superstructure – GF RCC Wall Rebar Fixing – 70% completed; GF Wall Concrete 30% completed • School Building - FF RCC Wall Rebar Fixing – 15% completed; | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 27.01% | 25% | -2.01% | BCC Inspection | 2025-02-13 |  | 2025-05-26 | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – GF RCC Wall works to complete; FF Slab works to progress • Shelter Block - Superstructure - GF & FF Structure Strentheing & RCC Wall works to progress. • Shelter Block - Surface Preparation for CFRP Works. | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 11500494.3905 | 180000 | https://drive.google.com/thumbnail?id=1bSZghuFPNMDy724R2VmzwB1Jr2rl9y3T&sz=w1000 | https://drive.google.com/file/d/1bSZghuFPNMDy724R2VmzwB1Jr2rl9y3T/view?usp=drive_link | https://drive.google.com/thumbnail?id=18HTGOY9i7bxWMrMLMgWvctC0TQbGDm_d&sz=w1000 | https://drive.google.com/file/d/18HTGOY9i7bxWMrMLMgWvctC0TQbGDm_d/view?usp=drive_link | https://drive.google.com/thumbnail?id=1nxqhANLSmBJ-olV0_wGYRyXJpm4XiNGD&sz=w1000 | https://drive.google.com/file/d/1nxqhANLSmBJ-olV0_wGYRyXJpm4XiNGD/view?usp=drive_link
2024-09-06 | Madinat Zayed-School-P38 | P38 | SC-07 | 355 | 192 | 547 | • Annex Building - GF RCC Wall – Rebar fixing 96% Completed. • Annex Building - GF RCC Wall – Concrete pouring 60% Completed; FF Slab Staging works started • School Building - Superstructure – GF RCC Wall Rebar Fixing – 70% completed; GF Wall Concrete 30% completed • School Building - FF RCC Wall Rebar Fixing – 15% completed; | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 27.01% | 25% | -2.01% | BCC Issuance | 2025-03-04 |  | 2025-06-16 | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – GF RCC Wall works to complete; FF Slab works to progress • Shelter Block - Superstructure - GF & FF Structure Strentheing & RCC Wall works to progress. • Shelter Block - Surface Preparation for CFRP Works. | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 11500494.3905 | 180000 | https://drive.google.com/thumbnail?id=1bSZghuFPNMDy724R2VmzwB1Jr2rl9y3T&sz=w1000 | https://drive.google.com/file/d/1bSZghuFPNMDy724R2VmzwB1Jr2rl9y3T/view?usp=drive_link | https://drive.google.com/thumbnail?id=18HTGOY9i7bxWMrMLMgWvctC0TQbGDm_d&sz=w1000 | https://drive.google.com/file/d/18HTGOY9i7bxWMrMLMgWvctC0TQbGDm_d/view?usp=drive_link | https://drive.google.com/thumbnail?id=1nxqhANLSmBJ-olV0_wGYRyXJpm4XiNGD&sz=w1000 | https://drive.google.com/file/d/1nxqhANLSmBJ-olV0_wGYRyXJpm4XiNGD/view?usp=drive_link
2024-09-06 | Madinat Zayed-School-P38 | P38 | SC-07 | 355 | 192 | 547 | • Annex Building - GF RCC Wall – Rebar fixing 96% Completed. • Annex Building - GF RCC Wall – Concrete pouring 60% Completed; FF Slab Staging works started • School Building - Superstructure – GF RCC Wall Rebar Fixing – 70% completed; GF Wall Concrete 30% completed • School Building - FF RCC Wall Rebar Fixing – 15% completed; | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 27.01% | 25% | -2.01% | Completion | 2025-03-17 |  | 2025-06-30 | 2024-09-06 | •Bill No.4 – MEP Final Rate Agreement required – 09-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 09-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – GF RCC Wall works to complete; FF Slab works to progress • Shelter Block - Superstructure - GF & FF Structure Strentheing & RCC Wall works to progress. • Shelter Block - Surface Preparation for CFRP Works. | 78077600 | 0 | 78077600 | 1576709 |  | 79654309 | 11500494.3905 | 180000 | https://drive.google.com/thumbnail?id=1bSZghuFPNMDy724R2VmzwB1Jr2rl9y3T&sz=w1000 | https://drive.google.com/file/d/1bSZghuFPNMDy724R2VmzwB1Jr2rl9y3T/view?usp=drive_link | https://drive.google.com/thumbnail?id=18HTGOY9i7bxWMrMLMgWvctC0TQbGDm_d&sz=w1000 | https://drive.google.com/file/d/18HTGOY9i7bxWMrMLMgWvctC0TQbGDm_d/view?usp=drive_link | https://drive.google.com/thumbnail?id=1nxqhANLSmBJ-olV0_wGYRyXJpm4XiNGD&sz=w1000 | https://drive.google.com/file/d/1nxqhANLSmBJ-olV0_wGYRyXJpm4XiNGD/view?usp=drive_link
2024-09-13 | Al Shahama-Majlis-P547 | P547 | MJ-02 | 290 | 308 | 598 | 1-Excavation till Rfat Foundation Completed . 2-Pile head trimming on progress . 3-Pile Head Treatment ongoing . 4-Integrity test piles ongoing . 5-Leveling and compaction ongoing. 6. Raft PCC ongoing. 7-Disposal of Excavated Soil ongoing . 8-Gunting works ongoing . 9- Waterproofing ongoing 10- Dynamic test Completed. 11-TRM test ongoing . 12- Retaning wall startar bar on going 13- Raft Steel Activities on going | Substation Relocation. Shoring system from Secant to Continuous. Reduce the number of Piles static load test form 8Piles to 5piles . Pile Test from Sonic to TRM . | 47.76% | 38.08% | -9.68% | 1-Notice to Commence ( Contractual Milestone ) | 2023-12-05 | 2023-12-05 |  | 2024-09-19 | Risks1-Lifting Works ( Unsafe Lifting / Rigging ) Lack of 3rd party Inspection/ Riggers/ and the damaged rigging tackles,2-Poor Compliance ( Using of Fall Arrest Equipment at heights) , Scaffold Erection and Dismantling works ,3-Delivery of Long Lead Items ( Chillers & Generator & Air handling Unit ),4-Delays in response regarding to blast steel doors necessary enquiries/tests /reports /simulations,……..compliance with engineer enquiries as stated via Material submission rev. 04 that that required to be attended to avoid delays in manufacturing processing ,5-Contractor anticipation /repeated failed commitments found inaccurate/to be enhanced , and require Contractor action to increase the required resources to achieve anticipated productivity as committed .,6-Potential delay in the delivery of the PVKK valves (due to the geopolitical scene) may reflect /impact the schedule of raft casting.,7-Potential need for increasing the height of the intake shaft (potentially beyond the acceptable limit) in order to allow for the safe handling/lifting od MEP equipment by the telescopic crane Invalid statement , since the Creane that will be provided should comply 100% for the Contract specs &drgs without any modification to the structur of Shaft ,8-Potential delay in casting the raft due to multiple design changes of wall stemming from raft level as invalid stement ,9-Compromising the overall quality to meet the project time lin, like guniting without anti-termite and PCC without compaction/anti-termite. ,10-Incompitent dewatering plans at lower raft area risks the pile rebars to be exposed to salt water which could potentially cause corrosion of rebar and cracks on pile., 11-excess concrete without any compaction might potentially cause work that incomliance with project specs ,12-Loading of heavy machinaries on concrete before 24hrs could lead to potential structural craks,13-Non-availability of QA/QC inspector at night leads to the contractor to proceed with any works without maintaining the quality of the same.,14-AIC raised the concerns of ADDC thzta might will not be able to provide permenant Power supply to the project ,15-Client instruction to providethe required AV system (such as av sytem ) from nominated supplier that should be approved by client that might create time impact negatively against the completion of the required provisional to Shelter &Majles and Consutant reqyested to maintain standby equipment to avoid work stoppage ,16-Delay for the engineering submission especially for MBZ site, such as (shop drawings, method statement) , which reflecting on the coordination shop drawings approval. 17-Light fixture submittal not yet submitted for approval.,18-Regarding to Deliverd of all Chillers in Al Shahama & MBZ The Risk Expected to insert the Chillers inside Basement one backage for each chiller ,19-Regarding to Deliverd of all Generators Sets in Al Shahama & MBZ The Risk Expected to insert the Chillers inside Basement one backage for each chiller ,20-Deviation/obvious delays in time of supply the special equipment by Contractor that will lead to disturbance of work execution time line as well as installation , Testing &commissioning | Mitigation1-Apply the mandatory requirement for Lfting equipment as the contruction sector - OSHAD 34,.0 Safe lifting and lfiting accessories. SF , increase inspection procedure, Implement the control for contractor and subcontractor.,2-Allocate sufficient nos of Fall arrest Equipmet, Training and Awareness,Induction,Moniitoring and apply the Risk Assesment - refer to OSHAD SF no. 23 W& H . Scaffold to undergo with 3rd party Inspection,. Comply the requirements as per the engineered design scaffold. ,3-Contractor is requested to keep follow up with supplier /specialist to enable received the goods on time , and without affecting the planned delevery schedule ,4-After sevral reminderes to the Contarctor , subcontarector advised during last progress meeting that the door specialist attended to provde the neccesary certificates /tests as well , and will be issued to Engineer formally for review , and further acrtion ,5-Contractor is requested to secure all the necessary resources that should meet /cover all remaining SOW after study the productivities rate of each equipment /machines to enable provide the accurate dates of mitigation that should be attended upon enquired by Engineer /client,6-Consultant advised to place the PVKK valves 360 mm above the raft's level and produce at least 500 mm concrete upstand, however the same should be subject to coordination with specialist to avoid any miscoordination .construction errors that will not be able to rectify,7.1- Possibility of using in-situ dismantle/reassemble approach with all MEP equipment. 7.22- Possibility of doing without telescopic cranes altogether and provide middle slot in the intake shaft's cover slab to allow for the lifting of MEP equipment.,8-Contractor to finalize/freeze the upper raft layout in the light of coordination drawings. ,9-Contractor to implement quality toolbox at the beginning of each activity and at regular intervals to enlighten the importance of quality and sequence of activity.- Contractor should treat the invalid work localy to avoid any negative time implication against the overall project complation date ,10-Contractor to propose more efficient way of dewatering with more efficient equipments for operation to avoid availability of water table contact to steel rebair ,11-Contractor should have back-up plans for excess concrete in the mixeres (if any) everyday rather than creating abortive works.,12-Contractor should wait until the required time period for the concrete to achieve the required strength before loading. Area to be closed with precaution tapes to warn others the same. ,13-Contractor to assign ASAP a quality personal at night shift,14-Contractor is requested to liase with ADDC to varify the validy of ADDC wether they can provide th pemennat Power uspply to the project peioe requesting the Client supplort ,15-Contractor should abide to Client instruction ,16-Engineer coordinated with the contractor to Identify and prioritize the most critical SD, MS and method statements that are causing the most significant delays. 17-Engineer Hold daily workshop and bi-weekly progress meetings with the contractor team to monitor the status of submissions and address any bottlenecks immediately.,18&19-The Main contractor Shall be Submit Method Statement for installation Explain the plane to moving and reaching all Chillers & Generators to Correct location over Foundation with protection without any Risk.,,20- Contarctor requested to coordinate with specialist to provide valid /actual date of material delvery to verify the impact of late delevery (if any ) to submit undertaking letter to confirm the delivery schedule of the special equipment and on site . | *Completion of Excavate Soil Till Raft Foundation *Completion of Disposal of Excavated Materials *Completion of Site Cleaning and Preparation *Completion of Pile Head Breaking . *Completion of Raft PCC works . *Completion of Steel Reinforcement for Raft Foundation Fabrication and Delivery . * Completion TRM & Dynamic test *Completion of Pile Integrity Test *Completion the Screed and Raft R.FT *Completion of Raft Steel works . * Start of Starter bar for columns and walls | 85805249.48 | 0 | 85805249.48 | 3799481.4618 |  | 89604730.9418 | 17180863.6 | 1117487.2997 | https://drive.google.com/thumbnail?id=1Zy0KiYSeP-PDs5KIIeeW5fsWj9p4nkja&sz=w1000 | https://drive.google.com/file/d/1Zy0KiYSeP-PDs5KIIeeW5fsWj9p4nkja/view?usp=drive_link | https://drive.google.com/thumbnail?id=1uEFxmPjjwD8Nqb0QvhaTsvG7Fe2EVwdA&sz=w1000 | https://drive.google.com/file/d/1uEFxmPjjwD8Nqb0QvhaTsvG7Fe2EVwdA/view?usp=drive_link | https://drive.google.com/thumbnail?id=18smY9gvWxQDfgihbZYRWZ76-V_fFiVyk&sz=w1000 | https://drive.google.com/file/d/18smY9gvWxQDfgihbZYRWZ76-V_fFiVyk/view?usp=drive_link
2024-09-13 | Al Shahama-Majlis-P547 | P547 | MJ-02 | 290 | 308 | 598 | 1-Excavation till Rfat Foundation Completed . 2-Pile head trimming on progress . 3-Pile Head Treatment ongoing . 4-Integrity test piles ongoing . 5-Leveling and compaction ongoing. 6. Raft PCC ongoing. 7-Disposal of Excavated Soil ongoing . 8-Gunting works ongoing . 9- Waterproofing ongoing 10- Dynamic test Completed. 11-TRM test ongoing . 12- Retaning wall startar bar on going 13- Raft Steel Activities on going | Substation Relocation. Shoring system from Secant to Continuous. Piles static load test form 8Piles to 5piles . Pile Test from Sonic to TRM . | 47.76% | 38.08% | -9.68% | 2-Substructure- Earth work up to Raft Foundation (next Monitiring Milestone) | 2024-07-30 |  | 2024-09-28 | 2024-09-19 | Risks1-Lifting Works ( Unsafe Lifting / Rigging ) Lack of 3rd party Inspection/ Riggers/ and the damaged rigging tackles,2-Poor Compliance ( Using of Fall Arrest Equipment at heights) , Scaffold Erection and Dismantling works ,3-Delivery of Long Lead Items ( Chillers & Generator & Air handling Unit ),4-Delays in response regarding to blast steel doors necessary enquiries/tests /reports /simulations,……..compliance with engineer enquiries as stated via Material submission rev. 04 that that required to be attended to avoid delays in manufacturing processing ,5-Contractor anticipation /repeated failed commitments found inaccurate/to be enhanced , and require Contractor action to increase the required resources to achieve anticipated productivity as committed .,6-Potential delay in the delivery of the PVKK valves (due to the geopolitical scene) may reflect /impact the schedule of raft casting.,7-Potential need for increasing the height of the intake shaft (potentially beyond the acceptable limit) in order to allow for the safe handling/lifting od MEP equipment by the telescopic crane Invalid statement , since the Creane that will be provided should comply 100% for the Contract specs &drgs without any modification to the structur of Shaft ,8-Potential delay in casting the raft due to multiple design changes of wall stemming from raft level as invalid stement ,9-Compromising the overall quality to meet the project time lin, like guniting without anti-termite and PCC without compaction/anti-termite. ,10-Incompitent dewatering plans at lower raft area risks the pile rebars to be exposed to salt water which could potentially cause corrosion of rebar and cracks on pile., 11-excess concrete without any compaction might potentially cause work that incomliance with project specs ,12-Loading of heavy machinaries on concrete before 24hrs could lead to potential structural craks,13-Non-availability of QA/QC inspector at night leads to the contractor to proceed with any works without maintaining the quality of the same.,14-AIC raised the concerns of ADDC thzta might will not be able to provide permenant Power supply to the project ,15-Client instruction to providethe required AV system (such as av sytem ) from nominated supplier that should be approved by client that might create time impact negatively against the completion of the required provisional to Shelter &Majles and Consutant reqyested to maintain standby equipment to avoid work stoppage ,16-Delay for the engineering submission especially for MBZ site, such as (shop drawings, method statement) , which reflecting on the coordination shop drawings approval. 17-Light fixture submittal not yet submitted for approval.,18-Regarding to Deliverd of all Chillers in Al Shahama & MBZ The Risk Expected to insert the Chillers inside Basement one backage for each chiller ,19-Regarding to Deliverd of all Generators Sets in Al Shahama & MBZ The Risk Expected to insert the Chillers inside Basement one backage for each chiller ,20-Deviation/obvious delays in time of supply the special equipment by Contractor that will lead to disturbance of work execution time line as well as installation , Testing &commissioning | Mitigation1-Apply the mandatory requirement for Lfting equipment as the contruction sector - OSHAD 34,.0 Safe lifting and lfiting accessories. SF , increase inspection procedure, Implement the control for contractor and subcontractor.,2-Allocate sufficient nos of Fall arrest Equipmet, Training and Awareness,Induction,Moniitoring and apply the Risk Assesment - refer to OSHAD SF no. 23 W& H . Scaffold to undergo with 3rd party Inspection,. Comply the requirements as per the engineered design scaffold. ,3-Contractor is requested to keep follow up with supplier /specialist to enable received the goods on time , and without affecting the planned delevery schedule ,4-After sevral reminderes to the Contarctor , subcontarector advised during last progress meeting that the door specialist attended to provde the neccesary certificates /tests as well , and will be issued to Engineer formally for review , and further acrtion ,5-Contractor is requested to secure all the necessary resources that should meet /cover all remaining SOW after study the productivities rate of each equipment /machines to enable provide the accurate dates of mitigation that should be attended upon enquired by Engineer /client,6-Consultant advised to place the PVKK valves 360 mm above the raft's level and produce at least 500 mm concrete upstand, however the same should be subject to coordination with specialist to avoid any miscoordination .construction errors that will not be able to rectify,7.1- Possibility of using in-situ dismantle/reassemble approach with all MEP equipment. 7.22- Possibility of doing without telescopic cranes altogether and provide middle slot in the intake shaft's cover slab to allow for the lifting of MEP equipment.,8-Contractor to finalize/freeze the upper raft layout in the light of coordination drawings. ,9-Contractor to implement quality toolbox at the beginning of each activity and at regular intervals to enlighten the importance of quality and sequence of activity.- Contractor should treat the invalid work localy to avoid any negative time implication against the overall project complation date ,10-Contractor to propose more efficient way of dewatering with more efficient equipments for operation to avoid availability of water table contact to steel rebair ,11-Contractor should have back-up plans for excess concrete in the mixeres (if any) everyday rather than creating abortive works.,12-Contractor should wait until the required time period for the concrete to achieve the required strength before loading. Area to be closed with precaution tapes to warn others the same. ,13-Contractor to assign ASAP a quality personal at night shift,14-Contractor is requested to liase with ADDC to varify the validy of ADDC wether they can provide th pemennat Power uspply to the project peioe requesting the Client supplort ,15-Contractor should abide to Client instruction ,16-Engineer coordinated with the contractor to Identify and prioritize the most critical SD, MS and method statements that are causing the most significant delays. 17-Engineer Hold daily workshop and bi-weekly progress meetings with the contractor team to monitor the status of submissions and address any bottlenecks immediately.,18&19-The Main contractor Shall be Submit Method Statement for installation Explain the plane to moving and reaching all Chillers & Generators to Correct location over Foundation with protection without any Risk.,,20- Contarctor requested to coordinate with specialist to provide valid /actual date of material delvery to verify the impact of late delevery (if any ) to submit undertaking letter to confirm the delivery schedule of the special equipment and on site . | *Completion of Excavate Soil Till Raft Foundation *Completion of Disposal of Excavated Materials *Completion of Site Cleaning and Preparation *Completion of Pile Head Breaking . *Completion of Raft PCC works . *Completion of Steel Reinforcement for Raft Foundation Fabrication and Delivery . * Completion TRM & Dynamic test *Completion of Pile Integrity Test *Completion the Screed and Raft R.FT *Completion of Raft Steel works . * Start of Starter bar for columns and walls | 85805249.48 | 0 | 85805249.48 | 3799481.4618 |  | 89604730.9418 | 17180863.6 | 1117487.2997 | https://drive.google.com/thumbnail?id=1Zy0KiYSeP-PDs5KIIeeW5fsWj9p4nkja&sz=w1000 | https://drive.google.com/file/d/1Zy0KiYSeP-PDs5KIIeeW5fsWj9p4nkja/view?usp=drive_link | https://drive.google.com/thumbnail?id=1uEFxmPjjwD8Nqb0QvhaTsvG7Fe2EVwdA&sz=w1000 | https://drive.google.com/file/d/1uEFxmPjjwD8Nqb0QvhaTsvG7Fe2EVwdA/view?usp=drive_link | https://drive.google.com/thumbnail?id=18smY9gvWxQDfgihbZYRWZ76-V_fFiVyk&sz=w1000 | https://drive.google.com/file/d/18smY9gvWxQDfgihbZYRWZ76-V_fFiVyk/view?usp=drive_link
2024-09-13 | Al Shahama-Majlis-P547 | P547 | MJ-02 | 290 | 308 | 598 | 1-Excavation till Rfat Foundation Completed . 2-Pile head trimming on progress . 3-Pile Head Treatment ongoing . 4-Integrity test piles ongoing . 5-Leveling and compaction ongoing. 6. Raft PCC ongoing. 7-Disposal of Excavated Soil ongoing . 8-Gunting works ongoing . 9- Waterproofing ongoing 10- Dynamic test Completed. 11-TRM test ongoing . 12- Retaning wall startar bar on going 13- Raft Steel Activities on going | Substation Relocation. Shoring system from Secant to Continuous. Piles static load test form 8Piles to 5piles . Pile Test from Sonic to TRM . | 47.76% | 38.08% | -9.68% | 3-Superstructure-Basment | 2024-09-04 |  | 2024-11-20 | 2024-09-19 | Risks1-Lifting Works ( Unsafe Lifting / Rigging ) Lack of 3rd party Inspection/ Riggers/ and the damaged rigging tackles,2-Poor Compliance ( Using of Fall Arrest Equipment at heights) , Scaffold Erection and Dismantling works ,3-Delivery of Long Lead Items ( Chillers & Generator & Air handling Unit ),4-Delays in response regarding to blast steel doors necessary enquiries/tests /reports /simulations,……..compliance with engineer enquiries as stated via Material submission rev. 04 that that required to be attended to avoid delays in manufacturing processing ,5-Contractor anticipation /repeated failed commitments found inaccurate/to be enhanced , and require Contractor action to increase the required resources to achieve anticipated productivity as committed .,6-Potential delay in the delivery of the PVKK valves (due to the geopolitical scene) may reflect /impact the schedule of raft casting.,7-Potential need for increasing the height of the intake shaft (potentially beyond the acceptable limit) in order to allow for the safe handling/lifting od MEP equipment by the telescopic crane Invalid statement , since the Creane that will be provided should comply 100% for the Contract specs &drgs without any modification to the structur of Shaft ,8-Potential delay in casting the raft due to multiple design changes of wall stemming from raft level as invalid stement ,9-Compromising the overall quality to meet the project time lin, like guniting without anti-termite and PCC without compaction/anti-termite. ,10-Incompitent dewatering plans at lower raft area risks the pile rebars to be exposed to salt water which could potentially cause corrosion of rebar and cracks on pile., 11-excess concrete without any compaction might potentially cause work that incomliance with project specs ,12-Loading of heavy machinaries on concrete before 24hrs could lead to potential structural craks,13-Non-availability of QA/QC inspector at night leads to the contractor to proceed with any works without maintaining the quality of the same.,14-AIC raised the concerns of ADDC thzta might will not be able to provide permenant Power supply to the project ,15-Client instruction to providethe required AV system (such as av sytem ) from nominated supplier that should be approved by client that might create time impact negatively against the completion of the required provisional to Shelter &Majles and Consutant reqyested to maintain standby equipment to avoid work stoppage ,16-Delay for the engineering submission especially for MBZ site, such as (shop drawings, method statement) , which reflecting on the coordination shop drawings approval. 17-Light fixture submittal not yet submitted for approval.,18-Regarding to Deliverd of all Chillers in Al Shahama & MBZ The Risk Expected to insert the Chillers inside Basement one backage for each chiller ,19-Regarding to Deliverd of all Generators Sets in Al Shahama & MBZ The Risk Expected to insert the Chillers inside Basement one backage for each chiller ,20-Deviation/obvious delays in time of supply the special equipment by Contractor that will lead to disturbance of work execution time line as well as installation , Testing &commissioning | Mitigation1-Apply the mandatory requirement for Lfting equipment as the contruction sector - OSHAD 34,.0 Safe lifting and lfiting accessories. SF , increase inspection procedure, Implement the control for contractor and subcontractor.,2-Allocate sufficient nos of Fall arrest Equipmet, Training and Awareness,Induction,Moniitoring and apply the Risk Assesment - refer to OSHAD SF no. 23 W& H . Scaffold to undergo with 3rd party Inspection,. Comply the requirements as per the engineered design scaffold. ,3-Contractor is requested to keep follow up with supplier /specialist to enable received the goods on time , and without affecting the planned delevery schedule ,4-After sevral reminderes to the Contarctor , subcontarector advised during last progress meeting that the door specialist attended to provde the neccesary certificates /tests as well , and will be issued to Engineer formally for review , and further acrtion ,5-Contractor is requested to secure all the necessary resources that should meet /cover all remaining SOW after study the productivities rate of each equipment /machines to enable provide the accurate dates of mitigation that should be attended upon enquired by Engineer /client,6-Consultant advised to place the PVKK valves 360 mm above the raft's level and produce at least 500 mm concrete upstand, however the same should be subject to coordination with specialist to avoid any miscoordination .construction errors that will not be able to rectify,7.1- Possibility of using in-situ dismantle/reassemble approach with all MEP equipment. 7.22- Possibility of doing without telescopic cranes altogether and provide middle slot in the intake shaft's cover slab to allow for the lifting of MEP equipment.,8-Contractor to finalize/freeze the upper raft layout in the light of coordination drawings. ,9-Contractor to implement quality toolbox at the beginning of each activity and at regular intervals to enlighten the importance of quality and sequence of activity.- Contractor should treat the invalid work localy to avoid any negative time implication against the overall project complation date ,10-Contractor to propose more efficient way of dewatering with more efficient equipments for operation to avoid availability of water table contact to steel rebair ,11-Contractor should have back-up plans for excess concrete in the mixeres (if any) everyday rather than creating abortive works.,12-Contractor should wait until the required time period for the concrete to achieve the required strength before loading. Area to be closed with precaution tapes to warn others the same. ,13-Contractor to assign ASAP a quality personal at night shift,14-Contractor is requested to liase with ADDC to varify the validy of ADDC wether they can provide th pemennat Power uspply to the project peioe requesting the Client supplort ,15-Contractor should abide to Client instruction ,16-Engineer coordinated with the contractor to Identify and prioritize the most critical SD, MS and method statements that are causing the most significant delays. 17-Engineer Hold daily workshop and bi-weekly progress meetings with the contractor team to monitor the status of submissions and address any bottlenecks immediately.,18&19-The Main contractor Shall be Submit Method Statement for installation Explain the plane to moving and reaching all Chillers & Generators to Correct location over Foundation with protection without any Risk.,,20- Contarctor requested to coordinate with specialist to provide valid /actual date of material delvery to verify the impact of late delevery (if any ) to submit undertaking letter to confirm the delivery schedule of the special equipment and on site . | *Completion of Excavate Soil Till Raft Foundation *Completion of Disposal of Excavated Materials *Completion of Site Cleaning and Preparation *Completion of Pile Head Breaking . *Completion of Raft PCC works . *Completion of Steel Reinforcement for Raft Foundation Fabrication and Delivery . * Completion TRM & Dynamic test *Completion of Pile Integrity Test *Completion the Screed and Raft R.FT *Completion of Raft Steel works . * Start of Starter bar for columns and walls | 85805249.48 | 0 | 85805249.48 | 3799481.4618 |  | 89604730.9418 | 17180863.6 | 1117487.2997 | https://drive.google.com/thumbnail?id=1Zy0KiYSeP-PDs5KIIeeW5fsWj9p4nkja&sz=w1000 | https://drive.google.com/file/d/1Zy0KiYSeP-PDs5KIIeeW5fsWj9p4nkja/view?usp=drive_link | https://drive.google.com/thumbnail?id=1uEFxmPjjwD8Nqb0QvhaTsvG7Fe2EVwdA&sz=w1000 | https://drive.google.com/file/d/1uEFxmPjjwD8Nqb0QvhaTsvG7Fe2EVwdA/view?usp=drive_link | https://drive.google.com/thumbnail?id=18smY9gvWxQDfgihbZYRWZ76-V_fFiVyk&sz=w1000 | https://drive.google.com/file/d/18smY9gvWxQDfgihbZYRWZ76-V_fFiVyk/view?usp=drive_link
2024-09-13 | Al Shahama-Majlis-P547 | P547 | MJ-02 | 290 | 308 | 598 | 1-Excavation till Rfat Foundation Completed . 2-Pile head trimming on progress . 3-Pile Head Treatment ongoing . 4-Integrity test piles ongoing . 5-Leveling and compaction ongoing. 6. Raft PCC ongoing. 7-Disposal of Excavated Soil ongoing . 8-Gunting works ongoing . 9- Waterproofing ongoing 10- Dynamic test Completed. 11-TRM test ongoing . 12- Retaning wall startar bar on going 13- Raft Steel Activities on going | Substation Relocation. Shoring system from Secant to Continuous. Piles static load test form 8Piles to 5piles . Pile Test from Sonic to TRM . | 47.76% | 38.08% | -9.68% | 4-Superstructure-Majlis | 2025-07-18 |  | 2025-07-18 | 2024-09-19 | Risks1-Lifting Works ( Unsafe Lifting / Rigging ) Lack of 3rd party Inspection/ Riggers/ and the damaged rigging tackles,2-Poor Compliance ( Using of Fall Arrest Equipment at heights) , Scaffold Erection and Dismantling works ,3-Delivery of Long Lead Items ( Chillers & Generator & Air handling Unit ),4-Delays in response regarding to blast steel doors necessary enquiries/tests /reports /simulations,……..compliance with engineer enquiries as stated via Material submission rev. 04 that that required to be attended to avoid delays in manufacturing processing ,5-Contractor anticipation /repeated failed commitments found inaccurate/to be enhanced , and require Contractor action to increase the required resources to achieve anticipated productivity as committed .,6-Potential delay in the delivery of the PVKK valves (due to the geopolitical scene) may reflect /impact the schedule of raft casting.,7-Potential need for increasing the height of the intake shaft (potentially beyond the acceptable limit) in order to allow for the safe handling/lifting od MEP equipment by the telescopic crane Invalid statement , since the Creane that will be provided should comply 100% for the Contract specs &drgs without any modification to the structur of Shaft ,8-Potential delay in casting the raft due to multiple design changes of wall stemming from raft level as invalid stement ,9-Compromising the overall quality to meet the project time lin, like guniting without anti-termite and PCC without compaction/anti-termite. ,10-Incompitent dewatering plans at lower raft area risks the pile rebars to be exposed to salt water which could potentially cause corrosion of rebar and cracks on pile., 11-excess concrete without any compaction might potentially cause work that incomliance with project specs ,12-Loading of heavy machinaries on concrete before 24hrs could lead to potential structural craks,13-Non-availability of QA/QC inspector at night leads to the contractor to proceed with any works without maintaining the quality of the same.,14-AIC raised the concerns of ADDC thzta might will not be able to provide permenant Power supply to the project ,15-Client instruction to providethe required AV system (such as av sytem ) from nominated supplier that should be approved by client that might create time impact negatively against the completion of the required provisional to Shelter &Majles and Consutant reqyested to maintain standby equipment to avoid work stoppage ,16-Delay for the engineering submission especially for MBZ site, such as (shop drawings, method statement) , which reflecting on the coordination shop drawings approval. 17-Light fixture submittal not yet submitted for approval.,18-Regarding to Deliverd of all Chillers in Al Shahama & MBZ The Risk Expected to insert the Chillers inside Basement one backage for each chiller ,19-Regarding to Deliverd of all Generators Sets in Al Shahama & MBZ The Risk Expected to insert the Chillers inside Basement one backage for each chiller ,20-Deviation/obvious delays in time of supply the special equipment by Contractor that will lead to disturbance of work execution time line as well as installation , Testing &commissioning | Mitigation1-Apply the mandatory requirement for Lfting equipment as the contruction sector - OSHAD 34,.0 Safe lifting and lfiting accessories. SF , increase inspection procedure, Implement the control for contractor and subcontractor.,2-Allocate sufficient nos of Fall arrest Equipmet, Training and Awareness,Induction,Moniitoring and apply the Risk Assesment - refer to OSHAD SF no. 23 W& H . Scaffold to undergo with 3rd party Inspection,. Comply the requirements as per the engineered design scaffold. ,3-Contractor is requested to keep follow up with supplier /specialist to enable received the goods on time , and without affecting the planned delevery schedule ,4-After sevral reminderes to the Contarctor , subcontarector advised during last progress meeting that the door specialist attended to provde the neccesary certificates /tests as well , and will be issued to Engineer formally for review , and further acrtion ,5-Contractor is requested to secure all the necessary resources that should meet /cover all remaining SOW after study the productivities rate of each equipment /machines to enable provide the accurate dates of mitigation that should be attended upon enquired by Engineer /client,6-Consultant advised to place the PVKK valves 360 mm above the raft's level and produce at least 500 mm concrete upstand, however the same should be subject to coordination with specialist to avoid any miscoordination .construction errors that will not be able to rectify,7.1- Possibility of using in-situ dismantle/reassemble approach with all MEP equipment. 7.22- Possibility of doing without telescopic cranes altogether and provide middle slot in the intake shaft's cover slab to allow for the lifting of MEP equipment.,8-Contractor to finalize/freeze the upper raft layout in the light of coordination drawings. ,9-Contractor to implement quality toolbox at the beginning of each activity and at regular intervals to enlighten the importance of quality and sequence of activity.- Contractor should treat the invalid work localy to avoid any negative time implication against the overall project complation date ,10-Contractor to propose more efficient way of dewatering with more efficient equipments for operation to avoid availability of water table contact to steel rebair ,11-Contractor should have back-up plans for excess concrete in the mixeres (if any) everyday rather than creating abortive works.,12-Contractor should wait until the required time period for the concrete to achieve the required strength before loading. Area to be closed with precaution tapes to warn others the same. ,13-Contractor to assign ASAP a quality personal at night shift,14-Contractor is requested to liase with ADDC to varify the validy of ADDC wether they can provide th pemennat Power uspply to the project peioe requesting the Client supplort ,15-Contractor should abide to Client instruction ,16-Engineer coordinated with the contractor to Identify and prioritize the most critical SD, MS and method statements that are causing the most significant delays. 17-Engineer Hold daily workshop and bi-weekly progress meetings with the contractor team to monitor the status of submissions and address any bottlenecks immediately.,18&19-The Main contractor Shall be Submit Method Statement for installation Explain the plane to moving and reaching all Chillers & Generators to Correct location over Foundation with protection without any Risk.,,20- Contarctor requested to coordinate with specialist to provide valid /actual date of material delvery to verify the impact of late delevery (if any ) to submit undertaking letter to confirm the delivery schedule of the special equipment and on site . | *Completion of Excavate Soil Till Raft Foundation *Completion of Disposal of Excavated Materials *Completion of Site Cleaning and Preparation *Completion of Pile Head Breaking . *Completion of Raft PCC works . *Completion of Steel Reinforcement for Raft Foundation Fabrication and Delivery . * Completion TRM & Dynamic test *Completion of Pile Integrity Test *Completion the Screed and Raft R.FT *Completion of Raft Steel works . * Start of Starter bar for columns and walls | 85805249.48 | 0 | 85805249.48 | 3799481.4618 |  | 89604730.9418 | 17180863.6 | 1117487.2997 | https://drive.google.com/thumbnail?id=1Zy0KiYSeP-PDs5KIIeeW5fsWj9p4nkja&sz=w1000 | https://drive.google.com/file/d/1Zy0KiYSeP-PDs5KIIeeW5fsWj9p4nkja/view?usp=drive_link | https://drive.google.com/thumbnail?id=1uEFxmPjjwD8Nqb0QvhaTsvG7Fe2EVwdA&sz=w1000 | https://drive.google.com/file/d/1uEFxmPjjwD8Nqb0QvhaTsvG7Fe2EVwdA/view?usp=drive_link | https://drive.google.com/thumbnail?id=18smY9gvWxQDfgihbZYRWZ76-V_fFiVyk&sz=w1000 | https://drive.google.com/file/d/18smY9gvWxQDfgihbZYRWZ76-V_fFiVyk/view?usp=drive_link
2024-09-13 | Al Shahama-Majlis-P547 | P547 | MJ-02 | 290 | 308 | 598 | 1-Excavation till Rfat Foundation Completed . 2-Pile head trimming on progress . 3-Pile Head Treatment ongoing . 4-Integrity test piles ongoing . 5-Leveling and compaction ongoing. 6. Raft PCC ongoing. 7-Disposal of Excavated Soil ongoing . 8-Gunting works ongoing . 9- Waterproofing ongoing 10- Dynamic test Completed. 11-TRM test ongoing . 12- Retaning wall startar bar on going 13- Raft Steel Activities on going | Substation Relocation. Shoring system from Secant to Continuous. Piles static load test form 8Piles to 5piles . Pile Test from Sonic to TRM . | 47.76% | 38.08% | -9.68% | 5- Majlis - Power | 2025-07-23 |  | 2025-07-23 | 2024-09-19 | Risks1-Lifting Works ( Unsafe Lifting / Rigging ) Lack of 3rd party Inspection/ Riggers/ and the damaged rigging tackles,2-Poor Compliance ( Using of Fall Arrest Equipment at heights) , Scaffold Erection and Dismantling works ,3-Delivery of Long Lead Items ( Chillers & Generator & Air handling Unit ),4-Delays in response regarding to blast steel doors necessary enquiries/tests /reports /simulations,……..compliance with engineer enquiries as stated via Material submission rev. 04 that that required to be attended to avoid delays in manufacturing processing ,5-Contractor anticipation /repeated failed commitments found inaccurate/to be enhanced , and require Contractor action to increase the required resources to achieve anticipated productivity as committed .,6-Potential delay in the delivery of the PVKK valves (due to the geopolitical scene) may reflect /impact the schedule of raft casting.,7-Potential need for increasing the height of the intake shaft (potentially beyond the acceptable limit) in order to allow for the safe handling/lifting od MEP equipment by the telescopic crane Invalid statement , since the Creane that will be provided should comply 100% for the Contract specs &drgs without any modification to the structur of Shaft ,8-Potential delay in casting the raft due to multiple design changes of wall stemming from raft level as invalid stement ,9-Compromising the overall quality to meet the project time lin, like guniting without anti-termite and PCC without compaction/anti-termite. ,10-Incompitent dewatering plans at lower raft area risks the pile rebars to be exposed to salt water which could potentially cause corrosion of rebar and cracks on pile., 11-excess concrete without any compaction might potentially cause work that incomliance with project specs ,12-Loading of heavy machinaries on concrete before 24hrs could lead to potential structural craks,13-Non-availability of QA/QC inspector at night leads to the contractor to proceed with any works without maintaining the quality of the same.,14-AIC raised the concerns of ADDC thzta might will not be able to provide permenant Power supply to the project ,15-Client instruction to providethe required AV system (such as av sytem ) from nominated supplier that should be approved by client that might create time impact negatively against the completion of the required provisional to Shelter &Majles and Consutant reqyested to maintain standby equipment to avoid work stoppage ,16-Delay for the engineering submission especially for MBZ site, such as (shop drawings, method statement) , which reflecting on the coordination shop drawings approval. 17-Light fixture submittal not yet submitted for approval.,18-Regarding to Deliverd of all Chillers in Al Shahama & MBZ The Risk Expected to insert the Chillers inside Basement one backage for each chiller ,19-Regarding to Deliverd of all Generators Sets in Al Shahama & MBZ The Risk Expected to insert the Chillers inside Basement one backage for each chiller ,20-Deviation/obvious delays in time of supply the special equipment by Contractor that will lead to disturbance of work execution time line as well as installation , Testing &commissioning | Mitigation1-Apply the mandatory requirement for Lfting equipment as the contruction sector - OSHAD 34,.0 Safe lifting and lfiting accessories. SF , increase inspection procedure, Implement the control for contractor and subcontractor.,2-Allocate sufficient nos of Fall arrest Equipmet, Training and Awareness,Induction,Moniitoring and apply the Risk Assesment - refer to OSHAD SF no. 23 W& H . Scaffold to undergo with 3rd party Inspection,. Comply the requirements as per the engineered design scaffold. ,3-Contractor is requested to keep follow up with supplier /specialist to enable received the goods on time , and without affecting the planned delevery schedule ,4-After sevral reminderes to the Contarctor , subcontarector advised during last progress meeting that the door specialist attended to provde the neccesary certificates /tests as well , and will be issued to Engineer formally for review , and further acrtion ,5-Contractor is requested to secure all the necessary resources that should meet /cover all remaining SOW after study the productivities rate of each equipment /machines to enable provide the accurate dates of mitigation that should be attended upon enquired by Engineer /client,6-Consultant advised to place the PVKK valves 360 mm above the raft's level and produce at least 500 mm concrete upstand, however the same should be subject to coordination with specialist to avoid any miscoordination .construction errors that will not be able to rectify,7.1- Possibility of using in-situ dismantle/reassemble approach with all MEP equipment. 7.22- Possibility of doing without telescopic cranes altogether and provide middle slot in the intake shaft's cover slab to allow for the lifting of MEP equipment.,8-Contractor to finalize/freeze the upper raft layout in the light of coordination drawings. ,9-Contractor to implement quality toolbox at the beginning of each activity and at regular intervals to enlighten the importance of quality and sequence of activity.- Contractor should treat the invalid work localy to avoid any negative time implication against the overall project complation date ,10-Contractor to propose more efficient way of dewatering with more efficient equipments for operation to avoid availability of water table contact to steel rebair ,11-Contractor should have back-up plans for excess concrete in the mixeres (if any) everyday rather than creating abortive works.,12-Contractor should wait until the required time period for the concrete to achieve the required strength before loading. Area to be closed with precaution tapes to warn others the same. ,13-Contractor to assign ASAP a quality personal at night shift,14-Contractor is requested to liase with ADDC to varify the validy of ADDC wether they can provide th pemennat Power uspply to the project peioe requesting the Client supplort ,15-Contractor should abide to Client instruction ,16-Engineer coordinated with the contractor to Identify and prioritize the most critical SD, MS and method statements that are causing the most significant delays. 17-Engineer Hold daily workshop and bi-weekly progress meetings with the contractor team to monitor the status of submissions and address any bottlenecks immediately.,18&19-The Main contractor Shall be Submit Method Statement for installation Explain the plane to moving and reaching all Chillers & Generators to Correct location over Foundation with protection without any Risk.,,20- Contarctor requested to coordinate with specialist to provide valid /actual date of material delvery to verify the impact of late delevery (if any ) to submit undertaking letter to confirm the delivery schedule of the special equipment and on site . | *Completion of Excavate Soil Till Raft Foundation *Completion of Disposal of Excavated Materials *Completion of Site Cleaning and Preparation *Completion of Pile Head Breaking . *Completion of Raft PCC works . *Completion of Steel Reinforcement for Raft Foundation Fabrication and Delivery . * Completion TRM & Dynamic test *Completion of Pile Integrity Test *Completion the Screed and Raft R.FT *Completion of Raft Steel works . * Start of Starter bar for columns and walls | 85805249.48 | 0 | 85805249.48 | 3799481.4618 |  | 89604730.9418 | 17180863.6 | 1117487.2997 | https://drive.google.com/thumbnail?id=1Zy0KiYSeP-PDs5KIIeeW5fsWj9p4nkja&sz=w1000 | https://drive.google.com/file/d/1Zy0KiYSeP-PDs5KIIeeW5fsWj9p4nkja/view?usp=drive_link | https://drive.google.com/thumbnail?id=1uEFxmPjjwD8Nqb0QvhaTsvG7Fe2EVwdA&sz=w1000 | https://drive.google.com/file/d/1uEFxmPjjwD8Nqb0QvhaTsvG7Fe2EVwdA/view?usp=drive_link | https://drive.google.com/thumbnail?id=18smY9gvWxQDfgihbZYRWZ76-V_fFiVyk&sz=w1000 | https://drive.google.com/file/d/18smY9gvWxQDfgihbZYRWZ76-V_fFiVyk/view?usp=drive_link
2024-09-13 | Al Shahama-Majlis-P547 | P547 | MJ-02 | 290 | 308 | 598 | 1-Excavation till Rfat Foundation Completed . 2-Pile head trimming on progress . 3-Pile Head Treatment ongoing . 4-Integrity test piles ongoing . 5-Leveling and compaction ongoing. 6. Raft PCC ongoing. 7-Disposal of Excavated Soil ongoing . 8-Gunting works ongoing . 9- Waterproofing ongoing 10- Dynamic test Completed. 11-TRM test ongoing . 12- Retaning wall startar bar on going 13- Raft Steel Activities on going | Substation Relocation. Shoring system from Secant to Continuous. Piles static load test form 8Piles to 5piles . Pile Test from Sonic to TRM . | 47.76% | 38.08% | -9.68% | 6- Project Finsh date ( Contractual Milestone ) | 2025-07-24 |  | 2025-07-24 | 2024-09-19 | Risks1-Lifting Works ( Unsafe Lifting / Rigging ) Lack of 3rd party Inspection/ Riggers/ and the damaged rigging tackles,2-Poor Compliance ( Using of Fall Arrest Equipment at heights) , Scaffold Erection and Dismantling works ,3-Delivery of Long Lead Items ( Chillers & Generator & Air handling Unit ),4-Delays in response regarding to blast steel doors necessary enquiries/tests /reports /simulations,……..compliance with engineer enquiries as stated via Material submission rev. 04 that that required to be attended to avoid delays in manufacturing processing ,5-Contractor anticipation /repeated failed commitments found inaccurate/to be enhanced , and require Contractor action to increase the required resources to achieve anticipated productivity as committed .,6-Potential delay in the delivery of the PVKK valves (due to the geopolitical scene) may reflect /impact the schedule of raft casting.,7-Potential need for increasing the height of the intake shaft (potentially beyond the acceptable limit) in order to allow for the safe handling/lifting od MEP equipment by the telescopic crane Invalid statement , since the Creane that will be provided should comply 100% for the Contract specs &drgs without any modification to the structur of Shaft ,8-Potential delay in casting the raft due to multiple design changes of wall stemming from raft level as invalid stement ,9-Compromising the overall quality to meet the project time lin, like guniting without anti-termite and PCC without compaction/anti-termite. ,10-Incompitent dewatering plans at lower raft area risks the pile rebars to be exposed to salt water which could potentially cause corrosion of rebar and cracks on pile., 11-excess concrete without any compaction might potentially cause work that incomliance with project specs ,12-Loading of heavy machinaries on concrete before 24hrs could lead to potential structural craks,13-Non-availability of QA/QC inspector at night leads to the contractor to proceed with any works without maintaining the quality of the same.,14-AIC raised the concerns of ADDC thzta might will not be able to provide permenant Power supply to the project ,15-Client instruction to providethe required AV system (such as av sytem ) from nominated supplier that should be approved by client that might create time impact negatively against the completion of the required provisional to Shelter &Majles and Consutant reqyested to maintain standby equipment to avoid work stoppage ,16-Delay for the engineering submission especially for MBZ site, such as (shop drawings, method statement) , which reflecting on the coordination shop drawings approval. 17-Light fixture submittal not yet submitted for approval.,18-Regarding to Deliverd of all Chillers in Al Shahama & MBZ The Risk Expected to insert the Chillers inside Basement one backage for each chiller ,19-Regarding to Deliverd of all Generators Sets in Al Shahama & MBZ The Risk Expected to insert the Chillers inside Basement one backage for each chiller ,20-Deviation/obvious delays in time of supply the special equipment by Contractor that will lead to disturbance of work execution time line as well as installation , Testing &commissioning | Mitigation1-Apply the mandatory requirement for Lfting equipment as the contruction sector - OSHAD 34,.0 Safe lifting and lfiting accessories. SF , increase inspection procedure, Implement the control for contractor and subcontractor.,2-Allocate sufficient nos of Fall arrest Equipmet, Training and Awareness,Induction,Moniitoring and apply the Risk Assesment - refer to OSHAD SF no. 23 W& H . Scaffold to undergo with 3rd party Inspection,. Comply the requirements as per the engineered design scaffold. ,3-Contractor is requested to keep follow up with supplier /specialist to enable received the goods on time , and without affecting the planned delevery schedule ,4-After sevral reminderes to the Contarctor , subcontarector advised during last progress meeting that the door specialist attended to provde the neccesary certificates /tests as well , and will be issued to Engineer formally for review , and further acrtion ,5-Contractor is requested to secure all the necessary resources that should meet /cover all remaining SOW after study the productivities rate of each equipment /machines to enable provide the accurate dates of mitigation that should be attended upon enquired by Engineer /client,6-Consultant advised to place the PVKK valves 360 mm above the raft's level and produce at least 500 mm concrete upstand, however the same should be subject to coordination with specialist to avoid any miscoordination .construction errors that will not be able to rectify,7.1- Possibility of using in-situ dismantle/reassemble approach with all MEP equipment. 7.22- Possibility of doing without telescopic cranes altogether and provide middle slot in the intake shaft's cover slab to allow for the lifting of MEP equipment.,8-Contractor to finalize/freeze the upper raft layout in the light of coordination drawings. ,9-Contractor to implement quality toolbox at the beginning of each activity and at regular intervals to enlighten the importance of quality and sequence of activity.- Contractor should treat the invalid work localy to avoid any negative time implication against the overall project complation date ,10-Contractor to propose more efficient way of dewatering with more efficient equipments for operation to avoid availability of water table contact to steel rebair ,11-Contractor should have back-up plans for excess concrete in the mixeres (if any) everyday rather than creating abortive works.,12-Contractor should wait until the required time period for the concrete to achieve the required strength before loading. Area to be closed with precaution tapes to warn others the same. ,13-Contractor to assign ASAP a quality personal at night shift,14-Contractor is requested to liase with ADDC to varify the validy of ADDC wether they can provide th pemennat Power uspply to the project peioe requesting the Client supplort ,15-Contractor should abide to Client instruction ,16-Engineer coordinated with the contractor to Identify and prioritize the most critical SD, MS and method statements that are causing the most significant delays. 17-Engineer Hold daily workshop and bi-weekly progress meetings with the contractor team to monitor the status of submissions and address any bottlenecks immediately.,18&19-The Main contractor Shall be Submit Method Statement for installation Explain the plane to moving and reaching all Chillers & Generators to Correct location over Foundation with protection without any Risk.,,20- Contarctor requested to coordinate with specialist to provide valid /actual date of material delvery to verify the impact of late delevery (if any ) to submit undertaking letter to confirm the delivery schedule of the special equipment and on site . | *Completion of Excavate Soil Till Raft Foundation *Completion of Disposal of Excavated Materials *Completion of Site Cleaning and Preparation *Completion of Pile Head Breaking . *Completion of Raft PCC works . *Completion of Steel Reinforcement for Raft Foundation Fabrication and Delivery . * Completion TRM & Dynamic test *Completion of Pile Integrity Test *Completion the Screed and Raft R.FT *Completion of Raft Steel works . * Start of Starter bar for columns and walls | 85805249.48 | 0 | 85805249.48 | 3799481.4618 |  | 89604730.9418 | 17180863.6 | 1117487.2997 | https://drive.google.com/thumbnail?id=1Zy0KiYSeP-PDs5KIIeeW5fsWj9p4nkja&sz=w1000 | https://drive.google.com/file/d/1Zy0KiYSeP-PDs5KIIeeW5fsWj9p4nkja/view?usp=drive_link | https://drive.google.com/thumbnail?id=1uEFxmPjjwD8Nqb0QvhaTsvG7Fe2EVwdA&sz=w1000 | https://drive.google.com/file/d/1uEFxmPjjwD8Nqb0QvhaTsvG7Fe2EVwdA/view?usp=drive_link | https://drive.google.com/thumbnail?id=18smY9gvWxQDfgihbZYRWZ76-V_fFiVyk&sz=w1000 | https://drive.google.com/file/d/18smY9gvWxQDfgihbZYRWZ76-V_fFiVyk/view?usp=drive_link
2024-09-13 | Mohamed Bin Zayed City -Majlis-P19 | P19 | MJ-03 | 290 | 308 | 598 | *Piles Shoring Completed *Breaking of Shoring Head piles ongoing. *Breaking of Guide wall on going . *Excavation for Capping Beams *Casted of Main Piles on going *Dewatering Installation ongoing *Relocation Services ongoing. | As the recommendation from project's Engineer, Engineer have identified the need for an additional construction team by the contractor . | 47.79% | 26.86% | -20.93% | 1-Notice to Commence ( Contractual Milestone ) | 2023-12-05 | 2023-12-05 |  | 2024-09-19 | 1-Lifting Works ( Unsafe Lifting / Rigging ) Lack of 3rd party Inspection/ Riggers/ and the damaged rigging tackles,2-Inadequate Handling and Storage of Compress Gases,Risk- Const. ,3-Delay in work commencement of MBZ project due to delays in response from Contractor end regarding to NOC’s / Utility Relocation, in addition to delays in issuance of Updated affection plan .,,5-Delay in issuance of NOCs for MCC, Strom Water ,and Etisalat,6-The project will require night shift operations. This time compansation is essential to meet project deadlines,7-Contractor continuation of given invalid anticipation foe the conpletion of piling work to enable work night shift (24 days ) is still not applicable at this site due to the nature of the required activities that will not be allowed at such sensitive area , and Contractor should increase the resources to enable compensate the above mentioned restriction .,9-Piling work Subcontractor continuance equipment breakdown due to utilization of bad condition equipment ,10-Potential need for increasing the height of the intake shaft (potentially beyond the acceptable limit) in order to allow for the safe handling/liftg MEP equipment by the telescopic crane Not applicable so far since the contractor willing to supply TELESCOPIC CRAIN inaccrodance withg project specs ,11-Dewatering system not operated with full effiviency that will impact further work execution (capping beem & Excavation).,12-Potential high level of ingress of ground water flow during execution of work/ excavation,13-Compromising the overall quality to meet the project time lin, like guniting without anti-termite and PCC without compaction/anti-termite.,14-Improper backfilling near dead shutter of the lower raft with excess concrete without any compaction might potentially cause settlements ,15-Non-availability of Contractor QA/QC at night can leads to proceed with any non-compliance works .,15-Non-availability of Contractor QA/QC at night can leads to proceed with any non-compliance works .,16-Non-availability of Contractor QA/QC at night can leads to proceed with any non-compliance works .,17-AIC raised the concerns of ADDC might will not be able to provide permenant Power supply to the project ,18-Client instruction to providethe required AV system (such as av sytem ) from nominated supplier that should be approved by client that might create time impact negatively against the completion of the required provisional to Shelter &Majles and Consutant reqyested to maintain standby equipment to avoid work stoppage ,19-Delays in long lead items finalization of material procurment (such as light fixtures ,…,20-Chillers material delevery to Al Shahama & MBZ The Risk Expected to place the goods at Basement ,21-Generators procurment & placing the goods in basement & coordination with Crane specialist to avoid improper placement of the goods , as well as will affect negatively the methodoligy of O&M regarding to repair /replace the deffected partds (when required . ,22-Deviation/obvious delays in time of supply the special equipment by Contractor that will lead to disturbance of work execution time line as well as installation , Testing &commissioning | 1-Apply the mandatory requirement for Lfting equipment as the contruction sector - OSHAD 34,.0 Safe lifting and lfiting accessories. SF , increase inspection procedure, Implement the control for contractor and subcontractor.,2-Apply the COSHH assesment, Allocate resources for Compress gases requirements , Implement the Risk Assesment ,,3-Required Noc,s already obtained , and Contractor corrective action is required to allocat additiona l resources to overcome /compansate the occurred delays ,,5-Storm water removed from site plan patameter properties , and other services already relocated /removed ,6-Due to the natur of the MBZ Area noght shify is not possible , hoever Contractor can compansate the same by allocating additiona lresources /equipment ,7-Contyractor notified by the same , and instructed to focaus to provide valid timeline based on the required resources to expedite the progress , and meet project target plan ,9-Contractor conduct several meetings with Piling subcontractor to secure /replace all existing equipment that are in bad condirion to be replaced by other equipment that can continue piing work without stoppage that cirrently continuance breakdown /in bad condition ,10.1- Possibility of using in-situ dismantle/reassemble approach with all MEP equipment. 10.22- Possibility of doing without telescopic cranes altogether and provide middle slot in the intake shaft's cover slab to allow for the lifting of MEP equipment.,11-The engineer shall instruct the contractor to explore the possibility of starting capping beams construction without the need for activating internal dewatering system by exploring the use of external well point dewatering system for dewatering at such shallow level. ,12-Engineer instructed the contractor to provide a valid working plan to adress such possibility including submission of repair and injection materials and method statements, to be ready for utilization (when required) ,13-Contractor to implement quality improvement toolbox at the beginning of each activity and at regular intervals to enlighten the importance of quality and sequence of activity.,14-Contractor should have back-up plans for utilizing excess concrete (whenever required ) rather than creating abortive works by casting conce. At un resdy area (nor compacted /not spreayed by anti termite ,15 &16-Contractor to assign a quality personal at night shift,15 &16-Contractor to assign a quality personal at night shift,,17-Contractor is requested to liase with ADDC to varify the validy of ADDC wether they can provide th pemennat Power uspply to the project peioe requesting the Client supplort ,18-Contractor should abide to Client instruction ,19-Contrator is requested to update the procurment control log to anble identify the missing items that still not considered /not planned for matrial submission m and approval prior procurment ., 20&21-Main contractor is requested to Submit Method Statement of installation to verify the circulation plane of movement, to ensure O&M proper accessibility to all equipment .,, 22-Contarctor requested to coordinate with specialist to provide valid /actual date of material delvery to verify the impact of late delevery (if any ) to submit undertaking letter to confirm the delivery schedule of the special equipment and on site . | Relocation Services. -Complete the Main Piles. -Complete the Guide wall and shoring pile head breaking. -Start of Capping Beams and Struts activities | 78195477.46 | 0 | 78195477.46 | 3462518.5382 |  | 81657995.9982 | 4774958.11 | 1018381.2003 | https://drive.google.com/thumbnail?id=1YilrYlrEBR5j4gXQtSjyi1aNfDAiAnEu&sz=w1000 | https://drive.google.com/file/d/1YilrYlrEBR5j4gXQtSjyi1aNfDAiAnEu/view?usp=drive_link | https://drive.google.com/thumbnail?id=1nRiloij6wjknh-vdXufPMtF9ywgwSqpI&sz=w1000 | https://drive.google.com/file/d/1nRiloij6wjknh-vdXufPMtF9ywgwSqpI/view?usp=drive_link | https://drive.google.com/thumbnail?id=1DZ00kl6N0YvT2ZAXdhcx9VQ5hnPKYmSP&sz=w1000 | https://drive.google.com/file/d/1DZ00kl6N0YvT2ZAXdhcx9VQ5hnPKYmSP/view?usp=drive_link
2024-09-13 | Mohamed Bin Zayed City -Majlis-P19 | P19 | MJ-03 | 290 | 308 | 598 | *Piles Shoring Completed *Breaking of Shoring Head piles ongoing. *Breaking of Guide wall on going . *Excavation for Capping Beams *Casted of Main Piles on going *Dewatering Installation ongoing *Relocation Services ongoing. | As the recommendation from project's Engineer, Engineer have identified the need for an additional construction team by the contractor . | 47.79% | 26.86% | -20.93% | 2- Complation Mainpiles (next Monitiring Milestone) | 2024-07-30 |  | 2024-09-20 | 2024-09-19 | 1-Lifting Works ( Unsafe Lifting / Rigging ) Lack of 3rd party Inspection/ Riggers/ and the damaged rigging tackles,2-Inadequate Handling and Storage of Compress Gases,Risk- Const. ,3-Delay in work commencement of MBZ project due to delays in response from Contractor end regarding to NOC’s / Utility Relocation, in addition to delays in issuance of Updated affection plan .,,5-Delay in issuance of NOCs for MCC, Strom Water ,and Etisalat,6-The project will require night shift operations. This time compansation is essential to meet project deadlines,7-Contractor continuation of given invalid anticipation foe the conpletion of piling work to enable work night shift (24 days ) is still not applicable at this site due to the nature of the required activities that will not be allowed at such sensitive area , and Contractor should increase the resources to enable compensate the above mentioned restriction .,9-Piling work Subcontractor continuance equipment breakdown due to utilization of bad condition equipment ,10-Potential need for increasing the height of the intake shaft (potentially beyond the acceptable limit) in order to allow for the safe handling/liftg MEP equipment by the telescopic crane Not applicable so far since the contractor willing to supply TELESCOPIC CRAIN inaccrodance withg project specs ,11-Dewatering system not operated with full effiviency that will impact further work execution (capping beem & Excavation).,12-Potential high level of ingress of ground water flow during execution of work/ excavation,13-Compromising the overall quality to meet the project time lin, like guniting without anti-termite and PCC without compaction/anti-termite.,14-Improper backfilling near dead shutter of the lower raft with excess concrete without any compaction might potentially cause settlements ,15-Non-availability of Contractor QA/QC at night can leads to proceed with any non-compliance works .,15-Non-availability of Contractor QA/QC at night can leads to proceed with any non-compliance works .,16-Non-availability of Contractor QA/QC at night can leads to proceed with any non-compliance works .,17-AIC raised the concerns of ADDC might will not be able to provide permenant Power supply to the project ,18-Client instruction to providethe required AV system (such as av sytem ) from nominated supplier that should be approved by client that might create time impact negatively against the completion of the required provisional to Shelter &Majles and Consutant reqyested to maintain standby equipment to avoid work stoppage ,19-Delays in long lead items finalization of material procurment (such as light fixtures ,…,20-Chillers material delevery to Al Shahama & MBZ The Risk Expected to place the goods at Basement ,21-Generators procurment & placing the goods in basement & coordination with Crane specialist to avoid improper placement of the goods , as well as will affect negatively the methodoligy of O&M regarding to repair /replace the deffected partds (when required . ,22-Deviation/obvious delays in time of supply the special equipment by Contractor that will lead to disturbance of work execution time line as well as installation , Testing &commissioning | 1-Apply the mandatory requirement for Lfting equipment as the contruction sector - OSHAD 34,.0 Safe lifting and lfiting accessories. SF , increase inspection procedure, Implement the control for contractor and subcontractor.,2-Apply the COSHH assesment, Allocate resources for Compress gases requirements , Implement the Risk Assesment ,,3-Required Noc,s already obtained , and Contractor corrective action is required to allocat additiona l resources to overcome /compansate the occurred delays ,,5-Storm water removed from site plan patameter properties , and other services already relocated /removed ,6-Due to the natur of the MBZ Area noght shify is not possible , hoever Contractor can compansate the same by allocating additiona lresources /equipment ,7-Contyractor notified by the same , and instructed to focaus to provide valid timeline based on the required resources to expedite the progress , and meet project target plan ,9-Contractor conduct several meetings with Piling subcontractor to secure /replace all existing equipment that are in bad condirion to be replaced by other equipment that can continue piing work without stoppage that cirrently continuance breakdown /in bad condition ,10.1- Possibility of using in-situ dismantle/reassemble approach with all MEP equipment. 10.22- Possibility of doing without telescopic cranes altogether and provide middle slot in the intake shaft's cover slab to allow for the lifting of MEP equipment.,11-The engineer shall instruct the contractor to explore the possibility of starting capping beams construction without the need for activating internal dewatering system by exploring the use of external well point dewatering system for dewatering at such shallow level. ,12-Engineer instructed the contractor to provide a valid working plan to adress such possibility including submission of repair and injection materials and method statements, to be ready for utilization (when required) ,13-Contractor to implement quality improvement toolbox at the beginning of each activity and at regular intervals to enlighten the importance of quality and sequence of activity.,14-Contractor should have back-up plans for utilizing excess concrete (whenever required ) rather than creating abortive works by casting conce. At un resdy area (nor compacted /not spreayed by anti termite ,15 &16-Contractor to assign a quality personal at night shift,15 &16-Contractor to assign a quality personal at night shift,,17-Contractor is requested to liase with ADDC to varify the validy of ADDC wether they can provide th pemennat Power uspply to the project peioe requesting the Client supplort ,18-Contractor should abide to Client instruction ,19-Contrator is requested to update the procurment control log to anble identify the missing items that still not considered /not planned for matrial submission m and approval prior procurment ., 20&21-Main contractor is requested to Submit Method Statement of installation to verify the circulation plane of movement, to ensure O&M proper accessibility to all equipment .,, 22-Contarctor requested to coordinate with specialist to provide valid /actual date of material delvery to verify the impact of late delevery (if any ) to submit undertaking letter to confirm the delivery schedule of the special equipment and on site . | Relocation Services. -Complete the Main Piles. -Complete the Guide wall and shoring pile head breaking. -Start of Capping Beams and Struts activities | 78195477.46 | 0 | 78195477.46 | 3462518.5382 |  | 81657995.9982 | 4774958.11 | 1018381.2003 | https://drive.google.com/thumbnail?id=1YilrYlrEBR5j4gXQtSjyi1aNfDAiAnEu&sz=w1000 | https://drive.google.com/file/d/1YilrYlrEBR5j4gXQtSjyi1aNfDAiAnEu/view?usp=drive_link | https://drive.google.com/thumbnail?id=1nRiloij6wjknh-vdXufPMtF9ywgwSqpI&sz=w1000 | https://drive.google.com/file/d/1nRiloij6wjknh-vdXufPMtF9ywgwSqpI/view?usp=drive_link | https://drive.google.com/thumbnail?id=1DZ00kl6N0YvT2ZAXdhcx9VQ5hnPKYmSP&sz=w1000 | https://drive.google.com/file/d/1DZ00kl6N0YvT2ZAXdhcx9VQ5hnPKYmSP/view?usp=drive_link
2024-09-13 | Mohamed Bin Zayed City -Majlis-P19 | P19 | MJ-03 | 290 | 308 | 598 | *Piles Shoring Completed *Breaking of Shoring Head piles ongoing. *Breaking of Guide wall on going . *Excavation for Capping Beams *Casted of Main Piles on going *Dewatering Installation ongoing *Relocation Services ongoing. | As the recommendation from project's Engineer, Engineer have identified the need for an additional construction team by the contractor . | 47.79% | 26.86% | -20.93% | 3-Superstructure-Basment | 2025-07-19 |  | 2025-10-20 | 2024-09-19 | 1-Lifting Works ( Unsafe Lifting / Rigging ) Lack of 3rd party Inspection/ Riggers/ and the damaged rigging tackles,2-Inadequate Handling and Storage of Compress Gases,Risk- Const. ,3-Delay in work commencement of MBZ project due to delays in response from Contractor end regarding to NOC’s / Utility Relocation, in addition to delays in issuance of Updated affection plan .,,5-Delay in issuance of NOCs for MCC, Strom Water ,and Etisalat,6-The project will require night shift operations. This time compansation is essential to meet project deadlines,7-Contractor continuation of given invalid anticipation foe the conpletion of piling work to enable work night shift (24 days ) is still not applicable at this site due to the nature of the required activities that will not be allowed at such sensitive area , and Contractor should increase the resources to enable compensate the above mentioned restriction .,9-Piling work Subcontractor continuance equipment breakdown due to utilization of bad condition equipment ,10-Potential need for increasing the height of the intake shaft (potentially beyond the acceptable limit) in order to allow for the safe handling/liftg MEP equipment by the telescopic crane Not applicable so far since the contractor willing to supply TELESCOPIC CRAIN inaccrodance withg project specs ,11-Dewatering system not operated with full effiviency that will impact further work execution (capping beem & Excavation).,12-Potential high level of ingress of ground water flow during execution of work/ excavation,13-Compromising the overall quality to meet the project time lin, like guniting without anti-termite and PCC without compaction/anti-termite.,14-Improper backfilling near dead shutter of the lower raft with excess concrete without any compaction might potentially cause settlements ,15-Non-availability of Contractor QA/QC at night can leads to proceed with any non-compliance works .,15-Non-availability of Contractor QA/QC at night can leads to proceed with any non-compliance works .,16-Non-availability of Contractor QA/QC at night can leads to proceed with any non-compliance works .,17-AIC raised the concerns of ADDC might will not be able to provide permenant Power supply to the project ,18-Client instruction to providethe required AV system (such as av sytem ) from nominated supplier that should be approved by client that might create time impact negatively against the completion of the required provisional to Shelter &Majles and Consutant reqyested to maintain standby equipment to avoid work stoppage ,19-Delays in long lead items finalization of material procurment (such as light fixtures ,…,20-Chillers material delevery to Al Shahama & MBZ The Risk Expected to place the goods at Basement ,21-Generators procurment & placing the goods in basement & coordination with Crane specialist to avoid improper placement of the goods , as well as will affect negatively the methodoligy of O&M regarding to repair /replace the deffected partds (when required . ,22-Deviation/obvious delays in time of supply the special equipment by Contractor that will lead to disturbance of work execution time line as well as installation , Testing &commissioning | 1-Apply the mandatory requirement for Lfting equipment as the contruction sector - OSHAD 34,.0 Safe lifting and lfiting accessories. SF , increase inspection procedure, Implement the control for contractor and subcontractor.,2-Apply the COSHH assesment, Allocate resources for Compress gases requirements , Implement the Risk Assesment ,,3-Required Noc,s already obtained , and Contractor corrective action is required to allocat additiona l resources to overcome /compansate the occurred delays ,,5-Storm water removed from site plan patameter properties , and other services already relocated /removed ,6-Due to the natur of the MBZ Area noght shify is not possible , hoever Contractor can compansate the same by allocating additiona lresources /equipment ,7-Contyractor notified by the same , and instructed to focaus to provide valid timeline based on the required resources to expedite the progress , and meet project target plan ,9-Contractor conduct several meetings with Piling subcontractor to secure /replace all existing equipment that are in bad condirion to be replaced by other equipment that can continue piing work without stoppage that cirrently continuance breakdown /in bad condition ,10.1- Possibility of using in-situ dismantle/reassemble approach with all MEP equipment. 10.22- Possibility of doing without telescopic cranes altogether and provide middle slot in the intake shaft's cover slab to allow for the lifting of MEP equipment.,11-The engineer shall instruct the contractor to explore the possibility of starting capping beams construction without the need for activating internal dewatering system by exploring the use of external well point dewatering system for dewatering at such shallow level. ,12-Engineer instructed the contractor to provide a valid working plan to adress such possibility including submission of repair and injection materials and method statements, to be ready for utilization (when required) ,13-Contractor to implement quality improvement toolbox at the beginning of each activity and at regular intervals to enlighten the importance of quality and sequence of activity.,14-Contractor should have back-up plans for utilizing excess concrete (whenever required ) rather than creating abortive works by casting conce. At un resdy area (nor compacted /not spreayed by anti termite ,15 &16-Contractor to assign a quality personal at night shift,15 &16-Contractor to assign a quality personal at night shift,,17-Contractor is requested to liase with ADDC to varify the validy of ADDC wether they can provide th pemennat Power uspply to the project peioe requesting the Client supplort ,18-Contractor should abide to Client instruction ,19-Contrator is requested to update the procurment control log to anble identify the missing items that still not considered /not planned for matrial submission m and approval prior procurment ., 20&21-Main contractor is requested to Submit Method Statement of installation to verify the circulation plane of movement, to ensure O&M proper accessibility to all equipment .,, 22-Contarctor requested to coordinate with specialist to provide valid /actual date of material delvery to verify the impact of late delevery (if any ) to submit undertaking letter to confirm the delivery schedule of the special equipment and on site . | Relocation Services. -Complete the Main Piles. -Complete the Guide wall and shoring pile head breaking. -Start of Capping Beams and Struts activities | 78195477.46 | 0 | 78195477.46 | 3462518.5382 |  | 81657995.9982 | 4774958.11 | 1018381.2003 | https://drive.google.com/thumbnail?id=1YilrYlrEBR5j4gXQtSjyi1aNfDAiAnEu&sz=w1000 | https://drive.google.com/file/d/1YilrYlrEBR5j4gXQtSjyi1aNfDAiAnEu/view?usp=drive_link | https://drive.google.com/thumbnail?id=1nRiloij6wjknh-vdXufPMtF9ywgwSqpI&sz=w1000 | https://drive.google.com/file/d/1nRiloij6wjknh-vdXufPMtF9ywgwSqpI/view?usp=drive_link | https://drive.google.com/thumbnail?id=1DZ00kl6N0YvT2ZAXdhcx9VQ5hnPKYmSP&sz=w1000 | https://drive.google.com/file/d/1DZ00kl6N0YvT2ZAXdhcx9VQ5hnPKYmSP/view?usp=drive_link
2024-09-13 | Mohamed Bin Zayed City -Majlis-P19 | P19 | MJ-03 | 290 | 308 | 598 | *Piles Shoring Completed *Breaking of Shoring Head piles ongoing. *Breaking of Guide wall on going . *Excavation for Capping Beams *Casted of Main Piles on going *Dewatering Installation ongoing *Relocation Services ongoing. | As the recommendation from project's Engineer, Engineer have identified the need for an additional construction team by the contractor . | 47.79% | 26.86% | -20.93% | 2-Superstructure-Majlis | 2025-07-24 |  | 2025-08-30 | 2024-09-19 | 1-Lifting Works ( Unsafe Lifting / Rigging ) Lack of 3rd party Inspection/ Riggers/ and the damaged rigging tackles,2-Inadequate Handling and Storage of Compress Gases,Risk- Const. ,3-Delay in work commencement of MBZ project due to delays in response from Contractor end regarding to NOC’s / Utility Relocation, in addition to delays in issuance of Updated affection plan .,,5-Delay in issuance of NOCs for MCC, Strom Water ,and Etisalat,6-The project will require night shift operations. This time compansation is essential to meet project deadlines,7-Contractor continuation of given invalid anticipation foe the conpletion of piling work to enable work night shift (24 days ) is still not applicable at this site due to the nature of the required activities that will not be allowed at such sensitive area , and Contractor should increase the resources to enable compensate the above mentioned restriction .,9-Piling work Subcontractor continuance equipment breakdown due to utilization of bad condition equipment ,10-Potential need for increasing the height of the intake shaft (potentially beyond the acceptable limit) in order to allow for the safe handling/liftg MEP equipment by the telescopic crane Not applicable so far since the contractor willing to supply TELESCOPIC CRAIN inaccrodance withg project specs ,11-Dewatering system not operated with full effiviency that will impact further work execution (capping beem & Excavation).,12-Potential high level of ingress of ground water flow during execution of work/ excavation,13-Compromising the overall quality to meet the project time lin, like guniting without anti-termite and PCC without compaction/anti-termite.,14-Improper backfilling near dead shutter of the lower raft with excess concrete without any compaction might potentially cause settlements ,15-Non-availability of Contractor QA/QC at night can leads to proceed with any non-compliance works .,15-Non-availability of Contractor QA/QC at night can leads to proceed with any non-compliance works .,16-Non-availability of Contractor QA/QC at night can leads to proceed with any non-compliance works .,17-AIC raised the concerns of ADDC might will not be able to provide permenant Power supply to the project ,18-Client instruction to providethe required AV system (such as av sytem ) from nominated supplier that should be approved by client that might create time impact negatively against the completion of the required provisional to Shelter &Majles and Consutant reqyested to maintain standby equipment to avoid work stoppage ,19-Delays in long lead items finalization of material procurment (such as light fixtures ,…,20-Chillers material delevery to Al Shahama & MBZ The Risk Expected to place the goods at Basement ,21-Generators procurment & placing the goods in basement & coordination with Crane specialist to avoid improper placement of the goods , as well as will affect negatively the methodoligy of O&M regarding to repair /replace the deffected partds (when required . ,22-Deviation/obvious delays in time of supply the special equipment by Contractor that will lead to disturbance of work execution time line as well as installation , Testing &commissioning | 1-Apply the mandatory requirement for Lfting equipment as the contruction sector - OSHAD 34,.0 Safe lifting and lfiting accessories. SF , increase inspection procedure, Implement the control for contractor and subcontractor.,2-Apply the COSHH assesment, Allocate resources for Compress gases requirements , Implement the Risk Assesment ,,3-Required Noc,s already obtained , and Contractor corrective action is required to allocat additiona l resources to overcome /compansate the occurred delays ,,5-Storm water removed from site plan patameter properties , and other services already relocated /removed ,6-Due to the natur of the MBZ Area noght shify is not possible , hoever Contractor can compansate the same by allocating additiona lresources /equipment ,7-Contyractor notified by the same , and instructed to focaus to provide valid timeline based on the required resources to expedite the progress , and meet project target plan ,9-Contractor conduct several meetings with Piling subcontractor to secure /replace all existing equipment that are in bad condirion to be replaced by other equipment that can continue piing work without stoppage that cirrently continuance breakdown /in bad condition ,10.1- Possibility of using in-situ dismantle/reassemble approach with all MEP equipment. 10.22- Possibility of doing without telescopic cranes altogether and provide middle slot in the intake shaft's cover slab to allow for the lifting of MEP equipment.,11-The engineer shall instruct the contractor to explore the possibility of starting capping beams construction without the need for activating internal dewatering system by exploring the use of external well point dewatering system for dewatering at such shallow level. ,12-Engineer instructed the contractor to provide a valid working plan to adress such possibility including submission of repair and injection materials and method statements, to be ready for utilization (when required) ,13-Contractor to implement quality improvement toolbox at the beginning of each activity and at regular intervals to enlighten the importance of quality and sequence of activity.,14-Contractor should have back-up plans for utilizing excess concrete (whenever required ) rather than creating abortive works by casting conce. At un resdy area (nor compacted /not spreayed by anti termite ,15 &16-Contractor to assign a quality personal at night shift,15 &16-Contractor to assign a quality personal at night shift,,17-Contractor is requested to liase with ADDC to varify the validy of ADDC wether they can provide th pemennat Power uspply to the project peioe requesting the Client supplort ,18-Contractor should abide to Client instruction ,19-Contrator is requested to update the procurment control log to anble identify the missing items that still not considered /not planned for matrial submission m and approval prior procurment ., 20&21-Main contractor is requested to Submit Method Statement of installation to verify the circulation plane of movement, to ensure O&M proper accessibility to all equipment .,, 22-Contarctor requested to coordinate with specialist to provide valid /actual date of material delvery to verify the impact of late delevery (if any ) to submit undertaking letter to confirm the delivery schedule of the special equipment and on site . | Relocation Services. -Complete the Main Piles. -Complete the Guide wall and shoring pile head breaking. -Start of Capping Beams and Struts activities | 78195477.46 | 0 | 78195477.46 | 3462518.5382 |  | 81657995.9982 | 4774958.11 | 1018381.2003 | https://drive.google.com/thumbnail?id=1YilrYlrEBR5j4gXQtSjyi1aNfDAiAnEu&sz=w1000 | https://drive.google.com/file/d/1YilrYlrEBR5j4gXQtSjyi1aNfDAiAnEu/view?usp=drive_link | https://drive.google.com/thumbnail?id=1nRiloij6wjknh-vdXufPMtF9ywgwSqpI&sz=w1000 | https://drive.google.com/file/d/1nRiloij6wjknh-vdXufPMtF9ywgwSqpI/view?usp=drive_link | https://drive.google.com/thumbnail?id=1DZ00kl6N0YvT2ZAXdhcx9VQ5hnPKYmSP&sz=w1000 | https://drive.google.com/file/d/1DZ00kl6N0YvT2ZAXdhcx9VQ5hnPKYmSP/view?usp=drive_link
2024-09-13 | Mohamed Bin Zayed City -Majlis-P19 | P19 | MJ-03 | 290 | 308 | 598 | *Piles Shoring Completed *Breaking of Shoring Head piles ongoing. *Breaking of Guide wall on going . *Excavation for Capping Beams *Casted of Main Piles on going *Dewatering Installation ongoing *Relocation Services ongoing. | As the recommendation from project's Engineer, Engineer have identified the need for an additional construction team by the contractor . | 47.79% | 26.86% | -20.93% | 3- Majlis - Power | 2025-07-24 |  | 2025-10-01 | 2024-09-19 | 1-Lifting Works ( Unsafe Lifting / Rigging ) Lack of 3rd party Inspection/ Riggers/ and the damaged rigging tackles,2-Inadequate Handling and Storage of Compress Gases,Risk- Const. ,3-Delay in work commencement of MBZ project due to delays in response from Contractor end regarding to NOC’s / Utility Relocation, in addition to delays in issuance of Updated affection plan .,,5-Delay in issuance of NOCs for MCC, Strom Water ,and Etisalat,6-The project will require night shift operations. This time compansation is essential to meet project deadlines,7-Contractor continuation of given invalid anticipation foe the conpletion of piling work to enable work night shift (24 days ) is still not applicable at this site due to the nature of the required activities that will not be allowed at such sensitive area , and Contractor should increase the resources to enable compensate the above mentioned restriction .,9-Piling work Subcontractor continuance equipment breakdown due to utilization of bad condition equipment ,10-Potential need for increasing the height of the intake shaft (potentially beyond the acceptable limit) in order to allow for the safe handling/liftg MEP equipment by the telescopic crane Not applicable so far since the contractor willing to supply TELESCOPIC CRAIN inaccrodance withg project specs ,11-Dewatering system not operated with full effiviency that will impact further work execution (capping beem & Excavation).,12-Potential high level of ingress of ground water flow during execution of work/ excavation,13-Compromising the overall quality to meet the project time lin, like guniting without anti-termite and PCC without compaction/anti-termite.,14-Improper backfilling near dead shutter of the lower raft with excess concrete without any compaction might potentially cause settlements ,15-Non-availability of Contractor QA/QC at night can leads to proceed with any non-compliance works .,15-Non-availability of Contractor QA/QC at night can leads to proceed with any non-compliance works .,16-Non-availability of Contractor QA/QC at night can leads to proceed with any non-compliance works .,17-AIC raised the concerns of ADDC might will not be able to provide permenant Power supply to the project ,18-Client instruction to providethe required AV system (such as av sytem ) from nominated supplier that should be approved by client that might create time impact negatively against the completion of the required provisional to Shelter &Majles and Consutant reqyested to maintain standby equipment to avoid work stoppage ,19-Delays in long lead items finalization of material procurment (such as light fixtures ,…,20-Chillers material delevery to Al Shahama & MBZ The Risk Expected to place the goods at Basement ,21-Generators procurment & placing the goods in basement & coordination with Crane specialist to avoid improper placement of the goods , as well as will affect negatively the methodoligy of O&M regarding to repair /replace the deffected partds (when required . ,22-Deviation/obvious delays in time of supply the special equipment by Contractor that will lead to disturbance of work execution time line as well as installation , Testing &commissioning | 1-Apply the mandatory requirement for Lfting equipment as the contruction sector - OSHAD 34,.0 Safe lifting and lfiting accessories. SF , increase inspection procedure, Implement the control for contractor and subcontractor.,2-Apply the COSHH assesment, Allocate resources for Compress gases requirements , Implement the Risk Assesment ,,3-Required Noc,s already obtained , and Contractor corrective action is required to allocat additiona l resources to overcome /compansate the occurred delays ,,5-Storm water removed from site plan patameter properties , and other services already relocated /removed ,6-Due to the natur of the MBZ Area noght shify is not possible , hoever Contractor can compansate the same by allocating additiona lresources /equipment ,7-Contyractor notified by the same , and instructed to focaus to provide valid timeline based on the required resources to expedite the progress , and meet project target plan ,9-Contractor conduct several meetings with Piling subcontractor to secure /replace all existing equipment that are in bad condirion to be replaced by other equipment that can continue piing work without stoppage that cirrently continuance breakdown /in bad condition ,10.1- Possibility of using in-situ dismantle/reassemble approach with all MEP equipment. 10.22- Possibility of doing without telescopic cranes altogether and provide middle slot in the intake shaft's cover slab to allow for the lifting of MEP equipment.,11-The engineer shall instruct the contractor to explore the possibility of starting capping beams construction without the need for activating internal dewatering system by exploring the use of external well point dewatering system for dewatering at such shallow level. ,12-Engineer instructed the contractor to provide a valid working plan to adress such possibility including submission of repair and injection materials and method statements, to be ready for utilization (when required) ,13-Contractor to implement quality improvement toolbox at the beginning of each activity and at regular intervals to enlighten the importance of quality and sequence of activity.,14-Contractor should have back-up plans for utilizing excess concrete (whenever required ) rather than creating abortive works by casting conce. At un resdy area (nor compacted /not spreayed by anti termite ,15 &16-Contractor to assign a quality personal at night shift,15 &16-Contractor to assign a quality personal at night shift,,17-Contractor is requested to liase with ADDC to varify the validy of ADDC wether they can provide th pemennat Power uspply to the project peioe requesting the Client supplort ,18-Contractor should abide to Client instruction ,19-Contrator is requested to update the procurment control log to anble identify the missing items that still not considered /not planned for matrial submission m and approval prior procurment ., 20&21-Main contractor is requested to Submit Method Statement of installation to verify the circulation plane of movement, to ensure O&M proper accessibility to all equipment .,, 22-Contarctor requested to coordinate with specialist to provide valid /actual date of material delvery to verify the impact of late delevery (if any ) to submit undertaking letter to confirm the delivery schedule of the special equipment and on site . | Relocation Services. -Complete the Main Piles. -Complete the Guide wall and shoring pile head breaking. -Start of Capping Beams and Struts activities | 78195477.46 | 0 | 78195477.46 | 3462518.5382 |  | 81657995.9982 | 4774958.11 | 1018381.2003 | https://drive.google.com/thumbnail?id=1YilrYlrEBR5j4gXQtSjyi1aNfDAiAnEu&sz=w1000 | https://drive.google.com/file/d/1YilrYlrEBR5j4gXQtSjyi1aNfDAiAnEu/view?usp=drive_link | https://drive.google.com/thumbnail?id=1nRiloij6wjknh-vdXufPMtF9ywgwSqpI&sz=w1000 | https://drive.google.com/file/d/1nRiloij6wjknh-vdXufPMtF9ywgwSqpI/view?usp=drive_link | https://drive.google.com/thumbnail?id=1DZ00kl6N0YvT2ZAXdhcx9VQ5hnPKYmSP&sz=w1000 | https://drive.google.com/file/d/1DZ00kl6N0YvT2ZAXdhcx9VQ5hnPKYmSP/view?usp=drive_link
2024-09-13 | Mohamed Bin Zayed City -Majlis-P19 | P19 | MJ-03 | 290 | 308 | 598 | *Piles Shoring Completed *Breaking of Shoring Head piles ongoing. *Breaking of Guide wall on going . *Excavation for Capping Beams *Casted of Main Piles on going *Dewatering Installation ongoing *Relocation Services ongoing. | As the recommendation from project's Engineer, Engineer have identified the need for an additional construction team by the contractor . | 47.79% | 26.86% | -20.93% | 4- Project Finsh date ( Contractual Milestone ) | 2025-07-24 |  | 2025-10-25 | 2024-09-19 | 1-Lifting Works ( Unsafe Lifting / Rigging ) Lack of 3rd party Inspection/ Riggers/ and the damaged rigging tackles,2-Inadequate Handling and Storage of Compress Gases,Risk- Const. ,3-Delay in work commencement of MBZ project due to delays in response from Contractor end regarding to NOC’s / Utility Relocation, in addition to delays in issuance of Updated affection plan .,,5-Delay in issuance of NOCs for MCC, Strom Water ,and Etisalat,6-The project will require night shift operations. This time compansation is essential to meet project deadlines,7-Contractor continuation of given invalid anticipation foe the conpletion of piling work to enable work night shift (24 days ) is still not applicable at this site due to the nature of the required activities that will not be allowed at such sensitive area , and Contractor should increase the resources to enable compensate the above mentioned restriction .,9-Piling work Subcontractor continuance equipment breakdown due to utilization of bad condition equipment ,10-Potential need for increasing the height of the intake shaft (potentially beyond the acceptable limit) in order to allow for the safe handling/liftg MEP equipment by the telescopic crane Not applicable so far since the contractor willing to supply TELESCOPIC CRAIN inaccrodance withg project specs ,11-Dewatering system not operated with full effiviency that will impact further work execution (capping beem & Excavation).,12-Potential high level of ingress of ground water flow during execution of work/ excavation,13-Compromising the overall quality to meet the project time lin, like guniting without anti-termite and PCC without compaction/anti-termite.,14-Improper backfilling near dead shutter of the lower raft with excess concrete without any compaction might potentially cause settlements ,15-Non-availability of Contractor QA/QC at night can leads to proceed with any non-compliance works .,15-Non-availability of Contractor QA/QC at night can leads to proceed with any non-compliance works .,16-Non-availability of Contractor QA/QC at night can leads to proceed with any non-compliance works .,17-AIC raised the concerns of ADDC might will not be able to provide permenant Power supply to the project ,18-Client instruction to providethe required AV system (such as av sytem ) from nominated supplier that should be approved by client that might create time impact negatively against the completion of the required provisional to Shelter &Majles and Consutant reqyested to maintain standby equipment to avoid work stoppage ,19-Delays in long lead items finalization of material procurment (such as light fixtures ,…,20-Chillers material delevery to Al Shahama & MBZ The Risk Expected to place the goods at Basement ,21-Generators procurment & placing the goods in basement & coordination with Crane specialist to avoid improper placement of the goods , as well as will affect negatively the methodoligy of O&M regarding to repair /replace the deffected partds (when required . ,22-Deviation/obvious delays in time of supply the special equipment by Contractor that will lead to disturbance of work execution time line as well as installation , Testing &commissioning | 1-Apply the mandatory requirement for Lfting equipment as the contruction sector - OSHAD 34,.0 Safe lifting and lfiting accessories. SF , increase inspection procedure, Implement the control for contractor and subcontractor.,2-Apply the COSHH assesment, Allocate resources for Compress gases requirements , Implement the Risk Assesment ,,3-Required Noc,s already obtained , and Contractor corrective action is required to allocat additiona l resources to overcome /compansate the occurred delays ,,5-Storm water removed from site plan patameter properties , and other services already relocated /removed ,6-Due to the natur of the MBZ Area noght shify is not possible , hoever Contractor can compansate the same by allocating additiona lresources /equipment ,7-Contyractor notified by the same , and instructed to focaus to provide valid timeline based on the required resources to expedite the progress , and meet project target plan ,9-Contractor conduct several meetings with Piling subcontractor to secure /replace all existing equipment that are in bad condirion to be replaced by other equipment that can continue piing work without stoppage that cirrently continuance breakdown /in bad condition ,10.1- Possibility of using in-situ dismantle/reassemble approach with all MEP equipment. 10.22- Possibility of doing without telescopic cranes altogether and provide middle slot in the intake shaft's cover slab to allow for the lifting of MEP equipment.,11-The engineer shall instruct the contractor to explore the possibility of starting capping beams construction without the need for activating internal dewatering system by exploring the use of external well point dewatering system for dewatering at such shallow level. ,12-Engineer instructed the contractor to provide a valid working plan to adress such possibility including submission of repair and injection materials and method statements, to be ready for utilization (when required) ,13-Contractor to implement quality improvement toolbox at the beginning of each activity and at regular intervals to enlighten the importance of quality and sequence of activity.,14-Contractor should have back-up plans for utilizing excess concrete (whenever required ) rather than creating abortive works by casting conce. At un resdy area (nor compacted /not spreayed by anti termite ,15 &16-Contractor to assign a quality personal at night shift,15 &16-Contractor to assign a quality personal at night shift,,17-Contractor is requested to liase with ADDC to varify the validy of ADDC wether they can provide th pemennat Power uspply to the project peioe requesting the Client supplort ,18-Contractor should abide to Client instruction ,19-Contrator is requested to update the procurment control log to anble identify the missing items that still not considered /not planned for matrial submission m and approval prior procurment ., 20&21-Main contractor is requested to Submit Method Statement of installation to verify the circulation plane of movement, to ensure O&M proper accessibility to all equipment .,, 22-Contarctor requested to coordinate with specialist to provide valid /actual date of material delvery to verify the impact of late delevery (if any ) to submit undertaking letter to confirm the delivery schedule of the special equipment and on site . | Relocation Services. -Complete the Main Piles. -Complete the Guide wall and shoring pile head breaking. -Start of Capping Beams and Struts activities | 78195477.46 | 0 | 78195477.46 | 3462518.5382 |  | 81657995.9982 | 4774958.11 | 1018381.2003 | https://drive.google.com/thumbnail?id=1YilrYlrEBR5j4gXQtSjyi1aNfDAiAnEu&sz=w1000 | https://drive.google.com/file/d/1YilrYlrEBR5j4gXQtSjyi1aNfDAiAnEu/view?usp=drive_link | https://drive.google.com/thumbnail?id=1nRiloij6wjknh-vdXufPMtF9ywgwSqpI&sz=w1000 | https://drive.google.com/file/d/1nRiloij6wjknh-vdXufPMtF9ywgwSqpI/view?usp=drive_link | https://drive.google.com/thumbnail?id=1DZ00kl6N0YvT2ZAXdhcx9VQ5hnPKYmSP&sz=w1000 | https://drive.google.com/file/d/1DZ00kl6N0YvT2ZAXdhcx9VQ5hnPKYmSP/view?usp=drive_link
2024-09-13 | Madinat Al Riyad-Majlis-P3 | P3 | MJ-08 | 60 | 733 | 793 | 1) Site Offices for Client and Consultant: Foundation work is completed, portacabin erection is Completed , MEP & other finishing work in progress. 2) Baseline Programme : Madinat Al Riyad Cost Loaded program shall be submitted on 20-Sep-24. 3) Shelter: Shoring Excavation and Guide Wall Reinforcement Work in Progress 4) Engineering Works Submissions: The submissions for prequalification's, material approvals, and shop drawings are actively in progress. 5) Concrete Design Mix: C40 shoring / C50 Piling concrete trail mix completed, while others are still in progress. | *Submission of baseline program revision in comliance with Engineer comments. *Execution Plan for Shoring & Piling Works. *Program of work for piling & shoring works from specialized subcontractor | 0% | 0% | 0% | Project Commencement | 2024-07-23 | 2024-07-23 |  | 2024-09-20 | 1) Issuance of Night Shift Permit 2)Execution Plan Finalization for Piling & Shoring Works | 1) Action required 2) Specialized Contractors will Provide Execution Plan | • RiyadCost Loaded Program Submission on 20-Sep-24 • Client & Consultant Office Porta Cabin Installation • Material Submission for Cement,Bitumen Paint & Concrete Repair • Access Road Construction • Shelter Area Shoring Excavation | 117010730 | 0 | 117010730 | 3645800 |  | 120656530 |  |  | https://drive.google.com/thumbnail?id=1ivqBk1OAmLirXhfrxLBzeUL_jJxegxDI&sz=w1000 | https://drive.google.com/file/d/1ivqBk1OAmLirXhfrxLBzeUL_jJxegxDI/view?usp=drive_link | https://drive.google.com/thumbnail?id=1ErzZnaGRbRgYHrCEwMv-7ly4fAk80jPD&sz=w1000 | https://drive.google.com/file/d/1ErzZnaGRbRgYHrCEwMv-7ly4fAk80jPD/view?usp=drive_link | https://drive.google.com/thumbnail?id=12tCRalajPMVE-onCQiXS7R_4zEPBFs_C&sz=w1000 | https://drive.google.com/file/d/12tCRalajPMVE-onCQiXS7R_4zEPBFs_C/view?usp=drive_link
2024-09-13 | Madinat Al Riyad-Majlis-P3 | P3 | MJ-08 | 60 | 733 | 793 | 1) Site Offices for Client and Consultant: Foundation work is completed, portacabin erection is Completed , MEP & other finishing work in progress. 2) Baseline Programme : Madinat Al Riyad Cost Loaded program shall be submitted on 20-Sep-24. 3) Shelter: Shoring Excavation and Guide Wall Reinforcement Work in Progress 4) Engineering Works Submissions: The submissions for prequalification's, material approvals, and shop drawings are actively in progress. 5) Concrete Design Mix: C40 shoring / C50 Piling concrete trail mix completed, while others are still in progress. | *Submission of baseline program revision in comliance with Engineer comments. *Execution Plan for Shoring & Piling Works. *Program of work for piling & shoring works from specialized subcontractor | 0% | 0% | 0% | Construction Permit & NOC | 2024-08-15 | 2024-08-15 |  | 2024-09-20 | 1) Issuance of Night Shift Permit 2)Execution Plan Finalization for Piling & Shoring Works | 1) Action required 2) Specialized Contractors will Provide Execution Plan | • RiyadCost Loaded Program Submission on 20-Sep-24 • Client & Consultant Office Porta Cabin Installation • Material Submission for Cement,Bitumen Paint & Concrete Repair • Access Road Construction • Shelter Area Shoring Excavation | 117010730 |  | 117010730 | 3645800 |  | 120656530 |  |  | https://drive.google.com/thumbnail?id=1ivqBk1OAmLirXhfrxLBzeUL_jJxegxDI&sz=w1000 | https://drive.google.com/file/d/1ivqBk1OAmLirXhfrxLBzeUL_jJxegxDI/view?usp=drive_link | https://drive.google.com/thumbnail?id=1ErzZnaGRbRgYHrCEwMv-7ly4fAk80jPD&sz=w1000 | https://drive.google.com/file/d/1ErzZnaGRbRgYHrCEwMv-7ly4fAk80jPD/view?usp=drive_link | https://drive.google.com/thumbnail?id=12tCRalajPMVE-onCQiXS7R_4zEPBFs_C&sz=w1000 | https://drive.google.com/file/d/12tCRalajPMVE-onCQiXS7R_4zEPBFs_C/view?usp=drive_link
2024-09-13 | Madinat Al Riyad-Majlis-P3 | P3 | MJ-08 | 60 | 733 | 793 | 1) Site Offices for Client and Consultant: Foundation work is completed, portacabin erection is Completed , MEP & other finishing work in progress. 2) Baseline Programme : Madinat Al Riyad Cost Loaded program shall be submitted on 20-Sep-24. 3) Shelter: Shoring Excavation and Guide Wall Reinforcement Work in Progress 4) Engineering Works Submissions: The submissions for prequalification's, material approvals, and shop drawings are actively in progress. 5) Concrete Design Mix: C40 shoring / C50 Piling concrete trail mix completed, while others are still in progress. | *Submission of baseline program revision in comliance with Engineer comments. *Execution Plan for Shoring & Piling Works. *Program of work for piling & shoring works from specialized subcontractor | 0% | 0% | 0% | Site Moblization | 2024-09-23 |  | 2024-09-23 | 2024-09-20 | 1) Issuance of Night Shift Permit 2)Execution Plan Finalization for Piling & Shoring Works | 1) Action required 2) Specialized Contractors will Provide Execution Plan | • RiyadCost Loaded Program Submission on 20-Sep-24 • Client & Consultant Office Porta Cabin Installation • Material Submission for Cement,Bitumen Paint & Concrete Repair • Access Road Construction • Shelter Area Shoring Excavation | 117010730 |  | 117010730 | 3645800 |  | 120656530 |  |  | https://drive.google.com/thumbnail?id=1ivqBk1OAmLirXhfrxLBzeUL_jJxegxDI&sz=w1000 | https://drive.google.com/file/d/1ivqBk1OAmLirXhfrxLBzeUL_jJxegxDI/view?usp=drive_link | https://drive.google.com/thumbnail?id=1ErzZnaGRbRgYHrCEwMv-7ly4fAk80jPD&sz=w1000 | https://drive.google.com/file/d/1ErzZnaGRbRgYHrCEwMv-7ly4fAk80jPD/view?usp=drive_link | https://drive.google.com/thumbnail?id=12tCRalajPMVE-onCQiXS7R_4zEPBFs_C&sz=w1000 | https://drive.google.com/file/d/12tCRalajPMVE-onCQiXS7R_4zEPBFs_C/view?usp=drive_link
2024-09-13 | Madinat Al Riyad-Majlis-P3 | P3 | MJ-08 | 60 | 733 | 793 | 1) Site Offices for Client and Consultant: Foundation work is completed, portacabin erection is Completed , MEP & other finishing work in progress. 2) Baseline Programme : Madinat Al Riyad Cost Loaded program shall be submitted on 20-Sep-24. 3) Shelter: Shoring Excavation and Guide Wall Reinforcement Work in Progress 4) Engineering Works Submissions: The submissions for prequalification's, material approvals, and shop drawings are actively in progress. 5) Concrete Design Mix: C40 shoring / C50 Piling concrete trail mix completed, while others are still in progress. | *Submission of baseline program revision in comliance with Engineer comments. *Execution Plan for Shoring & Piling Works. *Program of work for piling & shoring works from specialized subcontractor | 0% | 0% | 0% | Engineering Works | 2026-01-31 |  | 2026-01-31 | 2024-09-20 | 1) Issuance of Night Shift Permit 2)Execution Plan Finalization for Piling & Shoring Works | 1) Action required 2) Specialized Contractors will Provide Execution Plan | • RiyadCost Loaded Program Submission on 20-Sep-24 • Client & Consultant Office Porta Cabin Installation • Material Submission for Cement,Bitumen Paint & Concrete Repair • Access Road Construction • Shelter Area Shoring Excavation | 117010730 |  | 117010730 | 3645800 |  | 120656530 |  |  | https://drive.google.com/thumbnail?id=1ivqBk1OAmLirXhfrxLBzeUL_jJxegxDI&sz=w1000 | https://drive.google.com/file/d/1ivqBk1OAmLirXhfrxLBzeUL_jJxegxDI/view?usp=drive_link | https://drive.google.com/thumbnail?id=1ErzZnaGRbRgYHrCEwMv-7ly4fAk80jPD&sz=w1000 | https://drive.google.com/file/d/1ErzZnaGRbRgYHrCEwMv-7ly4fAk80jPD/view?usp=drive_link | https://drive.google.com/thumbnail?id=12tCRalajPMVE-onCQiXS7R_4zEPBFs_C&sz=w1000 | https://drive.google.com/file/d/12tCRalajPMVE-onCQiXS7R_4zEPBFs_C/view?usp=drive_link
2024-09-13 | Madinat Al Riyad-Majlis-P3 | P3 | MJ-08 | 60 | 733 | 793 | 1) Site Offices for Client and Consultant: Foundation work is completed, portacabin erection is Completed , MEP & other finishing work in progress. 2) Baseline Programme : Madinat Al Riyad Cost Loaded program shall be submitted on 20-Sep-24. 3) Shelter: Shoring Excavation and Guide Wall Reinforcement Work in Progress 4) Engineering Works Submissions: The submissions for prequalification's, material approvals, and shop drawings are actively in progress. 5) Concrete Design Mix: C40 shoring / C50 Piling concrete trail mix completed, while others are still in progress. | *Submission of baseline program revision in comliance with Engineer comments. *Execution Plan for Shoring & Piling Works. *Program of work for piling & shoring works from specialized subcontractor | 0% | 0% | 0% | Construction of Shelter | 2026-09-15 |  | 2026-09-15 | 2024-09-20 | 1) Issuance of Night Shift Permit 2)Execution Plan Finalization for Piling & Shoring Works | 1) Action required 2) Specialized Contractors will Provide Execution Plan | • RiyadCost Loaded Program Submission on 20-Sep-24 • Client & Consultant Office Porta Cabin Installation • Material Submission for Cement,Bitumen Paint & Concrete Repair • Access Road Construction • Shelter Area Shoring Excavation | 117010730 |  | 117010730 | 3645800 |  | 120656530 |  |  | https://drive.google.com/thumbnail?id=1ivqBk1OAmLirXhfrxLBzeUL_jJxegxDI&sz=w1000 | https://drive.google.com/file/d/1ivqBk1OAmLirXhfrxLBzeUL_jJxegxDI/view?usp=drive_link | https://drive.google.com/thumbnail?id=1ErzZnaGRbRgYHrCEwMv-7ly4fAk80jPD&sz=w1000 | https://drive.google.com/file/d/1ErzZnaGRbRgYHrCEwMv-7ly4fAk80jPD/view?usp=drive_link | https://drive.google.com/thumbnail?id=12tCRalajPMVE-onCQiXS7R_4zEPBFs_C&sz=w1000 | https://drive.google.com/file/d/12tCRalajPMVE-onCQiXS7R_4zEPBFs_C/view?usp=drive_link
2024-09-13 | Madinat Al Riyad-Majlis-P3 | P3 | MJ-08 | 60 | 733 | 793 | 1) Site Offices for Client and Consultant: Foundation work is completed, portacabin erection is Completed , MEP & other finishing work in progress. 2) Baseline Programme : Madinat Al Riyad Cost Loaded program shall be submitted on 20-Sep-24. 3) Shelter: Shoring Excavation and Guide Wall Reinforcement Work in Progress 4) Engineering Works Submissions: The submissions for prequalification's, material approvals, and shop drawings are actively in progress. 5) Concrete Design Mix: C40 shoring / C50 Piling concrete trail mix completed, while others are still in progress. | *Submission of baseline program revision in comliance with Engineer comments. *Execution Plan for Shoring & Piling Works. *Program of work for piling & shoring works from specialized subcontractor | 0% | 0% | 0% | Construction of Majlis | 2026-07-24 |  | 2026-07-24 | 2024-09-20 | 1) Issuance of Night Shift Permit 2)Execution Plan Finalization for Piling & Shoring Works | 1) Action required 2) Specialized Contractors will Provide Execution Plan | • RiyadCost Loaded Program Submission on 20-Sep-24 • Client & Consultant Office Porta Cabin Installation • Material Submission for Cement,Bitumen Paint & Concrete Repair • Access Road Construction • Shelter Area Shoring Excavation | 117010730 |  | 117010730 | 3645800 |  | 120656530 |  |  | https://drive.google.com/thumbnail?id=1ivqBk1OAmLirXhfrxLBzeUL_jJxegxDI&sz=w1000 | https://drive.google.com/file/d/1ivqBk1OAmLirXhfrxLBzeUL_jJxegxDI/view?usp=drive_link | https://drive.google.com/thumbnail?id=1ErzZnaGRbRgYHrCEwMv-7ly4fAk80jPD&sz=w1000 | https://drive.google.com/file/d/1ErzZnaGRbRgYHrCEwMv-7ly4fAk80jPD/view?usp=drive_link | https://drive.google.com/thumbnail?id=12tCRalajPMVE-onCQiXS7R_4zEPBFs_C&sz=w1000 | https://drive.google.com/file/d/12tCRalajPMVE-onCQiXS7R_4zEPBFs_C/view?usp=drive_link
2024-09-13 | Madinat Al Riyad-Majlis-P3 | P3 | MJ-08 | 60 | 733 | 793 | 1) Site Offices for Client and Consultant: Foundation work is completed, portacabin erection is Completed , MEP & other finishing work in progress. 2) Baseline Programme : Madinat Al Riyad Cost Loaded program shall be submitted on 20-Sep-24. 3) Shelter: Shoring Excavation and Guide Wall Reinforcement Work in Progress 4) Engineering Works Submissions: The submissions for prequalification's, material approvals, and shop drawings are actively in progress. 5) Concrete Design Mix: C40 shoring / C50 Piling concrete trail mix completed, while others are still in progress. | *Submission of baseline program revision in comliance with Engineer comments. *Execution Plan for Shoring & Piling Works. *Program of work for piling & shoring works from specialized subcontractor | 0% | 0% | 0% | Construction of Pump Room | 2026-11-02 |  | 2026-11-02 | 2024-09-20 | 1) Issuance of Night Shift Permit 2)Execution Plan Finalization for Piling & Shoring Works | 1) Action required 2) Specialized Contractors will Provide Execution Plan | • RiyadCost Loaded Program Submission on 20-Sep-24 • Client & Consultant Office Porta Cabin Installation • Material Submission for Cement,Bitumen Paint & Concrete Repair • Access Road Construction • Shelter Area Shoring Excavation | 117010730 |  | 117010730 | 3645800 |  | 120656530 |  |  | https://drive.google.com/thumbnail?id=1ivqBk1OAmLirXhfrxLBzeUL_jJxegxDI&sz=w1000 | https://drive.google.com/file/d/1ivqBk1OAmLirXhfrxLBzeUL_jJxegxDI/view?usp=drive_link | https://drive.google.com/thumbnail?id=1ErzZnaGRbRgYHrCEwMv-7ly4fAk80jPD&sz=w1000 | https://drive.google.com/file/d/1ErzZnaGRbRgYHrCEwMv-7ly4fAk80jPD/view?usp=drive_link | https://drive.google.com/thumbnail?id=12tCRalajPMVE-onCQiXS7R_4zEPBFs_C&sz=w1000 | https://drive.google.com/file/d/12tCRalajPMVE-onCQiXS7R_4zEPBFs_C/view?usp=drive_link
2024-09-13 | Madinat Al Riyad-Majlis-P3 | P3 | MJ-08 | 60 | 733 | 793 | 1) Site Offices for Client and Consultant: Foundation work is completed, portacabin erection is Completed , MEP & other finishing work in progress. 2) Baseline Programme : Madinat Al Riyad Cost Loaded program shall be submitted on 20-Sep-24. 3) Shelter: Shoring Excavation and Guide Wall Reinforcement Work in Progress 4) Engineering Works Submissions: The submissions for prequalification's, material approvals, and shop drawings are actively in progress. 5) Concrete Design Mix: C40 shoring / C50 Piling concrete trail mix completed, while others are still in progress. | *Submission of baseline program revision in comliance with Engineer comments. *Execution Plan for Shoring & Piling Works. *Program of work for piling & shoring works from specialized subcontractor | 0% | 0% | 0% | Construction of Substation | 2025-05-12 |  | 2025-05-12 | 2024-09-20 | 1) Issuance of Night Shift Permit 2)Execution Plan Finalization for Piling & Shoring Works | 1) Action required 2) Specialized Contractors will Provide Execution Plan | • RiyadCost Loaded Program Submission on 20-Sep-24 • Client & Consultant Office Porta Cabin Installation • Material Submission for Cement,Bitumen Paint & Concrete Repair • Access Road Construction • Shelter Area Shoring Excavation | 117010730 |  | 117010730 | 3645800 |  | 120656530 |  |  | https://drive.google.com/thumbnail?id=1ivqBk1OAmLirXhfrxLBzeUL_jJxegxDI&sz=w1000 | https://drive.google.com/file/d/1ivqBk1OAmLirXhfrxLBzeUL_jJxegxDI/view?usp=drive_link | https://drive.google.com/thumbnail?id=1ErzZnaGRbRgYHrCEwMv-7ly4fAk80jPD&sz=w1000 | https://drive.google.com/file/d/1ErzZnaGRbRgYHrCEwMv-7ly4fAk80jPD/view?usp=drive_link | https://drive.google.com/thumbnail?id=12tCRalajPMVE-onCQiXS7R_4zEPBFs_C&sz=w1000 | https://drive.google.com/file/d/12tCRalajPMVE-onCQiXS7R_4zEPBFs_C/view?usp=drive_link
2024-09-13 | Madinat Al Riyad-Majlis-P3 | P3 | MJ-08 | 60 | 733 | 793 | 1) Site Offices for Client and Consultant: Foundation work is completed, portacabin erection is Completed , MEP & other finishing work in progress. 2) Baseline Programme : Madinat Al Riyad Cost Loaded program shall be submitted on 20-Sep-24. 3) Shelter: Shoring Excavation and Guide Wall Reinforcement Work in Progress 4) Engineering Works Submissions: The submissions for prequalification's, material approvals, and shop drawings are actively in progress. 5) Concrete Design Mix: C40 shoring / C50 Piling concrete trail mix completed, while others are still in progress. | *Submission of baseline program revision in comliance with Engineer comments. *Execution Plan for Shoring & Piling Works. *Program of work for piling & shoring works from specialized subcontractor | 0% | 0% | 0% | External Works | 2026-04-14 |  | 2026-04-14 | 2024-09-20 | 1) Issuance of Night Shift Permit 2)Execution Plan Finalization for Piling & Shoring Works | 1) Action required 2) Specialized Contractors will Provide Execution Plan | • RiyadCost Loaded Program Submission on 20-Sep-24 • Client & Consultant Office Porta Cabin Installation • Material Submission for Cement,Bitumen Paint & Concrete Repair • Access Road Construction • Shelter Area Shoring Excavation | 117010730 |  | 117010730 | 3645800 |  | 120656530 |  |  | https://drive.google.com/thumbnail?id=1ivqBk1OAmLirXhfrxLBzeUL_jJxegxDI&sz=w1000 | https://drive.google.com/file/d/1ivqBk1OAmLirXhfrxLBzeUL_jJxegxDI/view?usp=drive_link | https://drive.google.com/thumbnail?id=1ErzZnaGRbRgYHrCEwMv-7ly4fAk80jPD&sz=w1000 | https://drive.google.com/file/d/1ErzZnaGRbRgYHrCEwMv-7ly4fAk80jPD/view?usp=drive_link | https://drive.google.com/thumbnail?id=12tCRalajPMVE-onCQiXS7R_4zEPBFs_C&sz=w1000 | https://drive.google.com/file/d/12tCRalajPMVE-onCQiXS7R_4zEPBFs_C/view?usp=drive_link
2024-09-13 | Madinat Al Riyad-Majlis-P3 | P3 | MJ-08 | 60 | 733 | 793 | 1) Site Offices for Client and Consultant: Foundation work is completed, portacabin erection is Completed , MEP & other finishing work in progress. 2) Baseline Programme : Madinat Al Riyad Cost Loaded program shall be submitted on 20-Sep-24. 3) Shelter: Shoring Excavation and Guide Wall Reinforcement Work in Progress 4) Engineering Works Submissions: The submissions for prequalification's, material approvals, and shop drawings are actively in progress. 5) Concrete Design Mix: C40 shoring / C50 Piling concrete trail mix completed, while others are still in progress. | *Submission of baseline program revision in comliance with Engineer comments. *Execution Plan for Shoring & Piling Works. *Program of work for piling & shoring works from specialized subcontractor | 0% | 0% | 0% | Testing & Commissioning | 2026-09-21 |  | 2026-09-21 | 2024-09-20 | 1) Issuance of Night Shift Permit 2)Execution Plan Finalization for Piling & Shoring Works | 1) Action required 2) Specialized Contractors will Provide Execution Plan | • RiyadCost Loaded Program Submission on 20-Sep-24 • Client & Consultant Office Porta Cabin Installation • Material Submission for Cement,Bitumen Paint & Concrete Repair • Access Road Construction • Shelter Area Shoring Excavation | 117010730 |  | 117010730 | 3645800 |  | 120656530 |  |  | https://drive.google.com/thumbnail?id=1ivqBk1OAmLirXhfrxLBzeUL_jJxegxDI&sz=w1000 | https://drive.google.com/file/d/1ivqBk1OAmLirXhfrxLBzeUL_jJxegxDI/view?usp=drive_link | https://drive.google.com/thumbnail?id=1ErzZnaGRbRgYHrCEwMv-7ly4fAk80jPD&sz=w1000 | https://drive.google.com/file/d/1ErzZnaGRbRgYHrCEwMv-7ly4fAk80jPD/view?usp=drive_link | https://drive.google.com/thumbnail?id=12tCRalajPMVE-onCQiXS7R_4zEPBFs_C&sz=w1000 | https://drive.google.com/file/d/12tCRalajPMVE-onCQiXS7R_4zEPBFs_C/view?usp=drive_link
2024-09-13 | Madinat Al Riyad-Majlis-P3 | P3 | MJ-08 | 60 | 733 | 793 | 1) Site Offices for Client and Consultant: Foundation work is completed, portacabin erection is Completed , MEP & other finishing work in progress. 2) Baseline Programme : Madinat Al Riyad Cost Loaded program shall be submitted on 20-Sep-24. 3) Shelter: Shoring Excavation and Guide Wall Reinforcement Work in Progress 4) Engineering Works Submissions: The submissions for prequalification's, material approvals, and shop drawings are actively in progress. 5) Concrete Design Mix: C40 shoring / C50 Piling concrete trail mix completed, while others are still in progress. | *Submission of baseline program revision in comliance with Engineer comments. *Execution Plan for Shoring & Piling Works. *Program of work for piling & shoring works from specialized subcontractor | 0% | 0% | 0% | Authorities Approvals | 2026-10-09 |  | 2026-10-09 | 2024-09-20 | 1) Issuance of Night Shift Permit 2)Execution Plan Finalization for Piling & Shoring Works | 1) Action required 2) Specialized Contractors will Provide Execution Plan | • RiyadCost Loaded Program Submission on 20-Sep-24 • Client & Consultant Office Porta Cabin Installation • Material Submission for Cement,Bitumen Paint & Concrete Repair • Access Road Construction • Shelter Area Shoring Excavation | 117010730 |  | 117010730 | 3645800 |  | 120656530 |  |  | https://drive.google.com/thumbnail?id=1ivqBk1OAmLirXhfrxLBzeUL_jJxegxDI&sz=w1000 | https://drive.google.com/file/d/1ivqBk1OAmLirXhfrxLBzeUL_jJxegxDI/view?usp=drive_link | https://drive.google.com/thumbnail?id=1ErzZnaGRbRgYHrCEwMv-7ly4fAk80jPD&sz=w1000 | https://drive.google.com/file/d/1ErzZnaGRbRgYHrCEwMv-7ly4fAk80jPD/view?usp=drive_link | https://drive.google.com/thumbnail?id=12tCRalajPMVE-onCQiXS7R_4zEPBFs_C&sz=w1000 | https://drive.google.com/file/d/12tCRalajPMVE-onCQiXS7R_4zEPBFs_C/view?usp=drive_link
2024-09-13 | Madinat Al Riyad-Majlis-P3 | P3 | MJ-08 | 60 | 733 | 793 | 1) Site Offices for Client and Consultant: Foundation work is completed, portacabin erection is Completed , MEP & other finishing work in progress. 2) Baseline Programme : Madinat Al Riyad Cost Loaded program shall be submitted on 20-Sep-24. 3) Shelter: Shoring Excavation and Guide Wall Reinforcement Work in Progress 4) Engineering Works Submissions: The submissions for prequalification's, material approvals, and shop drawings are actively in progress. 5) Concrete Design Mix: C40 shoring / C50 Piling concrete trail mix completed, while others are still in progress. | *Submission of baseline program revision in comliance with Engineer comments. *Execution Plan for Shoring & Piling Works. *Program of work for piling & shoring works from specialized subcontractor | 0% | 0% | 0% | Substantial Completion | 2026-09-23 |  | 2026-09-23 | 2024-09-20 | 1) Issuance of Night Shift Permit 2)Execution Plan Finalization for Piling & Shoring Works | 1) Action required 2) Specialized Contractors will Provide Execution Plan | • RiyadCost Loaded Program Submission on 20-Sep-24 • Client & Consultant Office Porta Cabin Installation • Material Submission for Cement,Bitumen Paint & Concrete Repair • Access Road Construction • Shelter Area Shoring Excavation | 117010730 |  | 117010730 | 3645800 |  | 120656530 |  |  | https://drive.google.com/thumbnail?id=1ivqBk1OAmLirXhfrxLBzeUL_jJxegxDI&sz=w1000 | https://drive.google.com/file/d/1ivqBk1OAmLirXhfrxLBzeUL_jJxegxDI/view?usp=drive_link | https://drive.google.com/thumbnail?id=1ErzZnaGRbRgYHrCEwMv-7ly4fAk80jPD&sz=w1000 | https://drive.google.com/file/d/1ErzZnaGRbRgYHrCEwMv-7ly4fAk80jPD/view?usp=drive_link | https://drive.google.com/thumbnail?id=12tCRalajPMVE-onCQiXS7R_4zEPBFs_C&sz=w1000 | https://drive.google.com/file/d/12tCRalajPMVE-onCQiXS7R_4zEPBFs_C/view?usp=drive_link
2024-09-13 | Al Shamkhah-Majlis-P6 | P6 | MJ-09 | 60 | 733 | 793 | 1) Shelter : Excavation for Shoring work in progress. 2) Mosque : Backfilling Work in Progress for piling . 3) Baseline Programme : AlShamkha Cost Loaded program shall be submitted on 20-Sep-24. 4) Site Offices for Client and Consultant: Foundation work is completed, portacabin erection is Completed , MEP & other finishing work in progress. 5) Engineering Works Submissions: The submissions for prequalification's, material approvals, and shop drawings are actively in progress. 6) Concrete Design Mix : C40 shoring / C50 Piling concrete trail mix completed, while others are still in progress. | *Submission of baseline program revision in comliance with Engineer comments. *Execution Plan for Shoring & Piling Works. *Program of work for piling & shoring works from specialized subcontractor | 0% | 0% | 0% | Project Commencement | 2024-07-23 | 2024-07-23 |  | 2024-09-20 | 1) Issuance of Night Shift Permit 2)Possibility of High Water Table 3)Execution Plan Finalization for Piling & Shoring Works | 1) Action required 2) Proactive Measures shall be adopted 3) Specialized Contractors will Provide Execution Plan | • Shamkha Cost Loaded Program Draft Submission on 13-Sep-24. Engineer review comments for the draft have been provided to contractor meantime. • Client & Consultant Office Porta Cabin Installation • Workers Rest Area Shed Fabrication • Access Road Construction • Excavation for Majlis • Shelter Area Shoring Excavation in Progress | 356759501 |  | 356759501 | 3645800 |  | 360405301 |  |  | https://drive.google.com/thumbnail?id=1fUENaPvI5EGQBpB2AP1I0ESrESO08iWA&sz=w1000 | https://drive.google.com/file/d/1fUENaPvI5EGQBpB2AP1I0ESrESO08iWA/view?usp=drive_link | https://drive.google.com/thumbnail?id=1YiebLoAQwQ3DDXk7k09Eme9jE5xzfvGC&sz=w1000 | https://drive.google.com/file/d/1YiebLoAQwQ3DDXk7k09Eme9jE5xzfvGC/view?usp=drive_link | https://drive.google.com/thumbnail?id=1Si-fSzjLqtub6Ffxa9vP4q5-r_GljdPA&sz=w1000 | https://drive.google.com/file/d/1Si-fSzjLqtub6Ffxa9vP4q5-r_GljdPA/view?usp=drive_link
2024-09-13 | Al Shamkhah-Majlis-P6 | P6 | MJ-09 | 60 | 733 | 793 | 1) Shelter : Excavation for Shoring work in progress. 2) Mosque : Backfilling Work in Progress for piling . 3) Baseline Programme : AlShamkha Cost Loaded program shall be submitted on 20-Sep-24. 4) Site Offices for Client and Consultant: Foundation work is completed, portacabin erection is Completed , MEP & other finishing work in progress. 5) Engineering Works Submissions: The submissions for prequalification's, material approvals, and shop drawings are actively in progress. 6) Concrete Design Mix : C40 shoring / C50 Piling concrete trail mix completed, while others are still in progress. | *Submission of baseline program revision in comliance with Engineer comments. *Execution Plan for Shoring & Piling Works. *Program of work for piling & shoring works from specialized subcontractor | 0% | 0% | 0% | Construction Permit & NOC | 2024-08-15 | 2024-08-15 |  | 2024-09-20 | 1) Issuance of Night Shift Permit 2)Possibility of High Water Table 3)Execution Plan Finalization for Piling & Shoring Works | 1) Action required 2) Proactive Measures shall be adopted 3) Specialized Contractors will Provide Execution Plan | • Shamkha Cost Loaded Program Draft Submission on 13-Sep-24. Engineer review comments for the draft have been provided to contractor meantime. • Client & Consultant Office Porta Cabin Installation • Workers Rest Area Shed Fabrication • Access Road Construction • Excavation for Majlis • Shelter Area Shoring Excavation in Progress | 356759501 |  | 356759501 | 3645800 |  | 360405301 |  |  | https://drive.google.com/thumbnail?id=1fUENaPvI5EGQBpB2AP1I0ESrESO08iWA&sz=w1000 | https://drive.google.com/file/d/1fUENaPvI5EGQBpB2AP1I0ESrESO08iWA/view?usp=drive_link | https://drive.google.com/thumbnail?id=1YiebLoAQwQ3DDXk7k09Eme9jE5xzfvGC&sz=w1000 | https://drive.google.com/file/d/1YiebLoAQwQ3DDXk7k09Eme9jE5xzfvGC/view?usp=drive_link | https://drive.google.com/thumbnail?id=1Si-fSzjLqtub6Ffxa9vP4q5-r_GljdPA&sz=w1000 | https://drive.google.com/file/d/1Si-fSzjLqtub6Ffxa9vP4q5-r_GljdPA/view?usp=drive_link
2024-09-13 | Al Shamkhah-Majlis-P6 | P6 | MJ-09 | 60 | 733 | 793 | 1) Shelter : Excavation for Shoring work in progress. 2) Mosque : Backfilling Work in Progress for piling . 3) Baseline Programme : AlShamkha Cost Loaded program shall be submitted on 20-Sep-24. 4) Site Offices for Client and Consultant: Foundation work is completed, portacabin erection is Completed , MEP & other finishing work in progress. 5) Engineering Works Submissions: The submissions for prequalification's, material approvals, and shop drawings are actively in progress. 6) Concrete Design Mix : C40 shoring / C50 Piling concrete trail mix completed, while others are still in progress. | *Submission of baseline program revision in comliance with Engineer comments. *Execution Plan for Shoring & Piling Works. *Program of work for piling & shoring works from specialized subcontractor | 0% | 0% | 0% | Site Moblization | 2026-09-20 |  | 2026-09-20 | 2024-09-20 | 1) Issuance of Night Shift Permit 2)Possibility of High Water Table 3)Execution Plan Finalization for Piling & Shoring Works | 1) Action required 2) Proactive Measures shall be adopted 3) Specialized Contractors will Provide Execution Plan | • Shamkha Cost Loaded Program Draft Submission on 13-Sep-24. Engineer review comments for the draft have been provided to contractor meantime. • Client & Consultant Office Porta Cabin Installation • Workers Rest Area Shed Fabrication • Access Road Construction • Excavation for Majlis • Shelter Area Shoring Excavation in Progress | 356759501 |  | 356759501 | 3645800 |  | 360405301 |  |  | https://drive.google.com/thumbnail?id=1fUENaPvI5EGQBpB2AP1I0ESrESO08iWA&sz=w1000 | https://drive.google.com/file/d/1fUENaPvI5EGQBpB2AP1I0ESrESO08iWA/view?usp=drive_link | https://drive.google.com/thumbnail?id=1YiebLoAQwQ3DDXk7k09Eme9jE5xzfvGC&sz=w1000 | https://drive.google.com/file/d/1YiebLoAQwQ3DDXk7k09Eme9jE5xzfvGC/view?usp=drive_link | https://drive.google.com/thumbnail?id=1Si-fSzjLqtub6Ffxa9vP4q5-r_GljdPA&sz=w1000 | https://drive.google.com/file/d/1Si-fSzjLqtub6Ffxa9vP4q5-r_GljdPA/view?usp=drive_link
2024-09-13 | Al Shamkhah-Majlis-P6 | P6 | MJ-09 | 60 | 733 | 793 | 1) Shelter : Excavation for Shoring work in progress. 2) Mosque : Backfilling Work in Progress for piling . 3) Baseline Programme : AlShamkha Cost Loaded program shall be submitted on 20-Sep-24. 4) Site Offices for Client and Consultant: Foundation work is completed, portacabin erection is Completed , MEP & other finishing work in progress. 5) Engineering Works Submissions: The submissions for prequalification's, material approvals, and shop drawings are actively in progress. 6) Concrete Design Mix : C40 shoring / C50 Piling concrete trail mix completed, while others are still in progress. | *Submission of baseline program revision in comliance with Engineer comments. *Execution Plan for Shoring & Piling Works. *Program of work for piling & shoring works from specialized subcontractor | 0% | 0% | 0% | Engineering Works | 2026-01-31 |  | 2026-01-31 | 2024-09-20 | 1) Issuance of Night Shift Permit 2)Possibility of High Water Table 3)Execution Plan Finalization for Piling & Shoring Works | 1) Action required 2) Proactive Measures shall be adopted 3) Specialized Contractors will Provide Execution Plan | • Shamkha Cost Loaded Program Draft Submission on 13-Sep-24. Engineer review comments for the draft have been provided to contractor meantime. • Client & Consultant Office Porta Cabin Installation • Workers Rest Area Shed Fabrication • Access Road Construction • Excavation for Majlis • Shelter Area Shoring Excavation in Progress | 356759501 |  | 356759501 | 3645800 |  | 360405301 |  |  | https://drive.google.com/thumbnail?id=1fUENaPvI5EGQBpB2AP1I0ESrESO08iWA&sz=w1000 | https://drive.google.com/file/d/1fUENaPvI5EGQBpB2AP1I0ESrESO08iWA/view?usp=drive_link | https://drive.google.com/thumbnail?id=1YiebLoAQwQ3DDXk7k09Eme9jE5xzfvGC&sz=w1000 | https://drive.google.com/file/d/1YiebLoAQwQ3DDXk7k09Eme9jE5xzfvGC/view?usp=drive_link | https://drive.google.com/thumbnail?id=1Si-fSzjLqtub6Ffxa9vP4q5-r_GljdPA&sz=w1000 | https://drive.google.com/file/d/1Si-fSzjLqtub6Ffxa9vP4q5-r_GljdPA/view?usp=drive_link
2024-09-13 | Al Shamkhah-Majlis-P6 | P6 | MJ-09 | 60 | 733 | 793 | 1) Shelter : Excavation for Shoring work in progress. 2) Mosque : Backfilling Work in Progress for piling . 3) Baseline Programme : AlShamkha Cost Loaded program shall be submitted on 20-Sep-24. 4) Site Offices for Client and Consultant: Foundation work is completed, portacabin erection is Completed , MEP & other finishing work in progress. 5) Engineering Works Submissions: The submissions for prequalification's, material approvals, and shop drawings are actively in progress. 6) Concrete Design Mix : C40 shoring / C50 Piling concrete trail mix completed, while others are still in progress. | *Submission of baseline program revision in comliance with Engineer comments. *Execution Plan for Shoring & Piling Works. *Program of work for piling & shoring works from specialized subcontractor | 0% | 0% | 0% | Shelter Construction | 2026-09-15 |  | 2026-09-15 | 2024-09-20 | 1) Issuance of Night Shift Permit 2)Possibility of High Water Table 3)Execution Plan Finalization for Piling & Shoring Works | 1) Action required 2) Proactive Measures shall be adopted 3) Specialized Contractors will Provide Execution Plan | • Shamkha Cost Loaded Program Draft Submission on 13-Sep-24. Engineer review comments for the draft have been provided to contractor meantime. • Client & Consultant Office Porta Cabin Installation • Workers Rest Area Shed Fabrication • Access Road Construction • Excavation for Majlis • Shelter Area Shoring Excavation in Progress | 356759501 |  | 356759501 | 3645800 |  | 360405301 |  |  | https://drive.google.com/thumbnail?id=1fUENaPvI5EGQBpB2AP1I0ESrESO08iWA&sz=w1000 | https://drive.google.com/file/d/1fUENaPvI5EGQBpB2AP1I0ESrESO08iWA/view?usp=drive_link | https://drive.google.com/thumbnail?id=1YiebLoAQwQ3DDXk7k09Eme9jE5xzfvGC&sz=w1000 | https://drive.google.com/file/d/1YiebLoAQwQ3DDXk7k09Eme9jE5xzfvGC/view?usp=drive_link | https://drive.google.com/thumbnail?id=1Si-fSzjLqtub6Ffxa9vP4q5-r_GljdPA&sz=w1000 | https://drive.google.com/file/d/1Si-fSzjLqtub6Ffxa9vP4q5-r_GljdPA/view?usp=drive_link
2024-09-13 | Al Shamkhah-Majlis-P6 | P6 | MJ-09 | 60 | 733 | 793 | 1) Shelter : Excavation for Shoring work in progress. 2) Mosque : Backfilling Work in Progress for piling . 3) Baseline Programme : AlShamkha Cost Loaded program shall be submitted on 20-Sep-24. 4) Site Offices for Client and Consultant: Foundation work is completed, portacabin erection is Completed , MEP & other finishing work in progress. 5) Engineering Works Submissions: The submissions for prequalification's, material approvals, and shop drawings are actively in progress. 6) Concrete Design Mix : C40 shoring / C50 Piling concrete trail mix completed, while others are still in progress. | *Submission of baseline program revision in comliance with Engineer comments. *Execution Plan for Shoring & Piling Works. *Program of work for piling & shoring works from specialized subcontractor | 0% | 0% | 0% | Mosque Constuction | 2026-03-09 |  | 2026-03-09 | 2024-09-20 | 1) Issuance of Night Shift Permit 2)Possibility of High Water Table 3)Execution Plan Finalization for Piling & Shoring Works | 1) Action required 2) Proactive Measures shall be adopted 3) Specialized Contractors will Provide Execution Plan | • Shamkha Cost Loaded Program Draft Submission on 13-Sep-24. Engineer review comments for the draft have been provided to contractor meantime. • Client & Consultant Office Porta Cabin Installation • Workers Rest Area Shed Fabrication • Access Road Construction • Excavation for Majlis • Shelter Area Shoring Excavation in Progress | 356759501 |  | 356759501 | 3645800 |  | 360405301 |  |  | https://drive.google.com/thumbnail?id=1fUENaPvI5EGQBpB2AP1I0ESrESO08iWA&sz=w1000 | https://drive.google.com/file/d/1fUENaPvI5EGQBpB2AP1I0ESrESO08iWA/view?usp=drive_link | https://drive.google.com/thumbnail?id=1YiebLoAQwQ3DDXk7k09Eme9jE5xzfvGC&sz=w1000 | https://drive.google.com/file/d/1YiebLoAQwQ3DDXk7k09Eme9jE5xzfvGC/view?usp=drive_link | https://drive.google.com/thumbnail?id=1Si-fSzjLqtub6Ffxa9vP4q5-r_GljdPA&sz=w1000 | https://drive.google.com/file/d/1Si-fSzjLqtub6Ffxa9vP4q5-r_GljdPA/view?usp=drive_link
2024-09-13 | Al Shamkhah-Majlis-P6 | P6 | MJ-09 | 60 | 733 | 793 | 1) Shelter : Excavation for Shoring work in progress. 2) Mosque : Backfilling Work in Progress for piling . 3) Baseline Programme : AlShamkha Cost Loaded program shall be submitted on 20-Sep-24. 4) Site Offices for Client and Consultant: Foundation work is completed, portacabin erection is Completed , MEP & other finishing work in progress. 5) Engineering Works Submissions: The submissions for prequalification's, material approvals, and shop drawings are actively in progress. 6) Concrete Design Mix : C40 shoring / C50 Piling concrete trail mix completed, while others are still in progress. | *Submission of baseline program revision in comliance with Engineer comments. *Execution Plan for Shoring & Piling Works. *Program of work for piling & shoring works from specialized subcontractor | 0% | 0% | 0% | Majlis Construction | 2026-07-09 |  | 2026-07-09 | 2024-09-20 | 1) Issuance of Night Shift Permit 2)Possibility of High Water Table 3)Execution Plan Finalization for Piling & Shoring Works | 1) Action required 2) Proactive Measures shall be adopted 3) Specialized Contractors will Provide Execution Plan | • Shamkha Cost Loaded Program Draft Submission on 13-Sep-24. Engineer review comments for the draft have been provided to contractor meantime. • Client & Consultant Office Porta Cabin Installation • Workers Rest Area Shed Fabrication • Access Road Construction • Excavation for Majlis • Shelter Area Shoring Excavation in Progress | 356759501 |  | 356759501 | 3645800 |  | 360405301 |  |  | https://drive.google.com/thumbnail?id=1fUENaPvI5EGQBpB2AP1I0ESrESO08iWA&sz=w1000 | https://drive.google.com/file/d/1fUENaPvI5EGQBpB2AP1I0ESrESO08iWA/view?usp=drive_link | https://drive.google.com/thumbnail?id=1YiebLoAQwQ3DDXk7k09Eme9jE5xzfvGC&sz=w1000 | https://drive.google.com/file/d/1YiebLoAQwQ3DDXk7k09Eme9jE5xzfvGC/view?usp=drive_link | https://drive.google.com/thumbnail?id=1Si-fSzjLqtub6Ffxa9vP4q5-r_GljdPA&sz=w1000 | https://drive.google.com/file/d/1Si-fSzjLqtub6Ffxa9vP4q5-r_GljdPA/view?usp=drive_link
2024-09-13 | Al Shamkhah-Majlis-P6 | P6 | MJ-09 | 60 | 733 | 793 | 1) Shelter : Excavation for Shoring work in progress. 2) Mosque : Backfilling Work in Progress for piling . 3) Baseline Programme : AlShamkha Cost Loaded program shall be submitted on 20-Sep-24. 4) Site Offices for Client and Consultant: Foundation work is completed, portacabin erection is Completed , MEP & other finishing work in progress. 5) Engineering Works Submissions: The submissions for prequalification's, material approvals, and shop drawings are actively in progress. 6) Concrete Design Mix : C40 shoring / C50 Piling concrete trail mix completed, while others are still in progress. | *Submission of baseline program revision in comliance with Engineer comments. *Execution Plan for Shoring & Piling Works. *Program of work for piling & shoring works from specialized subcontractor | 0% | 0% | 0% | Ablution Construction | 2026-01-09 |  | 2026-01-09 | 2024-09-20 | 1) Issuance of Night Shift Permit 2)Possibility of High Water Table 3)Execution Plan Finalization for Piling & Shoring Works | 1) Action required 2) Proactive Measures shall be adopted 3) Specialized Contractors will Provide Execution Plan | • Shamkha Cost Loaded Program Draft Submission on 13-Sep-24. Engineer review comments for the draft have been provided to contractor meantime. • Client & Consultant Office Porta Cabin Installation • Workers Rest Area Shed Fabrication • Access Road Construction • Excavation for Majlis • Shelter Area Shoring Excavation in Progress | 356759501 |  | 356759501 | 3645800 |  | 360405301 |  |  | https://drive.google.com/thumbnail?id=1fUENaPvI5EGQBpB2AP1I0ESrESO08iWA&sz=w1000 | https://drive.google.com/file/d/1fUENaPvI5EGQBpB2AP1I0ESrESO08iWA/view?usp=drive_link | https://drive.google.com/thumbnail?id=1YiebLoAQwQ3DDXk7k09Eme9jE5xzfvGC&sz=w1000 | https://drive.google.com/file/d/1YiebLoAQwQ3DDXk7k09Eme9jE5xzfvGC/view?usp=drive_link | https://drive.google.com/thumbnail?id=1Si-fSzjLqtub6Ffxa9vP4q5-r_GljdPA&sz=w1000 | https://drive.google.com/file/d/1Si-fSzjLqtub6Ffxa9vP4q5-r_GljdPA/view?usp=drive_link
2024-09-13 | Al Shamkhah-Majlis-P6 | P6 | MJ-09 | 60 | 733 | 793 | 1) Shelter : Excavation for Shoring work in progress. 2) Mosque : Backfilling Work in Progress for piling . 3) Baseline Programme : AlShamkha Cost Loaded program shall be submitted on 20-Sep-24. 4) Site Offices for Client and Consultant: Foundation work is completed, portacabin erection is Completed , MEP & other finishing work in progress. 5) Engineering Works Submissions: The submissions for prequalification's, material approvals, and shop drawings are actively in progress. 6) Concrete Design Mix : C40 shoring / C50 Piling concrete trail mix completed, while others are still in progress. | *Submission of baseline program revision in comliance with Engineer comments. *Execution Plan for Shoring & Piling Works. *Program of work for piling & shoring works from specialized subcontractor | 0% | 0% | 0% | Imam House Construction | 2026-07-22 |  | 2026-07-22 | 2024-09-20 | 1) Issuance of Night Shift Permit 2)Possibility of High Water Table 3)Execution Plan Finalization for Piling & Shoring Works | 1) Action required 2) Proactive Measures shall be adopted 3) Specialized Contractors will Provide Execution Plan | • Shamkha Cost Loaded Program Draft Submission on 13-Sep-24. Engineer review comments for the draft have been provided to contractor meantime. • Client & Consultant Office Porta Cabin Installation • Workers Rest Area Shed Fabrication • Access Road Construction • Excavation for Majlis • Shelter Area Shoring Excavation in Progress | 356759501 |  | 356759501 | 3645800 |  | 360405301 |  |  | https://drive.google.com/thumbnail?id=1fUENaPvI5EGQBpB2AP1I0ESrESO08iWA&sz=w1000 | https://drive.google.com/file/d/1fUENaPvI5EGQBpB2AP1I0ESrESO08iWA/view?usp=drive_link | https://drive.google.com/thumbnail?id=1YiebLoAQwQ3DDXk7k09Eme9jE5xzfvGC&sz=w1000 | https://drive.google.com/file/d/1YiebLoAQwQ3DDXk7k09Eme9jE5xzfvGC/view?usp=drive_link | https://drive.google.com/thumbnail?id=1Si-fSzjLqtub6Ffxa9vP4q5-r_GljdPA&sz=w1000 | https://drive.google.com/file/d/1Si-fSzjLqtub6Ffxa9vP4q5-r_GljdPA/view?usp=drive_link
2024-09-13 | Al Shamkhah-Majlis-P6 | P6 | MJ-09 | 60 | 733 | 793 | 1) Shelter : Excavation for Shoring work in progress. 2) Mosque : Backfilling Work in Progress for piling . 3) Baseline Programme : AlShamkha Cost Loaded program shall be submitted on 20-Sep-24. 4) Site Offices for Client and Consultant: Foundation work is completed, portacabin erection is Completed , MEP & other finishing work in progress. 5) Engineering Works Submissions: The submissions for prequalification's, material approvals, and shop drawings are actively in progress. 6) Concrete Design Mix : C40 shoring / C50 Piling concrete trail mix completed, while others are still in progress. | *Submission of baseline program revision in comliance with Engineer comments. *Execution Plan for Shoring & Piling Works. *Program of work for piling & shoring works from specialized subcontractor | 0% | 0% | 0% | Pump Room Construction | 2026-07-31 |  | 2026-07-31 | 2024-09-20 | 1) Issuance of Night Shift Permit 2)Possibility of High Water Table 3)Execution Plan Finalization for Piling & Shoring Works | 1) Action required 2) Proactive Measures shall be adopted 3) Specialized Contractors will Provide Execution Plan | • Shamkha Cost Loaded Program Draft Submission on 13-Sep-24. Engineer review comments for the draft have been provided to contractor meantime. • Client & Consultant Office Porta Cabin Installation • Workers Rest Area Shed Fabrication • Access Road Construction • Excavation for Majlis • Shelter Area Shoring Excavation in Progress | 356759501 |  | 356759501 | 3645800 |  | 360405301 |  |  | https://drive.google.com/thumbnail?id=1fUENaPvI5EGQBpB2AP1I0ESrESO08iWA&sz=w1000 | https://drive.google.com/file/d/1fUENaPvI5EGQBpB2AP1I0ESrESO08iWA/view?usp=drive_link | https://drive.google.com/thumbnail?id=1YiebLoAQwQ3DDXk7k09Eme9jE5xzfvGC&sz=w1000 | https://drive.google.com/file/d/1YiebLoAQwQ3DDXk7k09Eme9jE5xzfvGC/view?usp=drive_link | https://drive.google.com/thumbnail?id=1Si-fSzjLqtub6Ffxa9vP4q5-r_GljdPA&sz=w1000 | https://drive.google.com/file/d/1Si-fSzjLqtub6Ffxa9vP4q5-r_GljdPA/view?usp=drive_link
2024-09-13 | Al Shamkhah-Majlis-P6 | P6 | MJ-09 | 60 | 733 | 793 | 1) Shelter : Excavation for Shoring work in progress. 2) Mosque : Backfilling Work in Progress for piling . 3) Baseline Programme : AlShamkha Cost Loaded program shall be submitted on 20-Sep-24. 4) Site Offices for Client and Consultant: Foundation work is completed, portacabin erection is Completed , MEP & other finishing work in progress. 5) Engineering Works Submissions: The submissions for prequalification's, material approvals, and shop drawings are actively in progress. 6) Concrete Design Mix : C40 shoring / C50 Piling concrete trail mix completed, while others are still in progress. | *Submission of baseline program revision in comliance with Engineer comments. *Execution Plan for Shoring & Piling Works. *Program of work for piling & shoring works from specialized subcontractor | 0% | 0% | 0% | Sub Station Construction | 2025-05-12 |  | 2025-05-12 | 2024-09-20 | 1) Issuance of Night Shift Permit 2)Possibility of High Water Table 3)Execution Plan Finalization for Piling & Shoring Works | 1) Action required 2) Proactive Measures shall be adopted 3) Specialized Contractors will Provide Execution Plan | • Shamkha Cost Loaded Program Draft Submission on 13-Sep-24. Engineer review comments for the draft have been provided to contractor meantime. • Client & Consultant Office Porta Cabin Installation • Workers Rest Area Shed Fabrication • Access Road Construction • Excavation for Majlis • Shelter Area Shoring Excavation in Progress | 356759501 |  | 356759501 | 3645800 |  | 360405301 |  |  | https://drive.google.com/thumbnail?id=1fUENaPvI5EGQBpB2AP1I0ESrESO08iWA&sz=w1000 | https://drive.google.com/file/d/1fUENaPvI5EGQBpB2AP1I0ESrESO08iWA/view?usp=drive_link | https://drive.google.com/thumbnail?id=1YiebLoAQwQ3DDXk7k09Eme9jE5xzfvGC&sz=w1000 | https://drive.google.com/file/d/1YiebLoAQwQ3DDXk7k09Eme9jE5xzfvGC/view?usp=drive_link | https://drive.google.com/thumbnail?id=1Si-fSzjLqtub6Ffxa9vP4q5-r_GljdPA&sz=w1000 | https://drive.google.com/file/d/1Si-fSzjLqtub6Ffxa9vP4q5-r_GljdPA/view?usp=drive_link
2024-09-13 | Al Shamkhah-Majlis-P6 | P6 | MJ-09 | 60 | 733 | 793 | 1) Shelter : Excavation for Shoring work in progress. 2) Mosque : Backfilling Work in Progress for piling . 3) Baseline Programme : AlShamkha Cost Loaded program shall be submitted on 20-Sep-24. 4) Site Offices for Client and Consultant: Foundation work is completed, portacabin erection is Completed , MEP & other finishing work in progress. 5) Engineering Works Submissions: The submissions for prequalification's, material approvals, and shop drawings are actively in progress. 6) Concrete Design Mix : C40 shoring / C50 Piling concrete trail mix completed, while others are still in progress. | *Submission of baseline program revision in comliance with Engineer comments. *Execution Plan for Shoring & Piling Works. *Program of work for piling & shoring works from specialized subcontractor | 0% | 0% | 0% | External Works | 2026-04-14 |  | 2026-04-14 | 2024-09-20 | 1) Issuance of Night Shift Permit 2)Possibility of High Water Table 3)Execution Plan Finalization for Piling & Shoring Works | 1) Action required 2) Proactive Measures shall be adopted 3) Specialized Contractors will Provide Execution Plan | • Shamkha Cost Loaded Program Draft Submission on 13-Sep-24. Engineer review comments for the draft have been provided to contractor meantime. • Client & Consultant Office Porta Cabin Installation • Workers Rest Area Shed Fabrication • Access Road Construction • Excavation for Majlis • Shelter Area Shoring Excavation in Progress | 356759501 |  | 356759501 | 3645800 |  | 360405301 |  |  | https://drive.google.com/thumbnail?id=1fUENaPvI5EGQBpB2AP1I0ESrESO08iWA&sz=w1000 | https://drive.google.com/file/d/1fUENaPvI5EGQBpB2AP1I0ESrESO08iWA/view?usp=drive_link | https://drive.google.com/thumbnail?id=1YiebLoAQwQ3DDXk7k09Eme9jE5xzfvGC&sz=w1000 | https://drive.google.com/file/d/1YiebLoAQwQ3DDXk7k09Eme9jE5xzfvGC/view?usp=drive_link | https://drive.google.com/thumbnail?id=1Si-fSzjLqtub6Ffxa9vP4q5-r_GljdPA&sz=w1000 | https://drive.google.com/file/d/1Si-fSzjLqtub6Ffxa9vP4q5-r_GljdPA/view?usp=drive_link
2024-09-13 | Al Shamkhah-Majlis-P6 | P6 | MJ-09 | 60 | 733 | 793 | 1) Shelter : Excavation for Shoring work in progress. 2) Mosque : Backfilling Work in Progress for piling . 3) Baseline Programme : AlShamkha Cost Loaded program shall be submitted on 20-Sep-24. 4) Site Offices for Client and Consultant: Foundation work is completed, portacabin erection is Completed , MEP & other finishing work in progress. 5) Engineering Works Submissions: The submissions for prequalification's, material approvals, and shop drawings are actively in progress. 6) Concrete Design Mix : C40 shoring / C50 Piling concrete trail mix completed, while others are still in progress. | *Submission of baseline program revision in comliance with Engineer comments. *Execution Plan for Shoring & Piling Works. *Program of work for piling & shoring works from specialized subcontractor | 0% | 0% | 0% | Testing & Commissioning | 2026-09-21 |  | 2026-09-21 | 2024-09-20 | 1) Issuance of Night Shift Permit 2)Possibility of High Water Table 3)Execution Plan Finalization for Piling & Shoring Works | 1) Action required 2) Proactive Measures shall be adopted 3) Specialized Contractors will Provide Execution Plan | • Shamkha Cost Loaded Program Draft Submission on 13-Sep-24. Engineer review comments for the draft have been provided to contractor meantime. • Client & Consultant Office Porta Cabin Installation • Workers Rest Area Shed Fabrication • Access Road Construction • Excavation for Majlis • Shelter Area Shoring Excavation in Progress | 356759501 |  | 356759501 | 3645800 |  | 360405301 |  |  | https://drive.google.com/thumbnail?id=1fUENaPvI5EGQBpB2AP1I0ESrESO08iWA&sz=w1000 | https://drive.google.com/file/d/1fUENaPvI5EGQBpB2AP1I0ESrESO08iWA/view?usp=drive_link | https://drive.google.com/thumbnail?id=1YiebLoAQwQ3DDXk7k09Eme9jE5xzfvGC&sz=w1000 | https://drive.google.com/file/d/1YiebLoAQwQ3DDXk7k09Eme9jE5xzfvGC/view?usp=drive_link | https://drive.google.com/thumbnail?id=1Si-fSzjLqtub6Ffxa9vP4q5-r_GljdPA&sz=w1000 | https://drive.google.com/file/d/1Si-fSzjLqtub6Ffxa9vP4q5-r_GljdPA/view?usp=drive_link
2024-09-13 | Al Shamkhah-Majlis-P6 | P6 | MJ-09 | 60 | 733 | 793 | 1) Shelter : Excavation for Shoring work in progress. 2) Mosque : Backfilling Work in Progress for piling . 3) Baseline Programme : AlShamkha Cost Loaded program shall be submitted on 20-Sep-24. 4) Site Offices for Client and Consultant: Foundation work is completed, portacabin erection is Completed , MEP & other finishing work in progress. 5) Engineering Works Submissions: The submissions for prequalification's, material approvals, and shop drawings are actively in progress. 6) Concrete Design Mix : C40 shoring / C50 Piling concrete trail mix completed, while others are still in progress. | *Submission of baseline program revision in comliance with Engineer comments. *Execution Plan for Shoring & Piling Works. *Program of work for piling & shoring works from specialized subcontractor | 0% | 0% | 0% | Authorities Approvals | 2026-10-09 |  | 2026-10-09 | 2024-09-20 | 1) Issuance of Night Shift Permit 2)Possibility of High Water Table 3)Execution Plan Finalization for Piling & Shoring Works | 1) Action required 2) Proactive Measures shall be adopted 3) Specialized Contractors will Provide Execution Plan | • Shamkha Cost Loaded Program Draft Submission on 13-Sep-24. Engineer review comments for the draft have been provided to contractor meantime. • Client & Consultant Office Porta Cabin Installation • Workers Rest Area Shed Fabrication • Access Road Construction • Excavation for Majlis • Shelter Area Shoring Excavation in Progress | 356759501 |  | 356759501 | 3645800 |  | 360405301 |  |  | https://drive.google.com/thumbnail?id=1fUENaPvI5EGQBpB2AP1I0ESrESO08iWA&sz=w1000 | https://drive.google.com/file/d/1fUENaPvI5EGQBpB2AP1I0ESrESO08iWA/view?usp=drive_link | https://drive.google.com/thumbnail?id=1YiebLoAQwQ3DDXk7k09Eme9jE5xzfvGC&sz=w1000 | https://drive.google.com/file/d/1YiebLoAQwQ3DDXk7k09Eme9jE5xzfvGC/view?usp=drive_link | https://drive.google.com/thumbnail?id=1Si-fSzjLqtub6Ffxa9vP4q5-r_GljdPA&sz=w1000 | https://drive.google.com/file/d/1Si-fSzjLqtub6Ffxa9vP4q5-r_GljdPA/view?usp=drive_link
2024-09-13 | Al Shamkhah-Majlis-P6 | P6 | MJ-09 | 60 | 733 | 793 | 1) Shelter : Excavation for Shoring work in progress. 2) Mosque : Backfilling Work in Progress for piling . 3) Baseline Programme : AlShamkha Cost Loaded program shall be submitted on 20-Sep-24. 4) Site Offices for Client and Consultant: Foundation work is completed, portacabin erection is Completed , MEP & other finishing work in progress. 5) Engineering Works Submissions: The submissions for prequalification's, material approvals, and shop drawings are actively in progress. 6) Concrete Design Mix : C40 shoring / C50 Piling concrete trail mix completed, while others are still in progress. | *Submission of baseline program revision in comliance with Engineer comments. *Execution Plan for Shoring & Piling Works. *Program of work for piling & shoring works from specialized subcontractor | 0% | 0% | 0% | Substantial Completion | 2026-09-23 |  | 2026-09-23 | 2024-09-20 | 1) Issuance of Night Shift Permit 2)Possibility of High Water Table 3)Execution Plan Finalization for Piling & Shoring Works | 1) Action required 2) Proactive Measures shall be adopted 3) Specialized Contractors will Provide Execution Plan | • Shamkha Cost Loaded Program Draft Submission on 13-Sep-24. Engineer review comments for the draft have been provided to contractor meantime. • Client & Consultant Office Porta Cabin Installation • Workers Rest Area Shed Fabrication • Access Road Construction • Excavation for Majlis • Shelter Area Shoring Excavation in Progress | 356759501 |  | 356759501 | 3645800 |  | 360405301 |  |  | https://drive.google.com/thumbnail?id=1fUENaPvI5EGQBpB2AP1I0ESrESO08iWA&sz=w1000 | https://drive.google.com/file/d/1fUENaPvI5EGQBpB2AP1I0ESrESO08iWA/view?usp=drive_link | https://drive.google.com/thumbnail?id=1YiebLoAQwQ3DDXk7k09Eme9jE5xzfvGC&sz=w1000 | https://drive.google.com/file/d/1YiebLoAQwQ3DDXk7k09Eme9jE5xzfvGC/view?usp=drive_link | https://drive.google.com/thumbnail?id=1Si-fSzjLqtub6Ffxa9vP4q5-r_GljdPA&sz=w1000 | https://drive.google.com/file/d/1Si-fSzjLqtub6Ffxa9vP4q5-r_GljdPA/view?usp=drive_link
2024-09-13 | Baniyas-School-P77 | P77 | SC-01 | 193 | 356 | 549 | • Annex Building - GF Rebar fixing –48% Completed; Concrete 22% Completed • School Building - RCC Plinth Wall Concrete pouring 95% Completed; GF Rebar Fixing 62% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 3.84% | 16.53% | 12.69% | Notice to Commence | 2024-03-05 | 2024-03-05 |  | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Grade slab works to progress • Annex Building - GF RCC wall works to progress • Shelter Block - Substructure –RCC Wall upto Plinth to progress. • Shelter Block - RCC Wall Rebar Fixing to progress at GF & FF Level • Shelter Block - Surface Preparation for CRFP works | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 8897764.4965 | 180000 | https://drive.google.com/thumbnail?id=1nd2LuxXC_tnKKOUoZp-2rCmz6m31uExe&sz=w1000 | https://drive.google.com/file/d/1nd2LuxXC_tnKKOUoZp-2rCmz6m31uExe/view?usp=drive_link | https://drive.google.com/thumbnail?id=18gvd1UBIqDir1Ui4hKFDzLdKhiyxJeTK&sz=w1000 | https://drive.google.com/file/d/18gvd1UBIqDir1Ui4hKFDzLdKhiyxJeTK/view?usp=drive_link | https://drive.google.com/thumbnail?id=1oKDXnxtrdsnKiXx-rE-IOxBOcPslLQ0_&sz=w1000 | https://drive.google.com/file/d/1oKDXnxtrdsnKiXx-rE-IOxBOcPslLQ0_/view?usp=drive_link
2024-09-13 | Baniyas-School-P77 | P77 | SC-01 | 193 | 356 | 549 | • Annex Building - GF Rebar fixing –48% Completed; Concrete 22% Completed • School Building - RCC Plinth Wall Concrete pouring 95% Completed; GF Rebar Fixing 62% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 3.84% | 16.53% | 12.69% | Site Mobilization | 2024-04-09 | 2024-05-18 |  | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Grade slab works to progress • Annex Building - GF RCC wall works to progress • Shelter Block - Substructure –RCC Wall upto Plinth to progress. • Shelter Block - RCC Wall Rebar Fixing to progress at GF & FF Level • Shelter Block - Surface Preparation for CRFP works | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 8897764.4965 | 180000 | https://drive.google.com/thumbnail?id=1nd2LuxXC_tnKKOUoZp-2rCmz6m31uExe&sz=w1000 | https://drive.google.com/file/d/1nd2LuxXC_tnKKOUoZp-2rCmz6m31uExe/view?usp=drive_link | https://drive.google.com/thumbnail?id=18gvd1UBIqDir1Ui4hKFDzLdKhiyxJeTK&sz=w1000 | https://drive.google.com/file/d/18gvd1UBIqDir1Ui4hKFDzLdKhiyxJeTK/view?usp=drive_link | https://drive.google.com/thumbnail?id=1oKDXnxtrdsnKiXx-rE-IOxBOcPslLQ0_&sz=w1000 | https://drive.google.com/file/d/1oKDXnxtrdsnKiXx-rE-IOxBOcPslLQ0_/view?usp=drive_link
2024-09-13 | Baniyas-School-P77 | P77 | SC-01 | 193 | 356 | 549 | • Annex Building - GF Rebar fixing –48% Completed; Concrete 22% Completed • School Building - RCC Plinth Wall Concrete pouring 95% Completed; GF Rebar Fixing 62% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 3.84% | 16.53% | 12.69% | Building Permit | 2024-11-01 | 2024-08-06 |  | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Grade slab works to progress • Annex Building - GF RCC wall works to progress • Shelter Block - Substructure –RCC Wall upto Plinth to progress. • Shelter Block - RCC Wall Rebar Fixing to progress at GF & FF Level • Shelter Block - Surface Preparation for CRFP works | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 8897764.4965 | 180000 | https://drive.google.com/thumbnail?id=1nd2LuxXC_tnKKOUoZp-2rCmz6m31uExe&sz=w1000 | https://drive.google.com/file/d/1nd2LuxXC_tnKKOUoZp-2rCmz6m31uExe/view?usp=drive_link | https://drive.google.com/thumbnail?id=18gvd1UBIqDir1Ui4hKFDzLdKhiyxJeTK&sz=w1000 | https://drive.google.com/file/d/18gvd1UBIqDir1Ui4hKFDzLdKhiyxJeTK/view?usp=drive_link | https://drive.google.com/thumbnail?id=1oKDXnxtrdsnKiXx-rE-IOxBOcPslLQ0_&sz=w1000 | https://drive.google.com/file/d/1oKDXnxtrdsnKiXx-rE-IOxBOcPslLQ0_/view?usp=drive_link
2024-09-13 | Baniyas-School-P77 | P77 | SC-01 | 193 | 356 | 549 | • Annex Building - GF Rebar fixing –48% Completed; Concrete 22% Completed • School Building - RCC Plinth Wall Concrete pouring 95% Completed; GF Rebar Fixing 62% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 3.84% | 16.53% | 12.69% | School Substructure | 2025-01-21 |  | 2024-09-27 | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Grade slab works to progress • Annex Building - GF RCC wall works to progress • Shelter Block - Substructure –RCC Wall upto Plinth to progress. • Shelter Block - RCC Wall Rebar Fixing to progress at GF & FF Level • Shelter Block - Surface Preparation for CRFP works | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 8897764.4965 | 180000 | https://drive.google.com/thumbnail?id=1nd2LuxXC_tnKKOUoZp-2rCmz6m31uExe&sz=w1000 | https://drive.google.com/file/d/1nd2LuxXC_tnKKOUoZp-2rCmz6m31uExe/view?usp=drive_link | https://drive.google.com/thumbnail?id=18gvd1UBIqDir1Ui4hKFDzLdKhiyxJeTK&sz=w1000 | https://drive.google.com/file/d/18gvd1UBIqDir1Ui4hKFDzLdKhiyxJeTK/view?usp=drive_link | https://drive.google.com/thumbnail?id=1oKDXnxtrdsnKiXx-rE-IOxBOcPslLQ0_&sz=w1000 | https://drive.google.com/file/d/1oKDXnxtrdsnKiXx-rE-IOxBOcPslLQ0_/view?usp=drive_link
2024-09-13 | Baniyas-School-P77 | P77 | SC-01 | 193 | 356 | 549 | • Annex Building - GF Rebar fixing –48% Completed; Concrete 22% Completed • School Building - RCC Plinth Wall Concrete pouring 95% Completed; GF Rebar Fixing 62% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 3.84% | 16.53% | 12.69% | School Superstructure | 2025-04-28 |  | 2024-10-28 | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Grade slab works to progress • Annex Building - GF RCC wall works to progress • Shelter Block - Substructure –RCC Wall upto Plinth to progress. • Shelter Block - RCC Wall Rebar Fixing to progress at GF & FF Level • Shelter Block - Surface Preparation for CRFP works | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 8897764.4965 | 180000 | https://drive.google.com/thumbnail?id=1nd2LuxXC_tnKKOUoZp-2rCmz6m31uExe&sz=w1000 | https://drive.google.com/file/d/1nd2LuxXC_tnKKOUoZp-2rCmz6m31uExe/view?usp=drive_link | https://drive.google.com/thumbnail?id=18gvd1UBIqDir1Ui4hKFDzLdKhiyxJeTK&sz=w1000 | https://drive.google.com/file/d/18gvd1UBIqDir1Ui4hKFDzLdKhiyxJeTK/view?usp=drive_link | https://drive.google.com/thumbnail?id=1oKDXnxtrdsnKiXx-rE-IOxBOcPslLQ0_&sz=w1000 | https://drive.google.com/file/d/1oKDXnxtrdsnKiXx-rE-IOxBOcPslLQ0_/view?usp=drive_link
2024-09-13 | Baniyas-School-P77 | P77 | SC-01 | 193 | 356 | 549 | • Annex Building - GF Rebar fixing –48% Completed; Concrete 22% Completed • School Building - RCC Plinth Wall Concrete pouring 95% Completed; GF Rebar Fixing 62% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 3.84% | 16.53% | 12.69% | Annex Substructure | 2025-01-22 | 2024-08-17 |  | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Grade slab works to progress • Annex Building - GF RCC wall works to progress • Shelter Block - Substructure –RCC Wall upto Plinth to progress. • Shelter Block - RCC Wall Rebar Fixing to progress at GF & FF Level • Shelter Block - Surface Preparation for CRFP works | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 8897764.4965 | 180000 | https://drive.google.com/thumbnail?id=1nd2LuxXC_tnKKOUoZp-2rCmz6m31uExe&sz=w1000 | https://drive.google.com/file/d/1nd2LuxXC_tnKKOUoZp-2rCmz6m31uExe/view?usp=drive_link | https://drive.google.com/thumbnail?id=18gvd1UBIqDir1Ui4hKFDzLdKhiyxJeTK&sz=w1000 | https://drive.google.com/file/d/18gvd1UBIqDir1Ui4hKFDzLdKhiyxJeTK/view?usp=drive_link | https://drive.google.com/thumbnail?id=1oKDXnxtrdsnKiXx-rE-IOxBOcPslLQ0_&sz=w1000 | https://drive.google.com/file/d/1oKDXnxtrdsnKiXx-rE-IOxBOcPslLQ0_/view?usp=drive_link
2024-09-13 | Baniyas-School-P77 | P77 | SC-01 | 193 | 356 | 549 | • Annex Building - GF Rebar fixing –48% Completed; Concrete 22% Completed • School Building - RCC Plinth Wall Concrete pouring 95% Completed; GF Rebar Fixing 62% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 3.84% | 16.53% | 12.69% | Annex Superstructure | 2025-04-21 |  | 2025-01-16 | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Grade slab works to progress • Annex Building - GF RCC wall works to progress • Shelter Block - Substructure –RCC Wall upto Plinth to progress. • Shelter Block - RCC Wall Rebar Fixing to progress at GF & FF Level • Shelter Block - Surface Preparation for CRFP works | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 8897764.4965 | 180000 | https://drive.google.com/thumbnail?id=1nd2LuxXC_tnKKOUoZp-2rCmz6m31uExe&sz=w1000 | https://drive.google.com/file/d/1nd2LuxXC_tnKKOUoZp-2rCmz6m31uExe/view?usp=drive_link | https://drive.google.com/thumbnail?id=18gvd1UBIqDir1Ui4hKFDzLdKhiyxJeTK&sz=w1000 | https://drive.google.com/file/d/18gvd1UBIqDir1Ui4hKFDzLdKhiyxJeTK/view?usp=drive_link | https://drive.google.com/thumbnail?id=1oKDXnxtrdsnKiXx-rE-IOxBOcPslLQ0_&sz=w1000 | https://drive.google.com/file/d/1oKDXnxtrdsnKiXx-rE-IOxBOcPslLQ0_/view?usp=drive_link
2024-09-13 | Baniyas-School-P77 | P77 | SC-01 | 193 | 356 | 549 | • Annex Building - GF Rebar fixing –48% Completed; Concrete 22% Completed • School Building - RCC Plinth Wall Concrete pouring 95% Completed; GF Rebar Fixing 62% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 3.84% | 16.53% | 12.69% | MEP & Finishes | 2025-07-19 |  | 2025-06-18 | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Grade slab works to progress • Annex Building - GF RCC wall works to progress • Shelter Block - Substructure –RCC Wall upto Plinth to progress. • Shelter Block - RCC Wall Rebar Fixing to progress at GF & FF Level • Shelter Block - Surface Preparation for CRFP works | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 8897764.4965 | 180000 | https://drive.google.com/thumbnail?id=1nd2LuxXC_tnKKOUoZp-2rCmz6m31uExe&sz=w1000 | https://drive.google.com/file/d/1nd2LuxXC_tnKKOUoZp-2rCmz6m31uExe/view?usp=drive_link | https://drive.google.com/thumbnail?id=18gvd1UBIqDir1Ui4hKFDzLdKhiyxJeTK&sz=w1000 | https://drive.google.com/file/d/18gvd1UBIqDir1Ui4hKFDzLdKhiyxJeTK/view?usp=drive_link | https://drive.google.com/thumbnail?id=1oKDXnxtrdsnKiXx-rE-IOxBOcPslLQ0_&sz=w1000 | https://drive.google.com/file/d/1oKDXnxtrdsnKiXx-rE-IOxBOcPslLQ0_/view?usp=drive_link
2024-09-13 | Baniyas-School-P77 | P77 | SC-01 | 193 | 356 | 549 | • Annex Building - GF Rebar fixing –48% Completed; Concrete 22% Completed • School Building - RCC Plinth Wall Concrete pouring 95% Completed; GF Rebar Fixing 62% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 3.84% | 16.53% | 12.69% | BCC Inspection | 2025-08-05 |  | 2025-06-30 | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Grade slab works to progress • Annex Building - GF RCC wall works to progress • Shelter Block - Substructure –RCC Wall upto Plinth to progress. • Shelter Block - RCC Wall Rebar Fixing to progress at GF & FF Level • Shelter Block - Surface Preparation for CRFP works | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 8897764.4965 | 180000 | https://drive.google.com/thumbnail?id=1nd2LuxXC_tnKKOUoZp-2rCmz6m31uExe&sz=w1000 | https://drive.google.com/file/d/1nd2LuxXC_tnKKOUoZp-2rCmz6m31uExe/view?usp=drive_link | https://drive.google.com/thumbnail?id=18gvd1UBIqDir1Ui4hKFDzLdKhiyxJeTK&sz=w1000 | https://drive.google.com/file/d/18gvd1UBIqDir1Ui4hKFDzLdKhiyxJeTK/view?usp=drive_link | https://drive.google.com/thumbnail?id=1oKDXnxtrdsnKiXx-rE-IOxBOcPslLQ0_&sz=w1000 | https://drive.google.com/file/d/1oKDXnxtrdsnKiXx-rE-IOxBOcPslLQ0_/view?usp=drive_link
2024-09-13 | Baniyas-School-P77 | P77 | SC-01 | 193 | 356 | 549 | • Annex Building - GF Rebar fixing –48% Completed; Concrete 22% Completed • School Building - RCC Plinth Wall Concrete pouring 95% Completed; GF Rebar Fixing 62% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 3.84% | 16.53% | 12.69% | BCC Issuance | 2025-08-22 |  | 2025-07-17 | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Grade slab works to progress • Annex Building - GF RCC wall works to progress • Shelter Block - Substructure –RCC Wall upto Plinth to progress. • Shelter Block - RCC Wall Rebar Fixing to progress at GF & FF Level • Shelter Block - Surface Preparation for CRFP works | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 8897764.4965 | 180000 | https://drive.google.com/thumbnail?id=1nd2LuxXC_tnKKOUoZp-2rCmz6m31uExe&sz=w1000 | https://drive.google.com/file/d/1nd2LuxXC_tnKKOUoZp-2rCmz6m31uExe/view?usp=drive_link | https://drive.google.com/thumbnail?id=18gvd1UBIqDir1Ui4hKFDzLdKhiyxJeTK&sz=w1000 | https://drive.google.com/file/d/18gvd1UBIqDir1Ui4hKFDzLdKhiyxJeTK/view?usp=drive_link | https://drive.google.com/thumbnail?id=1oKDXnxtrdsnKiXx-rE-IOxBOcPslLQ0_&sz=w1000 | https://drive.google.com/file/d/1oKDXnxtrdsnKiXx-rE-IOxBOcPslLQ0_/view?usp=drive_link
2024-09-13 | Baniyas-School-P77 | P77 | SC-01 | 193 | 356 | 549 | • Annex Building - GF Rebar fixing –48% Completed; Concrete 22% Completed • School Building - RCC Plinth Wall Concrete pouring 95% Completed; GF Rebar Fixing 62% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 3.84% | 16.53% | 12.69% | Completion | 2025-09-04 |  | 2025-08-04 | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Grade slab works to progress • Annex Building - GF RCC wall works to progress • Shelter Block - Substructure –RCC Wall upto Plinth to progress. • Shelter Block - RCC Wall Rebar Fixing to progress at GF & FF Level • Shelter Block - Surface Preparation for CRFP works | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 8897764.4965 | 180000 | https://drive.google.com/thumbnail?id=1nd2LuxXC_tnKKOUoZp-2rCmz6m31uExe&sz=w1000 | https://drive.google.com/file/d/1nd2LuxXC_tnKKOUoZp-2rCmz6m31uExe/view?usp=drive_link | https://drive.google.com/thumbnail?id=18gvd1UBIqDir1Ui4hKFDzLdKhiyxJeTK&sz=w1000 | https://drive.google.com/file/d/18gvd1UBIqDir1Ui4hKFDzLdKhiyxJeTK/view?usp=drive_link | https://drive.google.com/thumbnail?id=1oKDXnxtrdsnKiXx-rE-IOxBOcPslLQ0_&sz=w1000 | https://drive.google.com/file/d/1oKDXnxtrdsnKiXx-rE-IOxBOcPslLQ0_/view?usp=drive_link
2024-09-13 | Al Shahama-School-P17 | P17 | SC-02 | 362 | 185 | 547 | • Annex Building - 1FF Slab - Staging & Shutter fixing100% Completed; Rebar Fixing 79% Completed • School Building - GF - RCC Wall Concrete 68% Completed, FF - Rebar Fixing 90% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 28.92% | 28.93% | 0.01% | Notice to Commence | 2023-09-18 | 2023-09-26 |  | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – FF Slab work & FF Wall Rebar, Shutter & Concrete pouring up to RF FL level • Shelter Block - Substructure – Waterproofing & Backfilling works. • Shelter Block - Superstructure - RCC wall to progress GF & 1FL • Shelter Block - Surface Preparation & Application of CFRP • Shelter Block - Roof Slab Strengthening works to progress | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 12271635.5944 | 180000 | https://drive.google.com/thumbnail?id=1W-gf0VbzbihbaBDbivu-eAIuFgmf1g2H&sz=w1000 | https://drive.google.com/file/d/1W-gf0VbzbihbaBDbivu-eAIuFgmf1g2H/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hqFUNz-YrJL1D-KF62ciGzKLn0jl5v4Y&sz=w1000 | https://drive.google.com/file/d/1hqFUNz-YrJL1D-KF62ciGzKLn0jl5v4Y/view?usp=drive_link | https://drive.google.com/thumbnail?id=1EFP77JsHwvOLRKb7NL4f0-WTRLI4zmhV&sz=w1000 | https://drive.google.com/file/d/1EFP77JsHwvOLRKb7NL4f0-WTRLI4zmhV/view?usp=drive_link
2024-09-13 | Al Shahama-School-P17 | P17 | SC-02 | 362 | 185 | 547 | • Annex Building - 1FF Slab - Staging & Shutter fixing100% Completed; Rebar Fixing 79% Completed • School Building - GF - RCC Wall Concrete 68% Completed, FF - Rebar Fixing 90% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 28.92% | 28.93% | 0.01% | Site Mobilization | 2023-10-21 | 2023-12-06 |  | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – FF Slab work & FF Wall Rebar, Shutter & Concrete pouring up to RF FL level • Shelter Block - Substructure – Waterproofing & Backfilling works. • Shelter Block - Superstructure - RCC wall to progress GF & 1FL • Shelter Block - Surface Preparation & Application of CFRP • Shelter Block - Roof Slab Strengthening works to progress | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 12271635.5944 | 180000 | https://drive.google.com/thumbnail?id=1W-gf0VbzbihbaBDbivu-eAIuFgmf1g2H&sz=w1000 | https://drive.google.com/file/d/1W-gf0VbzbihbaBDbivu-eAIuFgmf1g2H/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hqFUNz-YrJL1D-KF62ciGzKLn0jl5v4Y&sz=w1000 | https://drive.google.com/file/d/1hqFUNz-YrJL1D-KF62ciGzKLn0jl5v4Y/view?usp=drive_link | https://drive.google.com/thumbnail?id=1EFP77JsHwvOLRKb7NL4f0-WTRLI4zmhV&sz=w1000 | https://drive.google.com/file/d/1EFP77JsHwvOLRKb7NL4f0-WTRLI4zmhV/view?usp=drive_link
2024-09-13 | Al Shahama-School-P17 | P17 | SC-02 | 362 | 185 | 547 | • Annex Building - 1FF Slab - Staging & Shutter fixing100% Completed; Rebar Fixing 79% Completed • School Building - GF - RCC Wall Concrete 68% Completed, FF - Rebar Fixing 90% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 28.92% | 28.93% | 0.01% | Building Permit | 2024-05-17 | 2024-05-23 |  | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – FF Slab work & FF Wall Rebar, Shutter & Concrete pouring up to RF FL level • Shelter Block - Substructure – Waterproofing & Backfilling works. • Shelter Block - Superstructure - RCC wall to progress GF & 1FL • Shelter Block - Surface Preparation & Application of CFRP • Shelter Block - Roof Slab Strengthening works to progress | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 12271635.5944 | 180000 | https://drive.google.com/thumbnail?id=1W-gf0VbzbihbaBDbivu-eAIuFgmf1g2H&sz=w1000 | https://drive.google.com/file/d/1W-gf0VbzbihbaBDbivu-eAIuFgmf1g2H/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hqFUNz-YrJL1D-KF62ciGzKLn0jl5v4Y&sz=w1000 | https://drive.google.com/file/d/1hqFUNz-YrJL1D-KF62ciGzKLn0jl5v4Y/view?usp=drive_link | https://drive.google.com/thumbnail?id=1EFP77JsHwvOLRKb7NL4f0-WTRLI4zmhV&sz=w1000 | https://drive.google.com/file/d/1EFP77JsHwvOLRKb7NL4f0-WTRLI4zmhV/view?usp=drive_link
2024-09-13 | Al Shahama-School-P17 | P17 | SC-02 | 362 | 185 | 547 | • Annex Building - 1FF Slab - Staging & Shutter fixing100% Completed; Rebar Fixing 79% Completed • School Building - GF - RCC Wall Concrete 68% Completed, FF - Rebar Fixing 90% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 28.92% | 28.93% | 0.01% | School Substructure | 2024-08-06 |  | 2024-09-20 | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – FF Slab work & FF Wall Rebar, Shutter & Concrete pouring up to RF FL level • Shelter Block - Substructure – Waterproofing & Backfilling works. • Shelter Block - Superstructure - RCC wall to progress GF & 1FL • Shelter Block - Surface Preparation & Application of CFRP • Shelter Block - Roof Slab Strengthening works to progress | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 12271635.5944 | 180000 | https://drive.google.com/thumbnail?id=1W-gf0VbzbihbaBDbivu-eAIuFgmf1g2H&sz=w1000 | https://drive.google.com/file/d/1W-gf0VbzbihbaBDbivu-eAIuFgmf1g2H/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hqFUNz-YrJL1D-KF62ciGzKLn0jl5v4Y&sz=w1000 | https://drive.google.com/file/d/1hqFUNz-YrJL1D-KF62ciGzKLn0jl5v4Y/view?usp=drive_link | https://drive.google.com/thumbnail?id=1EFP77JsHwvOLRKb7NL4f0-WTRLI4zmhV&sz=w1000 | https://drive.google.com/file/d/1EFP77JsHwvOLRKb7NL4f0-WTRLI4zmhV/view?usp=drive_link
2024-09-13 | Al Shahama-School-P17 | P17 | SC-02 | 362 | 185 | 547 | • Annex Building - 1FF Slab - Staging & Shutter fixing100% Completed; Rebar Fixing 79% Completed • School Building - GF - RCC Wall Concrete 68% Completed, FF - Rebar Fixing 90% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 28.92% | 28.93% | 0.01% | School Superstructure | 2024-11-07 |  | 2024-10-08 | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – FF Slab work & FF Wall Rebar, Shutter & Concrete pouring up to RF FL level • Shelter Block - Substructure – Waterproofing & Backfilling works. • Shelter Block - Superstructure - RCC wall to progress GF & 1FL • Shelter Block - Surface Preparation & Application of CFRP • Shelter Block - Roof Slab Strengthening works to progress | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 12271635.5944 | 180000 | https://drive.google.com/thumbnail?id=1W-gf0VbzbihbaBDbivu-eAIuFgmf1g2H&sz=w1000 | https://drive.google.com/file/d/1W-gf0VbzbihbaBDbivu-eAIuFgmf1g2H/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hqFUNz-YrJL1D-KF62ciGzKLn0jl5v4Y&sz=w1000 | https://drive.google.com/file/d/1hqFUNz-YrJL1D-KF62ciGzKLn0jl5v4Y/view?usp=drive_link | https://drive.google.com/thumbnail?id=1EFP77JsHwvOLRKb7NL4f0-WTRLI4zmhV&sz=w1000 | https://drive.google.com/file/d/1EFP77JsHwvOLRKb7NL4f0-WTRLI4zmhV/view?usp=drive_link
2024-09-13 | Al Shahama-School-P17 | P17 | SC-02 | 362 | 185 | 547 | • Annex Building - 1FF Slab - Staging & Shutter fixing100% Completed; Rebar Fixing 79% Completed • School Building - GF - RCC Wall Concrete 68% Completed, FF - Rebar Fixing 90% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 28.92% | 28.93% | 0.01% | Annex Substructure | 2024-08-07 | 2024-07-04 |  | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – FF Slab work & FF Wall Rebar, Shutter & Concrete pouring up to RF FL level • Shelter Block - Substructure – Waterproofing & Backfilling works. • Shelter Block - Superstructure - RCC wall to progress GF & 1FL • Shelter Block - Surface Preparation & Application of CFRP • Shelter Block - Roof Slab Strengthening works to progress | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 12271635.5944 | 180000 | https://drive.google.com/thumbnail?id=1W-gf0VbzbihbaBDbivu-eAIuFgmf1g2H&sz=w1000 | https://drive.google.com/file/d/1W-gf0VbzbihbaBDbivu-eAIuFgmf1g2H/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hqFUNz-YrJL1D-KF62ciGzKLn0jl5v4Y&sz=w1000 | https://drive.google.com/file/d/1hqFUNz-YrJL1D-KF62ciGzKLn0jl5v4Y/view?usp=drive_link | https://drive.google.com/thumbnail?id=1EFP77JsHwvOLRKb7NL4f0-WTRLI4zmhV&sz=w1000 | https://drive.google.com/file/d/1EFP77JsHwvOLRKb7NL4f0-WTRLI4zmhV/view?usp=drive_link
2024-09-13 | Al Shahama-School-P17 | P17 | SC-02 | 362 | 185 | 547 | • Annex Building - 1FF Slab - Staging & Shutter fixing100% Completed; Rebar Fixing 79% Completed • School Building - GF - RCC Wall Concrete 68% Completed, FF - Rebar Fixing 90% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 28.92% | 28.93% | 0.01% | Annex Superstructure | 2024-10-31 |  | 2024-11-02 | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – FF Slab work & FF Wall Rebar, Shutter & Concrete pouring up to RF FL level • Shelter Block - Substructure – Waterproofing & Backfilling works. • Shelter Block - Superstructure - RCC wall to progress GF & 1FL • Shelter Block - Surface Preparation & Application of CFRP • Shelter Block - Roof Slab Strengthening works to progress | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 12271635.5944 | 180000 | https://drive.google.com/thumbnail?id=1W-gf0VbzbihbaBDbivu-eAIuFgmf1g2H&sz=w1000 | https://drive.google.com/file/d/1W-gf0VbzbihbaBDbivu-eAIuFgmf1g2H/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hqFUNz-YrJL1D-KF62ciGzKLn0jl5v4Y&sz=w1000 | https://drive.google.com/file/d/1hqFUNz-YrJL1D-KF62ciGzKLn0jl5v4Y/view?usp=drive_link | https://drive.google.com/thumbnail?id=1EFP77JsHwvOLRKb7NL4f0-WTRLI4zmhV&sz=w1000 | https://drive.google.com/file/d/1EFP77JsHwvOLRKb7NL4f0-WTRLI4zmhV/view?usp=drive_link
2024-09-13 | Al Shahama-School-P17 | P17 | SC-02 | 362 | 185 | 547 | • Annex Building - 1FF Slab - Staging & Shutter fixing100% Completed; Rebar Fixing 79% Completed • School Building - GF - RCC Wall Concrete 68% Completed, FF - Rebar Fixing 90% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 28.92% | 28.93% | 0.01% | MEP & Finishes | 2025-01-25 |  | 2025-05-06 | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – FF Slab work & FF Wall Rebar, Shutter & Concrete pouring up to RF FL level • Shelter Block - Substructure – Waterproofing & Backfilling works. • Shelter Block - Superstructure - RCC wall to progress GF & 1FL • Shelter Block - Surface Preparation & Application of CFRP • Shelter Block - Roof Slab Strengthening works to progress | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 12271635.5944 | 180000 | https://drive.google.com/thumbnail?id=1W-gf0VbzbihbaBDbivu-eAIuFgmf1g2H&sz=w1000 | https://drive.google.com/file/d/1W-gf0VbzbihbaBDbivu-eAIuFgmf1g2H/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hqFUNz-YrJL1D-KF62ciGzKLn0jl5v4Y&sz=w1000 | https://drive.google.com/file/d/1hqFUNz-YrJL1D-KF62ciGzKLn0jl5v4Y/view?usp=drive_link | https://drive.google.com/thumbnail?id=1EFP77JsHwvOLRKb7NL4f0-WTRLI4zmhV&sz=w1000 | https://drive.google.com/file/d/1EFP77JsHwvOLRKb7NL4f0-WTRLI4zmhV/view?usp=drive_link
2024-09-13 | Al Shahama-School-P17 | P17 | SC-02 | 362 | 185 | 547 | • Annex Building - 1FF Slab - Staging & Shutter fixing100% Completed; Rebar Fixing 79% Completed • School Building - GF - RCC Wall Concrete 68% Completed, FF - Rebar Fixing 90% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 28.92% | 28.93% | 0.01% | BCC Inspection | 2025-02-13 |  | 2025-05-26 | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – FF Slab work & FF Wall Rebar, Shutter & Concrete pouring up to RF FL level • Shelter Block - Substructure – Waterproofing & Backfilling works. • Shelter Block - Superstructure - RCC wall to progress GF & 1FL • Shelter Block - Surface Preparation & Application of CFRP • Shelter Block - Roof Slab Strengthening works to progress | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 12271635.5944 | 180000 | https://drive.google.com/thumbnail?id=1W-gf0VbzbihbaBDbivu-eAIuFgmf1g2H&sz=w1000 | https://drive.google.com/file/d/1W-gf0VbzbihbaBDbivu-eAIuFgmf1g2H/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hqFUNz-YrJL1D-KF62ciGzKLn0jl5v4Y&sz=w1000 | https://drive.google.com/file/d/1hqFUNz-YrJL1D-KF62ciGzKLn0jl5v4Y/view?usp=drive_link | https://drive.google.com/thumbnail?id=1EFP77JsHwvOLRKb7NL4f0-WTRLI4zmhV&sz=w1000 | https://drive.google.com/file/d/1EFP77JsHwvOLRKb7NL4f0-WTRLI4zmhV/view?usp=drive_link
2024-09-13 | Al Shahama-School-P17 | P17 | SC-02 | 362 | 185 | 547 | • Annex Building - 1FF Slab - Staging & Shutter fixing100% Completed; Rebar Fixing 79% Completed • School Building - GF - RCC Wall Concrete 68% Completed, FF - Rebar Fixing 90% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 28.92% | 28.93% | 0.01% | BCC Issuance | 2025-03-04 |  | 2025-06-16 | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – FF Slab work & FF Wall Rebar, Shutter & Concrete pouring up to RF FL level • Shelter Block - Substructure – Waterproofing & Backfilling works. • Shelter Block - Superstructure - RCC wall to progress GF & 1FL • Shelter Block - Surface Preparation & Application of CFRP • Shelter Block - Roof Slab Strengthening works to progress | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 12271635.5944 | 180000 | https://drive.google.com/thumbnail?id=1W-gf0VbzbihbaBDbivu-eAIuFgmf1g2H&sz=w1000 | https://drive.google.com/file/d/1W-gf0VbzbihbaBDbivu-eAIuFgmf1g2H/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hqFUNz-YrJL1D-KF62ciGzKLn0jl5v4Y&sz=w1000 | https://drive.google.com/file/d/1hqFUNz-YrJL1D-KF62ciGzKLn0jl5v4Y/view?usp=drive_link | https://drive.google.com/thumbnail?id=1EFP77JsHwvOLRKb7NL4f0-WTRLI4zmhV&sz=w1000 | https://drive.google.com/file/d/1EFP77JsHwvOLRKb7NL4f0-WTRLI4zmhV/view?usp=drive_link
2024-09-13 | Al Shahama-School-P17 | P17 | SC-02 | 362 | 185 | 547 | • Annex Building - 1FF Slab - Staging & Shutter fixing100% Completed; Rebar Fixing 79% Completed • School Building - GF - RCC Wall Concrete 68% Completed, FF - Rebar Fixing 90% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 28.92% | 28.93% | 0.01% | Completion | 2025-03-17 |  | 2025-06-30 | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – FF Slab work & FF Wall Rebar, Shutter & Concrete pouring up to RF FL level • Shelter Block - Substructure – Waterproofing & Backfilling works. • Shelter Block - Superstructure - RCC wall to progress GF & 1FL • Shelter Block - Surface Preparation & Application of CFRP • Shelter Block - Roof Slab Strengthening works to progress | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 12271635.5944 | 180000 | https://drive.google.com/thumbnail?id=1W-gf0VbzbihbaBDbivu-eAIuFgmf1g2H&sz=w1000 | https://drive.google.com/file/d/1W-gf0VbzbihbaBDbivu-eAIuFgmf1g2H/view?usp=drive_link | https://drive.google.com/thumbnail?id=1hqFUNz-YrJL1D-KF62ciGzKLn0jl5v4Y&sz=w1000 | https://drive.google.com/file/d/1hqFUNz-YrJL1D-KF62ciGzKLn0jl5v4Y/view?usp=drive_link | https://drive.google.com/thumbnail?id=1EFP77JsHwvOLRKb7NL4f0-WTRLI4zmhV&sz=w1000 | https://drive.google.com/file/d/1EFP77JsHwvOLRKb7NL4f0-WTRLI4zmhV/view?usp=drive_link
2024-09-13 | Al Sarouj-School-P2 | P2 | SC-03 | 289 | 258 | 547 | • Annex Building - Superstructure – Ground Floor RCC Wall 80% Completed; FF Slab Staging work 20% completed • School Building - RCC Wall Concrete Upto Plinth 98% completed • School Building - GF Wall Rebar Fixing – 32%; Concrete Pouring 12% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 10.92% | 19.23% | 8.31% | Notice to Commence | 2023-11-30 | 2023-11-30 |  | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab & Beam Works to progress • Annex Building - Superstructure works – RCC wall up to FF level to progress; FF Slab Works • Shelter Block - Substructure –works to complete • Shelter Block - Superstructure – RCC Wall work GF & FF Level • Shelter Block - Surface Preparation for CRFP works to progress | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 10955306.883 | 180000 | https://drive.google.com/thumbnail?id=1_Jil7Wkfj5WOP-6FE-VdY7qc0mLZ5DUM&sz=w1000 | https://drive.google.com/file/d/1_Jil7Wkfj5WOP-6FE-VdY7qc0mLZ5DUM/view?usp=drive_link | https://drive.google.com/thumbnail?id=1U_VfOs-qUWoEMVHPtt9sq2AZH--X8AwT&sz=w1000 | https://drive.google.com/file/d/1U_VfOs-qUWoEMVHPtt9sq2AZH--X8AwT/view?usp=drive_link | https://drive.google.com/thumbnail?id=1VU2oD951xXfxe0_lC75k2-XwxUlhDyj9&sz=w1000 | https://drive.google.com/file/d/1VU2oD951xXfxe0_lC75k2-XwxUlhDyj9/view?usp=drive_link
2024-09-13 | Al Sarouj-School-P2 | P2 | SC-03 | 289 | 258 | 547 | • Annex Building - Superstructure – Ground Floor RCC Wall 80% Completed; FF Slab Staging work 20% completed • School Building - RCC Wall Concrete Upto Plinth 98% completed • School Building - GF Wall Rebar Fixing – 32%; Concrete Pouring 12% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 10.92% | 19.23% | 8.31% | Site Mobilization | 2024-01-05 | 2024-01-06 |  | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab & Beam Works to progress • Annex Building - Superstructure works – RCC wall up to FF level to progress; FF Slab Works • Shelter Block - Substructure –works to complete • Shelter Block - Superstructure – RCC Wall work GF & FF Level • Shelter Block - Surface Preparation for CRFP works to progress | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 10955306.883 | 180000 | https://drive.google.com/thumbnail?id=1_Jil7Wkfj5WOP-6FE-VdY7qc0mLZ5DUM&sz=w1000 | https://drive.google.com/file/d/1_Jil7Wkfj5WOP-6FE-VdY7qc0mLZ5DUM/view?usp=drive_link | https://drive.google.com/thumbnail?id=1U_VfOs-qUWoEMVHPtt9sq2AZH--X8AwT&sz=w1000 | https://drive.google.com/file/d/1U_VfOs-qUWoEMVHPtt9sq2AZH--X8AwT/view?usp=drive_link | https://drive.google.com/thumbnail?id=1VU2oD951xXfxe0_lC75k2-XwxUlhDyj9&sz=w1000 | https://drive.google.com/file/d/1VU2oD951xXfxe0_lC75k2-XwxUlhDyj9/view?usp=drive_link
2024-09-13 | Al Sarouj-School-P2 | P2 | SC-03 | 289 | 258 | 547 | • Annex Building - Superstructure – Ground Floor RCC Wall 80% Completed; FF Slab Staging work 20% completed • School Building - RCC Wall Concrete Upto Plinth 98% completed • School Building - GF Wall Rebar Fixing – 32%; Concrete Pouring 12% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 10.92% | 19.23% | 8.31% | Building Permit | 2024-07-29 | 2024-06-20 |  | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab & Beam Works to progress • Annex Building - Superstructure works – RCC wall up to FF level to progress; FF Slab Works • Shelter Block - Substructure –works to complete • Shelter Block - Superstructure – RCC Wall work GF & FF Level • Shelter Block - Surface Preparation for CRFP works to progress | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 10955306.883 | 180000 | https://drive.google.com/thumbnail?id=1_Jil7Wkfj5WOP-6FE-VdY7qc0mLZ5DUM&sz=w1000 | https://drive.google.com/file/d/1_Jil7Wkfj5WOP-6FE-VdY7qc0mLZ5DUM/view?usp=drive_link | https://drive.google.com/thumbnail?id=1U_VfOs-qUWoEMVHPtt9sq2AZH--X8AwT&sz=w1000 | https://drive.google.com/file/d/1U_VfOs-qUWoEMVHPtt9sq2AZH--X8AwT/view?usp=drive_link | https://drive.google.com/thumbnail?id=1VU2oD951xXfxe0_lC75k2-XwxUlhDyj9&sz=w1000 | https://drive.google.com/file/d/1VU2oD951xXfxe0_lC75k2-XwxUlhDyj9/view?usp=drive_link
2024-09-13 | Al Sarouj-School-P2 | P2 | SC-03 | 289 | 258 | 547 | • Annex Building - Superstructure – Ground Floor RCC Wall 80% Completed; FF Slab Staging work 20% completed • School Building - RCC Wall Concrete Upto Plinth 98% completed • School Building - GF Wall Rebar Fixing – 32%; Concrete Pouring 12% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 10.92% | 19.23% | 8.31% | School Substructure | 2024-10-14 |  | 2024-09-27 | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab & Beam Works to progress • Annex Building - Superstructure works – RCC wall up to FF level to progress; FF Slab Works • Shelter Block - Substructure –works to complete • Shelter Block - Superstructure – RCC Wall work GF & FF Level • Shelter Block - Surface Preparation for CRFP works to progress | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 10955306.883 | 180000 | https://drive.google.com/thumbnail?id=1_Jil7Wkfj5WOP-6FE-VdY7qc0mLZ5DUM&sz=w1000 | https://drive.google.com/file/d/1_Jil7Wkfj5WOP-6FE-VdY7qc0mLZ5DUM/view?usp=drive_link | https://drive.google.com/thumbnail?id=1U_VfOs-qUWoEMVHPtt9sq2AZH--X8AwT&sz=w1000 | https://drive.google.com/file/d/1U_VfOs-qUWoEMVHPtt9sq2AZH--X8AwT/view?usp=drive_link | https://drive.google.com/thumbnail?id=1VU2oD951xXfxe0_lC75k2-XwxUlhDyj9&sz=w1000 | https://drive.google.com/file/d/1VU2oD951xXfxe0_lC75k2-XwxUlhDyj9/view?usp=drive_link
2024-09-13 | Al Sarouj-School-P2 | P2 | SC-03 | 289 | 258 | 547 | • Annex Building - Superstructure – Ground Floor RCC Wall 80% Completed; FF Slab Staging work 20% completed • School Building - RCC Wall Concrete Upto Plinth 98% completed • School Building - GF Wall Rebar Fixing – 32%; Concrete Pouring 12% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 10.92% | 19.23% | 8.31% | School Superstructure | 2025-01-20 |  | 2024-10-30 | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab & Beam Works to progress • Annex Building - Superstructure works – RCC wall up to FF level to progress; FF Slab Works • Shelter Block - Substructure –works to complete • Shelter Block - Superstructure – RCC Wall work GF & FF Level • Shelter Block - Surface Preparation for CRFP works to progress | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 10955306.883 | 180000 | https://drive.google.com/thumbnail?id=1_Jil7Wkfj5WOP-6FE-VdY7qc0mLZ5DUM&sz=w1000 | https://drive.google.com/file/d/1_Jil7Wkfj5WOP-6FE-VdY7qc0mLZ5DUM/view?usp=drive_link | https://drive.google.com/thumbnail?id=1U_VfOs-qUWoEMVHPtt9sq2AZH--X8AwT&sz=w1000 | https://drive.google.com/file/d/1U_VfOs-qUWoEMVHPtt9sq2AZH--X8AwT/view?usp=drive_link | https://drive.google.com/thumbnail?id=1VU2oD951xXfxe0_lC75k2-XwxUlhDyj9&sz=w1000 | https://drive.google.com/file/d/1VU2oD951xXfxe0_lC75k2-XwxUlhDyj9/view?usp=drive_link
2024-09-13 | Al Sarouj-School-P2 | P2 | SC-03 | 289 | 258 | 547 | • Annex Building - Superstructure – Ground Floor RCC Wall 80% Completed; FF Slab Staging work 20% completed • School Building - RCC Wall Concrete Upto Plinth 98% completed • School Building - GF Wall Rebar Fixing – 32%; Concrete Pouring 12% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 10.92% | 19.23% | 8.31% | Annex Substructure | 2024-10-15 | 2024-06-29 |  | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab & Beam Works to progress • Annex Building - Superstructure works – RCC wall up to FF level to progress; FF Slab Works • Shelter Block - Substructure –works to complete • Shelter Block - Superstructure – RCC Wall work GF & FF Level • Shelter Block - Surface Preparation for CRFP works to progress | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 10955306.883 | 180000 | https://drive.google.com/thumbnail?id=1_Jil7Wkfj5WOP-6FE-VdY7qc0mLZ5DUM&sz=w1000 | https://drive.google.com/file/d/1_Jil7Wkfj5WOP-6FE-VdY7qc0mLZ5DUM/view?usp=drive_link | https://drive.google.com/thumbnail?id=1U_VfOs-qUWoEMVHPtt9sq2AZH--X8AwT&sz=w1000 | https://drive.google.com/file/d/1U_VfOs-qUWoEMVHPtt9sq2AZH--X8AwT/view?usp=drive_link | https://drive.google.com/thumbnail?id=1VU2oD951xXfxe0_lC75k2-XwxUlhDyj9&sz=w1000 | https://drive.google.com/file/d/1VU2oD951xXfxe0_lC75k2-XwxUlhDyj9/view?usp=drive_link
2024-09-13 | Al Sarouj-School-P2 | P2 | SC-03 | 289 | 258 | 547 | • Annex Building - Superstructure – Ground Floor RCC Wall 80% Completed; FF Slab Staging work 20% completed • School Building - RCC Wall Concrete Upto Plinth 98% completed • School Building - GF Wall Rebar Fixing – 32%; Concrete Pouring 12% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 10.92% | 19.23% | 8.31% | Annex Superstructure | 2025-01-14 |  | 2024-11-08 | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab & Beam Works to progress • Annex Building - Superstructure works – RCC wall up to FF level to progress; FF Slab Works • Shelter Block - Substructure –works to complete • Shelter Block - Superstructure – RCC Wall work GF & FF Level • Shelter Block - Surface Preparation for CRFP works to progress | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 10955306.883 | 180000 | https://drive.google.com/thumbnail?id=1_Jil7Wkfj5WOP-6FE-VdY7qc0mLZ5DUM&sz=w1000 | https://drive.google.com/file/d/1_Jil7Wkfj5WOP-6FE-VdY7qc0mLZ5DUM/view?usp=drive_link | https://drive.google.com/thumbnail?id=1U_VfOs-qUWoEMVHPtt9sq2AZH--X8AwT&sz=w1000 | https://drive.google.com/file/d/1U_VfOs-qUWoEMVHPtt9sq2AZH--X8AwT/view?usp=drive_link | https://drive.google.com/thumbnail?id=1VU2oD951xXfxe0_lC75k2-XwxUlhDyj9&sz=w1000 | https://drive.google.com/file/d/1VU2oD951xXfxe0_lC75k2-XwxUlhDyj9/view?usp=drive_link
2024-09-13 | Al Sarouj-School-P2 | P2 | SC-03 | 289 | 258 | 547 | • Annex Building - Superstructure – Ground Floor RCC Wall 80% Completed; FF Slab Staging work 20% completed • School Building - RCC Wall Concrete Upto Plinth 98% completed • School Building - GF Wall Rebar Fixing – 32%; Concrete Pouring 12% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 10.92% | 19.23% | 8.31% | MEP & Finishes | 2025-04-10 |  | 2025-05-06 | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab & Beam Works to progress • Annex Building - Superstructure works – RCC wall up to FF level to progress; FF Slab Works • Shelter Block - Substructure –works to complete • Shelter Block - Superstructure – RCC Wall work GF & FF Level • Shelter Block - Surface Preparation for CRFP works to progress | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 10955306.883 | 180000 | https://drive.google.com/thumbnail?id=1_Jil7Wkfj5WOP-6FE-VdY7qc0mLZ5DUM&sz=w1000 | https://drive.google.com/file/d/1_Jil7Wkfj5WOP-6FE-VdY7qc0mLZ5DUM/view?usp=drive_link | https://drive.google.com/thumbnail?id=1U_VfOs-qUWoEMVHPtt9sq2AZH--X8AwT&sz=w1000 | https://drive.google.com/file/d/1U_VfOs-qUWoEMVHPtt9sq2AZH--X8AwT/view?usp=drive_link | https://drive.google.com/thumbnail?id=1VU2oD951xXfxe0_lC75k2-XwxUlhDyj9&sz=w1000 | https://drive.google.com/file/d/1VU2oD951xXfxe0_lC75k2-XwxUlhDyj9/view?usp=drive_link
2024-09-13 | Al Sarouj-School-P2 | P2 | SC-03 | 289 | 258 | 547 | • Annex Building - Superstructure – Ground Floor RCC Wall 80% Completed; FF Slab Staging work 20% completed • School Building - RCC Wall Concrete Upto Plinth 98% completed • School Building - GF Wall Rebar Fixing – 32%; Concrete Pouring 12% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 10.92% | 19.23% | 8.31% | BCC Inspection | 2025-04-29 |  | 2025-05-26 | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab & Beam Works to progress • Annex Building - Superstructure works – RCC wall up to FF level to progress; FF Slab Works • Shelter Block - Substructure –works to complete • Shelter Block - Superstructure – RCC Wall work GF & FF Level • Shelter Block - Surface Preparation for CRFP works to progress | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 10955306.883 | 180000 | https://drive.google.com/thumbnail?id=1_Jil7Wkfj5WOP-6FE-VdY7qc0mLZ5DUM&sz=w1000 | https://drive.google.com/file/d/1_Jil7Wkfj5WOP-6FE-VdY7qc0mLZ5DUM/view?usp=drive_link | https://drive.google.com/thumbnail?id=1U_VfOs-qUWoEMVHPtt9sq2AZH--X8AwT&sz=w1000 | https://drive.google.com/file/d/1U_VfOs-qUWoEMVHPtt9sq2AZH--X8AwT/view?usp=drive_link | https://drive.google.com/thumbnail?id=1VU2oD951xXfxe0_lC75k2-XwxUlhDyj9&sz=w1000 | https://drive.google.com/file/d/1VU2oD951xXfxe0_lC75k2-XwxUlhDyj9/view?usp=drive_link
2024-09-13 | Al Sarouj-School-P2 | P2 | SC-03 | 289 | 258 | 547 | • Annex Building - Superstructure – Ground Floor RCC Wall 80% Completed; FF Slab Staging work 20% completed • School Building - RCC Wall Concrete Upto Plinth 98% completed • School Building - GF Wall Rebar Fixing – 32%; Concrete Pouring 12% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 10.92% | 19.23% | 8.31% | BCC Issuance | 2025-05-16 |  | 2025-06-16 | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab & Beam Works to progress • Annex Building - Superstructure works – RCC wall up to FF level to progress; FF Slab Works • Shelter Block - Substructure –works to complete • Shelter Block - Superstructure – RCC Wall work GF & FF Level • Shelter Block - Surface Preparation for CRFP works to progress | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 10955306.883 | 180000 | https://drive.google.com/thumbnail?id=1_Jil7Wkfj5WOP-6FE-VdY7qc0mLZ5DUM&sz=w1000 | https://drive.google.com/file/d/1_Jil7Wkfj5WOP-6FE-VdY7qc0mLZ5DUM/view?usp=drive_link | https://drive.google.com/thumbnail?id=1U_VfOs-qUWoEMVHPtt9sq2AZH--X8AwT&sz=w1000 | https://drive.google.com/file/d/1U_VfOs-qUWoEMVHPtt9sq2AZH--X8AwT/view?usp=drive_link | https://drive.google.com/thumbnail?id=1VU2oD951xXfxe0_lC75k2-XwxUlhDyj9&sz=w1000 | https://drive.google.com/file/d/1VU2oD951xXfxe0_lC75k2-XwxUlhDyj9/view?usp=drive_link
2024-09-13 | Al Sarouj-School-P2 | P2 | SC-03 | 289 | 258 | 547 | • Annex Building - Superstructure – Ground Floor RCC Wall 80% Completed; FF Slab Staging work 20% completed • School Building - RCC Wall Concrete Upto Plinth 98% completed • School Building - GF Wall Rebar Fixing – 32%; Concrete Pouring 12% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 10.92% | 19.23% | 8.31% | Completion | 2025-05-29 |  | 2025-06-30 | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab & Beam Works to progress • Annex Building - Superstructure works – RCC wall up to FF level to progress; FF Slab Works • Shelter Block - Substructure –works to complete • Shelter Block - Superstructure – RCC Wall work GF & FF Level • Shelter Block - Surface Preparation for CRFP works to progress | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 10955306.883 | 180000 | https://drive.google.com/thumbnail?id=1_Jil7Wkfj5WOP-6FE-VdY7qc0mLZ5DUM&sz=w1000 | https://drive.google.com/file/d/1_Jil7Wkfj5WOP-6FE-VdY7qc0mLZ5DUM/view?usp=drive_link | https://drive.google.com/thumbnail?id=1U_VfOs-qUWoEMVHPtt9sq2AZH--X8AwT&sz=w1000 | https://drive.google.com/file/d/1U_VfOs-qUWoEMVHPtt9sq2AZH--X8AwT/view?usp=drive_link | https://drive.google.com/thumbnail?id=1VU2oD951xXfxe0_lC75k2-XwxUlhDyj9&sz=w1000 | https://drive.google.com/file/d/1VU2oD951xXfxe0_lC75k2-XwxUlhDyj9/view?usp=drive_link
2024-09-13 | Al Sarouj-School-P16 | P16 | SC-04 | 362 | 185 | 547 | • Annex Building -Grade Slab work PCC in progress; GF Wall Rebar fixing - 10% completed • GF RCC wall Rebar & Shutter fabrication ongoing • School Building - Plinth wall 97% completed; GF RCC Wall Rebar Fixing 25% done | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 28.92% | 16.2% | -12.72% | Notice to Commence | 2023-09-18 | 2023-09-26 |  | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure works to complete • Annex Building - Superstructure – GF RCC Wall works to progress • Shelter Block - Substructure – Plinth Wall construction to complete. • Shelter Block - GF – Rebar Fixing for Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 10206907.2387 | 180000 | https://drive.google.com/thumbnail?id=1XjKaIIKxhd8oZqb19P6albr-80-RL-hK&sz=w1000 | https://drive.google.com/file/d/1XjKaIIKxhd8oZqb19P6albr-80-RL-hK/view?usp=drive_link | https://drive.google.com/thumbnail?id=1eggsoLAPcrdATW-qSGgu_m3YksjLLiJO&sz=w1000 | https://drive.google.com/file/d/1eggsoLAPcrdATW-qSGgu_m3YksjLLiJO/view?usp=drive_link | https://drive.google.com/thumbnail?id=1-kULF92O7kA2Vy-9i1BZzi1_0bIC323S&sz=w1000 | https://drive.google.com/file/d/1-kULF92O7kA2Vy-9i1BZzi1_0bIC323S/view?usp=drive_link
2024-09-13 | Al Sarouj-School-P16 | P16 | SC-04 | 362 | 185 | 547 | • Annex Building -Grade Slab work PCC in progress; GF Wall Rebar fixing - 10% completed • GF RCC wall Rebar & Shutter fabrication ongoing • School Building - Plinth wall 97% completed; GF RCC Wall Rebar Fixing 25% done | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 28.92% | 16.2% | -12.72% | Site Mobilization | 2023-10-21 | 2024-01-06 |  | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure works to complete • Annex Building - Superstructure – GF RCC Wall works to progress • Shelter Block - Substructure – Plinth Wall construction to complete. • Shelter Block - GF – Rebar Fixing for Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 10206907.2387 | 180000 | https://drive.google.com/thumbnail?id=1XjKaIIKxhd8oZqb19P6albr-80-RL-hK&sz=w1000 | https://drive.google.com/file/d/1XjKaIIKxhd8oZqb19P6albr-80-RL-hK/view?usp=drive_link | https://drive.google.com/thumbnail?id=1eggsoLAPcrdATW-qSGgu_m3YksjLLiJO&sz=w1000 | https://drive.google.com/file/d/1eggsoLAPcrdATW-qSGgu_m3YksjLLiJO/view?usp=drive_link | https://drive.google.com/thumbnail?id=1-kULF92O7kA2Vy-9i1BZzi1_0bIC323S&sz=w1000 | https://drive.google.com/file/d/1-kULF92O7kA2Vy-9i1BZzi1_0bIC323S/view?usp=drive_link
2024-09-13 | Al Sarouj-School-P16 | P16 | SC-04 | 362 | 185 | 547 | • Annex Building -Grade Slab work PCC in progress; GF Wall Rebar fixing - 10% completed • GF RCC wall Rebar & Shutter fabrication ongoing • School Building - Plinth wall 97% completed; GF RCC Wall Rebar Fixing 25% done | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 28.92% | 16.2% | -12.72% | Building Permit | 2024-05-17 | 2024-06-20 |  | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure works to complete • Annex Building - Superstructure – GF RCC Wall works to progress • Shelter Block - Substructure – Plinth Wall construction to complete. • Shelter Block - GF – Rebar Fixing for Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 10206907.2387 | 180000 | https://drive.google.com/thumbnail?id=1XjKaIIKxhd8oZqb19P6albr-80-RL-hK&sz=w1000 | https://drive.google.com/file/d/1XjKaIIKxhd8oZqb19P6albr-80-RL-hK/view?usp=drive_link | https://drive.google.com/thumbnail?id=1eggsoLAPcrdATW-qSGgu_m3YksjLLiJO&sz=w1000 | https://drive.google.com/file/d/1eggsoLAPcrdATW-qSGgu_m3YksjLLiJO/view?usp=drive_link | https://drive.google.com/thumbnail?id=1-kULF92O7kA2Vy-9i1BZzi1_0bIC323S&sz=w1000 | https://drive.google.com/file/d/1-kULF92O7kA2Vy-9i1BZzi1_0bIC323S/view?usp=drive_link
2024-09-13 | Al Sarouj-School-P16 | P16 | SC-04 | 362 | 185 | 547 | • Annex Building -Grade Slab work PCC in progress; GF Wall Rebar fixing - 10% completed • GF RCC wall Rebar & Shutter fabrication ongoing • School Building - Plinth wall 97% completed; GF RCC Wall Rebar Fixing 25% done | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 28.92% | 16.2% | -12.72% | School Substructure | 2024-08-06 |  | 2024-09-27 | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure works to complete • Annex Building - Superstructure – GF RCC Wall works to progress • Shelter Block - Substructure – Plinth Wall construction to complete. • Shelter Block - GF – Rebar Fixing for Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 10206907.2387 | 180000 | https://drive.google.com/thumbnail?id=1XjKaIIKxhd8oZqb19P6albr-80-RL-hK&sz=w1000 | https://drive.google.com/file/d/1XjKaIIKxhd8oZqb19P6albr-80-RL-hK/view?usp=drive_link | https://drive.google.com/thumbnail?id=1eggsoLAPcrdATW-qSGgu_m3YksjLLiJO&sz=w1000 | https://drive.google.com/file/d/1eggsoLAPcrdATW-qSGgu_m3YksjLLiJO/view?usp=drive_link | https://drive.google.com/thumbnail?id=1-kULF92O7kA2Vy-9i1BZzi1_0bIC323S&sz=w1000 | https://drive.google.com/file/d/1-kULF92O7kA2Vy-9i1BZzi1_0bIC323S/view?usp=drive_link
2024-09-13 | Al Sarouj-School-P16 | P16 | SC-04 | 362 | 185 | 547 | • Annex Building -Grade Slab work PCC in progress; GF Wall Rebar fixing - 10% completed • GF RCC wall Rebar & Shutter fabrication ongoing • School Building - Plinth wall 97% completed; GF RCC Wall Rebar Fixing 25% done | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 28.92% | 16.2% | -12.72% | School Superstructure | 2024-11-07 |  | 2024-10-30 | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure works to complete • Annex Building - Superstructure – GF RCC Wall works to progress • Shelter Block - Substructure – Plinth Wall construction to complete. • Shelter Block - GF – Rebar Fixing for Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 10206907.2387 | 180000 | https://drive.google.com/thumbnail?id=1XjKaIIKxhd8oZqb19P6albr-80-RL-hK&sz=w1000 | https://drive.google.com/file/d/1XjKaIIKxhd8oZqb19P6albr-80-RL-hK/view?usp=drive_link | https://drive.google.com/thumbnail?id=1eggsoLAPcrdATW-qSGgu_m3YksjLLiJO&sz=w1000 | https://drive.google.com/file/d/1eggsoLAPcrdATW-qSGgu_m3YksjLLiJO/view?usp=drive_link | https://drive.google.com/thumbnail?id=1-kULF92O7kA2Vy-9i1BZzi1_0bIC323S&sz=w1000 | https://drive.google.com/file/d/1-kULF92O7kA2Vy-9i1BZzi1_0bIC323S/view?usp=drive_link
2024-09-13 | Al Sarouj-School-P16 | P16 | SC-04 | 362 | 185 | 547 | • Annex Building -Grade Slab work PCC in progress; GF Wall Rebar fixing - 10% completed • GF RCC wall Rebar & Shutter fabrication ongoing • School Building - Plinth wall 97% completed; GF RCC Wall Rebar Fixing 25% done | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 28.92% | 16.2% | -12.72% | Annex Substructure | 2024-08-07 | 2024-09-06 |  | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure works to complete • Annex Building - Superstructure – GF RCC Wall works to progress • Shelter Block - Substructure – Plinth Wall construction to complete. • Shelter Block - GF – Rebar Fixing for Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 10206907.2387 | 180000 | https://drive.google.com/thumbnail?id=1XjKaIIKxhd8oZqb19P6albr-80-RL-hK&sz=w1000 | https://drive.google.com/file/d/1XjKaIIKxhd8oZqb19P6albr-80-RL-hK/view?usp=drive_link | https://drive.google.com/thumbnail?id=1eggsoLAPcrdATW-qSGgu_m3YksjLLiJO&sz=w1000 | https://drive.google.com/file/d/1eggsoLAPcrdATW-qSGgu_m3YksjLLiJO/view?usp=drive_link | https://drive.google.com/thumbnail?id=1-kULF92O7kA2Vy-9i1BZzi1_0bIC323S&sz=w1000 | https://drive.google.com/file/d/1-kULF92O7kA2Vy-9i1BZzi1_0bIC323S/view?usp=drive_link
2024-09-13 | Al Sarouj-School-P16 | P16 | SC-04 | 362 | 185 | 547 | • Annex Building -Grade Slab work PCC in progress; GF Wall Rebar fixing - 10% completed • GF RCC wall Rebar & Shutter fabrication ongoing • School Building - Plinth wall 97% completed; GF RCC Wall Rebar Fixing 25% done | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 28.92% | 16.2% | -12.72% | Annex Superstructure | 2024-10-31 |  | 2024-11-27 | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure works to complete • Annex Building - Superstructure – GF RCC Wall works to progress • Shelter Block - Substructure – Plinth Wall construction to complete. • Shelter Block - GF – Rebar Fixing for Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 10206907.2387 | 180000 | https://drive.google.com/thumbnail?id=1XjKaIIKxhd8oZqb19P6albr-80-RL-hK&sz=w1000 | https://drive.google.com/file/d/1XjKaIIKxhd8oZqb19P6albr-80-RL-hK/view?usp=drive_link | https://drive.google.com/thumbnail?id=1eggsoLAPcrdATW-qSGgu_m3YksjLLiJO&sz=w1000 | https://drive.google.com/file/d/1eggsoLAPcrdATW-qSGgu_m3YksjLLiJO/view?usp=drive_link | https://drive.google.com/thumbnail?id=1-kULF92O7kA2Vy-9i1BZzi1_0bIC323S&sz=w1000 | https://drive.google.com/file/d/1-kULF92O7kA2Vy-9i1BZzi1_0bIC323S/view?usp=drive_link
2024-09-13 | Al Sarouj-School-P16 | P16 | SC-04 | 362 | 185 | 547 | • Annex Building -Grade Slab work PCC in progress; GF Wall Rebar fixing - 10% completed • GF RCC wall Rebar & Shutter fabrication ongoing • School Building - Plinth wall 97% completed; GF RCC Wall Rebar Fixing 25% done | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 28.92% | 16.2% | -12.72% | MEP & Finishes | 2025-01-25 |  | 2025-05-06 | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure works to complete • Annex Building - Superstructure – GF RCC Wall works to progress • Shelter Block - Substructure – Plinth Wall construction to complete. • Shelter Block - GF – Rebar Fixing for Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 10206907.2387 | 180000 | https://drive.google.com/thumbnail?id=1XjKaIIKxhd8oZqb19P6albr-80-RL-hK&sz=w1000 | https://drive.google.com/file/d/1XjKaIIKxhd8oZqb19P6albr-80-RL-hK/view?usp=drive_link | https://drive.google.com/thumbnail?id=1eggsoLAPcrdATW-qSGgu_m3YksjLLiJO&sz=w1000 | https://drive.google.com/file/d/1eggsoLAPcrdATW-qSGgu_m3YksjLLiJO/view?usp=drive_link | https://drive.google.com/thumbnail?id=1-kULF92O7kA2Vy-9i1BZzi1_0bIC323S&sz=w1000 | https://drive.google.com/file/d/1-kULF92O7kA2Vy-9i1BZzi1_0bIC323S/view?usp=drive_link
2024-09-13 | Al Sarouj-School-P16 | P16 | SC-04 | 362 | 185 | 547 | • Annex Building -Grade Slab work PCC in progress; GF Wall Rebar fixing - 10% completed • GF RCC wall Rebar & Shutter fabrication ongoing • School Building - Plinth wall 97% completed; GF RCC Wall Rebar Fixing 25% done | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 28.92% | 16.2% | -12.72% | BCC Inspection | 2025-02-13 |  | 2025-05-26 | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure works to complete • Annex Building - Superstructure – GF RCC Wall works to progress • Shelter Block - Substructure – Plinth Wall construction to complete. • Shelter Block - GF – Rebar Fixing for Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 10206907.2387 | 180000 | https://drive.google.com/thumbnail?id=1XjKaIIKxhd8oZqb19P6albr-80-RL-hK&sz=w1000 | https://drive.google.com/file/d/1XjKaIIKxhd8oZqb19P6albr-80-RL-hK/view?usp=drive_link | https://drive.google.com/thumbnail?id=1eggsoLAPcrdATW-qSGgu_m3YksjLLiJO&sz=w1000 | https://drive.google.com/file/d/1eggsoLAPcrdATW-qSGgu_m3YksjLLiJO/view?usp=drive_link | https://drive.google.com/thumbnail?id=1-kULF92O7kA2Vy-9i1BZzi1_0bIC323S&sz=w1000 | https://drive.google.com/file/d/1-kULF92O7kA2Vy-9i1BZzi1_0bIC323S/view?usp=drive_link
2024-09-13 | Al Sarouj-School-P16 | P16 | SC-04 | 362 | 185 | 547 | • Annex Building -Grade Slab work PCC in progress; GF Wall Rebar fixing - 10% completed • GF RCC wall Rebar & Shutter fabrication ongoing • School Building - Plinth wall 97% completed; GF RCC Wall Rebar Fixing 25% done | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 28.92% | 16.2% | -12.72% | BCC Issuance | 2025-03-04 |  | 2025-06-16 | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure works to complete • Annex Building - Superstructure – GF RCC Wall works to progress • Shelter Block - Substructure – Plinth Wall construction to complete. • Shelter Block - GF – Rebar Fixing for Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 10206907.2387 | 180000 | https://drive.google.com/thumbnail?id=1XjKaIIKxhd8oZqb19P6albr-80-RL-hK&sz=w1000 | https://drive.google.com/file/d/1XjKaIIKxhd8oZqb19P6albr-80-RL-hK/view?usp=drive_link | https://drive.google.com/thumbnail?id=1eggsoLAPcrdATW-qSGgu_m3YksjLLiJO&sz=w1000 | https://drive.google.com/file/d/1eggsoLAPcrdATW-qSGgu_m3YksjLLiJO/view?usp=drive_link | https://drive.google.com/thumbnail?id=1-kULF92O7kA2Vy-9i1BZzi1_0bIC323S&sz=w1000 | https://drive.google.com/file/d/1-kULF92O7kA2Vy-9i1BZzi1_0bIC323S/view?usp=drive_link
2024-09-13 | Al Sarouj-School-P16 | P16 | SC-04 | 362 | 185 | 547 | • Annex Building -Grade Slab work PCC in progress; GF Wall Rebar fixing - 10% completed • GF RCC wall Rebar & Shutter fabrication ongoing • School Building - Plinth wall 97% completed; GF RCC Wall Rebar Fixing 25% done | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 28.92% | 16.2% | -12.72% | Completion | 2025-03-17 |  | 2025-06-30 | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure works to complete • Annex Building - Superstructure – GF RCC Wall works to progress • Shelter Block - Substructure – Plinth Wall construction to complete. • Shelter Block - GF – Rebar Fixing for Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 10206907.2387 | 180000 | https://drive.google.com/thumbnail?id=1XjKaIIKxhd8oZqb19P6albr-80-RL-hK&sz=w1000 | https://drive.google.com/file/d/1XjKaIIKxhd8oZqb19P6albr-80-RL-hK/view?usp=drive_link | https://drive.google.com/thumbnail?id=1eggsoLAPcrdATW-qSGgu_m3YksjLLiJO&sz=w1000 | https://drive.google.com/file/d/1eggsoLAPcrdATW-qSGgu_m3YksjLLiJO/view?usp=drive_link | https://drive.google.com/thumbnail?id=1-kULF92O7kA2Vy-9i1BZzi1_0bIC323S&sz=w1000 | https://drive.google.com/file/d/1-kULF92O7kA2Vy-9i1BZzi1_0bIC323S/view?usp=drive_link
2024-09-13 | Al Sila-School-P43 | P43 | SC-05 | 362 | 185 | 547 | • Annex Building - GF - RCC Wall Rebar Fixing 94% completed; GF RCC Wall Concrete Cast - 55% Completed • School Building - RCC Plinth Wall - 98% Completed, GF Wall Rebar Fixing 28% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 28.92% | 20.35% | -8.57% | Notice to Commence | 2023-09-18 | 2023-09-26 |  | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works to Complete • Annex Building - Superstructure works – GF RCC Wall works & FF Slab Works • Shelter Block - RCC Plinth Wall & GF Wall Works to progress • Shelter Block - Roof Slab Strenthening Works to progress • Shelter Block - Surface Preparation for CFRP works | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 10232670.5172 | 180000 | https://drive.google.com/thumbnail?id=1b2eV06jwkZD183bC3zSDazL4_RSDXHSq&sz=w1000 | https://drive.google.com/file/d/1b2eV06jwkZD183bC3zSDazL4_RSDXHSq/view?usp=drive_link | https://drive.google.com/thumbnail?id=1PNmp5EMW5WyKjKqULNrxDdbiU7_eGUj0&sz=w1000 | https://drive.google.com/file/d/1PNmp5EMW5WyKjKqULNrxDdbiU7_eGUj0/view?usp=drive_link | https://drive.google.com/thumbnail?id=1862llNXCy3_gI0LM41mc5JpDXdHEOV2P&sz=w1000 | https://drive.google.com/file/d/1862llNXCy3_gI0LM41mc5JpDXdHEOV2P/view?usp=drive_link
2024-09-13 | Al Sila-School-P43 | P43 | SC-05 | 362 | 185 | 547 | • Annex Building - GF - RCC Wall Rebar Fixing 94% completed; GF RCC Wall Concrete Cast - 55% Completed • School Building - RCC Plinth Wall - 98% Completed, GF Wall Rebar Fixing 28% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 28.92% | 20.35% | -8.57% | Site Mobilization | 2023-10-21 | 2024-01-06 |  | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works to Complete • Annex Building - Superstructure works – GF RCC Wall works & FF Slab Works • Shelter Block - RCC Plinth Wall & GF Wall Works to progress • Shelter Block - Roof Slab Strenthening Works to progress • Shelter Block - Surface Preparation for CFRP works | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 10232670.5172 | 180000 | https://drive.google.com/thumbnail?id=1b2eV06jwkZD183bC3zSDazL4_RSDXHSq&sz=w1000 | https://drive.google.com/file/d/1b2eV06jwkZD183bC3zSDazL4_RSDXHSq/view?usp=drive_link | https://drive.google.com/thumbnail?id=1PNmp5EMW5WyKjKqULNrxDdbiU7_eGUj0&sz=w1000 | https://drive.google.com/file/d/1PNmp5EMW5WyKjKqULNrxDdbiU7_eGUj0/view?usp=drive_link | https://drive.google.com/thumbnail?id=1862llNXCy3_gI0LM41mc5JpDXdHEOV2P&sz=w1000 | https://drive.google.com/file/d/1862llNXCy3_gI0LM41mc5JpDXdHEOV2P/view?usp=drive_link
2024-09-13 | Al Sila-School-P43 | P43 | SC-05 | 362 | 185 | 547 | • Annex Building - GF - RCC Wall Rebar Fixing 94% completed; GF RCC Wall Concrete Cast - 55% Completed • School Building - RCC Plinth Wall - 98% Completed, GF Wall Rebar Fixing 28% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 28.92% | 20.35% | -8.57% | Building Permit | 2024-05-17 | 2024-06-04 |  | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works to Complete • Annex Building - Superstructure works – GF RCC Wall works & FF Slab Works • Shelter Block - RCC Plinth Wall & GF Wall Works to progress • Shelter Block - Roof Slab Strenthening Works to progress • Shelter Block - Surface Preparation for CFRP works | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 10232670.5172 | 180000 | https://drive.google.com/thumbnail?id=1b2eV06jwkZD183bC3zSDazL4_RSDXHSq&sz=w1000 | https://drive.google.com/file/d/1b2eV06jwkZD183bC3zSDazL4_RSDXHSq/view?usp=drive_link | https://drive.google.com/thumbnail?id=1PNmp5EMW5WyKjKqULNrxDdbiU7_eGUj0&sz=w1000 | https://drive.google.com/file/d/1PNmp5EMW5WyKjKqULNrxDdbiU7_eGUj0/view?usp=drive_link | https://drive.google.com/thumbnail?id=1862llNXCy3_gI0LM41mc5JpDXdHEOV2P&sz=w1000 | https://drive.google.com/file/d/1862llNXCy3_gI0LM41mc5JpDXdHEOV2P/view?usp=drive_link
2024-09-13 | Al Sila-School-P43 | P43 | SC-05 | 362 | 185 | 547 | • Annex Building - GF - RCC Wall Rebar Fixing 94% completed; GF RCC Wall Concrete Cast - 55% Completed • School Building - RCC Plinth Wall - 98% Completed, GF Wall Rebar Fixing 28% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 28.92% | 20.35% | -8.57% | School Substructure | 2024-08-06 |  | 2024-09-28 | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works to Complete • Annex Building - Superstructure works – GF RCC Wall works & FF Slab Works • Shelter Block - RCC Plinth Wall & GF Wall Works to progress • Shelter Block - Roof Slab Strenthening Works to progress • Shelter Block - Surface Preparation for CFRP works | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 10232670.5172 | 180000 | https://drive.google.com/thumbnail?id=1b2eV06jwkZD183bC3zSDazL4_RSDXHSq&sz=w1000 | https://drive.google.com/file/d/1b2eV06jwkZD183bC3zSDazL4_RSDXHSq/view?usp=drive_link | https://drive.google.com/thumbnail?id=1PNmp5EMW5WyKjKqULNrxDdbiU7_eGUj0&sz=w1000 | https://drive.google.com/file/d/1PNmp5EMW5WyKjKqULNrxDdbiU7_eGUj0/view?usp=drive_link | https://drive.google.com/thumbnail?id=1862llNXCy3_gI0LM41mc5JpDXdHEOV2P&sz=w1000 | https://drive.google.com/file/d/1862llNXCy3_gI0LM41mc5JpDXdHEOV2P/view?usp=drive_link
2024-09-13 | Al Sila-School-P43 | P43 | SC-05 | 362 | 185 | 547 | • Annex Building - GF - RCC Wall Rebar Fixing 94% completed; GF RCC Wall Concrete Cast - 55% Completed • School Building - RCC Plinth Wall - 98% Completed, GF Wall Rebar Fixing 28% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 28.92% | 20.35% | -8.57% | School Superstructure | 2024-11-07 |  | 2024-10-10 | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works to Complete • Annex Building - Superstructure works – GF RCC Wall works & FF Slab Works • Shelter Block - RCC Plinth Wall & GF Wall Works to progress • Shelter Block - Roof Slab Strenthening Works to progress • Shelter Block - Surface Preparation for CFRP works | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 10232670.5172 | 180000 | https://drive.google.com/thumbnail?id=1b2eV06jwkZD183bC3zSDazL4_RSDXHSq&sz=w1000 | https://drive.google.com/file/d/1b2eV06jwkZD183bC3zSDazL4_RSDXHSq/view?usp=drive_link | https://drive.google.com/thumbnail?id=1PNmp5EMW5WyKjKqULNrxDdbiU7_eGUj0&sz=w1000 | https://drive.google.com/file/d/1PNmp5EMW5WyKjKqULNrxDdbiU7_eGUj0/view?usp=drive_link | https://drive.google.com/thumbnail?id=1862llNXCy3_gI0LM41mc5JpDXdHEOV2P&sz=w1000 | https://drive.google.com/file/d/1862llNXCy3_gI0LM41mc5JpDXdHEOV2P/view?usp=drive_link
2024-09-13 | Al Sila-School-P43 | P43 | SC-05 | 362 | 185 | 547 | • Annex Building - GF - RCC Wall Rebar Fixing 94% completed; GF RCC Wall Concrete Cast - 55% Completed • School Building - RCC Plinth Wall - 98% Completed, GF Wall Rebar Fixing 28% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 28.92% | 20.35% | -8.57% | Annex Substructure | 2024-08-07 | 2024-08-31 |  | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works to Complete • Annex Building - Superstructure works – GF RCC Wall works & FF Slab Works • Shelter Block - RCC Plinth Wall & GF Wall Works to progress • Shelter Block - Roof Slab Strenthening Works to progress • Shelter Block - Surface Preparation for CFRP works | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 10232670.5172 | 180000 | https://drive.google.com/thumbnail?id=1b2eV06jwkZD183bC3zSDazL4_RSDXHSq&sz=w1000 | https://drive.google.com/file/d/1b2eV06jwkZD183bC3zSDazL4_RSDXHSq/view?usp=drive_link | https://drive.google.com/thumbnail?id=1PNmp5EMW5WyKjKqULNrxDdbiU7_eGUj0&sz=w1000 | https://drive.google.com/file/d/1PNmp5EMW5WyKjKqULNrxDdbiU7_eGUj0/view?usp=drive_link | https://drive.google.com/thumbnail?id=1862llNXCy3_gI0LM41mc5JpDXdHEOV2P&sz=w1000 | https://drive.google.com/file/d/1862llNXCy3_gI0LM41mc5JpDXdHEOV2P/view?usp=drive_link
2024-09-13 | Al Sila-School-P43 | P43 | SC-05 | 362 | 185 | 547 | • Annex Building - GF - RCC Wall Rebar Fixing 94% completed; GF RCC Wall Concrete Cast - 55% Completed • School Building - RCC Plinth Wall - 98% Completed, GF Wall Rebar Fixing 28% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 28.92% | 20.35% | -8.57% | Annex Superstructure | 2024-10-31 |  | 2024-11-16 | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works to Complete • Annex Building - Superstructure works – GF RCC Wall works & FF Slab Works • Shelter Block - RCC Plinth Wall & GF Wall Works to progress • Shelter Block - Roof Slab Strenthening Works to progress • Shelter Block - Surface Preparation for CFRP works | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 10232670.5172 | 180000 | https://drive.google.com/thumbnail?id=1b2eV06jwkZD183bC3zSDazL4_RSDXHSq&sz=w1000 | https://drive.google.com/file/d/1b2eV06jwkZD183bC3zSDazL4_RSDXHSq/view?usp=drive_link | https://drive.google.com/thumbnail?id=1PNmp5EMW5WyKjKqULNrxDdbiU7_eGUj0&sz=w1000 | https://drive.google.com/file/d/1PNmp5EMW5WyKjKqULNrxDdbiU7_eGUj0/view?usp=drive_link | https://drive.google.com/thumbnail?id=1862llNXCy3_gI0LM41mc5JpDXdHEOV2P&sz=w1000 | https://drive.google.com/file/d/1862llNXCy3_gI0LM41mc5JpDXdHEOV2P/view?usp=drive_link
2024-09-13 | Al Sila-School-P43 | P43 | SC-05 | 362 | 185 | 547 | • Annex Building - GF - RCC Wall Rebar Fixing 94% completed; GF RCC Wall Concrete Cast - 55% Completed • School Building - RCC Plinth Wall - 98% Completed, GF Wall Rebar Fixing 28% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 28.92% | 20.35% | -8.57% | MEP & Finishes | 2025-01-25 |  | 2025-05-06 | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works to Complete • Annex Building - Superstructure works – GF RCC Wall works & FF Slab Works • Shelter Block - RCC Plinth Wall & GF Wall Works to progress • Shelter Block - Roof Slab Strenthening Works to progress • Shelter Block - Surface Preparation for CFRP works | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 10232670.5172 | 180000 | https://drive.google.com/thumbnail?id=1b2eV06jwkZD183bC3zSDazL4_RSDXHSq&sz=w1000 | https://drive.google.com/file/d/1b2eV06jwkZD183bC3zSDazL4_RSDXHSq/view?usp=drive_link | https://drive.google.com/thumbnail?id=1PNmp5EMW5WyKjKqULNrxDdbiU7_eGUj0&sz=w1000 | https://drive.google.com/file/d/1PNmp5EMW5WyKjKqULNrxDdbiU7_eGUj0/view?usp=drive_link | https://drive.google.com/thumbnail?id=1862llNXCy3_gI0LM41mc5JpDXdHEOV2P&sz=w1000 | https://drive.google.com/file/d/1862llNXCy3_gI0LM41mc5JpDXdHEOV2P/view?usp=drive_link
2024-09-13 | Al Sila-School-P43 | P43 | SC-05 | 362 | 185 | 547 | • Annex Building - GF - RCC Wall Rebar Fixing 94% completed; GF RCC Wall Concrete Cast - 55% Completed • School Building - RCC Plinth Wall - 98% Completed, GF Wall Rebar Fixing 28% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 28.92% | 20.35% | -8.57% | BCC Inspection | 2025-02-13 |  | 2025-05-26 | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works to Complete • Annex Building - Superstructure works – GF RCC Wall works & FF Slab Works • Shelter Block - RCC Plinth Wall & GF Wall Works to progress • Shelter Block - Roof Slab Strenthening Works to progress • Shelter Block - Surface Preparation for CFRP works | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 10232670.5172 | 180000 | https://drive.google.com/thumbnail?id=1b2eV06jwkZD183bC3zSDazL4_RSDXHSq&sz=w1000 | https://drive.google.com/file/d/1b2eV06jwkZD183bC3zSDazL4_RSDXHSq/view?usp=drive_link | https://drive.google.com/thumbnail?id=1PNmp5EMW5WyKjKqULNrxDdbiU7_eGUj0&sz=w1000 | https://drive.google.com/file/d/1PNmp5EMW5WyKjKqULNrxDdbiU7_eGUj0/view?usp=drive_link | https://drive.google.com/thumbnail?id=1862llNXCy3_gI0LM41mc5JpDXdHEOV2P&sz=w1000 | https://drive.google.com/file/d/1862llNXCy3_gI0LM41mc5JpDXdHEOV2P/view?usp=drive_link
2024-09-13 | Al Sila-School-P43 | P43 | SC-05 | 362 | 185 | 547 | • Annex Building - GF - RCC Wall Rebar Fixing 94% completed; GF RCC Wall Concrete Cast - 55% Completed • School Building - RCC Plinth Wall - 98% Completed, GF Wall Rebar Fixing 28% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 28.92% | 20.35% | -8.57% | BCC Issuance | 2025-03-04 |  | 2025-06-16 | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works to Complete • Annex Building - Superstructure works – GF RCC Wall works & FF Slab Works • Shelter Block - RCC Plinth Wall & GF Wall Works to progress • Shelter Block - Roof Slab Strenthening Works to progress • Shelter Block - Surface Preparation for CFRP works | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 10232670.5172 | 180000 | https://drive.google.com/thumbnail?id=1b2eV06jwkZD183bC3zSDazL4_RSDXHSq&sz=w1000 | https://drive.google.com/file/d/1b2eV06jwkZD183bC3zSDazL4_RSDXHSq/view?usp=drive_link | https://drive.google.com/thumbnail?id=1PNmp5EMW5WyKjKqULNrxDdbiU7_eGUj0&sz=w1000 | https://drive.google.com/file/d/1PNmp5EMW5WyKjKqULNrxDdbiU7_eGUj0/view?usp=drive_link | https://drive.google.com/thumbnail?id=1862llNXCy3_gI0LM41mc5JpDXdHEOV2P&sz=w1000 | https://drive.google.com/file/d/1862llNXCy3_gI0LM41mc5JpDXdHEOV2P/view?usp=drive_link
2024-09-13 | Al Sila-School-P43 | P43 | SC-05 | 362 | 185 | 547 | • Annex Building - GF - RCC Wall Rebar Fixing 94% completed; GF RCC Wall Concrete Cast - 55% Completed • School Building - RCC Plinth Wall - 98% Completed, GF Wall Rebar Fixing 28% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 28.92% | 20.35% | -8.57% | Completion | 2025-03-17 |  | 2025-06-30 | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works to Complete • Annex Building - Superstructure works – GF RCC Wall works & FF Slab Works • Shelter Block - RCC Plinth Wall & GF Wall Works to progress • Shelter Block - Roof Slab Strenthening Works to progress • Shelter Block - Surface Preparation for CFRP works | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 10232670.5172 | 180000 | https://drive.google.com/thumbnail?id=1b2eV06jwkZD183bC3zSDazL4_RSDXHSq&sz=w1000 | https://drive.google.com/file/d/1b2eV06jwkZD183bC3zSDazL4_RSDXHSq/view?usp=drive_link | https://drive.google.com/thumbnail?id=1PNmp5EMW5WyKjKqULNrxDdbiU7_eGUj0&sz=w1000 | https://drive.google.com/file/d/1PNmp5EMW5WyKjKqULNrxDdbiU7_eGUj0/view?usp=drive_link | https://drive.google.com/thumbnail?id=1862llNXCy3_gI0LM41mc5JpDXdHEOV2P&sz=w1000 | https://drive.google.com/file/d/1862llNXCy3_gI0LM41mc5JpDXdHEOV2P/view?usp=drive_link
2024-09-13 | Madinat Zayed-School-P105 | P105 | SC-06 | 362 | 185 | 547 | • Annex Building - Superstructure – GF RCC Wall Concrete Cast 100 % completed • Annex Building - FF Slab Staging & Formwork fixing 90% completed; Rebar fixing 79% completed • School Building - Substructure –Plinth Wall Concrete 95% completed • School Building - GF RCC Wall Rebar Fixing – 35% completed; Shutter fixing 15% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 29.03% | 21.88% | -7.15% | Notice to Commence | 2023-09-18 | 2023-09-26 |  | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works to progress • Annex Building - Superstructure works – GF RCC Wall works & FF Slab Works • Shelter Block - Substructure – Plinth Wall Works to complete; Existing Structure Strengthening works to progress. • Shelter Block - Superstructure - GF & FF Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 10862786.8946 | 180000 | https://drive.google.com/thumbnail?id=13q2lrMXyrD-jFwOUSAmyXAyHguPjfyop&sz=w1000 | https://drive.google.com/file/d/13q2lrMXyrD-jFwOUSAmyXAyHguPjfyop/view?usp=drive_link | https://drive.google.com/thumbnail?id=1oGYK0VIxvZWojb4mGJZZsBVC1SfDMY6y&sz=w1000 | https://drive.google.com/file/d/1oGYK0VIxvZWojb4mGJZZsBVC1SfDMY6y/view?usp=drive_link | https://drive.google.com/thumbnail?id=1QZ18QaTmJF4nT-dAtMgJlTUA-K3sOYAQ&sz=w1000 | https://drive.google.com/file/d/1QZ18QaTmJF4nT-dAtMgJlTUA-K3sOYAQ/view?usp=drive_link
2024-09-13 | Madinat Zayed-School-P105 | P105 | SC-06 | 362 | 185 | 547 | • Annex Building - Superstructure – GF RCC Wall Concrete Cast 100 % completed • Annex Building - FF Slab Staging & Formwork fixing 90% completed; Rebar fixing 79% completed • School Building - Substructure –Plinth Wall Concrete 95% completed • School Building - GF RCC Wall Rebar Fixing – 35% completed; Shutter fixing 15% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 29.03% | 21.88% | -7.15% | Site Mobilization | 2023-10-21 | 2024-01-06 |  | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works to progress • Annex Building - Superstructure works – GF RCC Wall works & FF Slab Works • Shelter Block - Substructure – Plinth Wall Works to complete; Existing Structure Strengthening works to progress. • Shelter Block - Superstructure - GF & FF Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 10862786.8946 | 180000 | https://drive.google.com/thumbnail?id=13q2lrMXyrD-jFwOUSAmyXAyHguPjfyop&sz=w1000 | https://drive.google.com/file/d/13q2lrMXyrD-jFwOUSAmyXAyHguPjfyop/view?usp=drive_link | https://drive.google.com/thumbnail?id=1oGYK0VIxvZWojb4mGJZZsBVC1SfDMY6y&sz=w1000 | https://drive.google.com/file/d/1oGYK0VIxvZWojb4mGJZZsBVC1SfDMY6y/view?usp=drive_link | https://drive.google.com/thumbnail?id=1QZ18QaTmJF4nT-dAtMgJlTUA-K3sOYAQ&sz=w1000 | https://drive.google.com/file/d/1QZ18QaTmJF4nT-dAtMgJlTUA-K3sOYAQ/view?usp=drive_link
2024-09-13 | Madinat Zayed-School-P105 | P105 | SC-06 | 362 | 185 | 547 | • Annex Building - Superstructure – GF RCC Wall Concrete Cast 100 % completed • Annex Building - FF Slab Staging & Formwork fixing 90% completed; Rebar fixing 79% completed • School Building - Substructure –Plinth Wall Concrete 95% completed • School Building - GF RCC Wall Rebar Fixing – 35% completed; Shutter fixing 15% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 29.03% | 21.88% | -7.15% | Building Permit | 2024-05-17 | 2024-05-23 |  | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works to progress • Annex Building - Superstructure works – GF RCC Wall works & FF Slab Works • Shelter Block - Substructure – Plinth Wall Works to complete; Existing Structure Strengthening works to progress. • Shelter Block - Superstructure - GF & FF Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 10862786.8946 | 180000 | https://drive.google.com/thumbnail?id=13q2lrMXyrD-jFwOUSAmyXAyHguPjfyop&sz=w1000 | https://drive.google.com/file/d/13q2lrMXyrD-jFwOUSAmyXAyHguPjfyop/view?usp=drive_link | https://drive.google.com/thumbnail?id=1oGYK0VIxvZWojb4mGJZZsBVC1SfDMY6y&sz=w1000 | https://drive.google.com/file/d/1oGYK0VIxvZWojb4mGJZZsBVC1SfDMY6y/view?usp=drive_link | https://drive.google.com/thumbnail?id=1QZ18QaTmJF4nT-dAtMgJlTUA-K3sOYAQ&sz=w1000 | https://drive.google.com/file/d/1QZ18QaTmJF4nT-dAtMgJlTUA-K3sOYAQ/view?usp=drive_link
2024-09-13 | Madinat Zayed-School-P105 | P105 | SC-06 | 362 | 185 | 547 | • Annex Building - Superstructure – GF RCC Wall Concrete Cast 100 % completed • Annex Building - FF Slab Staging & Formwork fixing 90% completed; Rebar fixing 79% completed • School Building - Substructure –Plinth Wall Concrete 95% completed • School Building - GF RCC Wall Rebar Fixing – 35% completed; Shutter fixing 15% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 29.03% | 21.88% | -7.15% | School Substructure | 2024-08-06 |  | 2024-09-27 | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works to progress • Annex Building - Superstructure works – GF RCC Wall works & FF Slab Works • Shelter Block - Substructure – Plinth Wall Works to complete; Existing Structure Strengthening works to progress. • Shelter Block - Superstructure - GF & FF Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 10862786.8946 | 180000 | https://drive.google.com/thumbnail?id=13q2lrMXyrD-jFwOUSAmyXAyHguPjfyop&sz=w1000 | https://drive.google.com/file/d/13q2lrMXyrD-jFwOUSAmyXAyHguPjfyop/view?usp=drive_link | https://drive.google.com/thumbnail?id=1oGYK0VIxvZWojb4mGJZZsBVC1SfDMY6y&sz=w1000 | https://drive.google.com/file/d/1oGYK0VIxvZWojb4mGJZZsBVC1SfDMY6y/view?usp=drive_link | https://drive.google.com/thumbnail?id=1QZ18QaTmJF4nT-dAtMgJlTUA-K3sOYAQ&sz=w1000 | https://drive.google.com/file/d/1QZ18QaTmJF4nT-dAtMgJlTUA-K3sOYAQ/view?usp=drive_link
2024-09-13 | Madinat Zayed-School-P105 | P105 | SC-06 | 362 | 185 | 547 | • Annex Building - Superstructure – GF RCC Wall Concrete Cast 100 % completed • Annex Building - FF Slab Staging & Formwork fixing 90% completed; Rebar fixing 79% completed • School Building - Substructure –Plinth Wall Concrete 95% completed • School Building - GF RCC Wall Rebar Fixing – 35% completed; Shutter fixing 15% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 29.03% | 21.88% | -7.15% | School Superstructure | 2024-11-07 |  | 2024-10-29 | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works to progress • Annex Building - Superstructure works – GF RCC Wall works & FF Slab Works • Shelter Block - Substructure – Plinth Wall Works to complete; Existing Structure Strengthening works to progress. • Shelter Block - Superstructure - GF & FF Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 10862786.8946 | 180000 | https://drive.google.com/thumbnail?id=13q2lrMXyrD-jFwOUSAmyXAyHguPjfyop&sz=w1000 | https://drive.google.com/file/d/13q2lrMXyrD-jFwOUSAmyXAyHguPjfyop/view?usp=drive_link | https://drive.google.com/thumbnail?id=1oGYK0VIxvZWojb4mGJZZsBVC1SfDMY6y&sz=w1000 | https://drive.google.com/file/d/1oGYK0VIxvZWojb4mGJZZsBVC1SfDMY6y/view?usp=drive_link | https://drive.google.com/thumbnail?id=1QZ18QaTmJF4nT-dAtMgJlTUA-K3sOYAQ&sz=w1000 | https://drive.google.com/file/d/1QZ18QaTmJF4nT-dAtMgJlTUA-K3sOYAQ/view?usp=drive_link
2024-09-13 | Madinat Zayed-School-P105 | P105 | SC-06 | 362 | 185 | 547 | • Annex Building - Superstructure – GF RCC Wall Concrete Cast 100 % completed • Annex Building - FF Slab Staging & Formwork fixing 90% completed; Rebar fixing 79% completed • School Building - Substructure –Plinth Wall Concrete 95% completed • School Building - GF RCC Wall Rebar Fixing – 35% completed; Shutter fixing 15% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 29.03% | 21.88% | -7.15% | Annex Substructure | 2024-08-06 | 2024-07-13 |  | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works to progress • Annex Building - Superstructure works – GF RCC Wall works & FF Slab Works • Shelter Block - Substructure – Plinth Wall Works to complete; Existing Structure Strengthening works to progress. • Shelter Block - Superstructure - GF & FF Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 10862786.8946 | 180000 | https://drive.google.com/thumbnail?id=13q2lrMXyrD-jFwOUSAmyXAyHguPjfyop&sz=w1000 | https://drive.google.com/file/d/13q2lrMXyrD-jFwOUSAmyXAyHguPjfyop/view?usp=drive_link | https://drive.google.com/thumbnail?id=1oGYK0VIxvZWojb4mGJZZsBVC1SfDMY6y&sz=w1000 | https://drive.google.com/file/d/1oGYK0VIxvZWojb4mGJZZsBVC1SfDMY6y/view?usp=drive_link | https://drive.google.com/thumbnail?id=1QZ18QaTmJF4nT-dAtMgJlTUA-K3sOYAQ&sz=w1000 | https://drive.google.com/file/d/1QZ18QaTmJF4nT-dAtMgJlTUA-K3sOYAQ/view?usp=drive_link
2024-09-13 | Madinat Zayed-School-P105 | P105 | SC-06 | 362 | 185 | 547 | • Annex Building - Superstructure – GF RCC Wall Concrete Cast 100 % completed • Annex Building - FF Slab Staging & Formwork fixing 90% completed; Rebar fixing 79% completed • School Building - Substructure –Plinth Wall Concrete 95% completed • School Building - GF RCC Wall Rebar Fixing – 35% completed; Shutter fixing 15% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 29.03% | 21.88% | -7.15% | Annex Superstructure | 2024-10-31 |  | 2024-11-01 | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works to progress • Annex Building - Superstructure works – GF RCC Wall works & FF Slab Works • Shelter Block - Substructure – Plinth Wall Works to complete; Existing Structure Strengthening works to progress. • Shelter Block - Superstructure - GF & FF Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 10862786.8946 | 180000 | https://drive.google.com/thumbnail?id=13q2lrMXyrD-jFwOUSAmyXAyHguPjfyop&sz=w1000 | https://drive.google.com/file/d/13q2lrMXyrD-jFwOUSAmyXAyHguPjfyop/view?usp=drive_link | https://drive.google.com/thumbnail?id=1oGYK0VIxvZWojb4mGJZZsBVC1SfDMY6y&sz=w1000 | https://drive.google.com/file/d/1oGYK0VIxvZWojb4mGJZZsBVC1SfDMY6y/view?usp=drive_link | https://drive.google.com/thumbnail?id=1QZ18QaTmJF4nT-dAtMgJlTUA-K3sOYAQ&sz=w1000 | https://drive.google.com/file/d/1QZ18QaTmJF4nT-dAtMgJlTUA-K3sOYAQ/view?usp=drive_link
2024-09-13 | Madinat Zayed-School-P105 | P105 | SC-06 | 362 | 185 | 547 | • Annex Building - Superstructure – GF RCC Wall Concrete Cast 100 % completed • Annex Building - FF Slab Staging & Formwork fixing 90% completed; Rebar fixing 79% completed • School Building - Substructure –Plinth Wall Concrete 95% completed • School Building - GF RCC Wall Rebar Fixing – 35% completed; Shutter fixing 15% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 29.03% | 21.88% | -7.15% | MEP & Finishes | 2025-01-25 |  | 2025-05-06 | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works to progress • Annex Building - Superstructure works – GF RCC Wall works & FF Slab Works • Shelter Block - Substructure – Plinth Wall Works to complete; Existing Structure Strengthening works to progress. • Shelter Block - Superstructure - GF & FF Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 10862786.8946 | 180000 | https://drive.google.com/thumbnail?id=13q2lrMXyrD-jFwOUSAmyXAyHguPjfyop&sz=w1000 | https://drive.google.com/file/d/13q2lrMXyrD-jFwOUSAmyXAyHguPjfyop/view?usp=drive_link | https://drive.google.com/thumbnail?id=1oGYK0VIxvZWojb4mGJZZsBVC1SfDMY6y&sz=w1000 | https://drive.google.com/file/d/1oGYK0VIxvZWojb4mGJZZsBVC1SfDMY6y/view?usp=drive_link | https://drive.google.com/thumbnail?id=1QZ18QaTmJF4nT-dAtMgJlTUA-K3sOYAQ&sz=w1000 | https://drive.google.com/file/d/1QZ18QaTmJF4nT-dAtMgJlTUA-K3sOYAQ/view?usp=drive_link
2024-09-13 | Madinat Zayed-School-P105 | P105 | SC-06 | 362 | 185 | 547 | • Annex Building - Superstructure – GF RCC Wall Concrete Cast 100 % completed • Annex Building - FF Slab Staging & Formwork fixing 90% completed; Rebar fixing 79% completed • School Building - Substructure –Plinth Wall Concrete 95% completed • School Building - GF RCC Wall Rebar Fixing – 35% completed; Shutter fixing 15% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 29.03% | 21.88% | -7.15% | BCC Inspection | 2025-02-13 |  | 2025-05-26 | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works to progress • Annex Building - Superstructure works – GF RCC Wall works & FF Slab Works • Shelter Block - Substructure – Plinth Wall Works to complete; Existing Structure Strengthening works to progress. • Shelter Block - Superstructure - GF & FF Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 10862786.8946 | 180000 | https://drive.google.com/thumbnail?id=13q2lrMXyrD-jFwOUSAmyXAyHguPjfyop&sz=w1000 | https://drive.google.com/file/d/13q2lrMXyrD-jFwOUSAmyXAyHguPjfyop/view?usp=drive_link | https://drive.google.com/thumbnail?id=1oGYK0VIxvZWojb4mGJZZsBVC1SfDMY6y&sz=w1000 | https://drive.google.com/file/d/1oGYK0VIxvZWojb4mGJZZsBVC1SfDMY6y/view?usp=drive_link | https://drive.google.com/thumbnail?id=1QZ18QaTmJF4nT-dAtMgJlTUA-K3sOYAQ&sz=w1000 | https://drive.google.com/file/d/1QZ18QaTmJF4nT-dAtMgJlTUA-K3sOYAQ/view?usp=drive_link
2024-09-13 | Madinat Zayed-School-P105 | P105 | SC-06 | 362 | 185 | 547 | • Annex Building - Superstructure – GF RCC Wall Concrete Cast 100 % completed • Annex Building - FF Slab Staging & Formwork fixing 90% completed; Rebar fixing 79% completed • School Building - Substructure –Plinth Wall Concrete 95% completed • School Building - GF RCC Wall Rebar Fixing – 35% completed; Shutter fixing 15% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 29.03% | 21.88% | -7.15% | BCC Issuance | 2025-03-04 |  | 2025-06-16 | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works to progress • Annex Building - Superstructure works – GF RCC Wall works & FF Slab Works • Shelter Block - Substructure – Plinth Wall Works to complete; Existing Structure Strengthening works to progress. • Shelter Block - Superstructure - GF & FF Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 10862786.8946 | 180000 | https://drive.google.com/thumbnail?id=13q2lrMXyrD-jFwOUSAmyXAyHguPjfyop&sz=w1000 | https://drive.google.com/file/d/13q2lrMXyrD-jFwOUSAmyXAyHguPjfyop/view?usp=drive_link | https://drive.google.com/thumbnail?id=1oGYK0VIxvZWojb4mGJZZsBVC1SfDMY6y&sz=w1000 | https://drive.google.com/file/d/1oGYK0VIxvZWojb4mGJZZsBVC1SfDMY6y/view?usp=drive_link | https://drive.google.com/thumbnail?id=1QZ18QaTmJF4nT-dAtMgJlTUA-K3sOYAQ&sz=w1000 | https://drive.google.com/file/d/1QZ18QaTmJF4nT-dAtMgJlTUA-K3sOYAQ/view?usp=drive_link
2024-09-13 | Madinat Zayed-School-P105 | P105 | SC-06 | 362 | 185 | 547 | • Annex Building - Superstructure – GF RCC Wall Concrete Cast 100 % completed • Annex Building - FF Slab Staging & Formwork fixing 90% completed; Rebar fixing 79% completed • School Building - Substructure –Plinth Wall Concrete 95% completed • School Building - GF RCC Wall Rebar Fixing – 35% completed; Shutter fixing 15% completed | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 29.03% | 21.88% | -7.15% | Completion | 2025-03-17 |  | 2025-06-30 | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Substructure – Grade Slab Works to progress • Annex Building - Superstructure works – GF RCC Wall works & FF Slab Works • Shelter Block - Substructure – Plinth Wall Works to complete; Existing Structure Strengthening works to progress. • Shelter Block - Superstructure - GF & FF Wall to progress • Shelter Block - Surface Preparation for CFRP | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 10862786.8946 | 180000 | https://drive.google.com/thumbnail?id=13q2lrMXyrD-jFwOUSAmyXAyHguPjfyop&sz=w1000 | https://drive.google.com/file/d/13q2lrMXyrD-jFwOUSAmyXAyHguPjfyop/view?usp=drive_link | https://drive.google.com/thumbnail?id=1oGYK0VIxvZWojb4mGJZZsBVC1SfDMY6y&sz=w1000 | https://drive.google.com/file/d/1oGYK0VIxvZWojb4mGJZZsBVC1SfDMY6y/view?usp=drive_link | https://drive.google.com/thumbnail?id=1QZ18QaTmJF4nT-dAtMgJlTUA-K3sOYAQ&sz=w1000 | https://drive.google.com/file/d/1QZ18QaTmJF4nT-dAtMgJlTUA-K3sOYAQ/view?usp=drive_link
2024-09-13 | Madinat Zayed-School-P38 | P38 | SC-07 | 362 | 185 | 547 | • Annex Building - GF RCC Wall – Rebar fixing 98% Completed. • Annex Building - GF RCC Wall – Concrete pouring 60% Completed; FF Slab Staging works 15% Completed • School Building - Superstructure – GF RCC Wall Rebar Fixing – 85% completed; GF Wall Concrete 42% completed • School Building - FF RCC Wall Rebar Fixing – 24% completed; | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 29.03% | 26.21% | -2.82% | Notice to Commence | 2023-09-18 | 2023-09-26 |  | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – GF RCC Wall works to complete; FF Slab works to progress • Shelter Block - Superstructure - GF & FF Structure Strentheing & RCC Wall works to progress. • Shelter Block - Surface Preparation for CFRP Works. | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 11500494.3905 | 180000 | https://drive.google.com/thumbnail?id=1xxrE3LPgzlDH2hVcRgO9_8Tj9dwrwVwk&sz=w1000 | https://drive.google.com/file/d/1xxrE3LPgzlDH2hVcRgO9_8Tj9dwrwVwk/view?usp=drive_link | https://drive.google.com/thumbnail?id=1oxqPS_1tBA-gVsLfO5IQXOGLDroKN7-w&sz=w1000 | https://drive.google.com/file/d/1oxqPS_1tBA-gVsLfO5IQXOGLDroKN7-w/view?usp=drive_link | https://drive.google.com/thumbnail?id=1m_ZcOGPlgePKQ5iHcOHOG_LcxNkDkiJ-&sz=w1000 | https://drive.google.com/file/d/1m_ZcOGPlgePKQ5iHcOHOG_LcxNkDkiJ-/view?usp=drive_link
2024-09-13 | Madinat Zayed-School-P38 | P38 | SC-07 | 362 | 185 | 547 | • Annex Building - GF RCC Wall – Rebar fixing 98% Completed. • Annex Building - GF RCC Wall – Concrete pouring 60% Completed; FF Slab Staging works 15% Completed • School Building - Superstructure – GF RCC Wall Rebar Fixing – 85% completed; GF Wall Concrete 42% completed • School Building - FF RCC Wall Rebar Fixing – 24% completed; | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 29.03% | 26.21% | -2.82% | Site Mobilization | 2023-10-21 | 2024-01-13 |  | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – GF RCC Wall works to complete; FF Slab works to progress • Shelter Block - Superstructure - GF & FF Structure Strentheing & RCC Wall works to progress. • Shelter Block - Surface Preparation for CFRP Works. | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 11500494.3905 | 180000 | https://drive.google.com/thumbnail?id=1xxrE3LPgzlDH2hVcRgO9_8Tj9dwrwVwk&sz=w1000 | https://drive.google.com/file/d/1xxrE3LPgzlDH2hVcRgO9_8Tj9dwrwVwk/view?usp=drive_link | https://drive.google.com/thumbnail?id=1oxqPS_1tBA-gVsLfO5IQXOGLDroKN7-w&sz=w1000 | https://drive.google.com/file/d/1oxqPS_1tBA-gVsLfO5IQXOGLDroKN7-w/view?usp=drive_link | https://drive.google.com/thumbnail?id=1m_ZcOGPlgePKQ5iHcOHOG_LcxNkDkiJ-&sz=w1000 | https://drive.google.com/file/d/1m_ZcOGPlgePKQ5iHcOHOG_LcxNkDkiJ-/view?usp=drive_link
2024-09-13 | Madinat Zayed-School-P38 | P38 | SC-07 | 362 | 185 | 547 | • Annex Building - GF RCC Wall – Rebar fixing 98% Completed. • Annex Building - GF RCC Wall – Concrete pouring 60% Completed; FF Slab Staging works 15% Completed • School Building - Superstructure – GF RCC Wall Rebar Fixing – 85% completed; GF Wall Concrete 42% completed • School Building - FF RCC Wall Rebar Fixing – 24% completed; | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 29.03% | 26.21% | -2.82% | Building Permit | 2024-05-17 | 2024-05-27 |  | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – GF RCC Wall works to complete; FF Slab works to progress • Shelter Block - Superstructure - GF & FF Structure Strentheing & RCC Wall works to progress. • Shelter Block - Surface Preparation for CFRP Works. | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 11500494.3905 | 180000 | https://drive.google.com/thumbnail?id=1xxrE3LPgzlDH2hVcRgO9_8Tj9dwrwVwk&sz=w1000 | https://drive.google.com/file/d/1xxrE3LPgzlDH2hVcRgO9_8Tj9dwrwVwk/view?usp=drive_link | https://drive.google.com/thumbnail?id=1oxqPS_1tBA-gVsLfO5IQXOGLDroKN7-w&sz=w1000 | https://drive.google.com/file/d/1oxqPS_1tBA-gVsLfO5IQXOGLDroKN7-w/view?usp=drive_link | https://drive.google.com/thumbnail?id=1m_ZcOGPlgePKQ5iHcOHOG_LcxNkDkiJ-&sz=w1000 | https://drive.google.com/file/d/1m_ZcOGPlgePKQ5iHcOHOG_LcxNkDkiJ-/view?usp=drive_link
2024-09-13 | Madinat Zayed-School-P38 | P38 | SC-07 | 362 | 185 | 547 | • Annex Building - GF RCC Wall – Rebar fixing 98% Completed. • Annex Building - GF RCC Wall – Concrete pouring 60% Completed; FF Slab Staging works 15% Completed • School Building - Superstructure – GF RCC Wall Rebar Fixing – 85% completed; GF Wall Concrete 42% completed • School Building - FF RCC Wall Rebar Fixing – 24% completed; | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 29.03% | 26.21% | -2.82% | School Substructure | 2024-08-06 | 2024-08-21 |  | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – GF RCC Wall works to complete; FF Slab works to progress • Shelter Block - Superstructure - GF & FF Structure Strentheing & RCC Wall works to progress. • Shelter Block - Surface Preparation for CFRP Works. | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 11500494.3905 | 180000 | https://drive.google.com/thumbnail?id=1xxrE3LPgzlDH2hVcRgO9_8Tj9dwrwVwk&sz=w1000 | https://drive.google.com/file/d/1xxrE3LPgzlDH2hVcRgO9_8Tj9dwrwVwk/view?usp=drive_link | https://drive.google.com/thumbnail?id=1oxqPS_1tBA-gVsLfO5IQXOGLDroKN7-w&sz=w1000 | https://drive.google.com/file/d/1oxqPS_1tBA-gVsLfO5IQXOGLDroKN7-w/view?usp=drive_link | https://drive.google.com/thumbnail?id=1m_ZcOGPlgePKQ5iHcOHOG_LcxNkDkiJ-&sz=w1000 | https://drive.google.com/file/d/1m_ZcOGPlgePKQ5iHcOHOG_LcxNkDkiJ-/view?usp=drive_link
2024-09-13 | Madinat Zayed-School-P38 | P38 | SC-07 | 362 | 185 | 547 | • Annex Building - GF RCC Wall – Rebar fixing 98% Completed. • Annex Building - GF RCC Wall – Concrete pouring 60% Completed; FF Slab Staging works 15% Completed • School Building - Superstructure – GF RCC Wall Rebar Fixing – 85% completed; GF Wall Concrete 42% completed • School Building - FF RCC Wall Rebar Fixing – 24% completed; | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 29.03% | 26.21% | -2.82% | School Superstructure | 2024-11-07 |  | 2024-10-26 | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – GF RCC Wall works to complete; FF Slab works to progress • Shelter Block - Superstructure - GF & FF Structure Strentheing & RCC Wall works to progress. • Shelter Block - Surface Preparation for CFRP Works. | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 11500494.3905 | 180000 | https://drive.google.com/thumbnail?id=1xxrE3LPgzlDH2hVcRgO9_8Tj9dwrwVwk&sz=w1000 | https://drive.google.com/file/d/1xxrE3LPgzlDH2hVcRgO9_8Tj9dwrwVwk/view?usp=drive_link | https://drive.google.com/thumbnail?id=1oxqPS_1tBA-gVsLfO5IQXOGLDroKN7-w&sz=w1000 | https://drive.google.com/file/d/1oxqPS_1tBA-gVsLfO5IQXOGLDroKN7-w/view?usp=drive_link | https://drive.google.com/thumbnail?id=1m_ZcOGPlgePKQ5iHcOHOG_LcxNkDkiJ-&sz=w1000 | https://drive.google.com/file/d/1m_ZcOGPlgePKQ5iHcOHOG_LcxNkDkiJ-/view?usp=drive_link
2024-09-13 | Madinat Zayed-School-P38 | P38 | SC-07 | 362 | 185 | 547 | • Annex Building - GF RCC Wall – Rebar fixing 98% Completed. • Annex Building - GF RCC Wall – Concrete pouring 60% Completed; FF Slab Staging works 15% Completed • School Building - Superstructure – GF RCC Wall Rebar Fixing – 85% completed; GF Wall Concrete 42% completed • School Building - FF RCC Wall Rebar Fixing – 24% completed; | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 29.03% | 26.21% | -2.82% | Annex Substructure | 2024-08-06 | 2024-07-31 |  | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – GF RCC Wall works to complete; FF Slab works to progress • Shelter Block - Superstructure - GF & FF Structure Strentheing & RCC Wall works to progress. • Shelter Block - Surface Preparation for CFRP Works. | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 11500494.3905 | 180000 | https://drive.google.com/thumbnail?id=1xxrE3LPgzlDH2hVcRgO9_8Tj9dwrwVwk&sz=w1000 | https://drive.google.com/file/d/1xxrE3LPgzlDH2hVcRgO9_8Tj9dwrwVwk/view?usp=drive_link | https://drive.google.com/thumbnail?id=1oxqPS_1tBA-gVsLfO5IQXOGLDroKN7-w&sz=w1000 | https://drive.google.com/file/d/1oxqPS_1tBA-gVsLfO5IQXOGLDroKN7-w/view?usp=drive_link | https://drive.google.com/thumbnail?id=1m_ZcOGPlgePKQ5iHcOHOG_LcxNkDkiJ-&sz=w1000 | https://drive.google.com/file/d/1m_ZcOGPlgePKQ5iHcOHOG_LcxNkDkiJ-/view?usp=drive_link
2024-09-13 | Madinat Zayed-School-P38 | P38 | SC-07 | 362 | 185 | 547 | • Annex Building - GF RCC Wall – Rebar fixing 98% Completed. • Annex Building - GF RCC Wall – Concrete pouring 60% Completed; FF Slab Staging works 15% Completed • School Building - Superstructure – GF RCC Wall Rebar Fixing – 85% completed; GF Wall Concrete 42% completed • School Building - FF RCC Wall Rebar Fixing – 24% completed; | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 29.03% | 26.21% | -2.82% | Annex Superstructure | 2024-10-31 |  | 2024-11-08 | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – GF RCC Wall works to complete; FF Slab works to progress • Shelter Block - Superstructure - GF & FF Structure Strentheing & RCC Wall works to progress. • Shelter Block - Surface Preparation for CFRP Works. | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 11500494.3905 | 180000 | https://drive.google.com/thumbnail?id=1xxrE3LPgzlDH2hVcRgO9_8Tj9dwrwVwk&sz=w1000 | https://drive.google.com/file/d/1xxrE3LPgzlDH2hVcRgO9_8Tj9dwrwVwk/view?usp=drive_link | https://drive.google.com/thumbnail?id=1oxqPS_1tBA-gVsLfO5IQXOGLDroKN7-w&sz=w1000 | https://drive.google.com/file/d/1oxqPS_1tBA-gVsLfO5IQXOGLDroKN7-w/view?usp=drive_link | https://drive.google.com/thumbnail?id=1m_ZcOGPlgePKQ5iHcOHOG_LcxNkDkiJ-&sz=w1000 | https://drive.google.com/file/d/1m_ZcOGPlgePKQ5iHcOHOG_LcxNkDkiJ-/view?usp=drive_link
2024-09-13 | Madinat Zayed-School-P38 | P38 | SC-07 | 362 | 185 | 547 | • Annex Building - GF RCC Wall – Rebar fixing 98% Completed. • Annex Building - GF RCC Wall – Concrete pouring 60% Completed; FF Slab Staging works 15% Completed • School Building - Superstructure – GF RCC Wall Rebar Fixing – 85% completed; GF Wall Concrete 42% completed • School Building - FF RCC Wall Rebar Fixing – 24% completed; | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 29.03% | 26.21% | -2.82% | MEP & Finishes | 2025-01-25 |  | 2025-05-06 | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – GF RCC Wall works to complete; FF Slab works to progress • Shelter Block - Superstructure - GF & FF Structure Strentheing & RCC Wall works to progress. • Shelter Block - Surface Preparation for CFRP Works. | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 11500494.3905 | 180000 | https://drive.google.com/thumbnail?id=1xxrE3LPgzlDH2hVcRgO9_8Tj9dwrwVwk&sz=w1000 | https://drive.google.com/file/d/1xxrE3LPgzlDH2hVcRgO9_8Tj9dwrwVwk/view?usp=drive_link | https://drive.google.com/thumbnail?id=1oxqPS_1tBA-gVsLfO5IQXOGLDroKN7-w&sz=w1000 | https://drive.google.com/file/d/1oxqPS_1tBA-gVsLfO5IQXOGLDroKN7-w/view?usp=drive_link | https://drive.google.com/thumbnail?id=1m_ZcOGPlgePKQ5iHcOHOG_LcxNkDkiJ-&sz=w1000 | https://drive.google.com/file/d/1m_ZcOGPlgePKQ5iHcOHOG_LcxNkDkiJ-/view?usp=drive_link
2024-09-13 | Madinat Zayed-School-P38 | P38 | SC-07 | 362 | 185 | 547 | • Annex Building - GF RCC Wall – Rebar fixing 98% Completed. • Annex Building - GF RCC Wall – Concrete pouring 60% Completed; FF Slab Staging works 15% Completed • School Building - Superstructure – GF RCC Wall Rebar Fixing – 85% completed; GF Wall Concrete 42% completed • School Building - FF RCC Wall Rebar Fixing – 24% completed; | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 29.03% | 26.21% | -2.82% | BCC Inspection | 2025-02-13 |  | 2025-05-26 | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – GF RCC Wall works to complete; FF Slab works to progress • Shelter Block - Superstructure - GF & FF Structure Strentheing & RCC Wall works to progress. • Shelter Block - Surface Preparation for CFRP Works. | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 11500494.3905 | 180000 | https://drive.google.com/thumbnail?id=1xxrE3LPgzlDH2hVcRgO9_8Tj9dwrwVwk&sz=w1000 | https://drive.google.com/file/d/1xxrE3LPgzlDH2hVcRgO9_8Tj9dwrwVwk/view?usp=drive_link | https://drive.google.com/thumbnail?id=1oxqPS_1tBA-gVsLfO5IQXOGLDroKN7-w&sz=w1000 | https://drive.google.com/file/d/1oxqPS_1tBA-gVsLfO5IQXOGLDroKN7-w/view?usp=drive_link | https://drive.google.com/thumbnail?id=1m_ZcOGPlgePKQ5iHcOHOG_LcxNkDkiJ-&sz=w1000 | https://drive.google.com/file/d/1m_ZcOGPlgePKQ5iHcOHOG_LcxNkDkiJ-/view?usp=drive_link
2024-09-13 | Madinat Zayed-School-P38 | P38 | SC-07 | 362 | 185 | 547 | • Annex Building - GF RCC Wall – Rebar fixing 98% Completed. • Annex Building - GF RCC Wall – Concrete pouring 60% Completed; FF Slab Staging works 15% Completed • School Building - Superstructure – GF RCC Wall Rebar Fixing – 85% completed; GF Wall Concrete 42% completed • School Building - FF RCC Wall Rebar Fixing – 24% completed; | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 29.03% | 26.21% | -2.82% | BCC Issuance | 2025-03-04 |  | 2025-06-16 | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – GF RCC Wall works to complete; FF Slab works to progress • Shelter Block - Superstructure - GF & FF Structure Strentheing & RCC Wall works to progress. • Shelter Block - Surface Preparation for CFRP Works. | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 11500494.3905 | 180000 | https://drive.google.com/thumbnail?id=1xxrE3LPgzlDH2hVcRgO9_8Tj9dwrwVwk&sz=w1000 | https://drive.google.com/file/d/1xxrE3LPgzlDH2hVcRgO9_8Tj9dwrwVwk/view?usp=drive_link | https://drive.google.com/thumbnail?id=1oxqPS_1tBA-gVsLfO5IQXOGLDroKN7-w&sz=w1000 | https://drive.google.com/file/d/1oxqPS_1tBA-gVsLfO5IQXOGLDroKN7-w/view?usp=drive_link | https://drive.google.com/thumbnail?id=1m_ZcOGPlgePKQ5iHcOHOG_LcxNkDkiJ-&sz=w1000 | https://drive.google.com/file/d/1m_ZcOGPlgePKQ5iHcOHOG_LcxNkDkiJ-/view?usp=drive_link
2024-09-13 | Madinat Zayed-School-P38 | P38 | SC-07 | 362 | 185 | 547 | • Annex Building - GF RCC Wall – Rebar fixing 98% Completed. • Annex Building - GF RCC Wall – Concrete pouring 60% Completed; FF Slab Staging works 15% Completed • School Building - Superstructure – GF RCC Wall Rebar Fixing – 85% completed; GF Wall Concrete 42% completed • School Building - FF RCC Wall Rebar Fixing – 24% completed; | • To minimize impact due to the MEP Agency finalization delay, the contractor proactively engaged an external agency for shop drawing preparation and initiated procurement. • School Construction is ongoing while awaiting final cost agreement with the employer. | 29.03% | 26.21% | -2.82% | Completion | 2025-03-17 |  | 2025-06-30 | 2024-09-20 | •Bill No.4 – MEP Final Rate Agreement required – 20-Sep-24 (hindering the mobilization of the MEP agency, impacting engineering & procurement processes) • Approval for Remaining Cost plus & Re-measurable Items required – 20-Sep-24 (Hampering the Annex & School building progress) • MEP Long lead items – The delayed mobilization of the MEP agency is hindering the submission and approval of long lead items (Impacted in the critical path) • Increased scope and work volume (Internal wall + External RCC Wall at School) due to design recommendation are impacting project progress. | • Prioritize the Submittal & approval process, faster open communication with stakeholders, and explore interim solutions if necessary. • Expedite approval requests, provide comprehensive documentation, expedite procurement of critical materials. • Implement parallel processing, prioritize agency mobilization, and explore alternative suppliers if needed. assess the potential benefits of local procurement. • Review the scope changes and construction methodology, Develop the plan to accommodate the increased work. communicate changes effectively, and implement robust change management processes. | • Annex Building - Superstructure works – GF RCC Wall works to complete; FF Slab works to progress • Shelter Block - Superstructure - GF & FF Structure Strentheing & RCC Wall works to progress. • Shelter Block - Surface Preparation for CFRP Works. | 78077600 | 0 | 78077600 | 1576709 | 0 | 79654309 | 11500494.3905 | 180000 | https://drive.google.com/thumbnail?id=1xxrE3LPgzlDH2hVcRgO9_8Tj9dwrwVwk&sz=w1000 | https://drive.google.com/file/d/1xxrE3LPgzlDH2hVcRgO9_8Tj9dwrwVwk/view?usp=drive_link | https://drive.google.com/thumbnail?id=1oxqPS_1tBA-gVsLfO5IQXOGLDroKN7-w&sz=w1000 | https://drive.google.com/file/d/1oxqPS_1tBA-gVsLfO5IQXOGLDroKN7-w/view?usp=drive_link | https://drive.google.com/thumbnail?id=1m_ZcOGPlgePKQ5iHcOHOG_LcxNkDkiJ-&sz=w1000 | https://drive.google.com/file/d/1m_ZcOGPlgePKQ5iHcOHOG_LcxNkDkiJ-/view?usp=drive_link
2024-09-13 | Zayed City-Majlis-P17 | P17 | MJ-04 | 110 | 620 | 730 | • Shoring guide is Completed • Secant piles is Completed | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. | 9.12% | 9.12% | 0% | Commencement Date | 2024-06-03 | 2024-06-03 |  | 2024-09-20 | • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval (if any) for Contractor's Pile Design. • Design update (if any), in compliance with sevene comments | • Resubmitted on 18 Sep.2024 & UR. • Coordinate with sevene for ADM review schedule. • Design team re-submitted to sevene on 20-sep-2024 | • Casting of Capping beam • Starting of Raft Piles. | 106953287.35 | 0 | 106953287.35 | 3824490.97 | 0 | 110777778.32 | 10680390 | 199302.08 | https://drive.google.com/thumbnail?id=1ruM5f-JPXrFoNb6xNaz40ic4CGr2kGvK&sz=w1000 | https://drive.google.com/file/d/1ruM5f-JPXrFoNb6xNaz40ic4CGr2kGvK/view | https://drive.google.com/thumbnail?id=1Q6MU9kG1fczWg0z99j87JV0I8dZyJDIP&sz=w1000 | https://drive.google.com/file/d/1Q6MU9kG1fczWg0z99j87JV0I8dZyJDIP/view | https://drive.google.com/thumbnail?id=1La3JnRLTGosBhQtrjluRdPiS-rya-Lxf&sz=w1000 | https://drive.google.com/file/d/1La3JnRLTGosBhQtrjluRdPiS-rya-Lxf/view
2024-09-13 | Zayed City-Majlis-P17 | P17 | MJ-04 | 110 | 620 | 730 | • Shoring guide is Completed • Secant piles is Completed | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. | 9.12% | 9.12% | 0% | Construction Permit | 2024-06-12 | 2024-05-27 |  | 2024-09-20 | • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval (if any) for Contractor's Pile Design. • Design update (if any), in compliance with sevene comments | • Resubmitted on 18 Sep.2024 & UR. • Coordinate with sevene for ADM review schedule. • Design team re-submitted to sevene on 20-sep-2024 | • Casting of Capping beam • Starting of Raft Piles. | 106953287.35 | 0 | 106953287.35 | 3824490.97 | 0 | 110777778.32 | 10680390 | 199302.08 | https://drive.google.com/thumbnail?id=1ruM5f-JPXrFoNb6xNaz40ic4CGr2kGvK&sz=w1000 | https://drive.google.com/file/d/1ruM5f-JPXrFoNb6xNaz40ic4CGr2kGvK/view | https://drive.google.com/thumbnail?id=1Q6MU9kG1fczWg0z99j87JV0I8dZyJDIP&sz=w1000 | https://drive.google.com/file/d/1Q6MU9kG1fczWg0z99j87JV0I8dZyJDIP/view | https://drive.google.com/thumbnail?id=1La3JnRLTGosBhQtrjluRdPiS-rya-Lxf&sz=w1000 | https://drive.google.com/file/d/1La3JnRLTGosBhQtrjluRdPiS-rya-Lxf/view
2024-09-13 | Zayed City-Majlis-P17 | P17 | MJ-04 | 110 | 620 | 730 | • Shoring guide is Completed • Secant piles is Completed | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. | 9.12% | 9.12% | 0% | Site Mobilization | 2024-07-10 | 2024-08-15 |  | 2024-09-20 | • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval (if any) for Contractor's Pile Design. • Design update (if any), in compliance with sevene comments | • Resubmitted on 18 Sep.2024 & UR. • Coordinate with sevene for ADM review schedule. • Design team re-submitted to sevene on 20-sep-2024 | • Casting of Capping beam • Starting of Raft Piles. | 106953287.35 | 0 | 106953287.35 | 3824490.97 | 0 | 110777778.32 | 10680390 | 199302.08 | https://drive.google.com/thumbnail?id=1ruM5f-JPXrFoNb6xNaz40ic4CGr2kGvK&sz=w1000 | https://drive.google.com/file/d/1ruM5f-JPXrFoNb6xNaz40ic4CGr2kGvK/view | https://drive.google.com/thumbnail?id=1Q6MU9kG1fczWg0z99j87JV0I8dZyJDIP&sz=w1000 | https://drive.google.com/file/d/1Q6MU9kG1fczWg0z99j87JV0I8dZyJDIP/view | https://drive.google.com/thumbnail?id=1La3JnRLTGosBhQtrjluRdPiS-rya-Lxf&sz=w1000 | https://drive.google.com/file/d/1La3JnRLTGosBhQtrjluRdPiS-rya-Lxf/view
2024-09-13 | Zayed City-Majlis-P17 | P17 | MJ-04 | 110 | 620 | 730 | • Shoring guide is Completed • Secant piles is Completed | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. | 9.12% | 9.12% | 0% | Shoring Drilling & Casting | 2024-09-30 |  | 2024-09-30 | 2024-09-20 | • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval (if any) for Contractor's Pile Design. • Design update (if any), in compliance with sevene comments | • Resubmitted on 18 Sep.2024 & UR. • Coordinate with sevene for ADM review schedule. • Design team re-submitted to sevene on 20-sep-2024 | • Casting of Capping beam • Starting of Raft Piles. | 106953287.35 | 0 | 106953287.35 | 3824490.97 | 0 | 110777778.32 | 10680390 | 199302.08 | https://drive.google.com/thumbnail?id=1ruM5f-JPXrFoNb6xNaz40ic4CGr2kGvK&sz=w1000 | https://drive.google.com/file/d/1ruM5f-JPXrFoNb6xNaz40ic4CGr2kGvK/view | https://drive.google.com/thumbnail?id=1Q6MU9kG1fczWg0z99j87JV0I8dZyJDIP&sz=w1000 | https://drive.google.com/file/d/1Q6MU9kG1fczWg0z99j87JV0I8dZyJDIP/view | https://drive.google.com/thumbnail?id=1La3JnRLTGosBhQtrjluRdPiS-rya-Lxf&sz=w1000 | https://drive.google.com/file/d/1La3JnRLTGosBhQtrjluRdPiS-rya-Lxf/view
2024-09-13 | Zayed City-Majlis-P17 | P17 | MJ-04 | 110 | 620 | 730 | • Shoring guide is Completed • Secant piles is Completed | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. | 9.12% | 9.12% | 0% | Piling Drilling & Casting | 2024-11-30 |  | 2024-11-30 | 2024-09-20 | • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval (if any) for Contractor's Pile Design. • Design update (if any), in compliance with sevene comments | • Resubmitted on 18 Sep.2024 & UR. • Coordinate with sevene for ADM review schedule. • Design team re-submitted to sevene on 20-sep-2024 | • Casting of Capping beam • Starting of Raft Piles. | 106953287.35 | 0 | 106953287.35 | 3824490.97 | 0 | 110777778.32 | 10680390 | 199302.08 | https://drive.google.com/thumbnail?id=1ruM5f-JPXrFoNb6xNaz40ic4CGr2kGvK&sz=w1000 | https://drive.google.com/file/d/1ruM5f-JPXrFoNb6xNaz40ic4CGr2kGvK/view | https://drive.google.com/thumbnail?id=1Q6MU9kG1fczWg0z99j87JV0I8dZyJDIP&sz=w1000 | https://drive.google.com/file/d/1Q6MU9kG1fczWg0z99j87JV0I8dZyJDIP/view | https://drive.google.com/thumbnail?id=1La3JnRLTGosBhQtrjluRdPiS-rya-Lxf&sz=w1000 | https://drive.google.com/file/d/1La3JnRLTGosBhQtrjluRdPiS-rya-Lxf/view
2024-09-13 | Zayed City-Majlis-P17 | P17 | MJ-04 | 110 | 620 | 730 | • Shoring guide is Completed • Secant piles is Completed | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. | 9.12% | 9.12% | 0% | Excavation | 2025-02-13 |  | 2025-02-13 | 2024-09-20 | • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval (if any) for Contractor's Pile Design. • Design update (if any), in compliance with sevene comments | • Resubmitted on 18 Sep.2024 & UR. • Coordinate with sevene for ADM review schedule. • Design team re-submitted to sevene on 20-sep-2024 | • Casting of Capping beam • Starting of Raft Piles. | 106953287.35 | 0 | 106953287.35 | 3824490.97 | 0 | 110777778.32 | 10680390 | 199302.08 | https://drive.google.com/thumbnail?id=1ruM5f-JPXrFoNb6xNaz40ic4CGr2kGvK&sz=w1000 | https://drive.google.com/file/d/1ruM5f-JPXrFoNb6xNaz40ic4CGr2kGvK/view | https://drive.google.com/thumbnail?id=1Q6MU9kG1fczWg0z99j87JV0I8dZyJDIP&sz=w1000 | https://drive.google.com/file/d/1Q6MU9kG1fczWg0z99j87JV0I8dZyJDIP/view | https://drive.google.com/thumbnail?id=1La3JnRLTGosBhQtrjluRdPiS-rya-Lxf&sz=w1000 | https://drive.google.com/file/d/1La3JnRLTGosBhQtrjluRdPiS-rya-Lxf/view
2024-09-13 | Zayed City-Majlis-P17 | P17 | MJ-04 | 110 | 620 | 730 | • Shoring guide is Completed • Secant piles is Completed | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. | 9.12% | 9.12% | 0% | Substructure | 2025-07-20 |  | 2025-07-20 | 2024-09-20 | • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval (if any) for Contractor's Pile Design. • Design update (if any), in compliance with sevene comments | • Resubmitted on 18 Sep.2024 & UR. • Coordinate with sevene for ADM review schedule. • Design team re-submitted to sevene on 20-sep-2024 | • Casting of Capping beam • Starting of Raft Piles. | 106953287.35 | 0 | 106953287.35 | 3824490.97 | 0 | 110777778.32 | 10680390 | 199302.08 | https://drive.google.com/thumbnail?id=1ruM5f-JPXrFoNb6xNaz40ic4CGr2kGvK&sz=w1000 | https://drive.google.com/file/d/1ruM5f-JPXrFoNb6xNaz40ic4CGr2kGvK/view | https://drive.google.com/thumbnail?id=1Q6MU9kG1fczWg0z99j87JV0I8dZyJDIP&sz=w1000 | https://drive.google.com/file/d/1Q6MU9kG1fczWg0z99j87JV0I8dZyJDIP/view | https://drive.google.com/thumbnail?id=1La3JnRLTGosBhQtrjluRdPiS-rya-Lxf&sz=w1000 | https://drive.google.com/file/d/1La3JnRLTGosBhQtrjluRdPiS-rya-Lxf/view
2024-09-13 | Zayed City-Majlis-P17 | P17 | MJ-04 | 110 | 620 | 730 | • Shoring guide is Completed • Secant piles is Completed | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. | 9.12% | 9.12% | 0% | Superstructure | 2025-11-13 |  | 2025-11-13 | 2024-09-20 | • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval (if any) for Contractor's Pile Design. • Design update (if any), in compliance with sevene comments | • Resubmitted on 18 Sep.2024 & UR. • Coordinate with sevene for ADM review schedule. • Design team re-submitted to sevene on 20-sep-2024 | • Casting of Capping beam • Starting of Raft Piles. | 106953287.35 | 0 | 106953287.35 | 3824490.97 | 0 | 110777778.32 | 10680390 | 199302.08 | https://drive.google.com/thumbnail?id=1ruM5f-JPXrFoNb6xNaz40ic4CGr2kGvK&sz=w1000 | https://drive.google.com/file/d/1ruM5f-JPXrFoNb6xNaz40ic4CGr2kGvK/view | https://drive.google.com/thumbnail?id=1Q6MU9kG1fczWg0z99j87JV0I8dZyJDIP&sz=w1000 | https://drive.google.com/file/d/1Q6MU9kG1fczWg0z99j87JV0I8dZyJDIP/view | https://drive.google.com/thumbnail?id=1La3JnRLTGosBhQtrjluRdPiS-rya-Lxf&sz=w1000 | https://drive.google.com/file/d/1La3JnRLTGosBhQtrjluRdPiS-rya-Lxf/view
2024-09-13 | Zayed City-Majlis-P17 | P17 | MJ-04 | 110 | 620 | 730 | • Shoring guide is Completed • Secant piles is Completed | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. | 9.12% | 9.12% | 0% | MEP & Finishes | 2026-05-08 |  | 2026-05-08 | 2024-09-20 | • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval (if any) for Contractor's Pile Design. • Design update (if any), in compliance with sevene comments | • Resubmitted on 18 Sep.2024 & UR. • Coordinate with sevene for ADM review schedule. • Design team re-submitted to sevene on 20-sep-2024 | • Casting of Capping beam • Starting of Raft Piles. | 106953287.35 | 0 | 106953287.35 | 3824490.97 | 0 | 110777778.32 | 10680390 | 199302.08 | https://drive.google.com/thumbnail?id=1ruM5f-JPXrFoNb6xNaz40ic4CGr2kGvK&sz=w1000 | https://drive.google.com/file/d/1ruM5f-JPXrFoNb6xNaz40ic4CGr2kGvK/view | https://drive.google.com/thumbnail?id=1Q6MU9kG1fczWg0z99j87JV0I8dZyJDIP&sz=w1000 | https://drive.google.com/file/d/1Q6MU9kG1fczWg0z99j87JV0I8dZyJDIP/view | https://drive.google.com/thumbnail?id=1La3JnRLTGosBhQtrjluRdPiS-rya-Lxf&sz=w1000 | https://drive.google.com/file/d/1La3JnRLTGosBhQtrjluRdPiS-rya-Lxf/view
2024-09-13 | Zayed City-Majlis-P17 | P17 | MJ-04 | 110 | 620 | 730 | • Shoring guide is Completed • Secant piles is Completed | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. | 9.12% | 9.12% | 0% | Authorities NOCs/BCC | 2026-05-29 |  | 2026-05-29 | 2024-09-20 | • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval (if any) for Contractor's Pile Design. • Design update (if any), in compliance with sevene comments | • Resubmitted on 18 Sep.2024 & UR. • Coordinate with sevene for ADM review schedule. • Design team re-submitted to sevene on 20-sep-2024 | • Casting of Capping beam • Starting of Raft Piles. | 106953287.35 | 0 | 106953287.35 | 3824490.97 | 0 | 110777778.32 | 10680390 | 199302.08 | https://drive.google.com/thumbnail?id=1ruM5f-JPXrFoNb6xNaz40ic4CGr2kGvK&sz=w1000 | https://drive.google.com/file/d/1ruM5f-JPXrFoNb6xNaz40ic4CGr2kGvK/view | https://drive.google.com/thumbnail?id=1Q6MU9kG1fczWg0z99j87JV0I8dZyJDIP&sz=w1000 | https://drive.google.com/file/d/1Q6MU9kG1fczWg0z99j87JV0I8dZyJDIP/view | https://drive.google.com/thumbnail?id=1La3JnRLTGosBhQtrjluRdPiS-rya-Lxf&sz=w1000 | https://drive.google.com/file/d/1La3JnRLTGosBhQtrjluRdPiS-rya-Lxf/view
2024-09-13 | Zayed City-Majlis-P17 | P17 | MJ-04 | 110 | 620 | 730 | • Shoring guide is Completed • Secant piles is Completed | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. | 9.12% | 9.12% | 0% | External Works | 2026-06-02 |  | 2026-06-02 | 2024-09-20 | • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval (if any) for Contractor's Pile Design. • Design update (if any), in compliance with sevene comments | • Resubmitted on 18 Sep.2024 & UR. • Coordinate with sevene for ADM review schedule. • Design team re-submitted to sevene on 20-sep-2024 | • Casting of Capping beam • Starting of Raft Piles. | 106953287.35 | 0 | 106953287.35 | 3824490.97 | 0 | 110777778.32 | 10680390 | 199302.08 | https://drive.google.com/thumbnail?id=1ruM5f-JPXrFoNb6xNaz40ic4CGr2kGvK&sz=w1000 | https://drive.google.com/file/d/1ruM5f-JPXrFoNb6xNaz40ic4CGr2kGvK/view | https://drive.google.com/thumbnail?id=1Q6MU9kG1fczWg0z99j87JV0I8dZyJDIP&sz=w1000 | https://drive.google.com/file/d/1Q6MU9kG1fczWg0z99j87JV0I8dZyJDIP/view | https://drive.google.com/thumbnail?id=1La3JnRLTGosBhQtrjluRdPiS-rya-Lxf&sz=w1000 | https://drive.google.com/file/d/1La3JnRLTGosBhQtrjluRdPiS-rya-Lxf/view
2024-09-13 | Zayed City-Majlis-P17 | P17 | MJ-04 | 110 | 620 | 730 | • Shoring guide is Completed • Secant piles is Completed | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. | 9.12% | 9.12% | 0% | Testing & Commissioning | 2026-06-02 |  | 2026-06-02 | 2024-09-20 | • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval (if any) for Contractor's Pile Design. • Design update (if any), in compliance with sevene comments | • Resubmitted on 18 Sep.2024 & UR. • Coordinate with sevene for ADM review schedule. • Design team re-submitted to sevene on 20-sep-2024 | • Casting of Capping beam • Starting of Raft Piles. | 106953287.35 | 0 | 106953287.35 | 3824490.97 | 0 | 110777778.32 | 10680390 | 199302.08 | https://drive.google.com/thumbnail?id=1ruM5f-JPXrFoNb6xNaz40ic4CGr2kGvK&sz=w1000 | https://drive.google.com/file/d/1ruM5f-JPXrFoNb6xNaz40ic4CGr2kGvK/view | https://drive.google.com/thumbnail?id=1Q6MU9kG1fczWg0z99j87JV0I8dZyJDIP&sz=w1000 | https://drive.google.com/file/d/1Q6MU9kG1fczWg0z99j87JV0I8dZyJDIP/view | https://drive.google.com/thumbnail?id=1La3JnRLTGosBhQtrjluRdPiS-rya-Lxf&sz=w1000 | https://drive.google.com/file/d/1La3JnRLTGosBhQtrjluRdPiS-rya-Lxf/view
2024-09-13 | Zayed City-Majlis-P17 | P17 | MJ-04 | 110 | 620 | 730 | • Shoring guide is Completed • Secant piles is Completed | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. | 9.12% | 9.12% | 0% | Substantial Completion | 2026-06-02 |  | 2026-06-02 | 2024-09-20 | • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval (if any) for Contractor's Pile Design. • Design update (if any), in compliance with sevene comments | • Resubmitted on 18 Sep.2024 & UR. • Coordinate with sevene for ADM review schedule. • Design team re-submitted to sevene on 20-sep-2024 | • Casting of Capping beam • Starting of Raft Piles. | 106953287.35 | 0 | 106953287.35 | 3824490.97 | 0 | 110777778.32 | 10680390 | 199302.08 | https://drive.google.com/thumbnail?id=1ruM5f-JPXrFoNb6xNaz40ic4CGr2kGvK&sz=w1000 | https://drive.google.com/file/d/1ruM5f-JPXrFoNb6xNaz40ic4CGr2kGvK/view | https://drive.google.com/thumbnail?id=1Q6MU9kG1fczWg0z99j87JV0I8dZyJDIP&sz=w1000 | https://drive.google.com/file/d/1Q6MU9kG1fczWg0z99j87JV0I8dZyJDIP/view | https://drive.google.com/thumbnail?id=1La3JnRLTGosBhQtrjluRdPiS-rya-Lxf&sz=w1000 | https://drive.google.com/file/d/1La3JnRLTGosBhQtrjluRdPiS-rya-Lxf/view
2024-09-13 | Baniyas-Majlis-P13 | P13 | MJ-05 | 110 | 620 | 730 | • Shoring guide wall Completed. • Secant piles Completed. • AWQAF approved Mosque Design. • ADDC accepted protection of existing FH/ water pipeline. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. & PS diversion of existing utilities at Plot P1. • Mosque design assigned to APG. | 7.91% | 8.09% | 0.18% | Commencement Date | 2024-06-03 | 2024-06-03 |  | 2024-09-20 | • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval (if any) for Contractor's Pile Design. • Design update (if any), in compliance with sevene comments | • Resubmitted on 18 Sep.2024 & UR. • Coordinate with sevene for ADM review schedule. • Design team re-submitted to sevene on 20-sep-2024 | • Casting of Capping Beam • Starting of Raft piles | 130388712.65 | 0 | 130388712.65 | 4662507.03 | 0 | 135051219.68 | 13053810 | 243591.44 | https://drive.google.com/thumbnail?id=1N6JLvInqt6UGVAo8jpPfLxV1anlM3LhC&sz=w1000 | https://drive.google.com/file/d/1N6JLvInqt6UGVAo8jpPfLxV1anlM3LhC/view | https://drive.google.com/thumbnail?id=1qZSXHwjD6UiZLiCnVCCPpTfeEZz74aAs&sz=w1000 | https://drive.google.com/file/d/1qZSXHwjD6UiZLiCnVCCPpTfeEZz74aAs/view | https://drive.google.com/thumbnail?id=197Upk1lRbxo1iH4nl3_asxDxnnQz-xvq&sz=w1000 | https://drive.google.com/file/d/197Upk1lRbxo1iH4nl3_asxDxnnQz-xvq/view
2024-09-13 | Baniyas-Majlis-P13 | P13 | MJ-05 | 110 | 620 | 730 | • Shoring guide wall Completed. • Secant piles Completed. • AWQAF approved Mosque Design. • ADDC accepted protection of existing FH/ water pipeline. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. & PS diversion of existing utilities at Plot P1. • Mosque design assigned to APG. | 7.91% | 8.09% | 0.18% | Construction Permit | 2024-06-12 | 2024-05-22 |  | 2024-09-20 | • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval (if any) for Contractor's Pile Design. • Design update (if any), in compliance with sevene comments | • Resubmitted on 18 Sep.2024 & UR. • Coordinate with sevene for ADM review schedule. • Design team re-submitted to sevene on 20-sep-2024 | • Casting of Capping Beam • Starting of Raft piles | 130388712.65 | 0 | 130388712.65 | 4662507.03 | 0 | 135051219.68 | 13053810 | 243591.44 | https://drive.google.com/thumbnail?id=1N6JLvInqt6UGVAo8jpPfLxV1anlM3LhC&sz=w1000 | https://drive.google.com/file/d/1N6JLvInqt6UGVAo8jpPfLxV1anlM3LhC/view | https://drive.google.com/thumbnail?id=1qZSXHwjD6UiZLiCnVCCPpTfeEZz74aAs&sz=w1000 | https://drive.google.com/file/d/1qZSXHwjD6UiZLiCnVCCPpTfeEZz74aAs/view | https://drive.google.com/thumbnail?id=197Upk1lRbxo1iH4nl3_asxDxnnQz-xvq&sz=w1000 | https://drive.google.com/file/d/197Upk1lRbxo1iH4nl3_asxDxnnQz-xvq/view
2024-09-13 | Baniyas-Majlis-P13 | P13 | MJ-05 | 110 | 620 | 730 | • Shoring guide wall Completed. • Secant piles Completed. • AWQAF approved Mosque Design. • ADDC accepted protection of existing FH/ water pipeline. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. & PS diversion of existing utilities at Plot P1. • Mosque design assigned to APG. | 7.91% | 8.09% | 0.18% | Site Mobilization | 2024-07-10 | 2024-08-08 |  | 2024-09-20 | • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval (if any) for Contractor's Pile Design. • Design update (if any), in compliance with sevene comments | • Resubmitted on 18 Sep.2024 & UR. • Coordinate with sevene for ADM review schedule. • Design team re-submitted to sevene on 20-sep-2024 | • Casting of Capping Beam • Starting of Raft piles | 130388712.65 | 0 | 130388712.65 | 4662507.03 | 0 | 135051219.68 | 13053810 | 243591.44 | https://drive.google.com/thumbnail?id=1N6JLvInqt6UGVAo8jpPfLxV1anlM3LhC&sz=w1000 | https://drive.google.com/file/d/1N6JLvInqt6UGVAo8jpPfLxV1anlM3LhC/view | https://drive.google.com/thumbnail?id=1qZSXHwjD6UiZLiCnVCCPpTfeEZz74aAs&sz=w1000 | https://drive.google.com/file/d/1qZSXHwjD6UiZLiCnVCCPpTfeEZz74aAs/view | https://drive.google.com/thumbnail?id=197Upk1lRbxo1iH4nl3_asxDxnnQz-xvq&sz=w1000 | https://drive.google.com/file/d/197Upk1lRbxo1iH4nl3_asxDxnnQz-xvq/view
2024-09-13 | Baniyas-Majlis-P13 | P13 | MJ-05 | 110 | 620 | 730 | • Shoring guide wall Completed. • Secant piles Completed. • AWQAF approved Mosque Design. • ADDC accepted protection of existing FH/ water pipeline. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. & PS diversion of existing utilities at Plot P1. • Mosque design assigned to APG. | 7.91% | 8.09% | 0.18% | Shoring Drilling & Casting | 2024-09-28 |  | 2024-09-28 | 2024-09-20 | • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval (if any) for Contractor's Pile Design. • Design update (if any), in compliance with sevene comments | • Resubmitted on 18 Sep.2024 & UR. • Coordinate with sevene for ADM review schedule. • Design team re-submitted to sevene on 20-sep-2024 | • Casting of Capping Beam • Starting of Raft piles | 130388712.65 | 0 | 130388712.65 | 4662507.03 | 0 | 135051219.68 | 13053810 | 243591.44 | https://drive.google.com/thumbnail?id=1N6JLvInqt6UGVAo8jpPfLxV1anlM3LhC&sz=w1000 | https://drive.google.com/file/d/1N6JLvInqt6UGVAo8jpPfLxV1anlM3LhC/view | https://drive.google.com/thumbnail?id=1qZSXHwjD6UiZLiCnVCCPpTfeEZz74aAs&sz=w1000 | https://drive.google.com/file/d/1qZSXHwjD6UiZLiCnVCCPpTfeEZz74aAs/view | https://drive.google.com/thumbnail?id=197Upk1lRbxo1iH4nl3_asxDxnnQz-xvq&sz=w1000 | https://drive.google.com/file/d/197Upk1lRbxo1iH4nl3_asxDxnnQz-xvq/view
2024-09-13 | Baniyas-Majlis-P13 | P13 | MJ-05 | 110 | 620 | 730 | • Shoring guide wall Completed. • Secant piles Completed. • AWQAF approved Mosque Design. • ADDC accepted protection of existing FH/ water pipeline. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. & PS diversion of existing utilities at Plot P1. • Mosque design assigned to APG. | 7.91% | 8.09% | 0.18% | Piling Drilling & Casting | 2024-11-29 |  | 2024-11-29 | 2024-09-20 | • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval (if any) for Contractor's Pile Design. • Design update (if any), in compliance with sevene comments | • Resubmitted on 18 Sep.2024 & UR. • Coordinate with sevene for ADM review schedule. • Design team re-submitted to sevene on 20-sep-2024 | • Casting of Capping Beam • Starting of Raft piles | 130388712.65 | 0 | 130388712.65 | 4662507.03 | 0 | 135051219.68 | 13053810 | 243591.44 | https://drive.google.com/thumbnail?id=1N6JLvInqt6UGVAo8jpPfLxV1anlM3LhC&sz=w1000 | https://drive.google.com/file/d/1N6JLvInqt6UGVAo8jpPfLxV1anlM3LhC/view | https://drive.google.com/thumbnail?id=1qZSXHwjD6UiZLiCnVCCPpTfeEZz74aAs&sz=w1000 | https://drive.google.com/file/d/1qZSXHwjD6UiZLiCnVCCPpTfeEZz74aAs/view | https://drive.google.com/thumbnail?id=197Upk1lRbxo1iH4nl3_asxDxnnQz-xvq&sz=w1000 | https://drive.google.com/file/d/197Upk1lRbxo1iH4nl3_asxDxnnQz-xvq/view
2024-09-13 | Baniyas-Majlis-P13 | P13 | MJ-05 | 110 | 620 | 730 | • Shoring guide wall Completed. • Secant piles Completed. • AWQAF approved Mosque Design. • ADDC accepted protection of existing FH/ water pipeline. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. & PS diversion of existing utilities at Plot P1. • Mosque design assigned to APG. | 7.91% | 8.09% | 0.18% | Excavation | 2025-02-12 |  | 2025-02-12 | 2024-09-20 | • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval (if any) for Contractor's Pile Design. • Design update (if any), in compliance with sevene comments | • Resubmitted on 18 Sep.2024 & UR. • Coordinate with sevene for ADM review schedule. • Design team re-submitted to sevene on 20-sep-2024 | • Casting of Capping Beam • Starting of Raft piles | 130388712.65 | 0 | 130388712.65 | 4662507.03 | 0 | 135051219.68 | 13053810 | 243591.44 | https://drive.google.com/thumbnail?id=1N6JLvInqt6UGVAo8jpPfLxV1anlM3LhC&sz=w1000 | https://drive.google.com/file/d/1N6JLvInqt6UGVAo8jpPfLxV1anlM3LhC/view | https://drive.google.com/thumbnail?id=1qZSXHwjD6UiZLiCnVCCPpTfeEZz74aAs&sz=w1000 | https://drive.google.com/file/d/1qZSXHwjD6UiZLiCnVCCPpTfeEZz74aAs/view | https://drive.google.com/thumbnail?id=197Upk1lRbxo1iH4nl3_asxDxnnQz-xvq&sz=w1000 | https://drive.google.com/file/d/197Upk1lRbxo1iH4nl3_asxDxnnQz-xvq/view
2024-09-13 | Baniyas-Majlis-P13 | P13 | MJ-05 | 110 | 620 | 730 | • Shoring guide wall Completed. • Secant piles Completed. • AWQAF approved Mosque Design. • ADDC accepted protection of existing FH/ water pipeline. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. & PS diversion of existing utilities at Plot P1. • Mosque design assigned to APG. | 7.91% | 8.09% | 0.18% | Substructure | 2025-07-20 |  | 2025-07-20 | 2024-09-20 | • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval (if any) for Contractor's Pile Design. • Design update (if any), in compliance with sevene comments | • Resubmitted on 18 Sep.2024 & UR. • Coordinate with sevene for ADM review schedule. • Design team re-submitted to sevene on 20-sep-2024 | • Casting of Capping Beam • Starting of Raft piles | 130388712.65 | 0 | 130388712.65 | 4662507.03 | 0 | 135051219.68 | 13053810 | 243591.44 | https://drive.google.com/thumbnail?id=1N6JLvInqt6UGVAo8jpPfLxV1anlM3LhC&sz=w1000 | https://drive.google.com/file/d/1N6JLvInqt6UGVAo8jpPfLxV1anlM3LhC/view | https://drive.google.com/thumbnail?id=1qZSXHwjD6UiZLiCnVCCPpTfeEZz74aAs&sz=w1000 | https://drive.google.com/file/d/1qZSXHwjD6UiZLiCnVCCPpTfeEZz74aAs/view | https://drive.google.com/thumbnail?id=197Upk1lRbxo1iH4nl3_asxDxnnQz-xvq&sz=w1000 | https://drive.google.com/file/d/197Upk1lRbxo1iH4nl3_asxDxnnQz-xvq/view
2024-09-13 | Baniyas-Majlis-P13 | P13 | MJ-05 | 110 | 620 | 730 | • Shoring guide wall Completed. • Secant piles Completed. • AWQAF approved Mosque Design. • ADDC accepted protection of existing FH/ water pipeline. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. & PS diversion of existing utilities at Plot P1. • Mosque design assigned to APG. | 7.91% | 8.09% | 0.18% | Superstructure | 2025-11-06 |  | 2025-11-06 | 2024-09-20 | • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval (if any) for Contractor's Pile Design. • Design update (if any), in compliance with sevene comments | • Resubmitted on 18 Sep.2024 & UR. • Coordinate with sevene for ADM review schedule. • Design team re-submitted to sevene on 20-sep-2024 | • Casting of Capping Beam • Starting of Raft piles | 130388712.65 | 0 | 130388712.65 | 4662507.03 | 0 | 135051219.68 | 13053810 | 243591.44 | https://drive.google.com/thumbnail?id=1N6JLvInqt6UGVAo8jpPfLxV1anlM3LhC&sz=w1000 | https://drive.google.com/file/d/1N6JLvInqt6UGVAo8jpPfLxV1anlM3LhC/view | https://drive.google.com/thumbnail?id=1qZSXHwjD6UiZLiCnVCCPpTfeEZz74aAs&sz=w1000 | https://drive.google.com/file/d/1qZSXHwjD6UiZLiCnVCCPpTfeEZz74aAs/view | https://drive.google.com/thumbnail?id=197Upk1lRbxo1iH4nl3_asxDxnnQz-xvq&sz=w1000 | https://drive.google.com/file/d/197Upk1lRbxo1iH4nl3_asxDxnnQz-xvq/view
2024-09-13 | Baniyas-Majlis-P13 | P13 | MJ-05 | 110 | 620 | 730 | • Shoring guide wall Completed. • Secant piles Completed. • AWQAF approved Mosque Design. • ADDC accepted protection of existing FH/ water pipeline. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. & PS diversion of existing utilities at Plot P1. • Mosque design assigned to APG. | 7.91% | 8.09% | 0.18% | MEP & Finishes | 2026-05-08 |  | 2026-05-08 | 2024-09-20 | • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval (if any) for Contractor's Pile Design. • Design update (if any), in compliance with sevene comments | • Resubmitted on 18 Sep.2024 & UR. • Coordinate with sevene for ADM review schedule. • Design team re-submitted to sevene on 20-sep-2024 | • Casting of Capping Beam • Starting of Raft piles | 130388712.65 | 0 | 130388712.65 | 4662507.03 | 0 | 135051219.68 | 13053810 | 243591.44 | https://drive.google.com/thumbnail?id=1N6JLvInqt6UGVAo8jpPfLxV1anlM3LhC&sz=w1000 | https://drive.google.com/file/d/1N6JLvInqt6UGVAo8jpPfLxV1anlM3LhC/view | https://drive.google.com/thumbnail?id=1qZSXHwjD6UiZLiCnVCCPpTfeEZz74aAs&sz=w1000 | https://drive.google.com/file/d/1qZSXHwjD6UiZLiCnVCCPpTfeEZz74aAs/view | https://drive.google.com/thumbnail?id=197Upk1lRbxo1iH4nl3_asxDxnnQz-xvq&sz=w1000 | https://drive.google.com/file/d/197Upk1lRbxo1iH4nl3_asxDxnnQz-xvq/view
2024-09-13 | Baniyas-Majlis-P13 | P13 | MJ-05 | 110 | 620 | 730 | • Shoring guide wall Completed. • Secant piles Completed. • AWQAF approved Mosque Design. • ADDC accepted protection of existing FH/ water pipeline. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. & PS diversion of existing utilities at Plot P1. • Mosque design assigned to APG. | 7.91% | 8.09% | 0.18% | Authorities NOCs/BCC | 2026-05-22 |  | 2026-05-22 | 2024-09-20 | • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval (if any) for Contractor's Pile Design. • Design update (if any), in compliance with sevene comments | • Resubmitted on 18 Sep.2024 & UR. • Coordinate with sevene for ADM review schedule. • Design team re-submitted to sevene on 20-sep-2024 | • Casting of Capping Beam • Starting of Raft piles | 130388712.65 | 0 | 130388712.65 | 4662507.03 | 0 | 135051219.68 | 13053810 | 243591.44 | https://drive.google.com/thumbnail?id=1N6JLvInqt6UGVAo8jpPfLxV1anlM3LhC&sz=w1000 | https://drive.google.com/file/d/1N6JLvInqt6UGVAo8jpPfLxV1anlM3LhC/view | https://drive.google.com/thumbnail?id=1qZSXHwjD6UiZLiCnVCCPpTfeEZz74aAs&sz=w1000 | https://drive.google.com/file/d/1qZSXHwjD6UiZLiCnVCCPpTfeEZz74aAs/view | https://drive.google.com/thumbnail?id=197Upk1lRbxo1iH4nl3_asxDxnnQz-xvq&sz=w1000 | https://drive.google.com/file/d/197Upk1lRbxo1iH4nl3_asxDxnnQz-xvq/view
2024-09-13 | Baniyas-Majlis-P13 | P13 | MJ-05 | 110 | 620 | 730 | • Shoring guide wall Completed. • Secant piles Completed. • AWQAF approved Mosque Design. • ADDC accepted protection of existing FH/ water pipeline. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. & PS diversion of existing utilities at Plot P1. • Mosque design assigned to APG. | 7.91% | 8.09% | 0.18% | External Works | 2026-06-01 |  | 2026-06-01 | 2024-09-20 | • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval (if any) for Contractor's Pile Design. • Design update (if any), in compliance with sevene comments | • Resubmitted on 18 Sep.2024 & UR. • Coordinate with sevene for ADM review schedule. • Design team re-submitted to sevene on 20-sep-2024 | • Casting of Capping Beam • Starting of Raft piles | 130388712.65 | 0 | 130388712.65 | 4662507.03 | 0 | 135051219.68 | 13053810 | 243591.44 | https://drive.google.com/thumbnail?id=1N6JLvInqt6UGVAo8jpPfLxV1anlM3LhC&sz=w1000 | https://drive.google.com/file/d/1N6JLvInqt6UGVAo8jpPfLxV1anlM3LhC/view | https://drive.google.com/thumbnail?id=1qZSXHwjD6UiZLiCnVCCPpTfeEZz74aAs&sz=w1000 | https://drive.google.com/file/d/1qZSXHwjD6UiZLiCnVCCPpTfeEZz74aAs/view | https://drive.google.com/thumbnail?id=197Upk1lRbxo1iH4nl3_asxDxnnQz-xvq&sz=w1000 | https://drive.google.com/file/d/197Upk1lRbxo1iH4nl3_asxDxnnQz-xvq/view
2024-09-13 | Baniyas-Majlis-P13 | P13 | MJ-05 | 110 | 620 | 730 | • Shoring guide wall Completed. • Secant piles Completed. • AWQAF approved Mosque Design. • ADDC accepted protection of existing FH/ water pipeline. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. & PS diversion of existing utilities at Plot P1. • Mosque design assigned to APG. | 7.91% | 8.09% | 0.18% | Testing & Commissioning | 2026-06-02 |  | 2026-06-02 | 2024-09-20 | • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval (if any) for Contractor's Pile Design. • Design update (if any), in compliance with sevene comments | • Resubmitted on 18 Sep.2024 & UR. • Coordinate with sevene for ADM review schedule. • Design team re-submitted to sevene on 20-sep-2024 | • Casting of Capping Beam • Starting of Raft piles | 130388712.65 | 0 | 130388712.65 | 4662507.03 | 0 | 135051219.68 | 13053810 | 243591.44 | https://drive.google.com/thumbnail?id=1N6JLvInqt6UGVAo8jpPfLxV1anlM3LhC&sz=w1000 | https://drive.google.com/file/d/1N6JLvInqt6UGVAo8jpPfLxV1anlM3LhC/view | https://drive.google.com/thumbnail?id=1qZSXHwjD6UiZLiCnVCCPpTfeEZz74aAs&sz=w1000 | https://drive.google.com/file/d/1qZSXHwjD6UiZLiCnVCCPpTfeEZz74aAs/view | https://drive.google.com/thumbnail?id=197Upk1lRbxo1iH4nl3_asxDxnnQz-xvq&sz=w1000 | https://drive.google.com/file/d/197Upk1lRbxo1iH4nl3_asxDxnnQz-xvq/view
2024-09-13 | Baniyas-Majlis-P13 | P13 | MJ-05 | 110 | 620 | 730 | • Shoring guide wall Completed. • Secant piles Completed. • AWQAF approved Mosque Design. • ADDC accepted protection of existing FH/ water pipeline. | • Optimized pile design rev.1, released to the Contractor. • Instruct Contractor for tech. & commercial of PS for shelter special sys. & PS diversion of existing utilities at Plot P1. • Mosque design assigned to APG. | 7.91% | 8.09% | 0.18% | Substantial Completion | 2026-06-02 |  | 2026-06-02 | 2024-09-20 | • Appoint specialist for shelter special system due to improper submission, affecting builder works & long lead items. • ADM approval (if any) for Contractor's Pile Design. • Design update (if any), in compliance with sevene comments | • Resubmitted on 18 Sep.2024 & UR. • Coordinate with sevene for ADM review schedule. • Design team re-submitted to sevene on 20-sep-2024 | • Casting of Capping Beam • Starting of Raft piles | 130388712.65 | 0 | 130388712.65 | 4662507.03 | 0 | 135051219.68 | 13053810 | 243591.44 | https://drive.google.com/thumbnail?id=1N6JLvInqt6UGVAo8jpPfLxV1anlM3LhC&sz=w1000 | https://drive.google.com/file/d/1N6JLvInqt6UGVAo8jpPfLxV1anlM3LhC/view | https://drive.google.com/thumbnail?id=1qZSXHwjD6UiZLiCnVCCPpTfeEZz74aAs&sz=w1000 | https://drive.google.com/file/d/1qZSXHwjD6UiZLiCnVCCPpTfeEZz74aAs/view | https://drive.google.com/thumbnail?id=197Upk1lRbxo1iH4nl3_asxDxnnQz-xvq&sz=w1000 | https://drive.google.com/file/d/197Upk1lRbxo1iH4nl3_asxDxnnQz-xvq/view
2024-09-13 | Khalifa City-Majlis-P2 | P2 | MJ-06 | 124 | 486 | 610 | • Building Permits issued on 21/05/2024 • Approval For Shoring Design 15/07/2024 • Completion of site fencing and sign board • Project Staff moved in to Site Office on 09/09/2024 • Relocation of Utilities started on 09/09/2024 • Relocation of three (3) existing ADDC cables completed on 13/09/2024 • Guide Beam started on 19/09/2024 | • Commencement Date 15/05/2024 | 5.42% | 2.28% | -3.14% | Notice to Commence | 2024-05-15 | 2024-05-15 |  | 2024-09-20 | • Relocation of existing ADDC feeder pillar. • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • Delay in submissions of and insurances and guarantees. • NOCs for fencing permit. (ADDC rejection) • Change of Piling Layout. | • Follow-up NOC from ADDC for shutdown to relocate feeder pillar. • Finalize the assignment of approved contractor to re-route the existing services-ongoing. • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities. Comply with Civil Defence requirements for inspection and approval. • Finalize the re-route the existing services procurement and commence the execution of re-routing.(PS) • Finalized the selection of shelter special equipment. Procurement of MEP subcontractor. • Prepare for the start of Shoring Works (after Issuance of NOC from ADDC). • Guide Beam and Shoring works. | 94981423.15 | 0 | 94981423.15 | 3708466.35 | 0 | 98689889.5 | 1208000 |  | https://drive.google.com/thumbnail?id=1plIl4OwrTQiOuqIP5TrPp953bH0vUYQ-&sz=w1000 | https://drive.google.com/file/d/1plIl4OwrTQiOuqIP5TrPp953bH0vUYQ-/view?usp=drive_link | https://drive.google.com/thumbnail?id=1-9vqHAxMY7EOdGCf_1JiVVh1sMtEsHwD&sz=w1000 | https://drive.google.com/file/d/1-9vqHAxMY7EOdGCf_1JiVVh1sMtEsHwD/view?usp=drive_link | https://drive.google.com/thumbnail?id=1BakHXePkW3JZxwSnUkqqZxtPshE0ewsY&sz=w1000 | https://drive.google.com/file/d/1BakHXePkW3JZxwSnUkqqZxtPshE0ewsY/view?usp=drive_link
2024-09-13 | Khalifa City-Majlis-P2 | P2 | MJ-06 | 124 | 486 | 610 | • Building Permits issued on 21/05/2024 • Approval For Shoring Design 15/07/2024 • Completion of site fencing and sign board • Project Staff moved in to Site Office on 09/09/2024 • Relocation of Utilities started on 09/09/2024 • Relocation of three (3) existing ADDC cables completed on 13/09/2024 • Guide Beam started on 19/09/2024 | • Commencement Date 15/05/2024 | 5.42% | 2.28% | -3.14% | Building Permit | 2024-05-21 | 2024-05-21 |  | 2024-09-20 | • Relocation of existing ADDC feeder pillar. • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • Delay in submissions of and insurances and guarantees. • NOCs for fencing permit. (ADDC rejection) • Change of Piling Layout. | • Follow-up NOC from ADDC for shutdown to relocate feeder pillar. • Finalize the assignment of approved contractor to re-route the existing services-ongoing. • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities. Comply with Civil Defence requirements for inspection and approval. • Finalize the re-route the existing services procurement and commence the execution of re-routing.(PS) • Finalized the selection of shelter special equipment. Procurement of MEP subcontractor. • Prepare for the start of Shoring Works (after Issuance of NOC from ADDC). • Guide Beam and Shoring works. | 94981423.15 | 0 | 94981423.15 | 3708466.35 | 0 | 98689889.5 | 1208000 |  | https://drive.google.com/thumbnail?id=1plIl4OwrTQiOuqIP5TrPp953bH0vUYQ-&sz=w1000 | https://drive.google.com/file/d/1plIl4OwrTQiOuqIP5TrPp953bH0vUYQ-/view?usp=drive_link | https://drive.google.com/thumbnail?id=1-9vqHAxMY7EOdGCf_1JiVVh1sMtEsHwD&sz=w1000 | https://drive.google.com/file/d/1-9vqHAxMY7EOdGCf_1JiVVh1sMtEsHwD/view?usp=drive_link | https://drive.google.com/thumbnail?id=1BakHXePkW3JZxwSnUkqqZxtPshE0ewsY&sz=w1000 | https://drive.google.com/file/d/1BakHXePkW3JZxwSnUkqqZxtPshE0ewsY/view?usp=drive_link
2024-09-13 | Khalifa City-Majlis-P2 | P2 | MJ-06 | 124 | 486 | 610 | • Building Permits issued on 21/05/2024 • Approval For Shoring Design 15/07/2024 • Completion of site fencing and sign board • Project Staff moved in to Site Office on 09/09/2024 • Relocation of Utilities started on 09/09/2024 • Relocation of three (3) existing ADDC cables completed on 13/09/2024 • Guide Beam started on 19/09/2024 | • Commencement Date 15/05/2024 | 5.42% | 2.28% | -3.14% | Site Mobilization | 2024-07-22 |  | 2024-09-26 | 2024-09-20 | • Relocation of existing ADDC feeder pillar. • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • Delay in submissions of and insurances and guarantees. • NOCs for fencing permit. (ADDC rejection) • Change of Piling Layout. | • Follow-up NOC from ADDC for shutdown to relocate feeder pillar. • Finalize the assignment of approved contractor to re-route the existing services-ongoing. • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities. Comply with Civil Defence requirements for inspection and approval. • Finalize the re-route the existing services procurement and commence the execution of re-routing.(PS) • Finalized the selection of shelter special equipment. Procurement of MEP subcontractor. • Prepare for the start of Shoring Works (after Issuance of NOC from ADDC). • Guide Beam and Shoring works. | 94981423.15 | 0 | 94981423.15 | 3708466.35 | 0 | 98689889.5 | 1208000 |  | https://drive.google.com/thumbnail?id=1plIl4OwrTQiOuqIP5TrPp953bH0vUYQ-&sz=w1000 | https://drive.google.com/file/d/1plIl4OwrTQiOuqIP5TrPp953bH0vUYQ-/view?usp=drive_link | https://drive.google.com/thumbnail?id=1-9vqHAxMY7EOdGCf_1JiVVh1sMtEsHwD&sz=w1000 | https://drive.google.com/file/d/1-9vqHAxMY7EOdGCf_1JiVVh1sMtEsHwD/view?usp=drive_link | https://drive.google.com/thumbnail?id=1BakHXePkW3JZxwSnUkqqZxtPshE0ewsY&sz=w1000 | https://drive.google.com/file/d/1BakHXePkW3JZxwSnUkqqZxtPshE0ewsY/view?usp=drive_link
2024-09-13 | Khalifa City-Majlis-P2 | P2 | MJ-06 | 124 | 486 | 610 | • Building Permits issued on 21/05/2024 • Approval For Shoring Design 15/07/2024 • Completion of site fencing and sign board • Project Staff moved in to Site Office on 09/09/2024 • Relocation of Utilities started on 09/09/2024 • Relocation of three (3) existing ADDC cables completed on 13/09/2024 • Guide Beam started on 19/09/2024 | • Commencement Date 15/05/2024 | 5.42% | 2.28% | -3.14% | Guide Beam Completion | 2024-09-14 |  | 2024-10-26 | 2024-09-20 | • Relocation of existing ADDC feeder pillar. • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • Delay in submissions of and insurances and guarantees. • NOCs for fencing permit. (ADDC rejection) • Change of Piling Layout. | • Follow-up NOC from ADDC for shutdown to relocate feeder pillar. • Finalize the assignment of approved contractor to re-route the existing services-ongoing. • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities. Comply with Civil Defence requirements for inspection and approval. • Finalize the re-route the existing services procurement and commence the execution of re-routing.(PS) • Finalized the selection of shelter special equipment. Procurement of MEP subcontractor. • Prepare for the start of Shoring Works (after Issuance of NOC from ADDC). • Guide Beam and Shoring works. | 94981423.15 | 0 | 94981423.15 | 3708466.35 | 0 | 98689889.5 | 1208000 |  | https://drive.google.com/thumbnail?id=1plIl4OwrTQiOuqIP5TrPp953bH0vUYQ-&sz=w1000 | https://drive.google.com/file/d/1plIl4OwrTQiOuqIP5TrPp953bH0vUYQ-/view?usp=drive_link | https://drive.google.com/thumbnail?id=1-9vqHAxMY7EOdGCf_1JiVVh1sMtEsHwD&sz=w1000 | https://drive.google.com/file/d/1-9vqHAxMY7EOdGCf_1JiVVh1sMtEsHwD/view?usp=drive_link | https://drive.google.com/thumbnail?id=1BakHXePkW3JZxwSnUkqqZxtPshE0ewsY&sz=w1000 | https://drive.google.com/file/d/1BakHXePkW3JZxwSnUkqqZxtPshE0ewsY/view?usp=drive_link
2024-09-13 | Khalifa City-Majlis-P2 | P2 | MJ-06 | 124 | 486 | 610 | • Building Permits issued on 21/05/2024 • Approval For Shoring Design 15/07/2024 • Completion of site fencing and sign board • Project Staff moved in to Site Office on 09/09/2024 • Relocation of Utilities started on 09/09/2024 • Relocation of three (3) existing ADDC cables completed on 13/09/2024 • Guide Beam started on 19/09/2024 | • Commencement Date 15/05/2024 | 5.42% | 2.28% | -3.14% | Shoring Drilling & Casting Completion | 2024-09-14 |  | 2024-10-26 | 2024-09-20 | • Relocation of existing ADDC feeder pillar. • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • Delay in submissions of and insurances and guarantees. • NOCs for fencing permit. (ADDC rejection) • Change of Piling Layout. | • Follow-up NOC from ADDC for shutdown to relocate feeder pillar. • Finalize the assignment of approved contractor to re-route the existing services-ongoing. • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities. Comply with Civil Defence requirements for inspection and approval. • Finalize the re-route the existing services procurement and commence the execution of re-routing.(PS) • Finalized the selection of shelter special equipment. Procurement of MEP subcontractor. • Prepare for the start of Shoring Works (after Issuance of NOC from ADDC). • Guide Beam and Shoring works. | 94981423.15 | 0 | 94981423.15 | 3708466.35 | 0 | 98689889.5 | 1208000 |  | https://drive.google.com/thumbnail?id=1plIl4OwrTQiOuqIP5TrPp953bH0vUYQ-&sz=w1000 | https://drive.google.com/file/d/1plIl4OwrTQiOuqIP5TrPp953bH0vUYQ-/view?usp=drive_link | https://drive.google.com/thumbnail?id=1-9vqHAxMY7EOdGCf_1JiVVh1sMtEsHwD&sz=w1000 | https://drive.google.com/file/d/1-9vqHAxMY7EOdGCf_1JiVVh1sMtEsHwD/view?usp=drive_link | https://drive.google.com/thumbnail?id=1BakHXePkW3JZxwSnUkqqZxtPshE0ewsY&sz=w1000 | https://drive.google.com/file/d/1BakHXePkW3JZxwSnUkqqZxtPshE0ewsY/view?usp=drive_link
2024-09-13 | Khalifa City-Majlis-P2 | P2 | MJ-06 | 124 | 486 | 610 | • Building Permits issued on 21/05/2024 • Approval For Shoring Design 15/07/2024 • Completion of site fencing and sign board • Project Staff moved in to Site Office on 09/09/2024 • Relocation of Utilities started on 09/09/2024 • Relocation of three (3) existing ADDC cables completed on 13/09/2024 • Guide Beam started on 19/09/2024 | • Commencement Date 15/05/2024 | 5.42% | 2.28% | -3.14% | Shoring Capping Beam Completion | 2024-09-21 |  | 2024-11-02 | 2024-09-20 | • Relocation of existing ADDC feeder pillar. • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • Delay in submissions of and insurances and guarantees. • NOCs for fencing permit. (ADDC rejection) • Change of Piling Layout. | • Follow-up NOC from ADDC for shutdown to relocate feeder pillar. • Finalize the assignment of approved contractor to re-route the existing services-ongoing. • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities. Comply with Civil Defence requirements for inspection and approval. • Finalize the re-route the existing services procurement and commence the execution of re-routing.(PS) • Finalized the selection of shelter special equipment. Procurement of MEP subcontractor. • Prepare for the start of Shoring Works (after Issuance of NOC from ADDC). • Guide Beam and Shoring works. | 94981423.15 | 0 | 94981423.15 | 3708466.35 | 0 | 98689889.5 | 1208000 |  | https://drive.google.com/thumbnail?id=1plIl4OwrTQiOuqIP5TrPp953bH0vUYQ-&sz=w1000 | https://drive.google.com/file/d/1plIl4OwrTQiOuqIP5TrPp953bH0vUYQ-/view?usp=drive_link | https://drive.google.com/thumbnail?id=1-9vqHAxMY7EOdGCf_1JiVVh1sMtEsHwD&sz=w1000 | https://drive.google.com/file/d/1-9vqHAxMY7EOdGCf_1JiVVh1sMtEsHwD/view?usp=drive_link | https://drive.google.com/thumbnail?id=1BakHXePkW3JZxwSnUkqqZxtPshE0ewsY&sz=w1000 | https://drive.google.com/file/d/1BakHXePkW3JZxwSnUkqqZxtPshE0ewsY/view?usp=drive_link
2024-09-13 | Khalifa City-Majlis-P2 | P2 | MJ-06 | 124 | 486 | 610 | • Building Permits issued on 21/05/2024 • Approval For Shoring Design 15/07/2024 • Completion of site fencing and sign board • Project Staff moved in to Site Office on 09/09/2024 • Relocation of Utilities started on 09/09/2024 • Relocation of three (3) existing ADDC cables completed on 13/09/2024 • Guide Beam started on 19/09/2024 | • Commencement Date 15/05/2024 | 5.42% | 2.28% | -3.14% | Stage 1 Excavation Completion | 2024-09-21 |  | 2024-11-02 | 2024-09-20 | • Relocation of existing ADDC feeder pillar. • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • Delay in submissions of and insurances and guarantees. • NOCs for fencing permit. (ADDC rejection) • Change of Piling Layout. | • Follow-up NOC from ADDC for shutdown to relocate feeder pillar. • Finalize the assignment of approved contractor to re-route the existing services-ongoing. • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities. Comply with Civil Defence requirements for inspection and approval. • Finalize the re-route the existing services procurement and commence the execution of re-routing.(PS) • Finalized the selection of shelter special equipment. Procurement of MEP subcontractor. • Prepare for the start of Shoring Works (after Issuance of NOC from ADDC). • Guide Beam and Shoring works. | 94981423.15 | 0 | 94981423.15 | 3708466.35 | 0 | 98689889.5 | 1208000 |  | https://drive.google.com/thumbnail?id=1plIl4OwrTQiOuqIP5TrPp953bH0vUYQ-&sz=w1000 | https://drive.google.com/file/d/1plIl4OwrTQiOuqIP5TrPp953bH0vUYQ-/view?usp=drive_link | https://drive.google.com/thumbnail?id=1-9vqHAxMY7EOdGCf_1JiVVh1sMtEsHwD&sz=w1000 | https://drive.google.com/file/d/1-9vqHAxMY7EOdGCf_1JiVVh1sMtEsHwD/view?usp=drive_link | https://drive.google.com/thumbnail?id=1BakHXePkW3JZxwSnUkqqZxtPshE0ewsY&sz=w1000 | https://drive.google.com/file/d/1BakHXePkW3JZxwSnUkqqZxtPshE0ewsY/view?usp=drive_link
2024-09-13 | Mohamed Bin Zayed City-Majlis-P9 | P9 | MJ-07 | 124 | 486 | 610 | • Building Permits issued on 21/05/2024 • Completion of site fencing • Approval for Shoring Design 15/07/2024 • Guide Beam completed on 06/09/2024 | • Commencement Date 15/05/2024 | 7.3% | 3.21% | -4.09% | Notice to Commence | 2024-05-15 | 2024-05-15 |  | 2024-09-20 | • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • Delay in submissions of and insurances and grantees. • NOCs for fencing permit. • Finalize the authorities approval for the Mosque | • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) • Expedite the submission of revised Piling Layout. | • Complete site mobilization and establishment of site facilities. Comply with Civil Defence requirements for inspection and approval. • Finalized the selection of shelter special equipment.(ongoing) • Procurement of MEP subcontractor. • Secant Piles for shoring works(ongoing) • Shoring Capping Beam. • Stage 1 Excavation up to 3m. • Piling works. | 97238576.53 | 0 | 97238576.53 | 3344531.65 | 0 | 100583108.18 | 1208000 |  | https://drive.google.com/thumbnail?id=1nvLtx1HJOnLb38HmGIORDb_hqRjZMsuK&sz=w1000 | https://drive.google.com/file/d/1nvLtx1HJOnLb38HmGIORDb_hqRjZMsuK/view?usp=drive_link | https://drive.google.com/thumbnail?id=1FRRXo6J4o4AZtg9BHSw3llGraq7T31kv&sz=w1000 | https://drive.google.com/file/d/1FRRXo6J4o4AZtg9BHSw3llGraq7T31kv/view?usp=drive_link | https://drive.google.com/thumbnail?id=1AoH0Y4ciTRcsU5X6S4aZ3HZiPs325E2e&sz=w1000 | https://drive.google.com/file/d/1AoH0Y4ciTRcsU5X6S4aZ3HZiPs325E2e/view?usp=drive_link
2024-09-13 | Mohamed Bin Zayed City-Majlis-P9 | P9 | MJ-07 | 124 | 486 | 610 | • Building Permits issued on 21/05/2024 • Completion of site fencing • Approval for Shoring Design 15/07/2024 • Guide Beam completed on 06/09/2024 | • Commencement Date 15/05/2024 | 7.3% | 3.21% | -4.09% | Building Permit | 2024-05-21 | 2024-05-21 |  | 2024-09-20 | • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • Delay in submissions of and insurances and grantees. • NOCs for fencing permit. • Finalize the authorities approval for the Mosque | • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities. Comply with Civil Defence requirements for inspection and approval. • Finalized the selection of shelter special equipment.(ongoing) • Procurement of MEP subcontractor. • Secant Piles for shoring works(ongoing) • Shoring Capping Beam. • Stage 1 Excavation up to 3m. • Piling works. | 97238576.53 | 0 | 97238576.53 | 3344531.65 | 0 | 100583108.18 | 1208000 |  | https://drive.google.com/thumbnail?id=1nvLtx1HJOnLb38HmGIORDb_hqRjZMsuK&sz=w1000 | https://drive.google.com/file/d/1nvLtx1HJOnLb38HmGIORDb_hqRjZMsuK/view?usp=drive_link | https://drive.google.com/thumbnail?id=1FRRXo6J4o4AZtg9BHSw3llGraq7T31kv&sz=w1000 | https://drive.google.com/file/d/1FRRXo6J4o4AZtg9BHSw3llGraq7T31kv/view?usp=drive_link | https://drive.google.com/thumbnail?id=1AoH0Y4ciTRcsU5X6S4aZ3HZiPs325E2e&sz=w1000 | https://drive.google.com/file/d/1AoH0Y4ciTRcsU5X6S4aZ3HZiPs325E2e/view?usp=drive_link
2024-09-13 | Mohamed Bin Zayed City-Majlis-P9 | P9 | MJ-07 | 124 | 486 | 610 | • Building Permits issued on 21/05/2024 • Completion of site fencing • Approval for Shoring Design 15/07/2024 • Guide Beam completed on 06/09/2024 | • Commencement Date 15/05/2024 | 7.3% | 3.21% | -4.09% | Site Mobilization | 2024-07-20 |  | 2024-09-26 | 2024-09-20 | • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • Delay in submissions of and insurances and grantees. • NOCs for fencing permit. • Finalize the authorities approval for the Mosque | • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities. Comply with Civil Defence requirements for inspection and approval. • Finalized the selection of shelter special equipment.(ongoing) • Procurement of MEP subcontractor. • Secant Piles for shoring works(ongoing) • Shoring Capping Beam. • Stage 1 Excavation up to 3m. • Piling works. | 97238576.53 | 0 | 97238576.53 | 3344531.65 | 0 | 100583108.18 | 1208000 |  | https://drive.google.com/thumbnail?id=1nvLtx1HJOnLb38HmGIORDb_hqRjZMsuK&sz=w1000 | https://drive.google.com/file/d/1nvLtx1HJOnLb38HmGIORDb_hqRjZMsuK/view?usp=drive_link | https://drive.google.com/thumbnail?id=1FRRXo6J4o4AZtg9BHSw3llGraq7T31kv&sz=w1000 | https://drive.google.com/file/d/1FRRXo6J4o4AZtg9BHSw3llGraq7T31kv/view?usp=drive_link | https://drive.google.com/thumbnail?id=1AoH0Y4ciTRcsU5X6S4aZ3HZiPs325E2e&sz=w1000 | https://drive.google.com/file/d/1AoH0Y4ciTRcsU5X6S4aZ3HZiPs325E2e/view?usp=drive_link
2024-09-13 | Mohamed Bin Zayed City-Majlis-P9 | P9 | MJ-07 | 124 | 486 | 610 | • Building Permits issued on 21/05/2024 • Completion of site fencing • Approval for Shoring Design 15/07/2024 • Guide Beam completed on 06/09/2024 | • Commencement Date 15/05/2024 | 7.3% | 3.21% | -4.09% | Shoring & Piling Completion | 2024-11-07 |  | 2024-12-27 | 2024-09-20 | • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • Delay in submissions of and insurances and grantees. • NOCs for fencing permit. • Finalize the authorities approval for the Mosque | • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities. Comply with Civil Defence requirements for inspection and approval. • Finalized the selection of shelter special equipment.(ongoing) • Procurement of MEP subcontractor. • Secant Piles for shoring works(ongoing) • Shoring Capping Beam. • Stage 1 Excavation up to 3m. • Piling works. | 97238576.53 | 0 | 97238576.53 | 3344531.65 | 0 | 100583108.18 | 1208000 |  | https://drive.google.com/thumbnail?id=1nvLtx1HJOnLb38HmGIORDb_hqRjZMsuK&sz=w1000 | https://drive.google.com/file/d/1nvLtx1HJOnLb38HmGIORDb_hqRjZMsuK/view?usp=drive_link | https://drive.google.com/thumbnail?id=1FRRXo6J4o4AZtg9BHSw3llGraq7T31kv&sz=w1000 | https://drive.google.com/file/d/1FRRXo6J4o4AZtg9BHSw3llGraq7T31kv/view?usp=drive_link | https://drive.google.com/thumbnail?id=1AoH0Y4ciTRcsU5X6S4aZ3HZiPs325E2e&sz=w1000 | https://drive.google.com/file/d/1AoH0Y4ciTRcsU5X6S4aZ3HZiPs325E2e/view?usp=drive_link
2024-09-13 | Mohamed Bin Zayed City-Majlis-P9 | P9 | MJ-07 | 124 | 486 | 610 | • Building Permits issued on 21/05/2024 • Completion of site fencing • Approval for Shoring Design 15/07/2024 • Guide Beam completed on 06/09/2024 | • Commencement Date 15/05/2024 | 7.3% | 3.21% | -4.09% | Substructure | 2024-12-18 |  | 2025-02-06 | 2024-09-20 | • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • Delay in submissions of and insurances and grantees. • NOCs for fencing permit. • Finalize the authorities approval for the Mosque | • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities. Comply with Civil Defence requirements for inspection and approval. • Finalized the selection of shelter special equipment.(ongoing) • Procurement of MEP subcontractor. • Secant Piles for shoring works(ongoing) • Shoring Capping Beam. • Stage 1 Excavation up to 3m. • Piling works. | 97238576.53 | 0 | 97238576.53 | 3344531.65 | 0 | 100583108.18 | 1208000 |  | https://drive.google.com/thumbnail?id=1nvLtx1HJOnLb38HmGIORDb_hqRjZMsuK&sz=w1000 | https://drive.google.com/file/d/1nvLtx1HJOnLb38HmGIORDb_hqRjZMsuK/view?usp=drive_link | https://drive.google.com/thumbnail?id=1FRRXo6J4o4AZtg9BHSw3llGraq7T31kv&sz=w1000 | https://drive.google.com/file/d/1FRRXo6J4o4AZtg9BHSw3llGraq7T31kv/view?usp=drive_link | https://drive.google.com/thumbnail?id=1AoH0Y4ciTRcsU5X6S4aZ3HZiPs325E2e&sz=w1000 | https://drive.google.com/file/d/1AoH0Y4ciTRcsU5X6S4aZ3HZiPs325E2e/view?usp=drive_link
2024-09-13 | Mohamed Bin Zayed City-Majlis-P9 | P9 | MJ-07 | 124 | 486 | 610 | • Building Permits issued on 21/05/2024 • Completion of site fencing • Approval for Shoring Design 15/07/2024 • Guide Beam completed on 06/09/2024 | • Commencement Date 15/05/2024 | 7.3% | 3.21% | -4.09% | Superstructure | 2025-08-28 |  | 2025-10-17 | 2024-09-20 | • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • Delay in submissions of and insurances and grantees. • NOCs for fencing permit. • Finalize the authorities approval for the Mosque | • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities. Comply with Civil Defence requirements for inspection and approval. • Finalized the selection of shelter special equipment.(ongoing) • Procurement of MEP subcontractor. • Secant Piles for shoring works(ongoing) • Shoring Capping Beam. • Stage 1 Excavation up to 3m. • Piling works. | 97238576.53 | 0 | 97238576.53 | 3344531.65 | 0 | 100583108.18 | 1208000 |  | https://drive.google.com/thumbnail?id=1nvLtx1HJOnLb38HmGIORDb_hqRjZMsuK&sz=w1000 | https://drive.google.com/file/d/1nvLtx1HJOnLb38HmGIORDb_hqRjZMsuK/view?usp=drive_link | https://drive.google.com/thumbnail?id=1FRRXo6J4o4AZtg9BHSw3llGraq7T31kv&sz=w1000 | https://drive.google.com/file/d/1FRRXo6J4o4AZtg9BHSw3llGraq7T31kv/view?usp=drive_link | https://drive.google.com/thumbnail?id=1AoH0Y4ciTRcsU5X6S4aZ3HZiPs325E2e&sz=w1000 | https://drive.google.com/file/d/1AoH0Y4ciTRcsU5X6S4aZ3HZiPs325E2e/view?usp=drive_link
2024-09-13 | Mohamed Bin Zayed City-Majlis-P9 | P9 | MJ-07 | 124 | 486 | 610 | • Building Permits issued on 21/05/2024 • Completion of site fencing • Approval for Shoring Design 15/07/2024 • Guide Beam completed on 06/09/2024 | • Commencement Date 15/05/2024 | 7.3% | 3.21% | -4.09% | MEP | 2025-11-04 |  | 2025-12-24 | 2024-09-20 | • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • Delay in submissions of and insurances and grantees. • NOCs for fencing permit. • Finalize the authorities approval for the Mosque | • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities. Comply with Civil Defence requirements for inspection and approval. • Finalized the selection of shelter special equipment.(ongoing) • Procurement of MEP subcontractor. • Secant Piles for shoring works(ongoing) • Shoring Capping Beam. • Stage 1 Excavation up to 3m. • Piling works. | 97238576.53 | 0 | 97238576.53 | 3344531.65 | 0 | 100583108.18 | 1208000 |  | https://drive.google.com/thumbnail?id=1nvLtx1HJOnLb38HmGIORDb_hqRjZMsuK&sz=w1000 | https://drive.google.com/file/d/1nvLtx1HJOnLb38HmGIORDb_hqRjZMsuK/view?usp=drive_link | https://drive.google.com/thumbnail?id=1FRRXo6J4o4AZtg9BHSw3llGraq7T31kv&sz=w1000 | https://drive.google.com/file/d/1FRRXo6J4o4AZtg9BHSw3llGraq7T31kv/view?usp=drive_link | https://drive.google.com/thumbnail?id=1AoH0Y4ciTRcsU5X6S4aZ3HZiPs325E2e&sz=w1000 | https://drive.google.com/file/d/1AoH0Y4ciTRcsU5X6S4aZ3HZiPs325E2e/view?usp=drive_link
2024-09-13 | Mohamed Bin Zayed City-Majlis-P9 | P9 | MJ-07 | 124 | 486 | 610 | • Building Permits issued on 21/05/2024 • Completion of site fencing • Approval for Shoring Design 15/07/2024 • Guide Beam completed on 06/09/2024 | • Commencement Date 15/05/2024 | 7.3% | 3.21% | -4.09% | Power On | 2025-11-22 |  | 2026-01-11 | 2024-09-20 | • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • Delay in submissions of and insurances and grantees. • NOCs for fencing permit. • Finalize the authorities approval for the Mosque | • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities. Comply with Civil Defence requirements for inspection and approval. • Finalized the selection of shelter special equipment.(ongoing) • Procurement of MEP subcontractor. • Secant Piles for shoring works(ongoing) • Shoring Capping Beam. • Stage 1 Excavation up to 3m. • Piling works. | 97238576.53 | 0 | 97238576.53 | 3344531.65 | 0 | 100583108.18 | 1208000 |  | https://drive.google.com/thumbnail?id=1nvLtx1HJOnLb38HmGIORDb_hqRjZMsuK&sz=w1000 | https://drive.google.com/file/d/1nvLtx1HJOnLb38HmGIORDb_hqRjZMsuK/view?usp=drive_link | https://drive.google.com/thumbnail?id=1FRRXo6J4o4AZtg9BHSw3llGraq7T31kv&sz=w1000 | https://drive.google.com/file/d/1FRRXo6J4o4AZtg9BHSw3llGraq7T31kv/view?usp=drive_link | https://drive.google.com/thumbnail?id=1AoH0Y4ciTRcsU5X6S4aZ3HZiPs325E2e&sz=w1000 | https://drive.google.com/file/d/1AoH0Y4ciTRcsU5X6S4aZ3HZiPs325E2e/view?usp=drive_link
2024-09-13 | Mohamed Bin Zayed City-Majlis-P9 | P9 | MJ-07 | 124 | 486 | 610 | • Building Permits issued on 21/05/2024 • Completion of site fencing • Approval for Shoring Design 15/07/2024 • Guide Beam completed on 06/09/2024 | • Commencement Date 15/05/2024 | 7.3% | 3.21% | -4.09% | Interior Finishes | 2025-11-22 |  | 2026-01-11 | 2024-09-20 | • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • Delay in submissions of and insurances and grantees. • NOCs for fencing permit. • Finalize the authorities approval for the Mosque | • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities. Comply with Civil Defence requirements for inspection and approval. • Finalized the selection of shelter special equipment.(ongoing) • Procurement of MEP subcontractor. • Secant Piles for shoring works(ongoing) • Shoring Capping Beam. • Stage 1 Excavation up to 3m. • Piling works. | 97238576.53 | 0 | 97238576.53 | 3344531.65 | 0 | 100583108.18 | 1208000 |  | https://drive.google.com/thumbnail?id=1nvLtx1HJOnLb38HmGIORDb_hqRjZMsuK&sz=w1000 | https://drive.google.com/file/d/1nvLtx1HJOnLb38HmGIORDb_hqRjZMsuK/view?usp=drive_link | https://drive.google.com/thumbnail?id=1FRRXo6J4o4AZtg9BHSw3llGraq7T31kv&sz=w1000 | https://drive.google.com/file/d/1FRRXo6J4o4AZtg9BHSw3llGraq7T31kv/view?usp=drive_link | https://drive.google.com/thumbnail?id=1AoH0Y4ciTRcsU5X6S4aZ3HZiPs325E2e&sz=w1000 | https://drive.google.com/file/d/1AoH0Y4ciTRcsU5X6S4aZ3HZiPs325E2e/view?usp=drive_link
2024-09-13 | Mohamed Bin Zayed City-Majlis-P9 | P9 | MJ-07 | 124 | 486 | 610 | • Building Permits issued on 21/05/2024 • Completion of site fencing • Approval for Shoring Design 15/07/2024 • Guide Beam completed on 06/09/2024 | • Commencement Date 15/05/2024 | 7.3% | 3.21% | -4.09% | Substantial Completion | 2025-12-15 |  | 2026-02-03 | 2024-09-20 | • Limited man power resources. • Appointment of MEP subcontractor. • Shelter special Equipment and Long Lead Items (Purchasing and Delivery). • Delay in submissions of and insurances and grantees. • NOCs for fencing permit. • Finalize the authorities approval for the Mosque | • Hiring and Deploy the capable site staff . • Engineering works for long lead items. Expected completion date 31/10/2024-Ongoing • Expedite the submission of major subcontractor and supplier. • Review and decision for the special shelter equipment (Under technical review by Engineer) | • Complete site mobilization and establishment of site facilities. Comply with Civil Defence requirements for inspection and approval. • Finalized the selection of shelter special equipment.(ongoing) • Procurement of MEP subcontractor. • Secant Piles for shoring works(ongoing) • Shoring Capping Beam. • Stage 1 Excavation up to 3m. • Piling works. | 97238576.53 | 0 | 97238576.53 | 3344531.65 | 0 | 100583108.18 | 1208000 |  | https://drive.google.com/thumbnail?id=1nvLtx1HJOnLb38HmGIORDb_hqRjZMsuK&sz=w1000 | https://drive.google.com/file/d/1nvLtx1HJOnLb38HmGIORDb_hqRjZMsuK/view?usp=drive_link | https://drive.google.com/thumbnail?id=1FRRXo6J4o4AZtg9BHSw3llGraq7T31kv&sz=w1000 | https://drive.google.com/file/d/1FRRXo6J4o4AZtg9BHSw3llGraq7T31kv/view?usp=drive_link | https://drive.google.com/thumbnail?id=1AoH0Y4ciTRcsU5X6S4aZ3HZiPs325E2e&sz=w1000 | https://drive.google.com/file/d/1AoH0Y4ciTRcsU5X6S4aZ3HZiPs325E2e/view?usp=drive_link
2024-09-13 | Mohamed Bin Zayed City-Majlis-P2 | P2 | MJ-12 | 67 | 541 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 | Submission of IFC and Contract drawings to the contractor | 2.72% | 2.25% | -0.47% | Commencement Date | 2024-07-16 | 2024-07-16 |  | 2024-09-20 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S • IFC anf contract drawings submission | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 116841278.4538 | 0 | 116841278.4538 | 3229333.33 | 0 | 120070611.7838 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1hU_NG6jWFnAFsctWfxIixSLdfdg-2vbM&sz=w1000 | https://drive.google.com/file/d/1hU_NG6jWFnAFsctWfxIixSLdfdg-2vbM/view | https://drive.google.com/thumbnail?id=1AjudEJfSeA5pObV4i_-2eZywBMH4FjUH&sz=w1000 | https://drive.google.com/file/d/1AjudEJfSeA5pObV4i_-2eZywBMH4FjUH/view | https://drive.google.com/thumbnail?id=1PBCEYtD7A6r3bmKeU8hWJH7w8BXVVzH1&sz=w1000 | https://drive.google.com/file/d/1PBCEYtD7A6r3bmKeU8hWJH7w8BXVVzH1/view
2024-09-13 | Mohamed Bin Zayed City-Majlis-P2 | P2 | MJ-12 | 67 | 541 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 | Submission of IFC and Contract drawings to the contractor | 2.72% | 2.25% | -0.47% | Construction Permit | 2024-07-17 | 2024-07-17 |  | 2024-09-20 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S • IFC anf contract drawings submission | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 116841278.4538 | 0 | 116841278.4538 | 3229333.33 | 0 | 120070611.7838 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN&sz=w1000 | https://drive.google.com/file/d/1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN/view | https://drive.google.com/thumbnail?id=10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce&sz=w1000 | https://drive.google.com/file/d/10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce/view | https://drive.google.com/thumbnail?id=1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU&sz=w1000 | https://drive.google.com/file/d/1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU/view
2024-09-13 | Mohamed Bin Zayed City-Majlis-P2 | P2 | MJ-12 | 67 | 541 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 | Submission of IFC and Contract drawings to the contractor | 2.72% | 2.25% | -0.47% | Site Mobilization | 2024-10-25 |  | 2024-10-25 | 2024-09-20 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S • IFC anf contract drawings submission | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 116841278.4538 | 0 | 116841278.4538 | 3229333.33 | 0 | 120070611.7838 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN&sz=w1000 | https://drive.google.com/file/d/1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN/view | https://drive.google.com/thumbnail?id=10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce&sz=w1000 | https://drive.google.com/file/d/10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce/view | https://drive.google.com/thumbnail?id=1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU&sz=w1000 | https://drive.google.com/file/d/1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU/view
2024-09-13 | Mohamed Bin Zayed City-Majlis-P2 | P2 | MJ-12 | 67 | 541 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 | Submission of IFC and Contract drawings to the contractor | 2.72% | 2.25% | -0.47% | Shoring Drilling & Casting | 2024-11-25 |  | 2024-11-25 | 2024-09-20 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S • IFC anf contract drawings submission | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 116841278.4538 | 0 | 116841278.4538 | 3229333.33 | 0 | 120070611.7838 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN&sz=w1000 | https://drive.google.com/file/d/1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN/view | https://drive.google.com/thumbnail?id=10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce&sz=w1000 | https://drive.google.com/file/d/10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce/view | https://drive.google.com/thumbnail?id=1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU&sz=w1000 | https://drive.google.com/file/d/1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU/view
2024-09-13 | Mohamed Bin Zayed City-Majlis-P2 | P2 | MJ-12 | 67 | 541 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 | Submission of IFC and Contract drawings to the contractor | 2.72% | 2.25% | -0.47% | Piling Drilling & Casting | 2025-01-02 |  | 2025-01-02 | 2024-09-20 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S • IFC anf contract drawings submission | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 116841278.4538 | 0 | 116841278.4538 | 3229333.33 | 0 | 120070611.7838 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN&sz=w1000 | https://drive.google.com/file/d/1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN/view | https://drive.google.com/thumbnail?id=10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce&sz=w1000 | https://drive.google.com/file/d/10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce/view | https://drive.google.com/thumbnail?id=1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU&sz=w1000 | https://drive.google.com/file/d/1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU/view
2024-09-13 | Mohamed Bin Zayed City-Majlis-P2 | P2 | MJ-12 | 67 | 541 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 | Submission of IFC and Contract drawings to the contractor | 2.72% | 2.25% | -0.47% | Excavation | 2025-02-27 |  | 2025-02-27 | 2024-09-20 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S • IFC anf contract drawings submission | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 116841278.4538 | 0 | 116841278.4538 | 3229333.33 | 0 | 120070611.7838 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN&sz=w1000 | https://drive.google.com/file/d/1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN/view | https://drive.google.com/thumbnail?id=10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce&sz=w1000 | https://drive.google.com/file/d/10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce/view | https://drive.google.com/thumbnail?id=1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU&sz=w1000 | https://drive.google.com/file/d/1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU/view
2024-09-13 | Mohamed Bin Zayed City-Majlis-P2 | P2 | MJ-12 | 67 | 541 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 | Submission of IFC and Contract drawings to the contractor | 2.72% | 2.25% | -0.47% | Substructure | 2025-07-29 |  | 2025-07-29 | 2024-09-20 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S • IFC anf contract drawings submission | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 116841278.4538 | 0 | 116841278.4538 | 3229333.33 | 0 | 120070611.7838 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN&sz=w1000 | https://drive.google.com/file/d/1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN/view | https://drive.google.com/thumbnail?id=10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce&sz=w1000 | https://drive.google.com/file/d/10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce/view | https://drive.google.com/thumbnail?id=1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU&sz=w1000 | https://drive.google.com/file/d/1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU/view
2024-09-13 | Mohamed Bin Zayed City-Majlis-P2 | P2 | MJ-12 | 67 | 541 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 | Submission of IFC and Contract drawings to the contractor | 2.72% | 2.25% | -0.47% | Superstructure | 2025-11-28 |  | 2025-11-28 | 2024-09-20 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S • IFC anf contract drawings submission | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 116841278.4538 | 0 | 116841278.4538 | 3229333.33 | 0 | 120070611.7838 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN&sz=w1000 | https://drive.google.com/file/d/1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN/view | https://drive.google.com/thumbnail?id=10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce&sz=w1000 | https://drive.google.com/file/d/10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce/view | https://drive.google.com/thumbnail?id=1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU&sz=w1000 | https://drive.google.com/file/d/1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU/view
2024-09-13 | Mohamed Bin Zayed City-Majlis-P2 | P2 | MJ-12 | 67 | 541 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 | Submission of IFC and Contract drawings to the contractor | 2.72% | 2.25% | -0.47% | MEP & Finishes | 2026-02-12 |  | 2026-02-12 | 2024-09-20 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S • IFC anf contract drawings submission | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 116841278.4538 | 0 | 116841278.4538 | 3229333.33 | 0 | 120070611.7838 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN&sz=w1000 | https://drive.google.com/file/d/1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN/view | https://drive.google.com/thumbnail?id=10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce&sz=w1000 | https://drive.google.com/file/d/10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce/view | https://drive.google.com/thumbnail?id=1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU&sz=w1000 | https://drive.google.com/file/d/1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU/view
2024-09-13 | Mohamed Bin Zayed City-Majlis-P2 | P2 | MJ-12 | 67 | 541 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 | Submission of IFC and Contract drawings to the contractor | 2.72% | 2.25% | -0.47% | Authorities NOCs/BCC | 2026-03-05 |  | 2026-03-05 | 2024-09-20 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S • IFC anf contract drawings submission | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 116841278.4538 | 0 | 116841278.4538 | 3229333.33 | 0 | 120070611.7838 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN&sz=w1000 | https://drive.google.com/file/d/1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN/view | https://drive.google.com/thumbnail?id=10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce&sz=w1000 | https://drive.google.com/file/d/10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce/view | https://drive.google.com/thumbnail?id=1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU&sz=w1000 | https://drive.google.com/file/d/1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU/view
2024-09-13 | Mohamed Bin Zayed City-Majlis-P2 | P2 | MJ-12 | 67 | 541 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 | Submission of IFC and Contract drawings to the contractor | 2.72% | 2.25% | -0.47% | External Works | 2026-03-15 |  | 2026-03-15 | 2024-09-20 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S • IFC anf contract drawings submission | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 116841278.4538 | 0 | 116841278.4538 | 3229333.33 | 0 | 120070611.7838 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN&sz=w1000 | https://drive.google.com/file/d/1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN/view | https://drive.google.com/thumbnail?id=10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce&sz=w1000 | https://drive.google.com/file/d/10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce/view | https://drive.google.com/thumbnail?id=1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU&sz=w1000 | https://drive.google.com/file/d/1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU/view
2024-09-13 | Mohamed Bin Zayed City-Majlis-P2 | P2 | MJ-12 | 67 | 541 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 | Submission of IFC and Contract drawings to the contractor | 2.72% | 2.25% | -0.47% | Testing & Commissioning | 2026-03-15 |  | 2026-03-15 | 2024-09-20 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S • IFC anf contract drawings submission | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 116841278.4538 | 0 | 116841278.4538 | 3229333.33 | 0 | 120070611.7838 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN&sz=w1000 | https://drive.google.com/file/d/1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN/view | https://drive.google.com/thumbnail?id=10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce&sz=w1000 | https://drive.google.com/file/d/10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce/view | https://drive.google.com/thumbnail?id=1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU&sz=w1000 | https://drive.google.com/file/d/1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU/view
2024-09-13 | Mohamed Bin Zayed City-Majlis-P2 | P2 | MJ-12 | 67 | 541 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 | Submission of IFC and Contract drawings to the contractor | 2.72% | 2.25% | -0.47% | Substantial Completion | 2026-03-15 |  | 2026-03-15 | 2024-09-20 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S • IFC anf contract drawings submission | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 116841278.4538 | 0 | 116841278.4538 | 3229333.33 | 0 | 120070611.7838 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN&sz=w1000 | https://drive.google.com/file/d/1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN/view | https://drive.google.com/thumbnail?id=10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce&sz=w1000 | https://drive.google.com/file/d/10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce/view | https://drive.google.com/thumbnail?id=1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU&sz=w1000 | https://drive.google.com/file/d/1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU/view
2024-09-13 | Madinat Al Riyad-Majlis-P162 | P162 | MJ-13 | 67 | 541 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 | Submission of IFC and Contract drawings to the contractor | 2.72% | 2.26% | -0.46% | Commencement Date | 2024-07-16 | 2024-07-16 |  | 2024-09-20 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S • IFC anf contract drawings submission | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 98073241.5243 | 0 | 98073241.5243 | 3229333.33 | 0 | 101302574.8543 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN&sz=w1000 | https://drive.google.com/file/d/1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN/view | https://drive.google.com/thumbnail?id=10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce&sz=w1000 | https://drive.google.com/file/d/10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce/view | https://drive.google.com/thumbnail?id=1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU&sz=w1000 | https://drive.google.com/file/d/1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU/view
2024-09-13 | Madinat Al Riyad-Majlis-P162 | P162 | MJ-13 | 67 | 541 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 | Submission of IFC and Contract drawings to the contractor | 2.72% | 2.26% | -0.46% | Construction Permit | 2024-07-17 | 2024-07-17 |  | 2024-09-20 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S • IFC anf contract drawings submission | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 98073241.5243 | 0 | 98073241.5243 | 3229333.33 | 0 | 101302574.8543 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN&sz=w1000 | https://drive.google.com/file/d/1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN/view | https://drive.google.com/thumbnail?id=10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce&sz=w1000 | https://drive.google.com/file/d/10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce/view | https://drive.google.com/thumbnail?id=1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU&sz=w1000 | https://drive.google.com/file/d/1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU/view
2024-09-13 | Madinat Al Riyad-Majlis-P162 | P162 | MJ-13 | 67 | 541 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 | Submission of IFC and Contract drawings to the contractor | 2.72% | 2.26% | -0.46% | Site Mobilization | 2024-10-25 |  | 2024-10-25 | 2024-09-20 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S • IFC anf contract drawings submission | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 98073241.5243 | 0 | 98073241.5243 | 3229333.33 | 0 | 101302574.8543 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN&sz=w1000 | https://drive.google.com/file/d/1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN/view | https://drive.google.com/thumbnail?id=10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce&sz=w1000 | https://drive.google.com/file/d/10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce/view | https://drive.google.com/thumbnail?id=1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU&sz=w1000 | https://drive.google.com/file/d/1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU/view
2024-09-13 | Madinat Al Riyad-Majlis-P162 | P162 | MJ-13 | 67 | 541 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 | Submission of IFC and Contract drawings to the contractor | 2.72% | 2.26% | -0.46% | Shoring Drilling & Casting | 2024-11-25 |  | 2024-11-25 | 2024-09-20 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S • IFC anf contract drawings submission | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 98073241.5243 | 0 | 98073241.5243 | 3229333.33 | 0 | 101302574.8543 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN&sz=w1000 | https://drive.google.com/file/d/1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN/view | https://drive.google.com/thumbnail?id=10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce&sz=w1000 | https://drive.google.com/file/d/10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce/view | https://drive.google.com/thumbnail?id=1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU&sz=w1000 | https://drive.google.com/file/d/1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU/view
2024-09-13 | Madinat Al Riyad-Majlis-P162 | P162 | MJ-13 | 67 | 541 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 | Submission of IFC and Contract drawings to the contractor | 2.72% | 2.26% | -0.46% | Piling Drilling & Casting | 2025-01-02 |  | 2025-01-02 | 2024-09-20 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S • IFC anf contract drawings submission | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 98073241.5243 | 0 | 98073241.5243 | 3229333.33 | 0 | 101302574.8543 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN&sz=w1000 | https://drive.google.com/file/d/1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN/view | https://drive.google.com/thumbnail?id=10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce&sz=w1000 | https://drive.google.com/file/d/10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce/view | https://drive.google.com/thumbnail?id=1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU&sz=w1000 | https://drive.google.com/file/d/1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU/view
2024-09-13 | Madinat Al Riyad-Majlis-P162 | P162 | MJ-13 | 67 | 541 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 | Submission of IFC and Contract drawings to the contractor | 2.72% | 2.26% | -0.46% | Excavation | 2025-02-27 |  | 2025-02-27 | 2024-09-20 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S • IFC anf contract drawings submission | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 98073241.5243 | 0 | 98073241.5243 | 3229333.33 | 0 | 101302574.8543 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN&sz=w1000 | https://drive.google.com/file/d/1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN/view | https://drive.google.com/thumbnail?id=10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce&sz=w1000 | https://drive.google.com/file/d/10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce/view | https://drive.google.com/thumbnail?id=1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU&sz=w1000 | https://drive.google.com/file/d/1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU/view
2024-09-13 | Madinat Al Riyad-Majlis-P162 | P162 | MJ-13 | 67 | 541 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 | Submission of IFC and Contract drawings to the contractor | 2.72% | 2.26% | -0.46% | Substructure | 2025-07-29 |  | 2025-07-29 | 2024-09-20 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S • IFC anf contract drawings submission | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 98073241.5243 | 0 | 98073241.5243 | 3229333.33 | 0 | 101302574.8543 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN&sz=w1000 | https://drive.google.com/file/d/1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN/view | https://drive.google.com/thumbnail?id=10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce&sz=w1000 | https://drive.google.com/file/d/10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce/view | https://drive.google.com/thumbnail?id=1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU&sz=w1000 | https://drive.google.com/file/d/1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU/view
2024-09-13 | Madinat Al Riyad-Majlis-P162 | P162 | MJ-13 | 67 | 541 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 | Submission of IFC and Contract drawings to the contractor | 2.72% | 2.26% | -0.46% | Superstructure | 2025-11-28 |  | 2025-11-28 | 2024-09-20 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S • IFC anf contract drawings submission | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 98073241.5243 | 0 | 98073241.5243 | 3229333.33 | 0 | 101302574.8543 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN&sz=w1000 | https://drive.google.com/file/d/1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN/view | https://drive.google.com/thumbnail?id=10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce&sz=w1000 | https://drive.google.com/file/d/10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce/view | https://drive.google.com/thumbnail?id=1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU&sz=w1000 | https://drive.google.com/file/d/1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU/view
2024-09-13 | Madinat Al Riyad-Majlis-P162 | P162 | MJ-13 | 67 | 541 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 | Submission of IFC and Contract drawings to the contractor | 2.72% | 2.26% | -0.46% | MEP & Finishes | 2026-02-12 |  | 2026-02-12 | 2024-09-20 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S • IFC anf contract drawings submission | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 98073241.5243 | 0 | 98073241.5243 | 3229333.33 | 0 | 101302574.8543 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN&sz=w1000 | https://drive.google.com/file/d/1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN/view | https://drive.google.com/thumbnail?id=10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce&sz=w1000 | https://drive.google.com/file/d/10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce/view | https://drive.google.com/thumbnail?id=1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU&sz=w1000 | https://drive.google.com/file/d/1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU/view
2024-09-13 | Madinat Al Riyad-Majlis-P162 | P162 | MJ-13 | 67 | 541 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 | Submission of IFC and Contract drawings to the contractor | 2.72% | 2.26% | -0.46% | Authorities NOCs/BCC | 2026-03-05 |  | 2026-03-05 | 2024-09-20 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S • IFC anf contract drawings submission | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 98073241.5243 | 0 | 98073241.5243 | 3229333.33 | 0 | 101302574.8543 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN&sz=w1000 | https://drive.google.com/file/d/1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN/view | https://drive.google.com/thumbnail?id=10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce&sz=w1000 | https://drive.google.com/file/d/10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce/view | https://drive.google.com/thumbnail?id=1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU&sz=w1000 | https://drive.google.com/file/d/1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU/view
2024-09-13 | Madinat Al Riyad-Majlis-P162 | P162 | MJ-13 | 67 | 541 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 | Submission of IFC and Contract drawings to the contractor | 2.72% | 2.26% | -0.46% | External Works | 2026-03-15 |  | 2026-03-15 | 2024-09-20 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S • IFC anf contract drawings submission | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 98073241.5243 | 0 | 98073241.5243 | 3229333.33 | 0 | 101302574.8543 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN&sz=w1000 | https://drive.google.com/file/d/1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN/view | https://drive.google.com/thumbnail?id=10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce&sz=w1000 | https://drive.google.com/file/d/10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce/view | https://drive.google.com/thumbnail?id=1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU&sz=w1000 | https://drive.google.com/file/d/1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU/view
2024-09-13 | Madinat Al Riyad-Majlis-P162 | P162 | MJ-13 | 67 | 541 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 | Submission of IFC and Contract drawings to the contractor | 2.72% | 2.26% | -0.46% | Testing & Commissioning | 2026-03-15 |  | 2026-03-15 | 2024-09-20 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S • IFC anf contract drawings submission | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 98073241.5243 | 0 | 98073241.5243 | 3229333.33 | 0 | 101302574.8543 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN&sz=w1000 | https://drive.google.com/file/d/1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN/view | https://drive.google.com/thumbnail?id=10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce&sz=w1000 | https://drive.google.com/file/d/10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce/view | https://drive.google.com/thumbnail?id=1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU&sz=w1000 | https://drive.google.com/file/d/1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU/view
2024-09-13 | Madinat Al Riyad-Majlis-P162 | P162 | MJ-13 | 67 | 541 | 608 | • Building Permit issued on 23/07/2024 • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 | Submission of IFC and Contract drawings to the contractor | 2.72% | 2.26% | -0.46% | Substantial Completion | 2026-03-15 |  | 2026-03-15 | 2024-09-20 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S • IFC anf contract drawings submission | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 98073241.5243 | 0 | 98073241.5243 | 3229333.33 | 0 | 101302574.8543 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN&sz=w1000 | https://drive.google.com/file/d/1jjzR1RyL3evEhn3RbMY2vgThzWgq-fJN/view | https://drive.google.com/thumbnail?id=10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce&sz=w1000 | https://drive.google.com/file/d/10RRCP9PqW1a0aXZkHVOxVr_hGOY01_Ce/view | https://drive.google.com/thumbnail?id=1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU&sz=w1000 | https://drive.google.com/file/d/1MQhooDZfb_a8dh1XjYQap8rFcmtl5opU/view
2024-09-13 | Al Samhah-Majlis-P206 | P206 | MJ-14 | 67 | 541 | 608 | • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 | Submission of IFC and Contract drawings to the contractor | 2.72% | 2.25% | -0.47% | Commencement Date | 2024-07-16 | 2024-07-16 |  | 2024-09-20 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S • IFC anf contract drawings submission | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 110585480.0219 | 0 | 110585480.0219 | 3229333.33 | 0 | 113814813.3519 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1P8dv2yDVWK28813AIv4m4F9tgxPrdqDO&sz=w1000 | https://drive.google.com/file/d/1P8dv2yDVWK28813AIv4m4F9tgxPrdqDO/view | https://drive.google.com/thumbnail?id=11gAT3uSf6EhqY1gp7ESxBQx3ZJOIXz2O&sz=w1000 | https://drive.google.com/file/d/11gAT3uSf6EhqY1gp7ESxBQx3ZJOIXz2O/view | https://drive.google.com/thumbnail?id=10HQlUfuCM9rvKh755NA9pHKofaluje0o&sz=w1000 | https://drive.google.com/file/d/10HQlUfuCM9rvKh755NA9pHKofaluje0o/view
2024-09-13 | Al Samhah-Majlis-P206 | P206 | MJ-14 | 67 | 541 | 608 | • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 | Submission of IFC and Contract drawings to the contractor | 2.72% | 2.25% | -0.47% | Construction Permit | 2024-07-17 | 2024-09-17 |  | 2024-09-20 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S • IFC anf contract drawings submission | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 110585480.0219 | 0 | 110585480.0219 | 3229333.33 | 0 | 113814813.3519 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1P8dv2yDVWK28813AIv4m4F9tgxPrdqDO&sz=w1000 | https://drive.google.com/file/d/1P8dv2yDVWK28813AIv4m4F9tgxPrdqDO/view | https://drive.google.com/thumbnail?id=11gAT3uSf6EhqY1gp7ESxBQx3ZJOIXz2O&sz=w1000 | https://drive.google.com/file/d/11gAT3uSf6EhqY1gp7ESxBQx3ZJOIXz2O/view | https://drive.google.com/thumbnail?id=10HQlUfuCM9rvKh755NA9pHKofaluje0o&sz=w1000 | https://drive.google.com/file/d/10HQlUfuCM9rvKh755NA9pHKofaluje0o/view
2024-09-13 | Al Samhah-Majlis-P206 | P206 | MJ-14 | 67 | 541 | 608 | • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 | Submission of IFC and Contract drawings to the contractor | 2.72% | 2.25% | -0.47% | Site Mobilization | 2024-10-25 |  | 2024-10-25 | 2024-09-20 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S • IFC anf contract drawings submission | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 110585480.0219 | 0 | 110585480.0219 | 3229333.33 | 0 | 113814813.3519 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1P8dv2yDVWK28813AIv4m4F9tgxPrdqDO&sz=w1000 | https://drive.google.com/file/d/1P8dv2yDVWK28813AIv4m4F9tgxPrdqDO/view | https://drive.google.com/thumbnail?id=11gAT3uSf6EhqY1gp7ESxBQx3ZJOIXz2O&sz=w1000 | https://drive.google.com/file/d/11gAT3uSf6EhqY1gp7ESxBQx3ZJOIXz2O/view | https://drive.google.com/thumbnail?id=10HQlUfuCM9rvKh755NA9pHKofaluje0o&sz=w1000 | https://drive.google.com/file/d/10HQlUfuCM9rvKh755NA9pHKofaluje0o/view
2024-09-13 | Al Samhah-Majlis-P206 | P206 | MJ-14 | 67 | 541 | 608 | • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 | Submission of IFC and Contract drawings to the contractor | 2.72% | 2.25% | -0.47% | Shoring Drilling & Casting | 2024-11-25 |  | 2024-11-25 | 2024-09-20 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S • IFC anf contract drawings submission | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 110585480.0219 | 0 | 110585480.0219 | 3229333.33 | 0 | 113814813.3519 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1P8dv2yDVWK28813AIv4m4F9tgxPrdqDO&sz=w1000 | https://drive.google.com/file/d/1P8dv2yDVWK28813AIv4m4F9tgxPrdqDO/view | https://drive.google.com/thumbnail?id=11gAT3uSf6EhqY1gp7ESxBQx3ZJOIXz2O&sz=w1000 | https://drive.google.com/file/d/11gAT3uSf6EhqY1gp7ESxBQx3ZJOIXz2O/view | https://drive.google.com/thumbnail?id=10HQlUfuCM9rvKh755NA9pHKofaluje0o&sz=w1000 | https://drive.google.com/file/d/10HQlUfuCM9rvKh755NA9pHKofaluje0o/view
2024-09-13 | Al Samhah-Majlis-P206 | P206 | MJ-14 | 67 | 541 | 608 | • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 | Submission of IFC and Contract drawings to the contractor | 2.72% | 2.25% | -0.47% | Piling Drilling & Casting | 2025-01-02 |  | 2025-01-02 | 2024-09-20 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S • IFC anf contract drawings submission | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 110585480.0219 | 0 | 110585480.0219 | 3229333.33 | 0 | 113814813.3519 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1P8dv2yDVWK28813AIv4m4F9tgxPrdqDO&sz=w1000 | https://drive.google.com/file/d/1P8dv2yDVWK28813AIv4m4F9tgxPrdqDO/view | https://drive.google.com/thumbnail?id=11gAT3uSf6EhqY1gp7ESxBQx3ZJOIXz2O&sz=w1000 | https://drive.google.com/file/d/11gAT3uSf6EhqY1gp7ESxBQx3ZJOIXz2O/view | https://drive.google.com/thumbnail?id=10HQlUfuCM9rvKh755NA9pHKofaluje0o&sz=w1000 | https://drive.google.com/file/d/10HQlUfuCM9rvKh755NA9pHKofaluje0o/view
2024-09-13 | Al Samhah-Majlis-P206 | P206 | MJ-14 | 67 | 541 | 608 | • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 | Submission of IFC and Contract drawings to the contractor | 2.72% | 2.25% | -0.47% | Excavation | 2025-02-27 |  | 2025-02-27 | 2024-09-20 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S • IFC anf contract drawings submission | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 110585480.0219 | 0 | 110585480.0219 | 3229333.33 | 0 | 113814813.3519 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1P8dv2yDVWK28813AIv4m4F9tgxPrdqDO&sz=w1000 | https://drive.google.com/file/d/1P8dv2yDVWK28813AIv4m4F9tgxPrdqDO/view | https://drive.google.com/thumbnail?id=11gAT3uSf6EhqY1gp7ESxBQx3ZJOIXz2O&sz=w1000 | https://drive.google.com/file/d/11gAT3uSf6EhqY1gp7ESxBQx3ZJOIXz2O/view | https://drive.google.com/thumbnail?id=10HQlUfuCM9rvKh755NA9pHKofaluje0o&sz=w1000 | https://drive.google.com/file/d/10HQlUfuCM9rvKh755NA9pHKofaluje0o/view
2024-09-13 | Al Samhah-Majlis-P206 | P206 | MJ-14 | 67 | 541 | 608 | • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 | Submission of IFC and Contract drawings to the contractor | 2.72% | 2.25% | -0.47% | Substructure | 2025-07-29 |  | 2025-07-29 | 2024-09-20 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S • IFC anf contract drawings submission | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 110585480.0219 | 0 | 110585480.0219 | 3229333.33 | 0 | 113814813.3519 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1P8dv2yDVWK28813AIv4m4F9tgxPrdqDO&sz=w1000 | https://drive.google.com/file/d/1P8dv2yDVWK28813AIv4m4F9tgxPrdqDO/view | https://drive.google.com/thumbnail?id=11gAT3uSf6EhqY1gp7ESxBQx3ZJOIXz2O&sz=w1000 | https://drive.google.com/file/d/11gAT3uSf6EhqY1gp7ESxBQx3ZJOIXz2O/view | https://drive.google.com/thumbnail?id=10HQlUfuCM9rvKh755NA9pHKofaluje0o&sz=w1000 | https://drive.google.com/file/d/10HQlUfuCM9rvKh755NA9pHKofaluje0o/view
2024-09-13 | Al Samhah-Majlis-P206 | P206 | MJ-14 | 67 | 541 | 608 | • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 | Submission of IFC and Contract drawings to the contractor | 2.72% | 2.25% | -0.47% | Superstructure | 2025-11-28 |  | 2025-11-28 | 2024-09-20 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S • IFC anf contract drawings submission | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 110585480.0219 | 0 | 110585480.0219 | 3229333.33 | 0 | 113814813.3519 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1P8dv2yDVWK28813AIv4m4F9tgxPrdqDO&sz=w1000 | https://drive.google.com/file/d/1P8dv2yDVWK28813AIv4m4F9tgxPrdqDO/view | https://drive.google.com/thumbnail?id=11gAT3uSf6EhqY1gp7ESxBQx3ZJOIXz2O&sz=w1000 | https://drive.google.com/file/d/11gAT3uSf6EhqY1gp7ESxBQx3ZJOIXz2O/view | https://drive.google.com/thumbnail?id=10HQlUfuCM9rvKh755NA9pHKofaluje0o&sz=w1000 | https://drive.google.com/file/d/10HQlUfuCM9rvKh755NA9pHKofaluje0o/view
2024-09-13 | Al Samhah-Majlis-P206 | P206 | MJ-14 | 67 | 541 | 608 | • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 | Submission of IFC and Contract drawings to the contractor | 2.72% | 2.25% | -0.47% | MEP & Finishes | 2026-02-12 |  | 2026-02-12 | 2024-09-20 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S • IFC anf contract drawings submission | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 110585480.0219 | 0 | 110585480.0219 | 3229333.33 | 0 | 113814813.3519 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1P8dv2yDVWK28813AIv4m4F9tgxPrdqDO&sz=w1000 | https://drive.google.com/file/d/1P8dv2yDVWK28813AIv4m4F9tgxPrdqDO/view | https://drive.google.com/thumbnail?id=11gAT3uSf6EhqY1gp7ESxBQx3ZJOIXz2O&sz=w1000 | https://drive.google.com/file/d/11gAT3uSf6EhqY1gp7ESxBQx3ZJOIXz2O/view | https://drive.google.com/thumbnail?id=10HQlUfuCM9rvKh755NA9pHKofaluje0o&sz=w1000 | https://drive.google.com/file/d/10HQlUfuCM9rvKh755NA9pHKofaluje0o/view
2024-09-13 | Al Samhah-Majlis-P206 | P206 | MJ-14 | 67 | 541 | 608 | • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 | Submission of IFC and Contract drawings to the contractor | 2.72% | 2.25% | -0.47% | Authorities NOCs/BCC | 2026-03-05 |  | 2026-03-05 | 2024-09-20 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S • IFC anf contract drawings submission | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 110585480.0219 | 0 | 110585480.0219 | 3229333.33 | 0 | 113814813.3519 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1P8dv2yDVWK28813AIv4m4F9tgxPrdqDO&sz=w1000 | https://drive.google.com/file/d/1P8dv2yDVWK28813AIv4m4F9tgxPrdqDO/view | https://drive.google.com/thumbnail?id=11gAT3uSf6EhqY1gp7ESxBQx3ZJOIXz2O&sz=w1000 | https://drive.google.com/file/d/11gAT3uSf6EhqY1gp7ESxBQx3ZJOIXz2O/view | https://drive.google.com/thumbnail?id=10HQlUfuCM9rvKh755NA9pHKofaluje0o&sz=w1000 | https://drive.google.com/file/d/10HQlUfuCM9rvKh755NA9pHKofaluje0o/view
2024-09-13 | Al Samhah-Majlis-P206 | P206 | MJ-14 | 67 | 541 | 608 | • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 | Submission of IFC and Contract drawings to the contractor | 2.72% | 2.25% | -0.47% | External Works | 2026-03-15 |  | 2026-03-15 | 2024-09-20 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S • IFC anf contract drawings submission | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 110585480.0219 | 0 | 110585480.0219 | 3229333.33 | 0 | 113814813.3519 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1P8dv2yDVWK28813AIv4m4F9tgxPrdqDO&sz=w1000 | https://drive.google.com/file/d/1P8dv2yDVWK28813AIv4m4F9tgxPrdqDO/view | https://drive.google.com/thumbnail?id=11gAT3uSf6EhqY1gp7ESxBQx3ZJOIXz2O&sz=w1000 | https://drive.google.com/file/d/11gAT3uSf6EhqY1gp7ESxBQx3ZJOIXz2O/view | https://drive.google.com/thumbnail?id=10HQlUfuCM9rvKh755NA9pHKofaluje0o&sz=w1000 | https://drive.google.com/file/d/10HQlUfuCM9rvKh755NA9pHKofaluje0o/view
2024-09-13 | Al Samhah-Majlis-P206 | P206 | MJ-14 | 67 | 541 | 608 | • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 | Submission of IFC and Contract drawings to the contractor | 2.72% | 2.25% | -0.47% | Testing & Commissioning | 2026-03-15 |  | 2026-03-15 | 2024-09-20 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S • IFC anf contract drawings submission | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 110585480.0219 | 0 | 110585480.0219 | 3229333.33 | 0 | 113814813.3519 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1P8dv2yDVWK28813AIv4m4F9tgxPrdqDO&sz=w1000 | https://drive.google.com/file/d/1P8dv2yDVWK28813AIv4m4F9tgxPrdqDO/view | https://drive.google.com/thumbnail?id=11gAT3uSf6EhqY1gp7ESxBQx3ZJOIXz2O&sz=w1000 | https://drive.google.com/file/d/11gAT3uSf6EhqY1gp7ESxBQx3ZJOIXz2O/view | https://drive.google.com/thumbnail?id=10HQlUfuCM9rvKh755NA9pHKofaluje0o&sz=w1000 | https://drive.google.com/file/d/10HQlUfuCM9rvKh755NA9pHKofaluje0o/view
2024-09-13 | Al Samhah-Majlis-P206 | P206 | MJ-14 | 67 | 541 | 608 | • Contractor issued PO to the Sub-Contractor for Fencing and Signboard on 21/07/2024 | Submission of IFC and Contract drawings to the contractor | 2.72% | 2.25% | -0.47% | Substantial Completion | 2026-03-15 |  | 2026-03-15 | 2024-09-20 | • Submission the Advance Payment guarantee, Performance Bond • Resources availability • Shoring /Piling work Subcontractor appointment • MEP Subcontractor appointment • Safety risk • Permit , Construction NOC'S • IFC anf contract drawings submission | • Expedite submission of acontract deliverables • Finalize staff deployment and resources • Evaluate and appoint the shoring subcontractor • Evaluate and appoint the shoring subcontractor • Comply with safety plan | • Mobilizing the team for shoring works • Starting of Shoring works | 110585480.0219 | 0 | 110585480.0219 | 3229333.33 | 0 | 113814813.3519 |  | 56109.3767 | https://drive.google.com/thumbnail?id=1P8dv2yDVWK28813AIv4m4F9tgxPrdqDO&sz=w1000 | https://drive.google.com/file/d/1P8dv2yDVWK28813AIv4m4F9tgxPrdqDO/view | https://drive.google.com/thumbnail?id=11gAT3uSf6EhqY1gp7ESxBQx3ZJOIXz2O&sz=w1000 | https://drive.google.com/file/d/11gAT3uSf6EhqY1gp7ESxBQx3ZJOIXz2O/view | https://drive.google.com/thumbnail?id=10HQlUfuCM9rvKh755NA9pHKofaluje0o&sz=w1000 | https://drive.google.com/file/d/10HQlUfuCM9rvKh755NA9pHKofaluje0o/view
2024-09-13 | Al Danah-Car Park-P7 | P7 | CP-03 | 61 | 488 | 549 | 1. Building Permit Issued 2. Fence Installation for all Plots completed 3. Site Cabins installation In Progress (Utilities Works In Progress) | 1. Access to Site (Evacuation) 2. Stamped Complete IFC Packages (Specification & BOQ Pending) 3. ITC Assets to remove 4. Stamped BOQ to issue | 0.87% | 0.65% | -0.22% | Project Start Date | 2024-07-15 | 2024-07-15 |  | 2024-09-20 | 1.Timely Order & Delivery of MEP Equipmenst 2.Commencement & Completion of utility building including servise rooms and exterior envolop 3. Assumed the column should be clash free as per the issued IFC Drawings 4.building Permit condition to remove and revised bP to issued | All Early Works Packages including MEP to be on board to avoid any delay in construction and coordination's | 1. Structural Drawing Submission 2. Architecture GA Submission 3. Conduct the survey for the clashes with existing structural elements 3.Commencement of Core cutting in all plots and Steel structure testing 4. Basement – 3 - Setting Out activities | 113960984.64 | 0 | 113960984.64 | 5091000 |  | 119051984.64 |  |  | https://drive.google.com/thumbnail?id=1T7YIRQddf8thNan5EJFVaQpyLfl95ZI7&sz=w1000 | https://drive.google.com/file/d/1T7YIRQddf8thNan5EJFVaQpyLfl95ZI7/view?usp=drive_link | https://drive.google.com/thumbnail?id=14wgprJ2e6FNj1j69861AFl0UqCa1kpcQ&sz=w1000 | https://drive.google.com/file/d/14wgprJ2e6FNj1j69861AFl0UqCa1kpcQ/view?usp=drive_link | https://drive.google.com/thumbnail?id=1V-a_ob3pdPr21zpJrqWWTHOOFYV63CVx&sz=w1000 | https://drive.google.com/file/d/1V-a_ob3pdPr21zpJrqWWTHOOFYV63CVx/view?usp=drive_link
2024-09-13 | Al Danah-Car Park-P7 | P7 | CP-03 | 61 | 488 | 549 | 1. Building Permit Issued 2. Fence Installation for all Plots completed 3. Site Cabins installation In Progress (Utilities Works In Progress) | 1. Access to Site (Evacuation) 2. Stamped Complete IFC Packages (Specification & BOQ Pending) 3. ITC Assets to remove 4. Stamped BOQ to issue | 0.87% | 0.65% | -0.22% | Demolition Works | 2025-08-01 |  | 2024-10-28 | 2024-09-20 | 1.Timely Order & Delivery of MEP Equipmenst 2.Commencement & Completion of utility building including servise rooms and exterior envolop 3. Assumed the column should be clash free as per the issued IFC Drawings 4.building Permit condition to remove and revised bP to issued | All Early Works Packages including MEP to be on board to avoid any delay in construction and coordination's | 1. Structural Drawing Submission 2. Architecture GA Submission 3. Conduct the survey for the clashes with existing structural elements 3.Commencement of Core cutting in all plots and Steel structure testing 4. Basement – 3 - Setting Out activities | 113960984.64 | 0 | 113960984.64 | 5091000 |  | 119051984.64 |  |  | https://drive.google.com/thumbnail?id=1T7YIRQddf8thNan5EJFVaQpyLfl95ZI7&sz=w1000 | https://drive.google.com/file/d/1T7YIRQddf8thNan5EJFVaQpyLfl95ZI7/view?usp=drive_link | https://drive.google.com/thumbnail?id=14wgprJ2e6FNj1j69861AFl0UqCa1kpcQ&sz=w1000 | https://drive.google.com/file/d/14wgprJ2e6FNj1j69861AFl0UqCa1kpcQ/view?usp=drive_link | https://drive.google.com/thumbnail?id=1V-a_ob3pdPr21zpJrqWWTHOOFYV63CVx&sz=w1000 | https://drive.google.com/file/d/1V-a_ob3pdPr21zpJrqWWTHOOFYV63CVx/view?usp=drive_link
2024-09-13 | Al Danah-Car Park-P7 | P7 | CP-03 | 61 | 488 | 549 | 1. Building Permit Issued 2. Fence Installation for all Plots completed 3. Site Cabins installation In Progress (Utilities Works In Progress) | 1. Access to Site (Evacuation) 2. Stamped Complete IFC Packages (Specification & BOQ Pending) 3. ITC Assets to remove 4. Stamped BOQ to issue | 0.87% | 0.65% | -0.22% | Civil & Structural Works | 2025-05-31 |  | 2025-05-31 | 2024-09-20 | 1.Timely Order & Delivery of MEP Equipmenst 2.Commencement & Completion of utility building including servise rooms and exterior envolop 3. Assumed the column should be clash free as per the issued IFC Drawings 4.building Permit condition to remove and revised bP to issued | All Early Works Packages including MEP to be on board to avoid any delay in construction and coordination's | 1. Structural Drawing Submission 2. Architecture GA Submission 3. Conduct the survey for the clashes with existing structural elements 3.Commencement of Core cutting in all plots and Steel structure testing 4. Basement – 3 - Setting Out activities | 113960984.64 | 0 | 113960984.64 | 5091000 |  | 119051984.64 |  |  | https://drive.google.com/thumbnail?id=1T7YIRQddf8thNan5EJFVaQpyLfl95ZI7&sz=w1000 | https://drive.google.com/file/d/1T7YIRQddf8thNan5EJFVaQpyLfl95ZI7/view?usp=drive_link | https://drive.google.com/thumbnail?id=14wgprJ2e6FNj1j69861AFl0UqCa1kpcQ&sz=w1000 | https://drive.google.com/file/d/14wgprJ2e6FNj1j69861AFl0UqCa1kpcQ/view?usp=drive_link | https://drive.google.com/thumbnail?id=1V-a_ob3pdPr21zpJrqWWTHOOFYV63CVx&sz=w1000 | https://drive.google.com/file/d/1V-a_ob3pdPr21zpJrqWWTHOOFYV63CVx/view?usp=drive_link
2024-09-13 | Al Danah-Car Park-P7 | P7 | CP-03 | 61 | 488 | 549 | 1. Building Permit Issued 2. Fence Installation for all Plots completed 3. Site Cabins installation In Progress (Utilities Works In Progress) | 1. Access to Site (Evacuation) 2. Stamped Complete IFC Packages (Specification & BOQ Pending) 3. ITC Assets to remove 4. Stamped BOQ to issue | 0.87% | 0.65% | -0.22% | MEP Works | 2025-12-15 |  | 2025-09-30 | 2024-09-20 | 1.Timely Order & Delivery of MEP Equipmenst 2.Commencement & Completion of utility building including servise rooms and exterior envolop 3. Assumed the column should be clash free as per the issued IFC Drawings 4.building Permit condition to remove and revised bP to issued | All Early Works Packages including MEP to be on board to avoid any delay in construction and coordination's | 1. Structural Drawing Submission 2. Architecture GA Submission 3. Conduct the survey for the clashes with existing structural elements 3.Commencement of Core cutting in all plots and Steel structure testing 4. Basement – 3 - Setting Out activities | 113960984.64 | 0 | 113960984.64 | 5091000 |  | 119051984.64 |  |  | https://drive.google.com/thumbnail?id=1T7YIRQddf8thNan5EJFVaQpyLfl95ZI7&sz=w1000 | https://drive.google.com/file/d/1T7YIRQddf8thNan5EJFVaQpyLfl95ZI7/view?usp=drive_link | https://drive.google.com/thumbnail?id=14wgprJ2e6FNj1j69861AFl0UqCa1kpcQ&sz=w1000 | https://drive.google.com/file/d/14wgprJ2e6FNj1j69861AFl0UqCa1kpcQ/view?usp=drive_link | https://drive.google.com/thumbnail?id=1V-a_ob3pdPr21zpJrqWWTHOOFYV63CVx&sz=w1000 | https://drive.google.com/file/d/1V-a_ob3pdPr21zpJrqWWTHOOFYV63CVx/view?usp=drive_link
2024-09-13 | Al Danah-Car Park-P7 | P7 | CP-03 | 61 | 488 | 549 | 1. Building Permit Issued 2. Fence Installation for all Plots completed 3. Site Cabins installation In Progress (Utilities Works In Progress) | 1. Access to Site (Evacuation) 2. Stamped Complete IFC Packages (Specification & BOQ Pending) 3. ITC Assets to remove 4. Stamped BOQ to issue | 0.87% | 0.65% | -0.22% | Internal Finishes | 2025-12-15 |  | 2025-11-30 | 2024-09-20 | 1.Timely Order & Delivery of MEP Equipmenst 2.Commencement & Completion of utility building including servise rooms and exterior envolop 3. Assumed the column should be clash free as per the issued IFC Drawings 4.building Permit condition to remove and revised bP to issued | All Early Works Packages including MEP to be on board to avoid any delay in construction and coordination's | 1. Structural Drawing Submission 2. Architecture GA Submission 3. Conduct the survey for the clashes with existing structural elements 3.Commencement of Core cutting in all plots and Steel structure testing 4. Basement – 3 - Setting Out activities | 113960984.64 | 0 | 113960984.64 | 5091000 |  | 119051984.64 |  |  | https://drive.google.com/thumbnail?id=1T7YIRQddf8thNan5EJFVaQpyLfl95ZI7&sz=w1000 | https://drive.google.com/file/d/1T7YIRQddf8thNan5EJFVaQpyLfl95ZI7/view?usp=drive_link | https://drive.google.com/thumbnail?id=14wgprJ2e6FNj1j69861AFl0UqCa1kpcQ&sz=w1000 | https://drive.google.com/file/d/14wgprJ2e6FNj1j69861AFl0UqCa1kpcQ/view?usp=drive_link | https://drive.google.com/thumbnail?id=1V-a_ob3pdPr21zpJrqWWTHOOFYV63CVx&sz=w1000 | https://drive.google.com/file/d/1V-a_ob3pdPr21zpJrqWWTHOOFYV63CVx/view?usp=drive_link
2024-09-13 | Al Danah-Car Park-P7 | P7 | CP-03 | 61 | 488 | 549 | 1. Building Permit Issued 2. Fence Installation for all Plots completed 3. Site Cabins installation In Progress (Utilities Works In Progress) | 1. Access to Site (Evacuation) 2. Stamped Complete IFC Packages (Specification & BOQ Pending) 3. ITC Assets to remove 4. Stamped BOQ to issue | 0.87% | 0.65% | -0.22% | External Façade | 2025-12-23 |  | 2025-12-10 | 2024-09-20 | 1.Timely Order & Delivery of MEP Equipmenst 2.Commencement & Completion of utility building including servise rooms and exterior envolop 3. Assumed the column should be clash free as per the issued IFC Drawings 4.building Permit condition to remove and revised bP to issued | All Early Works Packages including MEP to be on board to avoid any delay in construction and coordination's | 1. Structural Drawing Submission 2. Architecture GA Submission 3. Conduct the survey for the clashes with existing structural elements 3.Commencement of Core cutting in all plots and Steel structure testing 4. Basement – 3 - Setting Out activities | 113960984.64 | 0 | 113960984.64 | 5091000 |  | 119051984.64 |  |  | https://drive.google.com/thumbnail?id=1T7YIRQddf8thNan5EJFVaQpyLfl95ZI7&sz=w1000 | https://drive.google.com/file/d/1T7YIRQddf8thNan5EJFVaQpyLfl95ZI7/view?usp=drive_link | https://drive.google.com/thumbnail?id=14wgprJ2e6FNj1j69861AFl0UqCa1kpcQ&sz=w1000 | https://drive.google.com/file/d/14wgprJ2e6FNj1j69861AFl0UqCa1kpcQ/view?usp=drive_link | https://drive.google.com/thumbnail?id=1V-a_ob3pdPr21zpJrqWWTHOOFYV63CVx&sz=w1000 | https://drive.google.com/file/d/1V-a_ob3pdPr21zpJrqWWTHOOFYV63CVx/view?usp=drive_link
2024-09-13 | Al Danah-Car Park-P7 | P7 | CP-03 | 61 | 488 | 549 | 1. Building Permit Issued 2. Fence Installation for all Plots completed 3. Site Cabins installation In Progress (Utilities Works In Progress) | 1. Access to Site (Evacuation) 2. Stamped Complete IFC Packages (Specification & BOQ Pending) 3. ITC Assets to remove 4. Stamped BOQ to issue | 0.87% | 0.65% | -0.22% | Infrastructure & Landscape | 2025-12-18 |  | 2025-12-18 | 2024-09-20 | [5 empty] | 0 | 5091000 |  | 5091000 |  |  | https://drive.google.com/thumbnail?id=1T7YIRQddf8thNan5EJFVaQpyLfl95ZI7&sz=w1000 | https://drive.google.com/file/d/1T7YIRQddf8thNan5EJFVaQpyLfl95ZI7/view?usp=drive_link | https://drive.google.com/thumbnail?id=14wgprJ2e6FNj1j69861AFl0UqCa1kpcQ&sz=w1000 | https://drive.google.com/file/d/14wgprJ2e6FNj1j69861AFl0UqCa1kpcQ/view?usp=drive_link | https://drive.google.com/thumbnail?id=1V-a_ob3pdPr21zpJrqWWTHOOFYV63CVx&sz=w1000 | https://drive.google.com/file/d/1V-a_ob3pdPr21zpJrqWWTHOOFYV63CVx/view?usp=drive_link
2024-09-13 | Al Danah-Car Park-P7 | P7 | CP-03 | 61 | 488 | 549 | 1. Building Permit Issued 2. Fence Installation for all Plots completed 3. Site Cabins installation In Progress (Utilities Works In Progress) | 1. Access to Site (Evacuation) 2. Stamped Complete IFC Packages (Specification & BOQ Pending) 3. ITC Assets to remove 4. Stamped BOQ to issue | 0.87% | 0.65% | -0.22% | Testing & Commissioning | 2025-12-30 |  | 2025-12-30 | 2024-09-20 | 1.Timely Order & Delivery of MEP Equipmenst 2.Commencement & Completion of utility building including servise rooms and exterior envolop 3. Assumed the column should be clash free as per the issued IFC Drawings 4.building Permit condition to remove and revised bP to issued | All Early Works Packages including MEP to be on board to avoid any delay in construction and coordination's | 1. Structural Drawing Submission 2. Architecture GA Submission 3. Conduct the survey for the clashes with existing structural elements 3.Commencement of Core cutting in all plots and Steel structure testing 4. Basement – 3 - Setting Out activities | 113960984.64 | 0 | 113960984.64 | 5091000 |  | 119051984.64 |  |  | https://drive.google.com/thumbnail?id=1T7YIRQddf8thNan5EJFVaQpyLfl95ZI7&sz=w1000 | https://drive.google.com/file/d/1T7YIRQddf8thNan5EJFVaQpyLfl95ZI7/view?usp=drive_link | https://drive.google.com/thumbnail?id=14wgprJ2e6FNj1j69861AFl0UqCa1kpcQ&sz=w1000 | https://drive.google.com/file/d/14wgprJ2e6FNj1j69861AFl0UqCa1kpcQ/view?usp=drive_link | https://drive.google.com/thumbnail?id=1V-a_ob3pdPr21zpJrqWWTHOOFYV63CVx&sz=w1000 | https://drive.google.com/file/d/1V-a_ob3pdPr21zpJrqWWTHOOFYV63CVx/view?usp=drive_link
2024-09-13 | Al Danah-Car Park-P7 | P7 | CP-03 | 61 | 488 | 549 | 1. Building Permit Issued 2. Fence Installation for all Plots completed 3. Site Cabins installation In Progress (Utilities Works In Progress) | 1. Access to Site (Evacuation) 2. Stamped Complete IFC Packages (Specification & BOQ Pending) 3. ITC Assets to remove 4. Stamped BOQ to issue | 0.87% | 0.65% | -0.22% | Project Completion | 2026-01-14 |  | 2026-01-14 | 2024-09-20 | 1.Timely Order & Delivery of MEP Equipmenst 2.Commencement & Completion of utility building including servise rooms and exterior envolop 3. Assumed the column should be clash free as per the issued IFC Drawings 4.building Permit condition to remove and revised bP to issued | All Early Works Packages including MEP to be on board to avoid any delay in construction and coordination's | 1. Structural Drawing Submission 2. Architecture GA Submission 3. Conduct the survey for the clashes with existing structural elements 3.Commencement of Core cutting in all plots and Steel structure testing 4. Basement – 3 - Setting Out activities | 113960984.64 | 0 | 113960984.64 | 5091000 |  | 119051984.64 |  |  | https://drive.google.com/thumbnail?id=1T7YIRQddf8thNan5EJFVaQpyLfl95ZI7&sz=w1000 | https://drive.google.com/file/d/1T7YIRQddf8thNan5EJFVaQpyLfl95ZI7/view?usp=drive_link | https://drive.google.com/thumbnail?id=14wgprJ2e6FNj1j69861AFl0UqCa1kpcQ&sz=w1000 | https://drive.google.com/file/d/14wgprJ2e6FNj1j69861AFl0UqCa1kpcQ/view?usp=drive_link | https://drive.google.com/thumbnail?id=1V-a_ob3pdPr21zpJrqWWTHOOFYV63CVx&sz=w1000 | https://drive.google.com/file/d/1V-a_ob3pdPr21zpJrqWWTHOOFYV63CVx/view?usp=drive_link
2024-09-13 | Al Danah-Car Park-P5 | P5 | CP-04 | 61 | 488 | 549 | 1. Building Permit Issued 2. Fence Installation for all Plots completed 3. Site Cabins installation In Progress (Utilities Works In Progress) | 1. Access to Site (Evacuation) 2. Stamped Complete IFC Packages (Specification & BOQ Pending) 3. ITC Assets to remove 4. Stamped BOQ to issue | 1.28% | 0.85% | -0.43% | Project Start Date | 2024-07-15 | 2024-07-15 |  | 2024-09-20 | 1.Timely Order & Delivery of MEP Equipmenst 2.Commencement & Completion of utility building including servise rooms and exterior envolop 3. Assumed the column should be clash free as per the issued IFC Drawings 4.building Permit condition to remove and revised bP to issued | All Early Works Packages including MEP to be on board to avoid any delay in construction and coordination's | 1. Demolition of Steel Structure after Access to site 2.Architecture GA Approval (TGC Submission Under Review) 3. Conduct the survey for the clashes with existing structural elements 3.Commencement of Core cutting in all plots and Steel structure testing 4. Basement – 3 - Setting Out activities | 227141911.59 | 0 | 227141911.59 | 5091000 |  | 232232911.59 |  |  | https://drive.google.com/thumbnail?id=1YykSkRS5Oz7UZj0FL5C-mjRrSyiXnWcq&sz=w1000 | https://drive.google.com/file/d/1YykSkRS5Oz7UZj0FL5C-mjRrSyiXnWcq/view?usp=drive_link | https://drive.google.com/thumbnail?id=1CuDlsnQtJB-PNdjg1ybnzwH7fvelUrHn&sz=w1000 | https://drive.google.com/file/d/1CuDlsnQtJB-PNdjg1ybnzwH7fvelUrHn/view?usp=drive_link | https://drive.google.com/thumbnail?id=1VJ4sHxvHEYoAx3IJfsB5VejT27JsC_8_&sz=w1000 | https://drive.google.com/file/d/1VJ4sHxvHEYoAx3IJfsB5VejT27JsC_8_/view?usp=drive_link
2024-09-13 | Al Danah-Car Park-P5 | P5 | CP-04 | 61 | 488 | 549 | 1. Building Permit Issued 2. Fence Installation for all Plots completed 3. Site Cabins installation In Progress (Utilities Works In Progress) | 1. Access to Site (Evacuation) 2. Stamped Complete IFC Packages (Specification & BOQ Pending) 3. ITC Assets to remove 4. Stamped BOQ to issue | 1.28% | 0.85% | -0.43% | Demolition Works | 2025-08-01 |  | 2024-10-28 | 2024-09-20 | 1.Timely Order & Delivery of MEP Equipmenst 2.Commencement & Completion of utility building including servise rooms and exterior envolop 3. Assumed the column should be clash free as per the issued IFC Drawings 4.building Permit condition to remove and revised bP to issued | All Early Works Packages including MEP to be on board to avoid any delay in construction and coordination's | 1. Demolition of Steel Structure after Access to site 2.Architecture GA Approval (TGC Submission Under Review) 3. Conduct the survey for the clashes with existing structural elements 3.Commencement of Core cutting in all plots and Steel structure testing 4. Basement – 3 - Setting Out activities | 227141911.59 | 0 | 227141911.59 | 5091000 |  | 232232911.59 |  |  | https://drive.google.com/thumbnail?id=1YykSkRS5Oz7UZj0FL5C-mjRrSyiXnWcq&sz=w1000 | https://drive.google.com/file/d/1YykSkRS5Oz7UZj0FL5C-mjRrSyiXnWcq/view?usp=drive_link | https://drive.google.com/thumbnail?id=1CuDlsnQtJB-PNdjg1ybnzwH7fvelUrHn&sz=w1000 | https://drive.google.com/file/d/1CuDlsnQtJB-PNdjg1ybnzwH7fvelUrHn/view?usp=drive_link | https://drive.google.com/thumbnail?id=1VJ4sHxvHEYoAx3IJfsB5VejT27JsC_8_&sz=w1000 | https://drive.google.com/file/d/1VJ4sHxvHEYoAx3IJfsB5VejT27JsC_8_/view?usp=drive_link
2024-09-13 | Al Danah-Car Park-P5 | P5 | CP-04 | 61 | 488 | 549 | 1. Building Permit Issued 2. Fence Installation for all Plots completed 3. Site Cabins installation In Progress (Utilities Works In Progress) | 1. Access to Site (Evacuation) 2. Stamped Complete IFC Packages (Specification & BOQ Pending) 3. ITC Assets to remove 4. Stamped BOQ to issue | 1.28% | 0.85% | -0.43% | Civil & Structural Works | 2025-05-31 |  | 2025-05-31 | 2024-09-20 | 1.Timely Order & Delivery of MEP Equipmenst 2.Commencement & Completion of utility building including servise rooms and exterior envolop 3. Assumed the column should be clash free as per the issued IFC Drawings 4.building Permit condition to remove and revised bP to issued | All Early Works Packages including MEP to be on board to avoid any delay in construction and coordination's | 1. Demolition of Steel Structure after Access to site 2.Architecture GA Approval (TGC Submission Under Review) 3. Conduct the survey for the clashes with existing structural elements 3.Commencement of Core cutting in all plots and Steel structure testing 4. Basement – 3 - Setting Out activities | 227141911.59 | 0 | 227141911.59 | 5091000 |  | 232232911.59 |  |  | https://drive.google.com/thumbnail?id=1YykSkRS5Oz7UZj0FL5C-mjRrSyiXnWcq&sz=w1000 | https://drive.google.com/file/d/1YykSkRS5Oz7UZj0FL5C-mjRrSyiXnWcq/view?usp=drive_link | https://drive.google.com/thumbnail?id=1CuDlsnQtJB-PNdjg1ybnzwH7fvelUrHn&sz=w1000 | https://drive.google.com/file/d/1CuDlsnQtJB-PNdjg1ybnzwH7fvelUrHn/view?usp=drive_link | https://drive.google.com/thumbnail?id=1VJ4sHxvHEYoAx3IJfsB5VejT27JsC_8_&sz=w1000 | https://drive.google.com/file/d/1VJ4sHxvHEYoAx3IJfsB5VejT27JsC_8_/view?usp=drive_link
2024-09-13 | Al Danah-Car Park-P5 | P5 | CP-04 | 61 | 488 | 549 | 1. Building Permit Issued 2. Fence Installation for all Plots completed 3. Site Cabins installation In Progress (Utilities Works In Progress) | 1. Access to Site (Evacuation) 2. Stamped Complete IFC Packages (Specification & BOQ Pending) 3. ITC Assets to remove 4. Stamped BOQ to issue | 1.28% | 0.85% | -0.43% | MEP Works | 2025-12-15 |  | 2025-09-30 | 2024-09-20 | 1.Timely Order & Delivery of MEP Equipmenst 2.Commencement & Completion of utility building including servise rooms and exterior envolop 3. Assumed the column should be clash free as per the issued IFC Drawings 4.building Permit condition to remove and revised bP to issued | All Early Works Packages including MEP to be on board to avoid any delay in construction and coordination's | 1. Demolition of Steel Structure after Access to site 2.Architecture GA Approval (TGC Submission Under Review) 3. Conduct the survey for the clashes with existing structural elements 3.Commencement of Core cutting in all plots and Steel structure testing 4. Basement – 3 - Setting Out activities | 227141911.59 | 0 | 227141911.59 | 5091000 |  | 232232911.59 |  |  | https://drive.google.com/thumbnail?id=1YykSkRS5Oz7UZj0FL5C-mjRrSyiXnWcq&sz=w1000 | https://drive.google.com/file/d/1YykSkRS5Oz7UZj0FL5C-mjRrSyiXnWcq/view?usp=drive_link | https://drive.google.com/thumbnail?id=1CuDlsnQtJB-PNdjg1ybnzwH7fvelUrHn&sz=w1000 | https://drive.google.com/file/d/1CuDlsnQtJB-PNdjg1ybnzwH7fvelUrHn/view?usp=drive_link | https://drive.google.com/thumbnail?id=1VJ4sHxvHEYoAx3IJfsB5VejT27JsC_8_&sz=w1000 | https://drive.google.com/file/d/1VJ4sHxvHEYoAx3IJfsB5VejT27JsC_8_/view?usp=drive_link
2024-09-13 | Al Danah-Car Park-P5 | P5 | CP-04 | 61 | 488 | 549 | 1. Building Permit Issued 2. Fence Installation for all Plots completed 3. Site Cabins installation In Progress (Utilities Works In Progress) | 1. Access to Site (Evacuation) 2. Stamped Complete IFC Packages (Specification & BOQ Pending) 3. ITC Assets to remove 4. Stamped BOQ to issue | 1.28% | 0.85% | -0.43% | Internal Finishes | 2025-12-15 |  | 2025-11-30 | 2024-09-20 | 1.Timely Order & Delivery of MEP Equipmenst 2.Commencement & Completion of utility building including servise rooms and exterior envolop 3. Assumed the column should be clash free as per the issued IFC Drawings 4.building Permit condition to remove and revised bP to issued | All Early Works Packages including MEP to be on board to avoid any delay in construction and coordination's | 1. Demolition of Steel Structure after Access to site 2.Architecture GA Approval (TGC Submission Under Review) 3. Conduct the survey for the clashes with existing structural elements 3.Commencement of Core cutting in all plots and Steel structure testing 4. Basement – 3 - Setting Out activities | 227141911.59 | 0 | 227141911.59 | 5091000 |  | 232232911.59 |  |  | https://drive.google.com/thumbnail?id=1YykSkRS5Oz7UZj0FL5C-mjRrSyiXnWcq&sz=w1000 | https://drive.google.com/file/d/1YykSkRS5Oz7UZj0FL5C-mjRrSyiXnWcq/view?usp=drive_link | https://drive.google.com/thumbnail?id=1CuDlsnQtJB-PNdjg1ybnzwH7fvelUrHn&sz=w1000 | https://drive.google.com/file/d/1CuDlsnQtJB-PNdjg1ybnzwH7fvelUrHn/view?usp=drive_link | https://drive.google.com/thumbnail?id=1VJ4sHxvHEYoAx3IJfsB5VejT27JsC_8_&sz=w1000 | https://drive.google.com/file/d/1VJ4sHxvHEYoAx3IJfsB5VejT27JsC_8_/view?usp=drive_link
2024-09-13 | Al Danah-Car Park-P5 | P5 | CP-04 | 61 | 488 | 549 | 1. Building Permit Issued 2. Fence Installation for all Plots completed 3. Site Cabins installation In Progress (Utilities Works In Progress) | 1. Access to Site (Evacuation) 2. Stamped Complete IFC Packages (Specification & BOQ Pending) 3. ITC Assets to remove 4. Stamped BOQ to issue | 1.28% | 0.85% | -0.43% | External Façade | 2025-12-23 |  | 2025-12-10 | 2024-09-20 | 1.Timely Order & Delivery of MEP Equipmenst 2.Commencement & Completion of utility building including servise rooms and exterior envolop 3. Assumed the column should be clash free as per the issued IFC Drawings 4.building Permit condition to remove and revised bP to issued | All Early Works Packages including MEP to be on board to avoid any delay in construction and coordination's | 1. Demolition of Steel Structure after Access to site 2.Architecture GA Approval (TGC Submission Under Review) 3. Conduct the survey for the clashes with existing structural elements 3.Commencement of Core cutting in all plots and Steel structure testing 4. Basement – 3 - Setting Out activities | 227141911.59 | 0 | 227141911.59 | 5091000 |  | 232232911.59 |  |  | https://drive.google.com/thumbnail?id=1YykSkRS5Oz7UZj0FL5C-mjRrSyiXnWcq&sz=w1000 | https://drive.google.com/file/d/1YykSkRS5Oz7UZj0FL5C-mjRrSyiXnWcq/view?usp=drive_link | https://drive.google.com/thumbnail?id=1CuDlsnQtJB-PNdjg1ybnzwH7fvelUrHn&sz=w1000 | https://drive.google.com/file/d/1CuDlsnQtJB-PNdjg1ybnzwH7fvelUrHn/view?usp=drive_link | https://drive.google.com/thumbnail?id=1VJ4sHxvHEYoAx3IJfsB5VejT27JsC_8_&sz=w1000 | https://drive.google.com/file/d/1VJ4sHxvHEYoAx3IJfsB5VejT27JsC_8_/view?usp=drive_link
2024-09-13 | Al Danah-Car Park-P5 | P5 | CP-04 | 61 | 488 | 549 | 1. Building Permit Issued 2. Fence Installation for all Plots completed 3. Site Cabins installation In Progress (Utilities Works In Progress) | 1. Access to Site (Evacuation) 2. Stamped Complete IFC Packages (Specification & BOQ Pending) 3. ITC Assets to remove 4. Stamped BOQ to issue | 1.28% | 0.85% | -0.43% | Infrastructure & Landscape | 2025-12-18 |  | 2025-12-18 | 2024-09-20 | 1.Timely Order & Delivery of MEP Equipmenst 2.Commencement & Completion of utility building including servise rooms and exterior envolop 3. Assumed the column should be clash free as per the issued IFC Drawings 4.building Permit condition to remove and revised bP to issued | All Early Works Packages including MEP to be on board to avoid any delay in construction and coordination's | 1. Demolition of Steel Structure after Access to site 2.Architecture GA Approval (TGC Submission Under Review) 3. Conduct the survey for the clashes with existing structural elements 3.Commencement of Core cutting in all plots and Steel structure testing 4. Basement – 3 - Setting Out activities | 227141911.59 | 0 | 227141911.59 | 5091000 |  | 232232911.59 |  |  | https://drive.google.com/thumbnail?id=1YykSkRS5Oz7UZj0FL5C-mjRrSyiXnWcq&sz=w1000 | https://drive.google.com/file/d/1YykSkRS5Oz7UZj0FL5C-mjRrSyiXnWcq/view?usp=drive_link | https://drive.google.com/thumbnail?id=1CuDlsnQtJB-PNdjg1ybnzwH7fvelUrHn&sz=w1000 | https://drive.google.com/file/d/1CuDlsnQtJB-PNdjg1ybnzwH7fvelUrHn/view?usp=drive_link | https://drive.google.com/thumbnail?id=1VJ4sHxvHEYoAx3IJfsB5VejT27JsC_8_&sz=w1000 | https://drive.google.com/file/d/1VJ4sHxvHEYoAx3IJfsB5VejT27JsC_8_/view?usp=drive_link
2024-09-13 | Al Danah-Car Park-P5 | P5 | CP-04 | 61 | 488 | 549 | 1. Building Permit Issued 2. Fence Installation for all Plots completed 3. Site Cabins installation In Progress (Utilities Works In Progress) | 1. Access to Site (Evacuation) 2. Stamped Complete IFC Packages (Specification & BOQ Pending) 3. ITC Assets to remove 4. Stamped BOQ to issue | 1.28% | 0.85% | -0.43% | Testing & Commissioning | 2025-12-30 |  | 2025-12-30 | 2024-09-20 | 1.Timely Order & Delivery of MEP Equipmenst 2.Commencement & Completion of utility building including servise rooms and exterior envolop 3. Assumed the column should be clash free as per the issued IFC Drawings 4.building Permit condition to remove and revised bP to issued | All Early Works Packages including MEP to be on board to avoid any delay in construction and coordination's | 1. Demolition of Steel Structure after Access to site 2.Architecture GA Approval (TGC Submission Under Review) 3. Conduct the survey for the clashes with existing structural elements 3.Commencement of Core cutting in all plots and Steel structure testing 4. Basement – 3 - Setting Out activities | 227141911.59 | 0 | 227141911.59 | 5091000 |  | 232232911.59 |  |  | https://drive.google.com/thumbnail?id=1YykSkRS5Oz7UZj0FL5C-mjRrSyiXnWcq&sz=w1000 | https://drive.google.com/file/d/1YykSkRS5Oz7UZj0FL5C-mjRrSyiXnWcq/view?usp=drive_link | https://drive.google.com/thumbnail?id=1CuDlsnQtJB-PNdjg1ybnzwH7fvelUrHn&sz=w1000 | https://drive.google.com/file/d/1CuDlsnQtJB-PNdjg1ybnzwH7fvelUrHn/view?usp=drive_link | https://drive.google.com/thumbnail?id=1VJ4sHxvHEYoAx3IJfsB5VejT27JsC_8_&sz=w1000 | https://drive.google.com/file/d/1VJ4sHxvHEYoAx3IJfsB5VejT27JsC_8_/view?usp=drive_link
2024-09-13 | Al Danah-Car Park-P5 | P5 | CP-04 | 61 | 488 | 549 | 1. Building Permit Issued 2. Fence Installation for all Plots completed 3. Site Cabins installation In Progress (Utilities Works In Progress) | 1. Access to Site (Evacuation) 2. Stamped Complete IFC Packages (Specification & BOQ Pending) 3. ITC Assets to remove 4. Stamped BOQ to issue | 1.28% | 0.85% | -0.43% | Project Completion | 2026-01-14 |  | 2026-01-14 | 2024-09-20 | 1.Timely Order & Delivery of MEP Equipmenst 2.Commencement & Completion of utility building including servise rooms and exterior envolop 3. Assumed the column should be clash free as per the issued IFC Drawings 4.building Permit condition to remove and revised bP to issued | All Early Works Packages including MEP to be on board to avoid any delay in construction and coordination's | 1. Demolition of Steel Structure after Access to site 2.Architecture GA Approval (TGC Submission Under Review) 3. Conduct the survey for the clashes with existing structural elements 3.Commencement of Core cutting in all plots and Steel structure testing 4. Basement – 3 - Setting Out activities | 227141911.59 | 0 | 227141911.59 | 5091000 |  | 232232911.59 |  |  | https://drive.google.com/thumbnail?id=1YykSkRS5Oz7UZj0FL5C-mjRrSyiXnWcq&sz=w1000 | https://drive.google.com/file/d/1YykSkRS5Oz7UZj0FL5C-mjRrSyiXnWcq/view?usp=drive_link | https://drive.google.com/thumbnail?id=1CuDlsnQtJB-PNdjg1ybnzwH7fvelUrHn&sz=w1000 | https://drive.google.com/file/d/1CuDlsnQtJB-PNdjg1ybnzwH7fvelUrHn/view?usp=drive_link | https://drive.google.com/thumbnail?id=1VJ4sHxvHEYoAx3IJfsB5VejT27JsC_8_&sz=w1000 | https://drive.google.com/file/d/1VJ4sHxvHEYoAx3IJfsB5VejT27JsC_8_/view?usp=drive_link
2024-09-13 | Al Danah-Car Park-P22 | P22 | CP-05 | 61 | 488 | 549 | 1. Building Permit Issued 2. Fence Installation for all Plots completed 3. Site Cabins installation In Progress (Utilities Works In Progress) | 1. Access to Site (Evacuation) 2. Stamped Complete IFC Packages (Specification & BOQ Pending) 3. ITC Assets to remove 4. Stamped BOQ to issue | 1.25% | 0.72% | -0.53% | Project Start Date | 2024-07-15 | 2024-07-15 |  | 2024-09-20 | 1.Timely Order & Delivery of MEP Equipmenst 2.Commencement & Completion of utility building including servise rooms and exterior envolop 3. Assumed the column should be clash free as per the issued IFC Drawings 4.building Permit condition to remove and revised bP to issued | All Early Works Packages including MEP to be on board to avoid any delay in construction and coordination's | 1. E11-P22 - Structural Drawing Submission 2. E11-P22 – Architecture GA Submission 3. Conduct the survey for the clashes with existing structural elements 3.Commencement of Core cutting in all plots and Steel structure testing 4. Basement – 3 - Setting Out activities | 156595787.4 | 0 | 156595787.4 | 5091000 |  | 161686787.4 |  |  | https://drive.google.com/thumbnail?id=1w6UPVTFIWsnJWkkyxF5dCN9sAVW3V2Q2&sz=w1000 | https://drive.google.com/file/d/1w6UPVTFIWsnJWkkyxF5dCN9sAVW3V2Q2/view?usp=drive_link | https://drive.google.com/thumbnail?id=1oou1Xw9DcJtqi1GXuDypx-S_Vc2uTt_m&sz=w1000 | https://drive.google.com/file/d/1oou1Xw9DcJtqi1GXuDypx-S_Vc2uTt_m/view?usp=drive_link | https://drive.google.com/thumbnail?id=1ngIc8spFoqQC5sawSrHTxKP7CmN_SYxy&sz=w1000 | https://drive.google.com/file/d/1ngIc8spFoqQC5sawSrHTxKP7CmN_SYxy/view?usp=drive_link
2024-09-13 | Al Danah-Car Park-P22 | P22 | CP-05 | 61 | 488 | 549 | 1. Building Permit Issued 2. Fence Installation for all Plots completed 3. Site Cabins installation In Progress (Utilities Works In Progress) | 1. Access to Site (Evacuation) 2. Stamped Complete IFC Packages (Specification & BOQ Pending) 3. ITC Assets to remove 4. Stamped BOQ to issue | 1.25% | 0.72% | -0.53% | Demolition Works | 2025-08-01 |  | 2024-10-28 | 2024-09-20 | 1.Timely Order & Delivery of MEP Equipmenst 2.Commencement & Completion of utility building including servise rooms and exterior envolop 3. Assumed the column should be clash free as per the issued IFC Drawings 4.building Permit condition to remove and revised bP to issued | All Early Works Packages including MEP to be on board to avoid any delay in construction and coordination's | 1. E11-P22 - Structural Drawing Submission 2. E11-P22 – Architecture GA Submission 3. Conduct the survey for the clashes with existing structural elements 3.Commencement of Core cutting in all plots and Steel structure testing 4. Basement – 3 - Setting Out activities | 156595787.4 | 0 | 156595787.4 | 5091000 |  | 161686787.4 |  |  | https://drive.google.com/thumbnail?id=1w6UPVTFIWsnJWkkyxF5dCN9sAVW3V2Q2&sz=w1000 | https://drive.google.com/file/d/1w6UPVTFIWsnJWkkyxF5dCN9sAVW3V2Q2/view?usp=drive_link | https://drive.google.com/thumbnail?id=1oou1Xw9DcJtqi1GXuDypx-S_Vc2uTt_m&sz=w1000 | https://drive.google.com/file/d/1oou1Xw9DcJtqi1GXuDypx-S_Vc2uTt_m/view?usp=drive_link | https://drive.google.com/thumbnail?id=1ngIc8spFoqQC5sawSrHTxKP7CmN_SYxy&sz=w1000 | https://drive.google.com/file/d/1ngIc8spFoqQC5sawSrHTxKP7CmN_SYxy/view?usp=drive_link
2024-09-13 | Al Danah-Car Park-P22 | P22 | CP-05 | 61 | 488 | 549 | 1. Building Permit Issued 2. Fence Installation for all Plots completed 3. Site Cabins installation In Progress (Utilities Works In Progress) | 1. Access to Site (Evacuation) 2. Stamped Complete IFC Packages (Specification & BOQ Pending) 3. ITC Assets to remove 4. Stamped BOQ to issue | 1.25% | 0.72% | -0.53% | Civil & Structural Works | 2025-05-31 |  | 2025-05-31 | 2024-09-20 | 1.Timely Order & Delivery of MEP Equipmenst 2.Commencement & Completion of utility building including servise rooms and exterior envolop 3. Assumed the column should be clash free as per the issued IFC Drawings 4.building Permit condition to remove and revised bP to issued | All Early Works Packages including MEP to be on board to avoid any delay in construction and coordination's | 1. E11-P22 - Structural Drawing Submission 2. E11-P22 – Architecture GA Submission 3. Conduct the survey for the clashes with existing structural elements 3.Commencement of Core cutting in all plots and Steel structure testing 4. Basement – 3 - Setting Out activities | 156595787.4 | 0 | 156595787.4 | 5091000 |  | 161686787.4 |  |  | https://drive.google.com/thumbnail?id=1w6UPVTFIWsnJWkkyxF5dCN9sAVW3V2Q2&sz=w1000 | https://drive.google.com/file/d/1w6UPVTFIWsnJWkkyxF5dCN9sAVW3V2Q2/view?usp=drive_link | https://drive.google.com/thumbnail?id=1oou1Xw9DcJtqi1GXuDypx-S_Vc2uTt_m&sz=w1000 | https://drive.google.com/file/d/1oou1Xw9DcJtqi1GXuDypx-S_Vc2uTt_m/view?usp=drive_link | https://drive.google.com/thumbnail?id=1ngIc8spFoqQC5sawSrHTxKP7CmN_SYxy&sz=w1000 | https://drive.google.com/file/d/1ngIc8spFoqQC5sawSrHTxKP7CmN_SYxy/view?usp=drive_link
2024-09-13 | Al Danah-Car Park-P22 | P22 | CP-05 | 61 | 488 | 549 | 1. Building Permit Issued 2. Fence Installation for all Plots completed 3. Site Cabins installation In Progress (Utilities Works In Progress) | 1. Access to Site (Evacuation) 2. Stamped Complete IFC Packages (Specification & BOQ Pending) 3. ITC Assets to remove 4. Stamped BOQ to issue | 1.25% | 0.72% | -0.53% | MEP Works | 2025-12-15 |  | 2025-09-30 | 2024-09-20 | 1.Timely Order & Delivery of MEP Equipmenst 2.Commencement & Completion of utility building including servise rooms and exterior envolop 3. Assumed the column should be clash free as per the issued IFC Drawings 4.building Permit condition to remove and revised bP to issued | All Early Works Packages including MEP to be on board to avoid any delay in construction and coordination's | 1. E11-P22 - Structural Drawing Submission 2. E11-P22 – Architecture GA Submission 3. Conduct the survey for the clashes with existing structural elements 3.Commencement of Core cutting in all plots and Steel structure testing 4. Basement – 3 - Setting Out activities | 156595787.4 | 0 | 156595787.4 | 5091000 |  | 161686787.4 |  |  | https://drive.google.com/thumbnail?id=1w6UPVTFIWsnJWkkyxF5dCN9sAVW3V2Q2&sz=w1000 | https://drive.google.com/file/d/1w6UPVTFIWsnJWkkyxF5dCN9sAVW3V2Q2/view?usp=drive_link | https://drive.google.com/thumbnail?id=1oou1Xw9DcJtqi1GXuDypx-S_Vc2uTt_m&sz=w1000 | https://drive.google.com/file/d/1oou1Xw9DcJtqi1GXuDypx-S_Vc2uTt_m/view?usp=drive_link | https://drive.google.com/thumbnail?id=1ngIc8spFoqQC5sawSrHTxKP7CmN_SYxy&sz=w1000 | https://drive.google.com/file/d/1ngIc8spFoqQC5sawSrHTxKP7CmN_SYxy/view?usp=drive_link
2024-09-13 | Al Danah-Car Park-P22 | P22 | CP-05 | 61 | 488 | 549 | 1. Building Permit Issued 2. Fence Installation for all Plots completed 3. Site Cabins installation In Progress (Utilities Works In Progress) | 1. Access to Site (Evacuation) 2. Stamped Complete IFC Packages (Specification & BOQ Pending) 3. ITC Assets to remove 4. Stamped BOQ to issue | 1.25% | 0.72% | -0.53% | Internal Finishes | 2025-12-15 |  | 2025-11-30 | 2024-09-20 | 1.Timely Order & Delivery of MEP Equipmenst 2.Commencement & Completion of utility building including servise rooms and exterior envolop 3. Assumed the column should be clash free as per the issued IFC Drawings 4.building Permit condition to remove and revised bP to issued | All Early Works Packages including MEP to be on board to avoid any delay in construction and coordination's | 1. E11-P22 - Structural Drawing Submission 2. E11-P22 – Architecture GA Submission 3. Conduct the survey for the clashes with existing structural elements 3.Commencement of Core cutting in all plots and Steel structure testing 4. Basement – 3 - Setting Out activities | 156595787.4 | 0 | 156595787.4 | 5091000 |  | 161686787.4 |  |  | https://drive.google.com/thumbnail?id=1w6UPVTFIWsnJWkkyxF5dCN9sAVW3V2Q2&sz=w1000 | https://drive.google.com/file/d/1w6UPVTFIWsnJWkkyxF5dCN9sAVW3V2Q2/view?usp=drive_link | https://drive.google.com/thumbnail?id=1oou1Xw9DcJtqi1GXuDypx-S_Vc2uTt_m&sz=w1000 | https://drive.google.com/file/d/1oou1Xw9DcJtqi1GXuDypx-S_Vc2uTt_m/view?usp=drive_link | https://drive.google.com/thumbnail?id=1ngIc8spFoqQC5sawSrHTxKP7CmN_SYxy&sz=w1000 | https://drive.google.com/file/d/1ngIc8spFoqQC5sawSrHTxKP7CmN_SYxy/view?usp=drive_link
2024-09-13 | Al Danah-Car Park-P22 | P22 | CP-05 | 61 | 488 | 549 | 1. Building Permit Issued 2. Fence Installation for all Plots completed 3. Site Cabins installation In Progress (Utilities Works In Progress) | 1. Access to Site (Evacuation) 2. Stamped Complete IFC Packages (Specification & BOQ Pending) 3. ITC Assets to remove 4. Stamped BOQ to issue | 1.25% | 0.72% | -0.53% | External Façade | 2025-12-23 |  | 2025-12-10 | 2024-09-20 | 1.Timely Order & Delivery of MEP Equipmenst 2.Commencement & Completion of utility building including servise rooms and exterior envolop 3. Assumed the column should be clash free as per the issued IFC Drawings 4.building Permit condition to remove and revised bP to issued | All Early Works Packages including MEP to be on board to avoid any delay in construction and coordination's | 1. E11-P22 - Structural Drawing Submission 2. E11-P22 – Architecture GA Submission 3. Conduct the survey for the clashes with existing structural elements 3.Commencement of Core cutting in all plots and Steel structure testing 4. Basement – 3 - Setting Out activities | 156595787.4 | 0 | 156595787.4 | 5091000 |  | 161686787.4 |  |  | https://drive.google.com/thumbnail?id=1w6UPVTFIWsnJWkkyxF5dCN9sAVW3V2Q2&sz=w1000 | https://drive.google.com/file/d/1w6UPVTFIWsnJWkkyxF5dCN9sAVW3V2Q2/view?usp=drive_link | https://drive.google.com/thumbnail?id=1oou1Xw9DcJtqi1GXuDypx-S_Vc2uTt_m&sz=w1000 | https://drive.google.com/file/d/1oou1Xw9DcJtqi1GXuDypx-S_Vc2uTt_m/view?usp=drive_link | https://drive.google.com/thumbnail?id=1ngIc8spFoqQC5sawSrHTxKP7CmN_SYxy&sz=w1000 | https://drive.google.com/file/d/1ngIc8spFoqQC5sawSrHTxKP7CmN_SYxy/view?usp=drive_link
2024-09-13 | Al Danah-Car Park-P22 | P22 | CP-05 | 61 | 488 | 549 | 1. Building Permit Issued 2. Fence Installation for all Plots completed 3. Site Cabins installation In Progress (Utilities Works In Progress) | 1. Access to Site (Evacuation) 2. Stamped Complete IFC Packages (Specification & BOQ Pending) 3. ITC Assets to remove 4. Stamped BOQ to issue | 1.25% | 0.72% | -0.53% | Infrastructure & Landscape | 2025-12-18 |  | 2025-12-18 | 2024-09-20 | 1.Timely Order & Delivery of MEP Equipmenst 2.Commencement & Completion of utility building including servise rooms and exterior envolop 3. Assumed the column should be clash free as per the issued IFC Drawings 4.building Permit condition to remove and revised bP to issued | All Early Works Packages including MEP to be on board to avoid any delay in construction and coordination's | 1. E11-P22 - Structural Drawing Submission 2. E11-P22 – Architecture GA Submission 3. Conduct the survey for the clashes with existing structural elements 3.Commencement of Core cutting in all plots and Steel structure testing 4. Basement – 3 - Setting Out activities | 156595787.4 | 0 | 156595787.4 | 5091000 |  | 161686787.4 |  |  | https://drive.google.com/thumbnail?id=1w6UPVTFIWsnJWkkyxF5dCN9sAVW3V2Q2&sz=w1000 | https://drive.google.com/file/d/1w6UPVTFIWsnJWkkyxF5dCN9sAVW3V2Q2/view?usp=drive_link | https://drive.google.com/thumbnail?id=1oou1Xw9DcJtqi1GXuDypx-S_Vc2uTt_m&sz=w1000 | https://drive.google.com/file/d/1oou1Xw9DcJtqi1GXuDypx-S_Vc2uTt_m/view?usp=drive_link | https://drive.google.com/thumbnail?id=1ngIc8spFoqQC5sawSrHTxKP7CmN_SYxy&sz=w1000 | https://drive.google.com/file/d/1ngIc8spFoqQC5sawSrHTxKP7CmN_SYxy/view?usp=drive_link
2024-09-13 | Al Danah-Car Park-P22 | P22 | CP-05 | 61 | 488 | 549 | 1. Building Permit Issued 2. Fence Installation for all Plots completed 3. Site Cabins installation In Progress (Utilities Works In Progress) | 1. Access to Site (Evacuation) 2. Stamped Complete IFC Packages (Specification & BOQ Pending) 3. ITC Assets to remove 4. Stamped BOQ to issue | 1.25% | 0.72% | -0.53% | Testing & Commissioning | 2025-12-30 |  | 2025-12-30 | 2024-09-20 | 1.Timely Order & Delivery of MEP Equipmenst 2.Commencement & Completion of utility building including servise rooms and exterior envolop 3. Assumed the column should be clash free as per the issued IFC Drawings 4.building Permit condition to remove and revised bP to issued | All Early Works Packages including MEP to be on board to avoid any delay in construction and coordination's | 1. E11-P22 - Structural Drawing Submission 2. E11-P22 – Architecture GA Submission 3. Conduct the survey for the clashes with existing structural elements 3.Commencement of Core cutting in all plots and Steel structure testing 4. Basement – 3 - Setting Out activities | 156595787.4 | 0 | 156595787.4 | 5091000 |  | 161686787.4 |  |  | https://drive.google.com/thumbnail?id=1w6UPVTFIWsnJWkkyxF5dCN9sAVW3V2Q2&sz=w1000 | https://drive.google.com/file/d/1w6UPVTFIWsnJWkkyxF5dCN9sAVW3V2Q2/view?usp=drive_link | https://drive.google.com/thumbnail?id=1oou1Xw9DcJtqi1GXuDypx-S_Vc2uTt_m&sz=w1000 | https://drive.google.com/file/d/1oou1Xw9DcJtqi1GXuDypx-S_Vc2uTt_m/view?usp=drive_link | https://drive.google.com/thumbnail?id=1ngIc8spFoqQC5sawSrHTxKP7CmN_SYxy&sz=w1000 | https://drive.google.com/file/d/1ngIc8spFoqQC5sawSrHTxKP7CmN_SYxy/view?usp=drive_link
2024-09-13 | Al Danah-Car Park-P22 | P22 | CP-05 | 61 | 488 | 549 | 1. Building Permit Issued 2. Fence Installation for all Plots completed 3. Site Cabins installation In Progress (Utilities Works In Progress) | 1. Access to Site (Evacuation) 2. Stamped Complete IFC Packages (Specification & BOQ Pending) 3. ITC Assets to remove 4. Stamped BOQ to issue | 1.25% | 0.72% | -0.53% | Project Completion | 2026-01-14 |  | 2026-01-14 | 2024-09-20 | 1.Timely Order & Delivery of MEP Equipmenst 2.Commencement & Completion of utility building including servise rooms and exterior envolop 3. Assumed the column should be clash free as per the issued IFC Drawings 4.building Permit condition to remove and revised bP to issued | All Early Works Packages including MEP to be on board to avoid any delay in construction and coordination's | 1. E11-P22 - Structural Drawing Submission 2. E11-P22 – Architecture GA Submission 3. Conduct the survey for the clashes with existing structural elements 3.Commencement of Core cutting in all plots and Steel structure testing 4. Basement – 3 - Setting Out activities | 156595787.4 | 0 | 156595787.4 | 5091000 |  | 161686787.4 |  |  | https://drive.google.com/thumbnail?id=1w6UPVTFIWsnJWkkyxF5dCN9sAVW3V2Q2&sz=w1000 | https://drive.google.com/file/d/1w6UPVTFIWsnJWkkyxF5dCN9sAVW3V2Q2/view?usp=drive_link | https://drive.google.com/thumbnail?id=1oou1Xw9DcJtqi1GXuDypx-S_Vc2uTt_m&sz=w1000 | https://drive.google.com/file/d/1oou1Xw9DcJtqi1GXuDypx-S_Vc2uTt_m/view?usp=drive_link | https://drive.google.com/thumbnail?id=1ngIc8spFoqQC5sawSrHTxKP7CmN_SYxy&sz=w1000 | https://drive.google.com/file/d/1ngIc8spFoqQC5sawSrHTxKP7CmN_SYxy/view?usp=drive_link
2024-09-13 | Al Danah-Car Park-P8 | P8 | CP-06 | 61 | 488 | 549 | 1. Building Permit Issued 2. Fence Installation for all Plots completed 3. Site Cabins installation In Progress (Utilities Works In Progress) | 1. Access to Site (Evacuation) 2. Stamped Complete IFC Packages (Specification & BOQ Pending) 3. ITC Assets to remove 4. Stamped BOQ to issue | 0.92% | 0.65% | -0.27% | Project Start Date | 2024-07-15 | 2024-07-15 |  | 2024-09-20 | 1.Timely Order & Delivery of MEP Equipmenst 2.Commencement & Completion of utility building including servise rooms and exterior envolop 3. Assumed the column should be clash free as per the issued IFC Drawings 4.building Permit condition to remove and revised bP to issued | All Early Works Packages including MEP to be on board to avoid any delay in construction and coordination's | 1. Architecture GA Submission 2. Conduct the survey for the clashes with existing structural elements 3.Commencement of Core cutting in all plots and Steel structure testing 4. Basement – 3 - Setting Out activities | 138529483.65 | 0 | 138529483.65 | 5091000 |  | 143620483.65 |  |  | https://drive.google.com/thumbnail?id=1ql2wmKd_mPzsUzcZkX5yKkUVALauijhq&sz=w1000 | https://drive.google.com/file/d/1ql2wmKd_mPzsUzcZkX5yKkUVALauijhq/view?usp=drive_link | https://drive.google.com/thumbnail?id=1WjDW2P48-BeEh7ExGxGXY9qQkIk4y4Uy&sz=w1000 | https://drive.google.com/file/d/1WjDW2P48-BeEh7ExGxGXY9qQkIk4y4Uy/view?usp=drive_link | https://drive.google.com/thumbnail?id=1LyxeudZcv-MJsdF41NW4BrCMx1QZxtcg&sz=w1000 | https://drive.google.com/file/d/1LyxeudZcv-MJsdF41NW4BrCMx1QZxtcg/view?usp=drive_link
2024-09-13 | Al Danah-Car Park-P8 | P8 | CP-06 | 61 | 488 | 549 | 1. Building Permit Issued 2. Fence Installation for all Plots completed 3. Site Cabins installation In Progress (Utilities Works In Progress) | 1. Access to Site (Evacuation) 2. Stamped Complete IFC Packages (Specification & BOQ Pending) 3. ITC Assets to remove 4. Stamped BOQ to issue | 0.92% | 0.65% | -0.27% | Demolition Works | 2025-08-01 |  | 2024-10-28 | 2024-09-20 | 1.Timely Order & Delivery of MEP Equipmenst 2.Commencement & Completion of utility building including servise rooms and exterior envolop 3. Assumed the column should be clash free as per the issued IFC Drawings 4.building Permit condition to remove and revised bP to issued | All Early Works Packages including MEP to be on board to avoid any delay in construction and coordination's | 1. Architecture GA Submission 2. Conduct the survey for the clashes with existing structural elements 3.Commencement of Core cutting in all plots and Steel structure testing 4. Basement – 3 - Setting Out activities | 138529483.65 | 0 | 138529483.65 | 5091000 |  | 143620483.65 |  |  | https://drive.google.com/thumbnail?id=1ql2wmKd_mPzsUzcZkX5yKkUVALauijhq&sz=w1000 | https://drive.google.com/file/d/1ql2wmKd_mPzsUzcZkX5yKkUVALauijhq/view?usp=drive_link | https://drive.google.com/thumbnail?id=1WjDW2P48-BeEh7ExGxGXY9qQkIk4y4Uy&sz=w1000 | https://drive.google.com/file/d/1WjDW2P48-BeEh7ExGxGXY9qQkIk4y4Uy/view?usp=drive_link | https://drive.google.com/thumbnail?id=1LyxeudZcv-MJsdF41NW4BrCMx1QZxtcg&sz=w1000 | https://drive.google.com/file/d/1LyxeudZcv-MJsdF41NW4BrCMx1QZxtcg/view?usp=drive_link
2024-09-13 | Al Danah-Car Park-P8 | P8 | CP-06 | 61 | 488 | 549 | 1. Building Permit Issued 2. Fence Installation for all Plots completed 3. Site Cabins installation In Progress (Utilities Works In Progress) | 1. Access to Site (Evacuation) 2. Stamped Complete IFC Packages (Specification & BOQ Pending) 3. ITC Assets to remove 4. Stamped BOQ to issue | 0.92% | 0.65% | -0.27% | Civil & Structural Works | 2025-05-31 |  | 2025-05-31 | 2024-09-20 | 1.Timely Order & Delivery of MEP Equipmenst 2.Commencement & Completion of utility building including servise rooms and exterior envolop 3. Assumed the column should be clash free as per the issued IFC Drawings 4.building Permit condition to remove and revised bP to issued | All Early Works Packages including MEP to be on board to avoid any delay in construction and coordination's | 1. Architecture GA Submission 2. Conduct the survey for the clashes with existing structural elements 3.Commencement of Core cutting in all plots and Steel structure testing 4. Basement – 3 - Setting Out activities | 138529483.65 | 0 | 138529483.65 | 5091000 |  | 143620483.65 |  |  | https://drive.google.com/thumbnail?id=1ql2wmKd_mPzsUzcZkX5yKkUVALauijhq&sz=w1000 | https://drive.google.com/file/d/1ql2wmKd_mPzsUzcZkX5yKkUVALauijhq/view?usp=drive_link | https://drive.google.com/thumbnail?id=1WjDW2P48-BeEh7ExGxGXY9qQkIk4y4Uy&sz=w1000 | https://drive.google.com/file/d/1WjDW2P48-BeEh7ExGxGXY9qQkIk4y4Uy/view?usp=drive_link | https://drive.google.com/thumbnail?id=1LyxeudZcv-MJsdF41NW4BrCMx1QZxtcg&sz=w1000 | https://drive.google.com/file/d/1LyxeudZcv-MJsdF41NW4BrCMx1QZxtcg/view?usp=drive_link
2024-09-13 | Al Danah-Car Park-P8 | P8 | CP-06 | 61 | 488 | 549 | 1. Building Permit Issued 2. Fence Installation for all Plots completed 3. Site Cabins installation In Progress (Utilities Works In Progress) | 1. Access to Site (Evacuation) 2. Stamped Complete IFC Packages (Specification & BOQ Pending) 3. ITC Assets to remove 4. Stamped BOQ to issue | 0.92% | 0.65% | -0.27% | MEP Works | 2025-12-15 |  | 2025-09-30 | 2024-09-20 | 1.Timely Order & Delivery of MEP Equipmenst 2.Commencement & Completion of utility building including servise rooms and exterior envolop 3. Assumed the column should be clash free as per the issued IFC Drawings 4.building Permit condition to remove and revised bP to issued | All Early Works Packages including MEP to be on board to avoid any delay in construction and coordination's | 1. Architecture GA Submission 2. Conduct the survey for the clashes with existing structural elements 3.Commencement of Core cutting in all plots and Steel structure testing 4. Basement – 3 - Setting Out activities | 138529483.65 | 0 | 138529483.65 | 5091000 |  | 143620483.65 |  |  | https://drive.google.com/thumbnail?id=1ql2wmKd_mPzsUzcZkX5yKkUVALauijhq&sz=w1000 | https://drive.google.com/file/d/1ql2wmKd_mPzsUzcZkX5yKkUVALauijhq/view?usp=drive_link | https://drive.google.com/thumbnail?id=1WjDW2P48-BeEh7ExGxGXY9qQkIk4y4Uy&sz=w1000 | https://drive.google.com/file/d/1WjDW2P48-BeEh7ExGxGXY9qQkIk4y4Uy/view?usp=drive_link | https://drive.google.com/thumbnail?id=1LyxeudZcv-MJsdF41NW4BrCMx1QZxtcg&sz=w1000 | https://drive.google.com/file/d/1LyxeudZcv-MJsdF41NW4BrCMx1QZxtcg/view?usp=drive_link
2024-09-13 | Al Danah-Car Park-P8 | P8 | CP-06 | 61 | 488 | 549 | 1. Building Permit Issued 2. Fence Installation for all Plots completed 3. Site Cabins installation In Progress (Utilities Works In Progress) | 1. Access to Site (Evacuation) 2. Stamped Complete IFC Packages (Specification & BOQ Pending) 3. ITC Assets to remove 4. Stamped BOQ to issue | 0.92% | 0.65% | -0.27% | Internal Finishes | 2025-12-15 |  | 2025-11-30 | 2024-09-20 | 1.Timely Order & Delivery of MEP Equipmenst 2.Commencement & Completion of utility building including servise rooms and exterior envolop 3. Assumed the column should be clash free as per the issued IFC Drawings 4.building Permit condition to remove and revised bP to issued | All Early Works Packages including MEP to be on board to avoid any delay in construction and coordination's | 1. Architecture GA Submission 2. Conduct the survey for the clashes with existing structural elements 3.Commencement of Core cutting in all plots and Steel structure testing 4. Basement – 3 - Setting Out activities | 138529483.65 | 0 | 138529483.65 | 5091000 |  | 143620483.65 |  |  | https://drive.google.com/thumbnail?id=1ql2wmKd_mPzsUzcZkX5yKkUVALauijhq&sz=w1000 | https://drive.google.com/file/d/1ql2wmKd_mPzsUzcZkX5yKkUVALauijhq/view?usp=drive_link | https://drive.google.com/thumbnail?id=1WjDW2P48-BeEh7ExGxGXY9qQkIk4y4Uy&sz=w1000 | https://drive.google.com/file/d/1WjDW2P48-BeEh7ExGxGXY9qQkIk4y4Uy/view?usp=drive_link | https://drive.google.com/thumbnail?id=1LyxeudZcv-MJsdF41NW4BrCMx1QZxtcg&sz=w1000 | https://drive.google.com/file/d/1LyxeudZcv-MJsdF41NW4BrCMx1QZxtcg/view?usp=drive_link
2024-09-13 | Al Danah-Car Park-P8 | P8 | CP-06 | 61 | 488 | 549 | 1. Building Permit Issued 2. Fence Installation for all Plots completed 3. Site Cabins installation In Progress (Utilities Works In Progress) | 1. Access to Site (Evacuation) 2. Stamped Complete IFC Packages (Specification & BOQ Pending) 3. ITC Assets to remove 4. Stamped BOQ to issue | 0.92% | 0.65% | -0.27% | External Façade | 2025-12-23 |  | 2025-12-10 | 2024-09-20 | 1.Timely Order & Delivery of MEP Equipmenst 2.Commencement & Completion of utility building including servise rooms and exterior envolop 3. Assumed the column should be clash free as per the issued IFC Drawings 4.building Permit condition to remove and revised bP to issued | All Early Works Packages including MEP to be on board to avoid any delay in construction and coordination's | 1. Architecture GA Submission 2. Conduct the survey for the clashes with existing structural elements 3.Commencement of Core cutting in all plots and Steel structure testing 4. Basement – 3 - Setting Out activities | 138529483.65 | 0 | 138529483.65 | 5091000 |  | 143620483.65 |  |  | https://drive.google.com/thumbnail?id=1ql2wmKd_mPzsUzcZkX5yKkUVALauijhq&sz=w1000 | https://drive.google.com/file/d/1ql2wmKd_mPzsUzcZkX5yKkUVALauijhq/view?usp=drive_link | https://drive.google.com/thumbnail?id=1WjDW2P48-BeEh7ExGxGXY9qQkIk4y4Uy&sz=w1000 | https://drive.google.com/file/d/1WjDW2P48-BeEh7ExGxGXY9qQkIk4y4Uy/view?usp=drive_link | https://drive.google.com/thumbnail?id=1LyxeudZcv-MJsdF41NW4BrCMx1QZxtcg&sz=w1000 | https://drive.google.com/file/d/1LyxeudZcv-MJsdF41NW4BrCMx1QZxtcg/view?usp=drive_link
2024-09-13 | Al Danah-Car Park-P8 | P8 | CP-06 | 61 | 488 | 549 | 1. Building Permit Issued 2. Fence Installation for all Plots completed 3. Site Cabins installation In Progress (Utilities Works In Progress) | 1. Access to Site (Evacuation) 2. Stamped Complete IFC Packages (Specification & BOQ Pending) 3. ITC Assets to remove 4. Stamped BOQ to issue | 0.92% | 0.65% | -0.27% | Infrastructure & Landscape | 2025-12-18 |  | 2025-12-18 | 2024-09-20 | 1.Timely Order & Delivery of MEP Equipmenst 2.Commencement & Completion of utility building including servise rooms and exterior envolop 3. Assumed the column should be clash free as per the issued IFC Drawings 4.building Permit condition to remove and revised bP to issued | All Early Works Packages including MEP to be on board to avoid any delay in construction and coordination's | 1. Architecture GA Submission 2. Conduct the survey for the clashes with existing structural elements 3.Commencement of Core cutting in all plots and Steel structure testing 4. Basement – 3 - Setting Out activities | 138529483.65 | 0 | 138529483.65 | 5091000 |  | 143620483.65 |  |  | https://drive.google.com/thumbnail?id=1ql2wmKd_mPzsUzcZkX5yKkUVALauijhq&sz=w1000 | https://drive.google.com/file/d/1ql2wmKd_mPzsUzcZkX5yKkUVALauijhq/view?usp=drive_link | https://drive.google.com/thumbnail?id=1WjDW2P48-BeEh7ExGxGXY9qQkIk4y4Uy&sz=w1000 | https://drive.google.com/file/d/1WjDW2P48-BeEh7ExGxGXY9qQkIk4y4Uy/view?usp=drive_link | https://drive.google.com/thumbnail?id=1LyxeudZcv-MJsdF41NW4BrCMx1QZxtcg&sz=w1000 | https://drive.google.com/file/d/1LyxeudZcv-MJsdF41NW4BrCMx1QZxtcg/view?usp=drive_link
2024-09-13 | Al Danah-Car Park-P8 | P8 | CP-06 | 61 | 488 | 549 | 1. Building Permit Issued 2. Fence Installation for all Plots completed 3. Site Cabins installation In Progress (Utilities Works In Progress) | 1. Access to Site (Evacuation) 2. Stamped Complete IFC Packages (Specification & BOQ Pending) 3. ITC Assets to remove 4. Stamped BOQ to issue | 0.92% | 0.65% | -0.27% | Testing & Commissioning | 2025-12-30 |  | 2025-12-30 | 2024-09-20 | 1.Timely Order & Delivery of MEP Equipmenst 2.Commencement & Completion of utility building including servise rooms and exterior envolop 3. Assumed the column should be clash free as per the issued IFC Drawings 4.building Permit condition to remove and revised bP to issued | All Early Works Packages including MEP to be on board to avoid any delay in construction and coordination's | 1. Architecture GA Submission 2. Conduct the survey for the clashes with existing structural elements 3.Commencement of Core cutting in all plots and Steel structure testing 4. Basement – 3 - Setting Out activities | 138529483.65 | 0 | 138529483.65 | 5091000 |  | 143620483.65 |  |  | https://drive.google.com/thumbnail?id=1ql2wmKd_mPzsUzcZkX5yKkUVALauijhq&sz=w1000 | https://drive.google.com/file/d/1ql2wmKd_mPzsUzcZkX5yKkUVALauijhq/view?usp=drive_link | https://drive.google.com/thumbnail?id=1WjDW2P48-BeEh7ExGxGXY9qQkIk4y4Uy&sz=w1000 | https://drive.google.com/file/d/1WjDW2P48-BeEh7ExGxGXY9qQkIk4y4Uy/view?usp=drive_link | https://drive.google.com/thumbnail?id=1LyxeudZcv-MJsdF41NW4BrCMx1QZxtcg&sz=w1000 | https://drive.google.com/file/d/1LyxeudZcv-MJsdF41NW4BrCMx1QZxtcg/view?usp=drive_link
2024-09-13 | Al Danah-Car Park-P8 | P8 | CP-06 | 61 | 488 | 549 | 1. Building Permit Issued 2. Fence Installation for all Plots completed 3. Site Cabins installation In Progress (Utilities Works In Progress) | 1. Access to Site (Evacuation) 2. Stamped Complete IFC Packages (Specification & BOQ Pending) 3. ITC Assets to remove 4. Stamped BOQ to issue | 0.92% | 0.65% | -0.27% | Project Completion | 2026-01-14 |  | 2026-01-14 | 2024-09-20 | 1.Timely Order & Delivery of MEP Equipmenst 2.Commencement & Completion of utility building including servise rooms and exterior envolop 3. Assumed the column should be clash free as per the issued IFC Drawings 4.building Permit condition to remove and revised bP to issued | All Early Works Packages including MEP to be on board to avoid any delay in construction and coordination's | 1. Architecture GA Submission 2. Conduct the survey for the clashes with existing structural elements 3.Commencement of Core cutting in all plots and Steel structure testing 4. Basement – 3 - Setting Out activities | 138529483.65 | 0 | 138529483.65 | 5091000 |  | 143620483.65 |  |  | https://drive.google.com/thumbnail?id=1ql2wmKd_mPzsUzcZkX5yKkUVALauijhq&sz=w1000 | https://drive.google.com/file/d/1ql2wmKd_mPzsUzcZkX5yKkUVALauijhq/view?usp=drive_link | https://drive.google.com/thumbnail?id=1WjDW2P48-BeEh7ExGxGXY9qQkIk4y4Uy&sz=w1000 | https://drive.google.com/file/d/1WjDW2P48-BeEh7ExGxGXY9qQkIk4y4Uy/view?usp=drive_link | https://drive.google.com/thumbnail?id=1LyxeudZcv-MJsdF41NW4BrCMx1QZxtcg&sz=w1000 | https://drive.google.com/file/d/1LyxeudZcv-MJsdF41NW4BrCMx1QZxtcg/view?usp=drive_link
2024-09-13 | Al Hili-Majlis-10 | 10 | MJ-10 | 61 | 547 | 608 | Offsite Office Construction 99% Existing Service Site Investigation work new services found other than NOC = 80% Relocation Works ( ETSALAT ) = Confirmed from Etisalat, site works can proceed = 50% Relocation Works ( AADC HV ) = Schedule for Shutdown Subcontractors Pre qualification Approval = 60 % | Additional resources employed to ensure the rigid execution of trial pits to locate existing underground services before commencing piling and shoring works. Coordinate with the relevant authorities to confirm that no services, other than those specified in the received NOCs, will be affected | 5.3% | 1.64% | -3.66% | Commencement | 4549500% | 4549500% |  | 4555500% | Potential delays in the relocation of underground services could impact the substructure work. Additionally, despite receiving the NOCs from the authorities, we have identified services not mentioned in the NOCs. These unreported services could potentially affect site operations and the mobilization of site offices. | The trial pit work was accelerated by adding resources and closely coordinating with the authorities (AADC, TRANSCO, AACM) and all relevant agencies. This was done to ensure that all services are identified and safe before starting the substructure work. | Mobilization = 100% Existing Services Relocation Works 85% Engineering Approvals Civil and Architecture Works = 30 % MEP Works = 30 % Client Approval of PS Items = 85% Procurement : Civil Works and Architecture 10% Construction: Shoring and piling 25% | 127500000 | 0 | 127500000 | 5957460 | 0 | 133457460 | 12500000 |  | https://drive.google.com/thumbnail?id=1mRE_86OJyxRYZgYUPJM_u7Ak456wW--d&sz=w1000 | https://drive.google.com/file/d/1mRE_86OJyxRYZgYUPJM_u7Ak456wW--d/view?usp=drive_link | https://drive.google.com/thumbnail?id=1PENkN1gZNt6kuWDXStzbi8Z0DiwcY8HX&sz=w1000 | https://drive.google.com/file/d/1PENkN1gZNt6kuWDXStzbi8Z0DiwcY8HX/view?usp=drive_link | https://drive.google.com/thumbnail?id=1W509JmdVlzeICueDgcivjNXJagqJa2qz&sz=w1000 | https://drive.google.com/file/d/1W509JmdVlzeICueDgcivjNXJagqJa2qz/view?usp=drive_link
2024-09-13 | Al Hili-Majlis-10 | 10 | MJ-10 | 61 | 547 | 608 | Offsite Office Construction 99% Existing Service Site Investigation work new services found other than NOC = 80% Relocation Works ( ETSALAT ) = Confirmed from Etisalat, site works can proceed = 50% Relocation Works ( AADC HV ) = Schedule for Shutdown Subcontractors Pre qualification Approval = 60 % | Additional resources employed to ensure the rigid execution of trial pits to locate existing underground services before commencing piling and shoring works. Coordinate with the relevant authorities to confirm that no services, other than those specified in the received NOCs, will be affected | 5.3% | 1.64% | -3.66% | Mobilization & Prelims | 4552400% | 4552400% |  | 4555500% | Potential delays in the relocation of underground services could impact the substructure work. Additionally, despite receiving the NOCs from the authorities, we have identified services not mentioned in the NOCs. These unreported services could potentially affect site operations and the mobilization of site offices. | The trial pit work was accelerated by adding resources and closely coordinating with the authorities (AADC, TRANSCO, AACM) and all relevant agencies. This was done to ensure that all services are identified and safe before starting the substructure work. | Mobilization = 100% Existing Services Relocation Works 85% Engineering Approvals Civil and Architecture Works = 30 % MEP Works = 30 % Client Approval of PS Items = 85% Procurement : Civil Works and Architecture 10% Construction: Shoring and piling 25% | 127500000 | 0 | 127500000 | 5957460 | 0 | 133457460 | 12500000 |  | https://drive.google.com/thumbnail?id=1mRE_86OJyxRYZgYUPJM_u7Ak456wW--d&sz=w1000 | https://drive.google.com/file/d/1mRE_86OJyxRYZgYUPJM_u7Ak456wW--d/view?usp=drive_link | https://drive.google.com/thumbnail?id=1PENkN1gZNt6kuWDXStzbi8Z0DiwcY8HX&sz=w1000 | https://drive.google.com/file/d/1PENkN1gZNt6kuWDXStzbi8Z0DiwcY8HX/view?usp=drive_link | https://drive.google.com/thumbnail?id=1W509JmdVlzeICueDgcivjNXJagqJa2qz&sz=w1000 | https://drive.google.com/file/d/1W509JmdVlzeICueDgcivjNXJagqJa2qz/view?usp=drive_link
2024-09-13 | Al Hili-Majlis-10 | 10 | MJ-10 | 61 | 547 | 608 | Offsite Office Construction 99% Existing Service Site Investigation work new services found other than NOC = 80% Relocation Works ( ETSALAT ) = Confirmed from Etisalat, site works can proceed = 50% Relocation Works ( AADC HV ) = Schedule for Shutdown Subcontractors Pre qualification Approval = 60 % | Additional resources employed to ensure the rigid execution of trial pits to locate existing underground services before commencing piling and shoring works. Coordinate with the relevant authorities to confirm that no services, other than those specified in the received NOCs, will be affected | 5.3% | 1.64% | -3.66% | Engineering | 4569700% |  | 4575100% | 4555500% | Potential delays in the relocation of underground services could impact the substructure work. Additionally, despite receiving the NOCs from the authorities, we have identified services not mentioned in the NOCs. These unreported services could potentially affect site operations and the mobilization of site offices. | The trial pit work was accelerated by adding resources and closely coordinating with the authorities (AADC, TRANSCO, AACM) and all relevant agencies. This was done to ensure that all services are identified and safe before starting the substructure work. | Mobilization = 100% Existing Services Relocation Works 85% Engineering Approvals Civil and Architecture Works = 30 % MEP Works = 30 % Client Approval of PS Items = 85% Procurement : Civil Works and Architecture 10% Construction: Shoring and piling 25% | 127500000 | 0 | 127500000 | 5957460 | 0 | 133457460 | 12500000 |  | https://drive.google.com/thumbnail?id=1mRE_86OJyxRYZgYUPJM_u7Ak456wW--d&sz=w1000 | https://drive.google.com/file/d/1mRE_86OJyxRYZgYUPJM_u7Ak456wW--d/view?usp=drive_link | https://drive.google.com/thumbnail?id=1PENkN1gZNt6kuWDXStzbi8Z0DiwcY8HX&sz=w1000 | https://drive.google.com/file/d/1PENkN1gZNt6kuWDXStzbi8Z0DiwcY8HX/view?usp=drive_link | https://drive.google.com/thumbnail?id=1W509JmdVlzeICueDgcivjNXJagqJa2qz&sz=w1000 | https://drive.google.com/file/d/1W509JmdVlzeICueDgcivjNXJagqJa2qz/view?usp=drive_link
2024-09-13 | Al Hili-Majlis-10 | 10 | MJ-10 | 61 | 547 | 608 | Offsite Office Construction 99% Existing Service Site Investigation work new services found other than NOC = 80% Relocation Works ( ETSALAT ) = Confirmed from Etisalat, site works can proceed = 50% Relocation Works ( AADC HV ) = Schedule for Shutdown Subcontractors Pre qualification Approval = 60 % | Additional resources employed to ensure the rigid execution of trial pits to locate existing underground services before commencing piling and shoring works. Coordinate with the relevant authorities to confirm that no services, other than those specified in the received NOCs, will be affected | 5.3% | 1.64% | -3.66% | Material Procurements | 4588600% |  | 4594000% | 4555500% | Potential delays in the relocation of underground services could impact the substructure work. Additionally, despite receiving the NOCs from the authorities, we have identified services not mentioned in the NOCs. These unreported services could potentially affect site operations and the mobilization of site offices. | The trial pit work was accelerated by adding resources and closely coordinating with the authorities (AADC, TRANSCO, AACM) and all relevant agencies. This was done to ensure that all services are identified and safe before starting the substructure work. | Mobilization = 100% Existing Services Relocation Works 85% Engineering Approvals Civil and Architecture Works = 30 % MEP Works = 30 % Client Approval of PS Items = 85% Procurement : Civil Works and Architecture 10% Construction: Shoring and piling 25% | 127500000 | 0 | 127500000 | 5957460 | 0 | 133457460 | 12500000 |  | https://drive.google.com/thumbnail?id=1mRE_86OJyxRYZgYUPJM_u7Ak456wW--d&sz=w1000 | https://drive.google.com/file/d/1mRE_86OJyxRYZgYUPJM_u7Ak456wW--d/view?usp=drive_link | https://drive.google.com/thumbnail?id=1PENkN1gZNt6kuWDXStzbi8Z0DiwcY8HX&sz=w1000 | https://drive.google.com/file/d/1PENkN1gZNt6kuWDXStzbi8Z0DiwcY8HX/view?usp=drive_link | https://drive.google.com/thumbnail?id=1W509JmdVlzeICueDgcivjNXJagqJa2qz&sz=w1000 | https://drive.google.com/file/d/1W509JmdVlzeICueDgcivjNXJagqJa2qz/view?usp=drive_link
2024-09-13 | Al Hili-Majlis-10 | 10 | MJ-10 | 61 | 547 | 608 | Offsite Office Construction 99% Existing Service Site Investigation work new services found other than NOC = 80% Relocation Works ( ETSALAT ) = Confirmed from Etisalat, site works can proceed = 50% Relocation Works ( AADC HV ) = Schedule for Shutdown Subcontractors Pre qualification Approval = 60 % | Additional resources employed to ensure the rigid execution of trial pits to locate existing underground services before commencing piling and shoring works. Coordinate with the relevant authorities to confirm that no services, other than those specified in the received NOCs, will be affected | 5.3% | 1.64% | -3.66% | Authority Approval & Closeout | 4610100% |  | 4613500% | 4555500% | Potential delays in the relocation of underground services could impact the substructure work. Additionally, despite receiving the NOCs from the authorities, we have identified services not mentioned in the NOCs. These unreported services could potentially affect site operations and the mobilization of site offices. | The trial pit work was accelerated by adding resources and closely coordinating with the authorities (AADC, TRANSCO, AACM) and all relevant agencies. This was done to ensure that all services are identified and safe before starting the substructure work. | Mobilization = 100% Existing Services Relocation Works 85% Engineering Approvals Civil and Architecture Works = 30 % MEP Works = 30 % Client Approval of PS Items = 85% Procurement : Civil Works and Architecture 10% Construction: Shoring and piling 25% | 127500000 | 0 | 127500000 | 5957460 | 0 | 133457460 | 12500000 |  | https://drive.google.com/thumbnail?id=1mRE_86OJyxRYZgYUPJM_u7Ak456wW--d&sz=w1000 | https://drive.google.com/file/d/1mRE_86OJyxRYZgYUPJM_u7Ak456wW--d/view?usp=drive_link | https://drive.google.com/thumbnail?id=1PENkN1gZNt6kuWDXStzbi8Z0DiwcY8HX&sz=w1000 | https://drive.google.com/file/d/1PENkN1gZNt6kuWDXStzbi8Z0DiwcY8HX/view?usp=drive_link | https://drive.google.com/thumbnail?id=1W509JmdVlzeICueDgcivjNXJagqJa2qz&sz=w1000 | https://drive.google.com/file/d/1W509JmdVlzeICueDgcivjNXJagqJa2qz/view?usp=drive_link
2024-09-13 | Al Hili-Majlis-10 | 10 | MJ-10 | 61 | 547 | 608 | Offsite Office Construction 99% Existing Service Site Investigation work new services found other than NOC = 80% Relocation Works ( ETSALAT ) = Confirmed from Etisalat, site works can proceed = 50% Relocation Works ( AADC HV ) = Schedule for Shutdown Subcontractors Pre qualification Approval = 60 % | Additional resources employed to ensure the rigid execution of trial pits to locate existing underground services before commencing piling and shoring works. Coordinate with the relevant authorities to confirm that no services, other than those specified in the received NOCs, will be affected | 5.3% | 1.64% | -3.66% | Testing & Commissioning | 4610100% |  | 4613500% | 4555500% | Potential delays in the relocation of underground services could impact the substructure work. Additionally, despite receiving the NOCs from the authorities, we have identified services not mentioned in the NOCs. These unreported services could potentially affect site operations and the mobilization of site offices. | The trial pit work was accelerated by adding resources and closely coordinating with the authorities (AADC, TRANSCO, AACM) and all relevant agencies. This was done to ensure that all services are identified and safe before starting the substructure work. | Mobilization = 100% Existing Services Relocation Works 85% Engineering Approvals Civil and Architecture Works = 30 % MEP Works = 30 % Client Approval of PS Items = 85% Procurement : Civil Works and Architecture 10% Construction: Shoring and piling 25% | 127500000 | 0 | 127500000 | 5957460 | 0 | 133457460 | 12500000 |  | https://drive.google.com/thumbnail?id=1mRE_86OJyxRYZgYUPJM_u7Ak456wW--d&sz=w1000 | https://drive.google.com/file/d/1mRE_86OJyxRYZgYUPJM_u7Ak456wW--d/view?usp=drive_link | https://drive.google.com/thumbnail?id=1PENkN1gZNt6kuWDXStzbi8Z0DiwcY8HX&sz=w1000 | https://drive.google.com/file/d/1PENkN1gZNt6kuWDXStzbi8Z0DiwcY8HX/view?usp=drive_link | https://drive.google.com/thumbnail?id=1W509JmdVlzeICueDgcivjNXJagqJa2qz&sz=w1000 | https://drive.google.com/file/d/1W509JmdVlzeICueDgcivjNXJagqJa2qz/view?usp=drive_link
2024-09-13 | Al Tiwayya-Majlis-13 | 13 | MJ-11 | 61 | 547 | 608 | Piling and Shoring Contractor Started Piling and Shoring Design Approved Traffic rerouting application in ITC in progress | Proceeded piling and shoring works. | 5.3% | 1.64% | -3.66% | Commencement | 4549500% | 4549500% |  | 4555500% | MEP Subcontractor company prequalification approval. | MEP Subcontractor will comply ASAP as per CEC Comments. | Mobilization = 100% Existing Services Relocation Works 85% Engineering Approvals Civil and Architecture Works = 30 % MEP Works = 30 % Client Approval of PS Items = 85% Procurement : Civil Works and Architecture 10% Construction: Shoring and piling 25% | 127500000 |  | 127500000 | 5957460 |  | 133457460 | 12500000 |  | https://drive.google.com/thumbnail?id=1TDJpApdYNq3AlENLBb73U5oWwKK28DF1&sz=w1000 | https://drive.google.com/file/d/1TDJpApdYNq3AlENLBb73U5oWwKK28DF1/view?usp=drive_link | https://drive.google.com/thumbnail?id=1XO6KFN11Xr9Vu-p4z4gv56Vfr7TRSm9W&sz=w1000 | https://drive.google.com/file/d/1XO6KFN11Xr9Vu-p4z4gv56Vfr7TRSm9W/view?usp=drive_link | https://drive.google.com/thumbnail?id=1l3XQXS4Q2FCMyGl__1oip2yGbK6ML46S&sz=w1000 | https://drive.google.com/file/d/1l3XQXS4Q2FCMyGl__1oip2yGbK6ML46S/view?usp=drive_link
2024-09-13 | Al Tiwayya-Majlis-13 | 13 | MJ-11 | 61 | 547 | 608 | Piling and Shoring Contractor Started Piling and Shoring Design Approved Traffic rerouting application in ITC in progress | Proceeded piling and shoring works. | 5.3% | 1.64% | -3.66% | Mobilization & Prelims | 4552400% | 4552400% |  | 4555500% | MEP Subcontractor company prequalification approval. | MEP Subcontractor will comply ASAP as per CEC Comments. | Mobilization = 100% Existing Services Relocation Works 85% Engineering Approvals Civil and Architecture Works = 30 % MEP Works = 30 % Client Approval of PS Items = 85% Procurement : Civil Works and Architecture 10% Construction: Shoring and piling 25% | 127500000 |  | 127500000 | 5957460 |  | 133457460 | 12500000 |  | https://drive.google.com/thumbnail?id=1TDJpApdYNq3AlENLBb73U5oWwKK28DF1&sz=w1000 | https://drive.google.com/file/d/1TDJpApdYNq3AlENLBb73U5oWwKK28DF1/view?usp=drive_link | https://drive.google.com/thumbnail?id=1XO6KFN11Xr9Vu-p4z4gv56Vfr7TRSm9W&sz=w1000 | https://drive.google.com/file/d/1XO6KFN11Xr9Vu-p4z4gv56Vfr7TRSm9W/view?usp=drive_link | https://drive.google.com/thumbnail?id=1l3XQXS4Q2FCMyGl__1oip2yGbK6ML46S&sz=w1000 | https://drive.google.com/file/d/1l3XQXS4Q2FCMyGl__1oip2yGbK6ML46S/view?usp=drive_link
2024-09-13 | Al Tiwayya-Majlis-13 | 13 | MJ-11 | 61 | 547 | 608 | Piling and Shoring Contractor Started Piling and Shoring Design Approved Traffic rerouting application in ITC in progress | Proceeded piling and shoring works. | 5.3% | 1.64% | -3.66% | Engineering | 4569700% |  | 4575100% | 4555500% | MEP Subcontractor company prequalification approval. | MEP Subcontractor will comply ASAP as per CEC Comments. | Mobilization = 100% Existing Services Relocation Works 85% Engineering Approvals Civil and Architecture Works = 30 % MEP Works = 30 % Client Approval of PS Items = 85% Procurement : Civil Works and Architecture 10% Construction: Shoring and piling 25% | 127500000 |  | 127500000 | 5957460 |  | 133457460 | 12500000 |  | https://drive.google.com/thumbnail?id=1TDJpApdYNq3AlENLBb73U5oWwKK28DF1&sz=w1000 | https://drive.google.com/file/d/1TDJpApdYNq3AlENLBb73U5oWwKK28DF1/view?usp=drive_link | https://drive.google.com/thumbnail?id=1XO6KFN11Xr9Vu-p4z4gv56Vfr7TRSm9W&sz=w1000 | https://drive.google.com/file/d/1XO6KFN11Xr9Vu-p4z4gv56Vfr7TRSm9W/view?usp=drive_link | https://drive.google.com/thumbnail?id=1l3XQXS4Q2FCMyGl__1oip2yGbK6ML46S&sz=w1000 | https://drive.google.com/file/d/1l3XQXS4Q2FCMyGl__1oip2yGbK6ML46S/view?usp=drive_link
2024-09-13 | Al Tiwayya-Majlis-13 | 13 | MJ-11 | 61 | 547 | 608 | Piling and Shoring Contractor Started Piling and Shoring Design Approved Traffic rerouting application in ITC in progress | Proceeded piling and shoring works. | 5.3% | 1.64% | -3.66% | Material Procurements | 4588600% |  | 4594000% | 4555500% | MEP Subcontractor company prequalification approval. | MEP Subcontractor will comply ASAP as per CEC Comments. | Mobilization = 100% Existing Services Relocation Works 85% Engineering Approvals Civil and Architecture Works = 30 % MEP Works = 30 % Client Approval of PS Items = 85% Procurement : Civil Works and Architecture 10% Construction: Shoring and piling 25% | 127500000 |  | 127500000 | 5957460 |  | 133457460 | 12500000 |  | https://drive.google.com/thumbnail?id=1TDJpApdYNq3AlENLBb73U5oWwKK28DF1&sz=w1000 | https://drive.google.com/file/d/1TDJpApdYNq3AlENLBb73U5oWwKK28DF1/view?usp=drive_link | https://drive.google.com/thumbnail?id=1XO6KFN11Xr9Vu-p4z4gv56Vfr7TRSm9W&sz=w1000 | https://drive.google.com/file/d/1XO6KFN11Xr9Vu-p4z4gv56Vfr7TRSm9W/view?usp=drive_link | https://drive.google.com/thumbnail?id=1l3XQXS4Q2FCMyGl__1oip2yGbK6ML46S&sz=w1000 | https://drive.google.com/file/d/1l3XQXS4Q2FCMyGl__1oip2yGbK6ML46S/view?usp=drive_link
2024-09-13 | Al Tiwayya-Majlis-13 | 13 | MJ-11 | 61 | 547 | 608 | Piling and Shoring Contractor Started Piling and Shoring Design Approved Traffic rerouting application in ITC in progress | Proceeded piling and shoring works. | 5.3% | 1.64% | -3.66% | Authority Approval & Closeout | 4610100% |  | 4613500% | 4555500% | MEP Subcontractor company prequalification approval. | MEP Subcontractor will comply ASAP as per CEC Comments. | Mobilization = 100% Existing Services Relocation Works 85% Engineering Approvals Civil and Architecture Works = 30 % MEP Works = 30 % Client Approval of PS Items = 85% Procurement : Civil Works and Architecture 10% Construction: Shoring and piling 25% | 127500000 |  | 127500000 | 5957460 |  | 133457460 | 12500000 |  | https://drive.google.com/thumbnail?id=1TDJpApdYNq3AlENLBb73U5oWwKK28DF1&sz=w1000 | https://drive.google.com/file/d/1TDJpApdYNq3AlENLBb73U5oWwKK28DF1/view?usp=drive_link | https://drive.google.com/thumbnail?id=1XO6KFN11Xr9Vu-p4z4gv56Vfr7TRSm9W&sz=w1000 | https://drive.google.com/file/d/1XO6KFN11Xr9Vu-p4z4gv56Vfr7TRSm9W/view?usp=drive_link | https://drive.google.com/thumbnail?id=1l3XQXS4Q2FCMyGl__1oip2yGbK6ML46S&sz=w1000 | https://drive.google.com/file/d/1l3XQXS4Q2FCMyGl__1oip2yGbK6ML46S/view?usp=drive_link
2024-09-13 | Al Tiwayya-Majlis-13 | 13 | MJ-11 | 61 | 547 | 608 | Piling and Shoring Contractor Started Piling and Shoring Design Approved Traffic rerouting application in ITC in progress | Proceeded piling and shoring works. | 5.3% | 1.64% | -3.66% | Testing & Commissioning | 4610100% |  | 4613500% | 4555500% | MEP Subcontractor company prequalification approval. | MEP Subcontractor will comply ASAP as per CEC Comments. | Mobilization = 100% Existing Services Relocation Works 85% Engineering Approvals Civil and Architecture Works = 30 % MEP Works = 30 % Client Approval of PS Items = 85% Procurement : Civil Works and Architecture 10% Construction: Shoring and piling 25% | 127500000 |  | 127500000 | 5957460 |  | 133457460 | 12500000 |  | https://drive.google.com/thumbnail?id=1TDJpApdYNq3AlENLBb73U5oWwKK28DF1&sz=w1000 | https://drive.google.com/file/d/1TDJpApdYNq3AlENLBb73U5oWwKK28DF1/view?usp=drive_link | https://drive.google.com/thumbnail?id=1XO6KFN11Xr9Vu-p4z4gv56Vfr7TRSm9W&sz=w1000 | https://drive.google.com/file/d/1XO6KFN11Xr9Vu-p4z4gv56Vfr7TRSm9W/view?usp=drive_link | https://drive.google.com/thumbnail?id=1l3XQXS4Q2FCMyGl__1oip2yGbK6ML46S&sz=w1000 | https://drive.google.com/file/d/1l3XQXS4Q2FCMyGl__1oip2yGbK6ML46S/view?usp=drive_link
2024-09-13 | Al Hili-Majlis-2 | 2 | MJ-16 | 0 | 0 | 0 | 1. Concept Report Completed and submitted to CPC for approval | 1. Approval from CPC on the Majlis concept 2. Post approval, detailed designs shall be commenced | 0% | 0% | 0% | Design Completion | 2024-11-30 |  | 2024-11-30 | 4555500% | Timely CPC approval | Follow up with CPC and address their comments promply | Commencement of detailed designs Completion of tendering process |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1qEmiD3wIIWaBK_n4jB1tWa-07pOtwaxm&sz=w1000 | https://drive.google.com/file/d/1qEmiD3wIIWaBK_n4jB1tWa-07pOtwaxm/view?usp=drive_link | https://drive.google.com/thumbnail?id=17mVlRlsRou-0EIrdkg4pHVFZuAsTDECi&sz=w1000 | https://drive.google.com/file/d/17mVlRlsRou-0EIrdkg4pHVFZuAsTDECi/view?usp=drive_link | https://drive.google.com/thumbnail?id=1PVqAblXmqsrUQNQz_eIs2ZoILINdprdI&sz=w1000 | https://drive.google.com/file/d/1PVqAblXmqsrUQNQz_eIs2ZoILINdprdI/view?usp=drive_link
2024-09-13 | Al Hili-Majlis-2 | 2 | MJ-16 | 0 | 0 | 0 | 1. Concept Report Completed and submitted to CPC for approval | 1. Approval from CPC on the Majlis concept 2. Post approval, detailed designs shall be commenced | 0% | 0% | 0% | Tender Completion | 2025-02-28 |  | 2025-02-28 | 4555500% | Timely CPC approval | Follow up with CPC and address their comments promply | Commencement of detailed designs Completion of tendering process |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1qEmiD3wIIWaBK_n4jB1tWa-07pOtwaxm&sz=w1000 | https://drive.google.com/file/d/1qEmiD3wIIWaBK_n4jB1tWa-07pOtwaxm/view?usp=drive_link | https://drive.google.com/thumbnail?id=17mVlRlsRou-0EIrdkg4pHVFZuAsTDECi&sz=w1000 | https://drive.google.com/file/d/17mVlRlsRou-0EIrdkg4pHVFZuAsTDECi/view?usp=drive_link | https://drive.google.com/thumbnail?id=1PVqAblXmqsrUQNQz_eIs2ZoILINdprdI&sz=w1000 | https://drive.google.com/file/d/1PVqAblXmqsrUQNQz_eIs2ZoILINdprdI/view?usp=drive_link
2024-09-13 | Al Hili-Majlis-2 | 2 | MJ-16 | 0 | 0 | 0 | 1. Concept Report Completed and submitted to CPC for approval | 1. Approval from CPC on the Majlis concept 2. Post approval, detailed designs shall be commenced | 0% | 0% | 0% | Construction Commencement | 2025-03-01 |  | 2025-03-01 | 4555500% | Timely CPC approval | Follow up with CPC and address their comments promply | Commencement of detailed designs Completion of tendering process |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1qEmiD3wIIWaBK_n4jB1tWa-07pOtwaxm&sz=w1000 | https://drive.google.com/file/d/1qEmiD3wIIWaBK_n4jB1tWa-07pOtwaxm/view?usp=drive_link | https://drive.google.com/thumbnail?id=17mVlRlsRou-0EIrdkg4pHVFZuAsTDECi&sz=w1000 | https://drive.google.com/file/d/17mVlRlsRou-0EIrdkg4pHVFZuAsTDECi/view?usp=drive_link | https://drive.google.com/thumbnail?id=1PVqAblXmqsrUQNQz_eIs2ZoILINdprdI&sz=w1000 | https://drive.google.com/file/d/1PVqAblXmqsrUQNQz_eIs2ZoILINdprdI/view?usp=drive_link
2024-09-13 | Al Hili-Majlis-2 | 2 | MJ-16 | 0 | 0 | 0 | 1. Concept Report Completed and submitted to CPC for approval | 1. Approval from CPC on the Majlis concept 2. Post approval, detailed designs shall be commenced | 0% | 0% | 0% | Construction Completion | 2026-10-31 |  | 2026-10-31 | 4555500% | Timely CPC approval | Follow up with CPC and address their comments promply | Commencement of detailed designs Completion of tendering process |  |  | 0 |  |  | 0 |  |  | https://drive.google.com/thumbnail?id=1qEmiD3wIIWaBK_n4jB1tWa-07pOtwaxm&sz=w1000 | https://drive.google.com/file/d/1qEmiD3wIIWaBK_n4jB1tWa-07pOtwaxm/view?usp=drive_link | https://drive.google.com/thumbnail?id=17mVlRlsRou-0EIrdkg4pHVFZuAsTDECi&sz=w1000 | https://drive.google.com/file/d/17mVlRlsRou-0EIrdkg4pHVFZuAsTDECi/view?usp=drive_link | https://drive.google.com/thumbnail?id=1PVqAblXmqsrUQNQz_eIs2ZoILINdprdI&sz=w1000 | https://drive.google.com/file/d/1PVqAblXmqsrUQNQz_eIs2ZoILINdprdI/view?usp=drive_link
Formulas:
Data Date = [Data Date, row above]
Forecast Date = [Forecast Date, row above]
Forecast Date = [Forecast Date, row above]+41
Planned Date = [Planned Date, row above]+30*20+9
Note on D1: ortensa adhamidhi: This is a formula used on the PowerBI file to create connections between both tables. It is automatic and no changes are needed
Note on P69: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To confirm if date is correct as the detail on the PP is 3-01-25
Note on D294: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: MJ12
Note on D307: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: MJ13
Note on D319: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: MJ14

## New Plots
S.No. | Project ID | Project Name | Region | District | Sector | Plot | Latitude | Longitude | Stakeholder
1 | NP-01 | Al Jimi5_10_11_27_DOH | Al Ain | Al Jimi | Administrative Center | 5_10_11_27_ | 24.2339 | 55.7238 | DOH
2 | NP-02 | FALAJ HAZZA'25_4_19_7_DOH | Al Ain | FALAJ HAZZA' | AL OWAINAH | 25_4_19_7_ | 24.1879 | 55.7373 | DOH
3 | NP-03 | AL DHAHRAH85_1_2_48_DOH | Al Ain | AL DHAHRAH | AL MALALEEH | 85_1_2_48_ | 24.0023 | 55.5661 | DOH
4 | NP-06 | Khalifa CitySE26_01_C22DMT | Abu Dhabi | Khalifa City | East 26_01 | SE26_01_C22 | 24.404 | 54.5936 | DMT
5 | NP-07 | Shakbout CityMSH31_P2DMT | Abu Dhabi | Shakbout City | MSH31_P2 | MSH31_P2 | 24.3908 | 54.6534 | DMT
6 | NP-08 | Al FalahP14DMT | Abu Dhabi | Al Falah | FA5 | P14 | 24.42 | 54.6978 | DMT
7 | NP-09 | Al FalahC2DMT | Abu Dhabi | Al Falah | FA3 | C2 | 24.4226 | 54.7304 | DMT
8 | NP-10 | AL SHAHAMAH NEWP1DMT | Abu Dhabi | AL SHAHAMAH NEW | AL BAHYAH | P1 | 24.5457 | 54.687 | DMT
9 | NP-11 | AL BAHYAH C16aDMT | Abu Dhabi | AL BAHYAH | AL BAHYAH NEW | C16a | 24.5626 | 54.6368 | DMT
10 | NP-12 | AL RAHBAHC2DMT | Abu Dhabi | AL RAHBAH | RAHBAH_C | C2 | 24.576 | 54.6897 | DMT
11 | NP-13 | Al SamhaC1DMT | Abu Dhabi | Al Samha | RAHBAH_N | C1 | 24.6379 | 54.729 | DMT
12 | NP-14 | Hili2-2-21-3DMT | Al Ain | Hili | UGDAT AL HUSOON | 2-2-21-3 | 24.3204 | 55.7965 | DMT
13 | NP-15 | AL SAROUJ19_6_14_8_DMT | Al Ain | AL SAROUJ | HAI AL WADI | 19_6_14_8_ | 24.1872 | 55.805 | DMT
14 | NP-16 | AL NOUD22_3_9_39_DMT | Al Ain | AL NOUD | WADI AL AIN 3 | 22_3_9_39_ | 24.1186 | 55.8326 | DMT
15 | NP-17 | AL DHAHIR81_5_4_22_DMT | Al Ain | AL DHAHIR | DHAHER 5 | 81_5_4_22_ | 24.0999 | 55.845 | DMT
16 | NP-18 | AL DHAHIRDMT | Al Ain | AL DHAHIR | DHAHER 3 |  | 24.0879 | 55.8331 | DMT
17 | NP-19 | AL AAMERAH65_3_10_4_DMT | Al Ain | AL AAMERAH | HAZZA AL BOUSH - WEST | 65_3_10_4_ | 24.2145 | 55.5353 | DMT
18 | NP-20 | RIMAH71_1_17_65_DMT | Al Ain | RIMAH | AL KHOWRAH 1 | 71_1_17_65_ | 24.1969 | 55.3314 | DMT
19 | NP-21 | AL MARFAMR8_P207ADEK | Al Dhafrah | AL MARFA | Al Dhafra Region | MR8_P207 | 24.0949 | 53.4806 | ADEK
20 | NP-22 | Al NahdahP2ADEK | Abu Dhabi | Al Nahdah | Al Wathabh North | P2 | 24.2734 | 54.6669 | ADEK
21 | NP-23 | Al RahbahP4ADEK | Abu Dhabi | Al Rahbah | Al Rahbah H | P4 | 24.6054 | 54.7049 | ADEK
22 | NP-24 | Al MarfaP92ADEK | Al Dhafrah | Al Marfa | MR1 | P92 | 24.0617 | 53.4535 | ADEK
23 | NP-25 | GHAYATHIP1020ADEK | Al Dhafrah | GHAYATHI | GHAYATHI | P1020 | 23.83584 | 52.814 | ADEK
24 | NP-26 | LiwaP170ADEK | Al Dhafrah | Liwa | AL LEEF | P170 | 23.1857 | 53.7849 | ADEK
Note on E7: Rheydel Monge Reorizo: To check again as there is no option for P14 in the website. Instead on numeric no. 14 only is available. Refer to ss
Note on E13: Rheydel Monge Reorizo: To revisit as the english translation in excel is vague
Note on E16: Rheydel Monge Reorizo: To revisit as the english translation in excel is vague
Note on E17: Rheydel Monge Reorizo: To revisit as the english translation in excel is vague
Note on E20: Rheydel Monge Reorizo: to check is supplied information is correct. Refer top attached ss